## Detailed_PR_Status
PROJECT | DISCIPLINE | EQUIPMENT | PR NUMBER | PR VENDOR NUMBER | VENDOR | STATUS | ELAPSED DAYS | REMARKS | VENDOR CONTACT | VENDOR EMAIL | PR ISSUED DATE (PRELIMINARY BOQ) | ENQUIRY SENT DATE | OFFER RECEIVED DATE REV-A | COMMENTS SENT FROM EDRC DATE REV-A | OFFER RECEIVED DATE REV-B | COMMENTS SENT FROM EDRC DATE REV-B | OFFER RECEIVED DATE REV-C | COMMENTS SENT FROM EDRC DATE REV-C | OFFER RECEIVED DATE REV-D | COMMENTS SENT FROM EDRC DATE REV-D | OFFER RECEIVED DATE REV-E | COMMENTS SENT FROM EDRC DATE REV-E | FINAL TECHNICAL CLEARANCE MEETING WITH VENDOR (PRE ORDER) | FINAL DOCUMENT RECEIVED FROM VENDOR (PRE ORDER) | SENT TO BU OPERATIONS | PRIORITY (T1/T2/T3) | PO ISSUED DATE | FINALIZED VENDOR | POST ORDER DOC/DRG RECEIVED DATE | COMMENTS SENT FROM EDRC DATE | FINAL TECHNICAL CLEARANCE MEETING WITH VENDOR (POST ORDER) | FINAL DOCUMENT RECEIVED FROM VENDOR (POST ORDER) | CLIENT APPROVAL DATE | PLANNED PRE-ORDER COMPLETION DATE | PLANNED PURCHASE-ORDER DATE | PLANNED POST-ORDER COMPLETION DATE | LAST MODIFIED BY
Agar Malwa | Process | Clariflocculator mechanism | LE20M187-P-WS-WT-PR-2002 | LE20M187-P-WS-WT-PR-2002-A | Shivpad | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 09.08.22 | 27.08.22 | [8 empty] | 08.09.22 | 19.09.22 | 29.09.22 |  | 29.09.22 | Shivpad | 07.10.22 | 19.12.22 | 23.12.22 | 23.12.22 | 03.01.23 |  |  | 28.11.22 | karthiga@lntecc.com
Agar Malwa | Process | Air Blower | LE20M187-P-WS-WT-PR-2003 | LE20M187-P-WS-WT-PR-2003-A | Everest | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 04.06.22 | 27.08.22 | [8 empty] | 08.09.22 | 15.09.22 | 15.09.22 |  | 15.09.22 | Everest | 19.09.22 | 19.09.22 | 23.09.22 | 23.09.22 | 20.10.22 |  |  | 14.11.22 | karthiga@lntecc.com
Agar Malwa | Process | Agitator | LE20M187-P-WS-WT-PR-2004 | LE20M187-P-WS-WT-PR-2004-A | Shivpad | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 01.04.21 | 24.04.21 | [8 empty] | 05.08.21 | 14.05.22 | 22.06.22 |  | 27.09.22 | Shivpad | 11.10.22 | 10.11.22 | 11.12.22 | 11.12.22 | 24.01.23 |  |  | 26.11.22 | karthiga@lntecc.com
Agar Malwa | Process | WTP Sluice gates | LE20M187-P-WS-WT-PR-2006 | LE20M187-P-WS-WT-PR-2006-A | Jash | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 29.01.21 | 10.07.21 | [8 empty] | 07.01.22 | 15.01.22 | 13.02.22 |  | 12.05.22 | Jash | 01.11.22 | 19.12.22 | 22.12.23 | 22.12.23 | 24.01.24 |  |  | 11.07.22 | karthiga@lntecc.com
Agar Malwa | Process | Chlorination system | LE20M187-P-WS-WT-PR-2007 | LE20M187-P-WS-WT-PR-2007-A | Zion | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 21.02.21 | 02.06.22 | [8 empty] | 17.07.22 | 27.07.22 | 14.08.22 |  | 16.09.22 | Zion | 19.09.22 | 19.09.22 | 30.10.22 | 30.10.22 | 23.11.23 |  |  | 15.11.22 | karthiga@lntecc.com
Agar Malwa | Process | Chlorine Tonner | LE20M187-P-WS-WT-PR-2008 | LE20M187-P-WS-WT-PR-2008-A | ISGEC | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 25.09.21 | 02.06.22 | [8 empty] | 27.07.23 | 29.07.23 | 04.08.23 |  | 09.08.23 | ISGEC | 22.09.23 | 22.09.23 | 04.10.23 | 04.10.23 | 13.11.23 |  |  | 08.10.23 | karthiga@lntecc.com
Agar Malwa | Process | Backwash pump | LE20M187-P-WS-WT-PR-2011 | LE20M187-P-WS-WT-PR-2011-A | WPIL | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 09.09.22 | 15.11.22 | [8 empty] | 26.11.22 | 29.12.22 | 30.12.22 |  | 30.12.22 | WPIL | 31.12.22 | 31.12.22 | 10.01.23 | 10.01.23 | 07.02.23 |  |  | 28.02.23 | karthiga@lntecc.com
Agar Malwa | Process | Submersible pump | LE20M187-P-WS-WT-PR-2012 | LE20M187-P-WS-WT-PR-2012-A | KSB | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 04.11.22 | 18.11.22 | [8 empty] | 24.11.22 | 06.12.22 | 27.12.22 |  | 28.12.22 | KSB | 31.12.22 | 26.04.23 | 28.04.23 | 28.04.23 | 31.05.23 |  |  | 26.02.23 | karthiga@lntecc.com
Agar Malwa | Process | Electrical hoist | LE20M187-P-WS-WT-PR-2013 | LE20M187-P-WS-WT-PR-2013-A | Indef | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 15.02.22 | 12.04.22 | [8 empty] | 16.02.23 | 19.03.23 | 23.03.23 |  | 08.06.23 | Indef | 14.07.23 | 20.07.23 | 25.07.23 | 25.07.23 | 23.08.23 |  |  | 07.08.23 | karthiga@lntecc.com
Agar Malwa | Process | Manual chain pulley block | LE20M187-P-WS-WT-PR-2014 | LE20M187-P-WS-WT-PR-2014-A | Indef | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 17.11.22 | 04.07.23 | [8 empty] | 06.07.23 | 08.07.23 | 12.07.23 |  | 13.07.23 | Indef | 14.07.23 | 20.07.23 | 25.07.23 | 25.07.23 | 23.08.23 |  |  | 11.09.23 | karthiga@lntecc.com
Agar Malwa | Process | Dosing pump | LE20M187-P-WS-WT-PR-2015 | LE20M187-P-WS-WT-PR-2015-A | SR Metering | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 05.06.22 | 16.07.22 | [8 empty] | 02.09.22 | 13.11.22 | 14.11.22 |  | 14.11.22 | SR Metering | 15.11.22 | 26.12.22 | 30.12.22 | 30.12.22 | 01.02.23 |  |  | 13.01.23 | karthiga@lntecc.com
Agar Malwa | Process | Submersible mixer | LE20M187-P-WS-WT-PR-2017 | LE20M187-P-WS-WT-PR-2017-A | FFP | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 25.11.21 | 25.03.22 | [8 empty] | 23.07.22 | 08.08.22 | 24.09.22 |  | 12.01.23 | FFP | 23.01.23 | 20.02.23 | 24.02.23 | 24.02.23 | 22.03.23 |  |  | 13.03.23 | karthiga@lntecc.com
Agar Malwa | Process | Dewatering pump | LE20M187-P-WS-WT-PR-2018 | LE20M187-P-WS-WT-PR-2018-A | KSB | Approved by Client | PR Closed |  |  |  | 24.01.21 | 24.01.21 | 10.10.21 | 26.11.21 | [8 empty] | 24.11.22 | 09.12.22 | 11.12.22 |  | 11.12.22 | KSB | 31.12.22 | 26.04.23 | 28.04.23 | 28.04.23 | 31.05.23 |  |  | 09.02.23 | karthiga@lntecc.com
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001 | LE20M187-M-001-A | WPIL | Approved by Client | PR Closed |  |  |  | 1.06.21 | 01.06.21 | 16.09.21 | 13.12.22 | [8 empty] | 12.01.23 | 12.01.23 | 25.01.23 | T1 | 05.04.23 | WPIL | 29.06.23 | 30.06.23 | 05.07.23 | 05.07.23 | 06.07.23 |  |  | 04.06.23 | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001 | LE20M187-M-001-B | WILO | Sent to BU Operations | PR Closed |  |  |  | 2.06.21 | 02.06.21 | 07.01.23 | 11.11.23 | [8 empty] | 15.11.23 | 20.11.23 | 02.12.23 | T2 | [10 empty] | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001 | LE20M187-M-001-C | KBL | Sent to BU Operations | PR Closed |  |  |  | 1.06.21 | 01.06.21 | 27.05.22 | 27.08.22 | [8 empty] | 25.12.22 | 07.01.23 | 25.01.23 | T3 | [6 empty] | 06.07.23 |  |  |  | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001 | LE20M187-M-001-D | FLOWMORE | Sent to BU Operations | PR Closed |  |  |  | 2.06.21 | 02.06.21 | 22.06.21 | 30.06.21 | [8 empty] | 01.07.21 | 01.07.21 | 01.07.21 | T4 | [6 empty] | 02.07.21 |  |  |  | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001-Lot2 | LE20M187-M-001-Lot2-A | WPIL | Sent to BU Operations | PR Closed |  |  |  | 2.06.21 | 02.06.21 | 24.10.23 | 18.11.23 | [8 empty] | 23.11.23 | 01.12.23 | 02.12.23 | T3 | [10 empty] | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001-Lot2 | LE20M187-M-001-Lot2-B | KBL | Sent to BU Operations | PR Closed |  |  |  | 2.06.21 | 02.06.21 | 26.03.22 | 30.08.23 | [8 empty] | 17.10.23 | 13.11.23 | 02.12.23 | T2 | [10 empty] | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001-Lot2 | LE20M187-M-001-Lot2-C | WILO | Approved by Client | PR Closed |  |  |  | 2.06.21 | 02.06.21 | 17.11.23 | 18.11.23 | [8 empty] | 18.11.23 | 18.11.23 | 02.12.23 | T1 | 13.12.23 | WILO | 19.12.23 | 19.12.23 | 19.12.23 | 19.12.23 | 04.03.24 |  |  | 11.02.24 | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001-Lot2 | LE20M187-M-001-Lot2-D | FLOWMORE | Sent to BU Operations | PR Closed |  |  |  | 2.06.21 | 02.06.21 | 18.01.23 | 02.05.23 | [8 empty] | 10.07.23 | 05.09.23 | 02.12.23 | T4 | [10 empty] | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | HSC PUMP | LE20M187-M-001-Lot2 | LE20M187-M-001-Lot2-E | KSB | Sent to BU Operations | PR Closed |  |  |  | 2.06.21 | 02.06.21 | 23.12.21 | 28.11.22 | [8 empty] | 20.05.23 | 10.07.23 | 02.12.23 | T5 | [10 empty] | karthiga@lntecc.com-02.05.2024-11:17:15
Agar Malwa | Mechanical | VT PUMP | LE20M187-M-002 | LE20M187-M-002-A | WPIL | Approved by Client | PR Closed |  |  |  | 18.06.21 | 18.06.21 | 09.05.22 | 16.08.22 | [8 empty] | 19.01.23 | 22.01.23 | 25.01.23 |  | 14.02.23 | WPIL | 28.05.23 | 25.06.23 | 02.07.23 | 02.07.23 | 06.07.23 |  |  | 15.04.23 | karthiga@lntecc.com
Agar Malwa | Mechanical | VT PUMP | LE20M187-M-002 | LE20M187-M-002-B | KBL | Sent to BU Operations | PR Closed |  |  |  | 18.06.21 | 18.06.21 | 07.07.21 | 13.07.21 | [8 empty] | 14.07.21 | 14.07.21 | 17.07.21 | [7 empty] | 18.07.21 |  |  |  | karthiga@lntecc.com
Agar Malwa | Mechanical | EOT CRANE | LE20M187-M-003 | LE20M187-M-003-A | JAPS | Approved by Client | PR Closed | Lot 1 & 2 - MFC given (Japs) |  |  | 1.06.21 | 01.06.21 | 05.01.23 | 08.03.23 | [8 empty] | 12.03.23 | 12.03.23 | 14.03.23 |  | 01.05.23 | JAPS | 08.08.23 | 10.08.23 | 11.08.23 | 11.08.23 | 13.08.23 |  |  | 30.06.23 | karthiga@lntecc.com
Agar Malwa | Mechanical | EOT CRANE | LE20M187-M-003 | LE20M187-M-003-B | REVA | Sent to BU Operations | PR Closed | Lot 1 & 2 - MFC given (Japs) |  |  | 1.06.21 | 01.06.21 | 04.10.22 | 02.01.23 | [8 empty] | 02.01.23 | 01.02.23 | 14.03.23 | [7 empty] | 13.08.23 |  |  |  | karthiga@lntecc.com
Agar Malwa | Mechanical | EOT CRANE | LE20M187-M-003 | LE20M187-M-003-C | INDEF | Sent to BU Operations | PR Closed | Lot 1 & 2 - MFC given (Japs) |  |  | 1.06.21 | 01.06.21 | 03.05.22 | 08.03.23 | [8 empty] | 12.03.23 | 12.03.23 | 14.03.23 | [7 empty] | 13.08.23 |  |  |  | karthiga@lntecc.com
Agar Malwa | Mechanical | PUMP HOUSE VALVES | LE20M187-M-004 | LE20M187-M-004-A | AVK | Approved by Client | PR Closed | POST ORDER CLEARED TO AVK |  |  | 29.09.21 | 29.09.21 | 13.12.21 | 05.04.22 | [8 empty] | 21.09.22 | 15.04.23 | 18.04.23 |  | 01.07.23 | AVK | 18.08.23 | 18.08.23 | 18.08.23 | 18.08.23 | 19.08.23 |  |  | 30.08.23 | karthiga@lntecc.com
Agar Malwa | Mechanical | PUMP HOUSE VALVES | LE20M187-M-004 | LE20M187-M-004-B | AVK | Pre-order technically cleared | 1010 | conditional clearance, POST ORDER CLEARED TO AVK |  |  | 29.09.21 | 29.09.21 | 15.10.21 | 18.10.21 | [8 empty] | 18.10.21 | 27.10.21 | [8 empty] | 29.10.21
Agar Malwa | Mechanical | PIPELINE VALVES | LE20M187-M-005 | LE20M187-M-005-A | AVK | Approved by Client | PR Closed | POST ORDER CLEARED TO AVK |  |  | 10.07.21 | 10.07.21 | 22.09.21 | 01.05.22 | [8 empty] | 13.08.22 | 03.10.22 | 18.04.23 |  | 01.07.23 | AVK | 07.08.23 | 11.08.23 | 18.08.23 | 18.08.23 | 19.08.23 |  |  | 30.08.23 | karthiga@lntecc.com
Agar Malwa | Mechanical | PIPELINE VALVES | LE20M187-M-005 | LE20M187-M-005-B | AVK | Pre-order technically cleared | 1091 | conditional clearance, POST ORDER CLEARED TO AVK |  |  | 10.07.21 | 10.07.21 | 04.08.21 | 06.08.21 | [8 empty] | 06.08.21 | 07.08.21 | [8 empty] | 09.08.21
Agar Malwa | Mechanical | DISMATLING JOINTS | LE20M187-M-006 | LE20M187-M-006-A | PRECISE | Approved by Client | PR Closed |  |  |  | 22.07.21 | 22.07.21 | 12.04.22 | 19.07.22 | [8 empty] | 19.12.22 | 23.06.23 | 01.07.23 |  | 13.08.23 | PRECISE | 20.08.23 | 28.08.23 | 08.09.23 | 21.09.23 | 05.10.23 |  |  | 12.10.23 | karthiga@lntecc.com
Agar Malwa | Mechanical | DISMATLING JOINTS | LE20M187-M-006 | LE20M187-M-006-B | PRECISE | Awaiting pre-offer from vendor | 1109 | POST ORDER CLEARED TO PRECISE |  |  | 22.07.21 | 22.07.21
Agar Malwa | Mechanical | SLUICE GATES | LE20M187-M-007 | LE20M187-M-007-A | HWE | Approved by Client | PR Closed |  |  |  | 18.09.21 | 18.09.21 | 01.03.22 | 01.05.22 | [8 empty] | 14.07.22 | 17.07.22 | 02.08.22 |  | 14.10.22 | HWE | 03.11.22 | 22.11.22 | 28.11.22 | 01.12.22 | 09.12.22 |  |  | 13.12.22 | karthiga@lntecc.com
Agar Malwa | Mechanical | SLUICE GATES | LE20M187-M-007 | LE20M187-M-007-B | JASH | Sent to BU Operations | PR Closed |  |  |  | 18.09.21 | 18.09.21 | 22.09.21 | 11.10.21 | [8 empty] | 14.10.21 | 17.10.21 | 17.10.21 | [7 empty] | 18.10.21 |  |  |  | karthiga@lntecc.com
Agar Malwa | Mechanical | DEWATERING PUMP | LE20M187-M-008 | LE20M187-M-008-A | JASCO | Pre-order technically cleared | 221 | awaiting offers from other vendors |  |  | 27.12.22 | 27.12.22 | 27.11.23 | 27.11.23 | [8 empty] | 28.11.23 | 20.12.23 | [8 empty] | 27.12.23 |  |  |  | karthiga@lntecc.com
Agar Malwa | Mechanical | DEWATERING PUMP | LE20M187-M-008 | LE20M187-M-008-B | JASCO | Awaiting pre-offer from vendor | 251 |  |  |  | 27.12.22 | 27.12.22 | 27.11.23
Agar Malwa | Mechanical | SURGE PROTECTION | LE20M187-M-009 | LE20M187-M-009-A | Jash | Awaiting pre-offer from vendor | 586 |  |  |  | 27.12.22 | 27.12.22 | [24 empty] | karthiga@lntecc.com
Agar Malwa | Mechanical | SURGE PROTECTION | LE20M187-M-009 | LE20M187-M-009-B | Sigma | Awaiting pre-offer from vendor | 586 |  |  |  | 27.12.22 | 27.12.22 | [24 empty] | karthiga@lntecc.com
Agar Malwa | Mechanical | SURGE PROTECTION | LE20M187-M-009 | LE20M187-M-009-C | Flownix | Awaiting pre-offer from vendor | 586 |  |  |  | 27.12.22 | 27.12.22 | [24 empty] | karthiga@lntecc.com
Agar Malwa | Mechanical | VENTILLATION | LE20M187-M-009 | LE20M187-M-010-A | POWER VENT SYSTEM | Pre-order technically cleared | 220 |  |  |  | 19.02.21 | 19.02.21 | 23.11.23 | 28.11.23 | [8 empty] | 13.12.23 | 23.12.23 | [8 empty] | 28.12.23 |  |  |  | karthiga@lntecc.com
Agar Malwa | Mechanical | ESR Flow Control Valve | LE20M187-M-1 | LE20M187-M-1-A | AVK | Awaiting pre-offer from vendor | 1262 |  |  |  | 19.02.21 | 19.02.21 | [24 empty] | karthiga@lntecc.com
Agar Malwa | Mechanical | ESR Flow Control Valve | LE20M187-M-1 | LE20M187-M-1-B | Dorot | Awaiting pre-offer from vendor | 1262 |  |  |  | 19.02.21 | 19.02.21 | [24 empty] | karthiga@lntecc.com
Agar Malwa | Mechanical | ESR Flow Control Valve | LE20M187-M-1 | LE20M187-M-1-C | Talis | Awaiting pre-offer from vendor | 1262 |  |  |  | 19.02.21 | 19.02.21 | [24 empty] | karthiga@lntecc.com
Agar Malwa | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M187-I-001 | LE20M187-I-001-A | AN instruments | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 20.01.23 | 09.02.23 | 12.02.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M187-I-001 | LE20M187-I-001-B | Hguru South | Approved by Client | PR Closed |  |  |  | 27.03.23 | 07.01.23 | 11.01.23 | 25.01.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T1 | 19.05.23 | Hguru South | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 |  |  | 18.07.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M187-I-001 | LE20M187-I-001-C | Measurecal | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 15.12.22 | 11.01.23 | 29.01.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M187-I-001 | LE20M187-I-001-D | SIAS | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 04.01.23 | 23.01.23 | 28.01.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Pressure Switch | LE20M187-I-002 | LE20M187-I-002-A | AN instruments | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 10.01.23 | 09.02.23 | 12.02.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Pressure Switch | LE20M187-I-002 | LE20M187-I-002-B | Hguru South | Approved by Client | PR Closed |  |  |  | 27.03.23 | 28.12.22 | 11.01.23 | 27.01.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T1 | 19.05.23 | Hguru South | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 |  |  | 18.07.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Pressure Switch | LE20M187-I-002 | LE20M187-I-002-C | Measurecal | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 12.12.22 | 11.01.23 | 11.01.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Pressure Switch | LE20M187-I-002 | LE20M187-I-002-D | SIAS | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 03.12.22 | 23.01.23 | 10.02.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Pressure transmitter | LE20M187-I-003 | LE20M187-I-003-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 16.03.23 | 07.12.22 | 14.12.22 | 14.12.22 | [8 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Pressure transmitter | LE20M187-I-003 | LE20M187-I-003-B | E&H | Approved by Client | PR Closed |  |  |  | 16.03.23 | 19.09.22 | 12.12.22 | 13.12.22 | [8 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T1 | 16.03.23 | E&H | 16.03.23 | 16.03.23 | 16.03.23 | 16.03.23 | 16.03.23 |  |  | 15.05.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Pressure transmitter | LE20M187-I-003 | LE20M187-I-003-C | Honeywell | Sent to BU Operations | PR Closed |  |  |  | 16.03.23 | 15.11.22 | 12.12.22 | 21.12.22 | [8 empty] | 28.12.22 | 28.12.22 | 28.12.22 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Float & Board Level gauge | LE20M187-I-004 | LE20M187-I-004-A | Pune Techtrol | Sent to BU Operations | PR Closed |  |  |  | 18.04.23 | 19.11.22 | 16.01.23 | 25.01.23 | [8 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Float & Board Level gauge | LE20M187-I-004 | LE20M187-I-004-B | SBEM | Approved by Client | PR Closed |  |  |  | 18.04.23 | 11.12.22 | 16.01.23 | 02.02.23 | [8 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T1 | 09.06.23 | SBEM | 09.06.23 | 09.06.23 | 09.06.23 | 09.06.23 | 09.06.23 |  |  | 08.08.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | level switch - Conductivity type | LE20M187-I-005 | LE20M187-I-005-A | Pune Techtrol | Sent to BU Operations | PR Closed |  |  |  | 18.04.23 | 28.12.22 | 16.01.23 | 23.01.23 | [8 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | level switch - Conductivity type | LE20M187-I-005 | LE20M187-I-005-B | SBEM | Approved by Client | PR Closed |  |  |  | 18.04.23 | 03.11.22 | 16.01.23 | 21.01.23 | [8 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T1 | 09.06.23 | SBEM | 09.06.23 | 09.06.23 | 09.06.23 | 09.06.23 | 09.06.23 |  |  | 08.08.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Ultrasonic level Transmitter | LE20M187-I-006 | LE20M187-I-006-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 28.12.22 | 07.02.23 | 12.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Ultrasonic level Transmitter | LE20M187-I-006 | LE20M187-I-006-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 18.08.22 | 02.01.23 | 18.01.23 | [8 empty] | 23.01.23 | 23.01.23 | 23.01.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Ultrasonic level Transmitter | LE20M187-I-006 | LE20M187-I-006-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 28.10.22 | 07.02.23 | 23.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Datasheet for Ultrasonic level Transmitter | LE20M187-I-006 | LE20M187-I-006-D | EiP Enviro | Approved by Client | PR Closed |  |  |  | 24.05.23 | 09.01.23 | 06.03.23 | 06.04.23 | [8 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EiP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Radar Level Transmitter | LE20M187-I-007 | LE20M187-I-007-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 28.01.23 | 07.02.23 | 27.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Radar Level Transmitter | LE20M187-I-007 | LE20M187-I-007-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 17.12.22 | 02.01.23 | 19.01.23 | [8 empty] | 23.01.23 | 23.01.23 | 23.01.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Radar Level Transmitter | LE20M187-I-007 | LE20M187-I-007-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 09.12.22 | 07.02.23 | 18.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Datasheet for Radar Level Transmitter | LE20M187-I-007 | LE20M187-I-007-D | EiP Enviro | Approved by Client | PR Closed |  |  |  | 24.05.23 | 22.02.23 | 06.03.23 | 07.04.23 | [8 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EiP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Loss of head transmitter | LE20M187-I-008 | LE20M187-I-008-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 16.03.23 | 27.09.22 | 14.12.22 | 14.12.22 | [8 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Loss of head transmitter | LE20M187-I-008 | LE20M187-I-008-B | E&H | Approved by Client | PR Closed |  |  |  | 16.03.23 | 11.09.22 | 12.12.22 | 13.12.22 | [8 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T1 | 16.03.23 | E&H | 16.03.23 | 16.03.23 | 16.03.23 | 16.03.23 | 16.03.23 |  |  | 15.05.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Loss of head transmitter | LE20M187-I-008 | LE20M187-I-008-C | Honeywell | Sent to BU Operations | PR Closed |  |  |  | 16.03.23 | 14.11.22 | 12.12.22 | 15.12.22 | [8 empty] | 28.12.22 | 28.12.22 | 28.12.22 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Rate for flow transmitter | LE20M187-I-009 | LE20M187-I-009-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 01.12.22 | 07.02.23 | 02.03.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Rate for flow transmitter | LE20M187-I-009 | LE20M187-I-009-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 01.09.22 | 02.01.23 | 15.01.23 | [8 empty] | 23.01.23 | 23.01.23 | 23.01.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Rate for flow transmitter | LE20M187-I-009 | LE20M187-I-009-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 10.11.22 | 07.02.23 | 08.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Datasheet for Rate for flow transmitter | LE20M187-I-009 | LE20M187-I-009-D | EiP Enviro | Approved by Client | PR Closed |  |  |  | 24.05.23 | 28.01.23 | 06.03.23 | 24.03.23 | [8 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EiP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Bypass Rotameter | LE20M187-I-010 | LE20M187-I-010-A | Eureka | Approved by Client | PR Closed |  |  |  | 13.02.23 | 08.02.23 | 10.02.23 | 12.02.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T2 | 11.02.24 | Eureka | 21.02.24 | 21.02.24 | 21.02.24 | 21.02.24 | 25.02.24 |  |  | 11.04.24 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Bypass Rotameter | LE20M187-I-010 | LE20M187-I-010-B | Scientific devices | Approved by Client | PR Closed |  |  |  | 13.02.23 | 07.02.23 | 10.02.23 | 12.02.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T1 | 11.02.24 | Scientific devices | 21.02.24 | 21.02.24 | 21.02.24 | 21.02.24 | 25.02.24 |  |  | 11.04.24 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Electromagnectic flow meter | LE20M187-I-011 | LE20M187-I-011-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 29.12.22 | 19.10.22 | 17.11.22 | 20.11.22 | [8 empty] | 02.12.22 | 02.12.22 | 02.12.22 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Electromagnectic flow meter | LE20M187-I-011 | LE20M187-I-011-B | Khrone | Approved by Client | PR Closed |  |  |  | 29.12.22 | 11.10.22 | 17.11.22 | 27.11.22 | [8 empty] | 02.12.22 | 02.12.22 | 02.12.22 | T1 | 03.11.23 | Khrone | 03.11.23 | 03.11.23 | 03.11.23 | 03.11.23 | 03.11.23 |  |  | 02.01.24 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Electromagnectic flow meter | LE20M187-I-011 | LE20M187-I-011-C | siemens | Sent to BU Operations | PR Closed |  |  |  | 29.12.22 | 12.10.22 | 17.11.22 | 24.11.22 | [8 empty] | 02.12.22 | 02.12.22 | 02.12.22 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Electromagnectic flow meter | LE20M187-I-011 | LE20M187-I-011-D | yokogawa | Sent to BU Operations | PR Closed |  |  |  | 29.12.22 | 28.10.22 | 17.11.22 | 22.11.22 | [8 empty] | 02.12.22 | 02.12.22 | 02.12.22 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M187-I-012 | LE20M187-I-012-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 08.11.22 | 07.02.23 | 11.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M187-I-012 | LE20M187-I-012-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 07.10.22 | 02.01.23 | 08.01.23 | [8 empty] | 23.01.23 | 23.01.23 | 23.01.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M187-I-012 | LE20M187-I-012-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 02.01.23 | 07.02.23 | 13.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Datasheet for Ultrasonic type Open channel flow transmitter | LE20M187-I-012 | LE20M187-I-012-D | EiP Enviro | Approved by Client | PR Closed |  |  |  | 24.05.23 | 08.01.23 | 06.03.23 | 01.04.23 | [8 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EiP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | VTC Flow meter | LE20M187-I-013 | LE20M187-I-013-A | Zenner | Approved by Client | PR Closed |  |  |  | 16.11.23 | 19.11.22 | 03.04.23 | 03.04.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T1 | 27.10.23 | Zenner | 27.10.23 | 02.11.23 | 17.11.23 | 23.11.23 | 23.11.23 |  |  | 26.12.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | VTC Flow meter | LE20M187-I-013 | LE20M187-I-013-B | Kranthi water meter | Sent to BU Operations | PR Closed |  |  |  | 16.11.23 | 18.01.23 | 03.04.23 | 03.04.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | pH Meter | LE20M187-I-014 | LE20M187-I-014-A | Emerson | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 23.09.23 | 25.09.23 | 30.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | pH Meter | LE20M187-I-014 | LE20M187-I-014-B | HACH | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 11.09.23 | 25.09.23 | 01.10.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | pH Meter | LE20M187-I-014 | LE20M187-I-014-C | ABB | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 04.09.23 | 25.09.23 | 29.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | pH Meter | LE20M187-I-014 | LE20M187-I-014-D | E&H | Approved by Client | PR Closed |  |  |  | 21.10.23 | 07.09.23 | 25.09.23 | 28.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T1 | 28.12.23 | E&H | 28.12.23 | 29.12.23 | 04.01.24 | 06.01.24 | 06.01.24 |  |  | 26.02.24 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Turbidity meter | LE20M187-I-015 | LE20M187-I-015-A | Emerson | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 21.09.23 | 25.09.23 | 30.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Turbidity meter | LE20M187-I-015 | LE20M187-I-015-B | HACH | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 09.09.23 | 25.09.23 | 29.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Turbidity meter | LE20M187-I-015 | LE20M187-I-015-C | ABB | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 15.09.23 | 25.09.23 | 25.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Turbidity meter | LE20M187-I-015 | LE20M187-I-015-D | E&H | Approved by Client | PR Closed |  |  |  | 21.10.23 | 04.09.23 | 25.09.23 | 26.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T1 | 28.12.23 | E&H | 28.12.23 | 29.12.23 | 04.01.24 | 06.01.24 | 06.01.24 |  |  | 26.02.24 | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Residual Chlorine Analyzer | LE20M187-I-016 | LE20M187-I-016-A | Emerson | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 14.09.23 | 25.09.23 | 26.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Residual Chlorine Analyzer | LE20M187-I-016 | LE20M187-I-016-B | HACH | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 31.08.23 | 25.09.23 | 26.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Residual Chlorine Analyzer | LE20M187-I-016 | LE20M187-I-016-C | ABB | Sent to BU Operations | PR Closed |  |  |  | 21.10.23 | 01.09.23 | 25.09.23 | 28.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:01
Agar Malwa | Instrumentation | Residual Chlorine Analyzer | LE20M187-I-016 | LE20M187-I-016-D | E&H | Approved by Client | PR Closed |  |  |  | 21.10.23 | 22.09.23 | 25.09.23 | 29.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T1 | 28.12.23 | E&H | 28.12.23 | 29.12.23 | 04.01.24 | 06.01.24 | 06.01.24 |  |  | 26.02.24 | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M187-I-017 | LE20M187-I-017-A | Autosys | Sent to BU Operations | PR Closed |  |  |  | 24.04.23 | 08.04.23 | 13.04.23 | 24.04.23 | [8 empty] | 24.08.23 | 24.08.23 | 24.08.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M187-I-017 | LE20M187-I-017-B | SIAS | Approved by Client | PR Closed |  |  |  | 24.04.23 | 07.03.23 | 16.03.23 | 24.04.23 | [8 empty] | 24.08.23 | 24.08.23 | 24.08.23 | T1 | 14.12.23 | SIAS | 14.12.23 | 15.12.23 | 20.12.23 | 05.01.24 | 05.01.24 |  |  | 12.02.24 | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M187-I-017 | LE20M187-I-017-C | COTMAC | Sent to BU Operations | PR Closed |  |  |  | 24.04.23 | 24.04.23 | 24.07.23 | 02.08.23 | [8 empty] | 25.08.23 | 25.08.23 | 25.08.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M187-I-017 | LE20M187-I-017-D | Mitsubishi | Sent to BU Operations | PR Closed |  |  |  | 24.04.23 | 10.04.23 | 13.04.23 | 24.04.23 | [8 empty] | 24.08.23 | 24.08.23 | 24.08.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M187-I-017 | LE20M187-I-017-E | Sai applied | Sent to BU Operations | PR Closed |  |  |  | 24.04.23 | 16.04.23 | 18.04.23 | 24.04.23 | [8 empty] | 24.08.23 | 24.08.23 | 24.08.23 | T5 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | instrumentation Control & signal Cables | LE20M187-I-018 | LE20M187-I-018-A | Axelon | Sent to BU Operations | PR Closed |  |  |  | 9.01.23 | 19.08.22 | 04.10.22 | 09.01.23 | [8 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | instrumentation Control & signal Cables | LE20M187-I-018 | LE20M187-I-018-B | Cords | Approved by Client | PR Closed |  |  |  | 9.01.23 | 30.07.22 | 04.10.22 | 09.01.23 | [8 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T1 | 16.03.23 | Cords | 16.03.23 | 22.04.23 | 10.10.23 | 16.03.24 | 16.03.24 |  |  | 15.05.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | instrumentation Control & signal Cables | LE20M187-I-018 | LE20M187-I-018-C | Delton | Sent to BU Operations | PR Closed |  |  |  | 9.01.23 | 11.07.22 | 04.10.22 | 09.01.23 | [8 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | instrumentation Control & signal Cables | LE20M187-I-018 | LE20M187-I-018-D | Thermo | Sent to BU Operations | PR Closed |  |  |  | 9.01.23 | 15.09.22 | 04.10.22 | 09.01.23 | [8 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | UPS | LE20M187-I-019 | LE20M187-I-019-A | Vertiv | Sent to BU Operations | PR Closed |  |  |  | 21.07.22 | 21.07.22 | 09.12.23 | 11.01.24 | [8 empty] | 11.01.24 | 11.01.24 | 11.01.24 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | UPS | LE20M187-I-019 | LE20M187-I-019-B | Hirel | Approved by Client | PR Closed |  |  |  | 21.07.22 | 21.07.22 | 09.12.23 | 16.12.23 | [8 empty] | 11.01.24 | 11.01.24 | 11.01.24 | T1 | 04.04.24 | Hirel | 04.04.24 | 04.04.24 | 04.04.24 | 04.04.24 | 04.04.24 |  |  | 03.06.24 | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | EPABX System | LE20M187-I-020 | LE20M187-I-020-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | EPABX System | LE20M187-I-020 | LE20M187-I-020-B | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | EPABX System | LE20M187-I-020 | LE20M187-I-020-C | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Instrumentation | Ultrasonic level transmitter | LE20M187-I-WS-WT-PR-5106 | LE20M187-I-WS-WT-PR-5106-D | EIP Enviro | Approved by Client | PR Closed |  |  |  | 24.05.23 | 24.05.23 | 19.06.23 | 20.06.23 | [8 empty] | 20.06.23 | 22.06.23 | 22.06.23 | T3 | 22.06.23 | EIP Enviro | 22.06.23 | 22.06.23 | 22.06.23 | 22.06.23 | 23.06.23 |  |  | 21.08.23 | SURENDHAR@lntecc.com-09.07.2024-14:29:02
Agar Malwa | Electrical | Transformer | LE20M187-E-001 | LE20M187-E-001-A | Vardhaman | Approved by Client | PR Closed |  |  |  | 18.10.22 | 18.10.22 | 31.12.22 | 23.01.23 | [8 empty] | 24.01.23 | 04.02.23 | 04.02.23 | T1 | 16.02.23 | Vardhaman | 25.05.23 | 17.06.23 | 23.06.23 | 26.06.23 | 26.06.23 |  |  | 17.04.23 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Transformer | LE20M187-E-001 | LE20M187-E-001-B | Uttam Bharat | Sent to BU Operations | PR Closed |  |  |  | 18.10.22 | 18.10.22 | 04.01.23 | 23.01.23 | [8 empty] | 30.01.23 | 06.02.23 | 06.02.23 | T1 | [10 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Transformer | LE20M187-E-001 | LE20M187-E-001-C | TBEA | Sent to BU Operations | PR Closed |  |  |  | 18.10.22 | 18.10.22 | 28.12.22 | 21.01.23 | [8 empty] | 24.01.23 | 07.02.23 | 07.02.23 | T1 | [10 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | LT Panel | LE20M187-E-002 | LE20M187-E-002-A | Universal | Sent to BU Operations | PR Closed |  |  |  | 1.11.22 | 01.11.22 | 27.12.22 | 30.12.22 | [8 empty] | 10.02.23 | 14.02.23 | 14.02.23 | T1 | [10 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | LT Panel | LE20M187-E-002 | LE20M187-E-002-B | BCH India | Sent to BU Operations | PR Closed |  |  |  | 1.11.22 | 01.11.22 | 27.12.22 | 31.12.22 | [8 empty] | 07.02.23 | 10.02.23 | 10.02.23 | T1 | [10 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | LT Panel | LE20M187-E-002 | LE20M187-E-002-C | SRCS | Approved by Client | PR Closed |  |  |  | 1.11.22 | 01.11.22 | 31.12.22 | 19.01.23 | [8 empty] | 08.02.23 | 11.02.23 | 11.02.23 | T1 | 21.02.23 | SRCS | 28.06.23 | 15.07.23 | 09.08.23 | 09.08.23 | 9.08.23 |  |  | 22.04.23 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | HT Panel | LE20M187-E-003 | LE20M187-E-003-A | HTS | Approved by Client | PR Closed |  |  |  | 4.11.22 | 04.11.22 | 27.12.22 | 30.12.22 | [8 empty] | 10.02.23 | 14.02.23 | 14.02.23 | T1 | 25.02.23 | HTS | 03.11.22 | 27.12.22 | 14.02.23 | 15.02.23 | 15.02.23 |  |  | 26.04.23 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | HT Panel | LE20M187-E-003 | LE20M187-E-003-B | Popular | Sent to BU Operations | PR Closed |  |  |  | 4.11.22 | 04.11.22 | 27.12.22 | 31.12.22 | [8 empty] | 07.02.23 | 10.02.23 | 10.02.23 | T1 | [10 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | HT Panel | LE20M187-E-003 | LE20M187-E-003-C | Universal | Sent to BU Operations | PR Closed |  |  |  | 4.11.22 | 04.11.22 | 31.12.22 | 19.01.23 | [8 empty] | 08.02.23 | 11.02.23 | 11.02.23 | T1 | [10 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Lighting Fixtures | LE20M187-E-004 | LE20M187-E-004-A | Bajaj | Approved by Client | PR Closed |  |  |  | 1.11.22 | 01.11.22 | 28.12.22 | 29.12.22 | [8 empty] | 01.01.23 | 05.01.23 | 06.01.23 | T1 | 13.02.23 | Bajaj | 17.06.23 | 04.08.23 | 11.08.23 | 11.08.23 | 11.8.23 |  |  | 14.04.23 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | LPBS & LDB | LE20M187-E-005 | LE20M187-E-005-A | Adaptive Engg | Approved by Client | PR Closed |  |  |  | 9.02.23 | 09.02.23 | 12.02.23 | 15.02.23 | [8 empty] | 16.02.23 | 16.02.23 | 16.02.23 | T1 | 12.08.23 | Adaptive Engg | 25.09.23 | 25.09.23 | 25.09.23 | 25.09.23 | 25.9.23 |  |  | 11.10.23 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | AAAC Conductor | LE20M187-E-006 | LE20M187-E-006-A | Mahavir Transmission | Approved by Client | PR Closed |  |  |  | 11.05.21 | 11.05.21 | 12.06.21 | 12.06.21 | [8 empty] | 15.06.21 | 15.06.21 | 17.06.21 | T1 | 08.07.21 | Mahavir Transmission | 27.01.23 | 27.01.23 | 27.01.23 | 27.01.23 | 27.1.23 |  |  | 06.09.21 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Control & Relay Panel | LE20M187-E-007 | LE20M187-E-007-A | Avana | Approved by Client | PR Closed |  |  |  | 24.11.22 | 24.11.22 | 22.12.22 | 25.12.22 | [8 empty] | 03.01.23 | 03.01.23 | 03.01.23 | T1 | 22.03.23 | Avana | 05.05.23 | 06.05.23 | 21.05.23 | 21.05.23 | 21.5.23 |  |  | 21.05.23 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | CT & PT | LE20M187-E-008 | LE20M187-E-008-A | Kalpa | Approved by Client | PR Closed |  |  |  | 24.11.22 | 24.11.22 | 22.12.22 | 25.12.22 | [8 empty] | 03.01.23 | 03.01.23 | 03.01.23 | T1 | 01.04.23 | Kalpa | 05.05.23 | 05.05.23 | 05.05.23 | 05.05.23 | 5.5.23 |  |  | 31.05.23 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Swicthyard Structures | LE20M187-E-009 | LE20M187-E-009-A | Topline | Approved by Client | PR Closed |  |  |  | 24.11.22 | 24.11.22 | 22.12.22 | 25.12.22 | [8 empty] | 03.01.23 | 03.01.23 | 03.01.23 | T1 | 26.06.23 | Topline | 01.07.23 | 18.07.23 | 02.08.23 | 02.08.23 | 2.8.23 |  |  | 25.08.23 | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | HT/ LT Power & Control Cables | LE20M187-E-010 | LE20M187-E-010-A | Purva | Pre-order pending with EDRC | 27 |  |  |  | 27.02.23 | 19.6.24 | 8.7.24 | [12 empty] | T1 | [10 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Cable Trays & Its accessories | LE20M187-E-011 | LE20M187-E-011-A | NIL | Awaiting pre-offer from vendor | 640 |  |  |  | 3.11.22 | 03.11.22 | [24 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Earthing & Lightning Materials | LE20M187-E-012 | LE20M187-E-012-A | NIL | Awaiting pre-offer from vendor | 642 |  |  |  | 1.11.22 | 01.11.22 | [24 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Galns & Lugs | LE20M187-E-013 | LE20M187-E-013-A | NIL | Awaiting pre-offer from vendor | 523 |  |  |  | 28.02.23 | 28.02.23 | [24 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Agar Malwa | Electrical | Safety Accessories | LE20M187-E-014 | LE20M187-E-014-A | NIL | Awaiting pre-offer from vendor | 573 |  |  |  | 9.01.23 | 09.01.23 | [24 empty] | karthik.ajithkumar@lntecc.com-10.07.2024-09:41:05
Amritsar | Process | Water Analysis Report | LE21M396-P-WS-WT-PR-2201 | LE21M396-P-WS-WT-PR-2201 | Noida testing laboratories | Regret offer | PR Closed | Site procurement |  |  |  | 12.02.21 | [24 empty] | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Solid Recirculation Clarifier | LE21M396-P-WS-WT-PR-2202 | LE21M396-P-WS-WT-PR-2202 | Triveni | Approved by Client | PR Closed |  |  |  |  | 19.03.22 | 27.10.22 | 05.11.22 | [8 empty] | 03.02.23 | 03.02.23 | 03.02.23 | Technically cleared | 13.06.23 | Triveni | 13.06.23 | 22.06.23 | 17.08.23 | 17.08.23 | 17.08.23 |  |  | 12.08.23 | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Air Blower | LE21M396-P-WS-WT-PR-2203 | LE21M396-P-WS-WT-PR-2203 | Kay | Approved by Client | PR Closed |  |  |  |  | 19.02.22 | 16.12.22 | 23.12.22 | [8 empty] | 22.02.23 | 22.02.23 | 22.02.23 | Technically Cleared | 05.04.23 | Kay | 05.04.23 | 06.04.23 | 26.04.23 | 26.04.23 | 26.04.23 |  |  | 04.06.23 | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Agitator | LE21M396-P-WS-WT-PR-2205 | LE21M396-P-WS-WT-PR-2205 | FFP | Approved by Client | PR Closed |  |  |  |  | 29.07.22 | 07.03.23 | 10.03.23 | [8 empty] | 20.10.23 | 20.10.23 | 30.10.23 | Technically cleared | 30.10.23 | FFP | 30.10.23 | 30.10.23 | 21.11.23 | 21.11.23 | 21.11.23 |  |  | 29.12.23 | kannan-p@lntecc.com-04.06.2024-15:38:15
Amritsar | Process | Sluice gates | LE21M396-P-WS-WT-PR-2206 | LE21M396-P-WS-WT-PR-2206 | Jash | Approved by Client | PR Closed |  |  |  |  | 24.11.22 | 19.01.23 | 21.01.23 | [8 empty] | 13.06.23 | 13.06.23 | 13.06.23 | Technically cleared | 13.06.23 | Jash | 14.07.23 | 27.07.23 | 09.08.23 | 09.08.23 | 09.08.23 |  |  | 12.08.23 | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Chlorination system | LE21M396-P-WS-WT-PR-2207 | LE21M396-P-WS-WT-PR-2207-A | Zion | Sent to BU Operations | 200 |  |  |  |  | 13.12.22 | 18.01.23 | 01.02.23 | [8 empty] | 17.01.24 | 17.01.24 | 17.01.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Chlorination system | LE21M396-P-WS-WT-PR-2207 | LE21M396-P-WS-WT-PR-2207-B | Metito | Sent to BU Operations | 199 |  |  |  |  | 13.12.22 | 11.04.23 | 18.04.23 | [8 empty] | 18.01.24 | 18.01.24 | 18.01.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Chlorination system | LE21M396-P-WS-WT-PR-2207 | LE21M396-P-WS-WT-PR-2207-C | CAPCO | Sent to BU Operations | 82 |  |  |  |  | 13.12.22 | 30.04.24 | 30.04.24 | [8 empty] | 14.05.24 | 14.05.24 | 14.05.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Chlorine Tonners | LE21M396-P-WS-WT-PR-2208 | LE21M396-P-WS-WT-PR-2208-A | Zion | Sent to BU Operations | 200 |  |  |  |  | 13.12.22 | 18.01.23 | 01.02.23 | [8 empty] | 17.01.24 | 17.01.24 | 17.01.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Chlorine Tonners | LE21M396-P-WS-WT-PR-2208 | LE21M396-P-WS-WT-PR-2208-B | Metito | Sent to BU Operations | 199 |  |  |  |  | 13.12.22 | 11.04.23 | 18.04.23 | [8 empty] | 18.01.24 | 18.01.24 | 18.01.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Chlorine Tonners | LE21M396-P-WS-WT-PR-2208 | LE21M396-P-WS-WT-PR-2208-C | CAPCO | Sent to BU Operations | 82 |  |  |  |  | 13.12.22 | 30.04.24 | 30.04.24 | [8 empty] | 14.05.24 | 14.05.24 | 14.05.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Sludge thickener | LE21M396-P-WS-WT-PR-2209 | LE21M396-P-WS-WT-PR-2209 | Triveni | Approved by Client | PR Closed |  |  |  |  | 29.03.22 | 27.10.22 | 05.10.22 | [8 empty] | 08.02.23 | 08.02.23 | 08.02.23 | Technically cleared | 31.10.23 | Triveni | 31.10.23 | 01.11.23 | 18.11.23 | 18.11.23 | 18.11.23 |  |  | 30.12.23 | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Filter media | LE21M396-P-WS-WT-PR-2210 | LE21M396-P-WS-WT-PR-2210 | Global adsorbents | Regret offer | PR Closed | Pre order cleared - Site procurement |  |  |  | 15.06.23 | [24 empty] | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Filter Nozzles | LE21M396-P-WS-WT-PR-2211 | LE21M396-P-WS-WT-PR-2211 | Guddi Plasticon | Approved by Client | PR Closed |  |  |  |  | 08.04.22 | 28.10.22 | 04.11.22 | [8 empty] | 02.12.22 | 02.12.22 | 02.12.22 | Technically cleared | 28.12.22 | Guddi Plasticon | 28.12.22 | 04.01.23 | 11.01.23 | 11.01.23 | 11.01.23 |  |  | 26.02.23 | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Centrifuge | LE21M396-P-WS-WT-PR-2212 | LE21M396-P-WS-WT-PR-2212 | Hiller | Approved by Client | PR Closed |  |  |  |  | 29.03.22 | 28.11.22 | 08.12.22 | [8 empty] | 01.03.23 | 01.03.23 | 01.03.23 | Technically cleared | 17.03.23 | Hiller | 17.03.23 | 17.03.23 | 10.05.23 | 10.05.23 | 10.05.23 |  |  | 16.05.23 | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Screw pump | LE21M396-P-WS-WT-PR-2213 | LE21M396-P-WS-WT-PR-2213 | CIRCOR | Approved by Client | PR Closed |  |  |  |  | 07.05.22 | 11.01.23 | 13.01.23 | [8 empty] | 01.04.23 | 01.04.23 | 01.04.23 | Technically cleared | 29.05.23 | CIRCOR | 29.05.23 | 29.05.23 | 15.07.23 | 15.07.23 | 15.07.23 |  |  | 28.07.23 | kannan-p@lntecc.com-04.06.2024-15:38:15
Amritsar | Process | Backwash pump | LE21M396-P-WS-WT-PR-2214 | LE21M396-P-WS-WT-PR-2214 | WILO | Approved by Client | PR Closed |  |  |  |  | 04.04.22 | 22.02.23 | 24.02.23 | [8 empty] | 06.03.23 | 06.03.23 | 06.03.23 | Technically cleared | 23.05.23 | WILO | 23.05.23 | 24.05.23 | 23.06.23 | 23.06.23 | 23.06.23 |  |  | 22.07.23 | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Submersible pump | LE21M396-P-WS-WT-PR-2215 | LE21M396-P-WS-WT-PR-2215 | Aqua pumps | Sent to BU Operations | 580 |  |  |  |  | 04.04.22 | 28.11.22 | 02.12.22 | [8 empty] | 02.01.23 | 02.01.23 | 02.01.23 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Electrical hoist | LE21M396-P-WS-WT-PR-2216 | LE21M396-P-WS-WT-PR-2216-A | Indef | Sent to BU Operations | 39 |  |  |  |  | 30.05.22 | 27.11.23 | 14.12.23 | 02.05.24 | 30.05.24 | [6 empty] | 25.06.24 | 26.06.24 | 26.06.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Electrical hoist | LE21M396-P-WS-WT-PR-2216 | LE21M396-P-WS-WT-PR-2216-B | Eddy | Pre-order comments issued | 68 |  |  |  |  | 30.05.22 | 21.05.24 | 28.05.24 | [19 empty] | 24.07.24 | 10.08.24 | 09.10.24 | kannan-p@lntecc.com-10.07.2024-15:50:23
Amritsar | Process | Crane | LE21M396-P-WS-WT-PR-2217 | LE21M396-P-WS-WT-PR-2217-A | Indef | Sent to BU Operations | 59 |  |  |  |  | 25.07.22 | 27.11.23 | 14.12.23 | 02.05.24 | 30.05.24 | [6 empty] | 06.06.24 | 06.06.24 | 06.06.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Crane | LE21M396-P-WS-WT-PR-2217 | LE21M396-P-WS-WT-PR-2217-B | Eddy | Pre-order comments issued | 68 |  |  |  |  | 25.07.22 | 21.05.24 | 28.05.24 | [19 empty] | 24.07.24 | 10.08.24 | 09.10.24 | kannan-p@lntecc.com-10.07.2024-15:50:23
Amritsar | Process | Manual chain pulley block | LE21M396-P-WS-WT-PR-2218 | LE21M396-P-WS-WT-PR-2218-A | Indef | Sent to BU Operations | 39 |  |  |  |  | 30.05.22 | 27.11.23 | 14.12.23 | 02.05.24 | 30.05.24 | [6 empty] | 25.06.24 | 26.06.24 | 26.06.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Manual chain pulley block | LE21M396-P-WS-WT-PR-2218 | LE21M396-P-WS-WT-PR-2218-B | Eddy | Pre-order comments issued | 68 |  |  |  |  | 30.05.22 | 21.05.24 | 28.05.24 | [19 empty] | 24.07.24 | 10.08.24 | 09.10.24 | kannan-p@lntecc.com-10.07.2024-15:50:23
Amritsar | Process | Dosing pump | LE21M396-P-WS-WT-PR-2219 | LE21M396-P-WS-WT-PR-2219 | Postive metering | Approved by Client | PR Closed |  |  |  |  | 07.05.22 | 26.12.22 | 28.12.22 | [8 empty] | 22.02.23 | 22.02.23 | 22.02.23 | Technically cleared | 22.02.23 | Postive metering | 07.04.23 | 10.04.23 | 09.05.23 | 09.05.23 | 09.05.23 |  |  | 23.04.23 | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Orifice plate | LE21M396-P-WS-WT-PR-2220 | LE21M396-P-WS-WT-PR-2220-A | General Instruments | Sent to BU Operations | 221 |  |  |  |  | 24.11.22 | 15.12.23 | 16.12.23 | [8 empty] | 27.12.23 | 27.12.23 | 27.12.23 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Orifice plate | LE21M396-P-WS-WT-PR-2220 | LE21M396-P-WS-WT-PR-2220-B | Scientific device | Sent to BU Operations | 67 |  |  |  |  | 24.11.22 | 03.03.24 | 04.03.24 | [8 empty] | 29.05.24 | 29.05.24 | 29.05.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Sampling pump | LE21M396-P-WS-WT-PR-2221 | LE21M396-P-WS-WT-PR-2221 | Johnson | Approved by Client | PR Closed |  |  |  |  | 25.07.22 | 09.02.24 | 09.02.24 | [8 empty] | 09.02.24 | 09.02.24 | 09.02.24 | Technically cleared | 09.02.24 | Johnson | 12.02.24 | 12.02.24 | 11.03.24 | 11.03.24 | 11.03.24 |  |  | 09.04.24 | kannan-p@lntecc.com-04.06.2024-15:38:16
Amritsar | Process | Submersible mixer | LE21M396-P-WS-WT-PR-2222 | LE21M396-P-WS-WT-PR-2222 | FFP | Approved by Client | PR Closed |  |  |  |  | 07.05.22 | 27.02.23 | 27.02.23 | [8 empty] | 19.04.23 | 19.04.23 | 19.04.23 | Technically cleared | 26.06.23 | FFP | 26.06.23 | 26.06.23 | 21.11.23 | 21.11.23 | 21.11.23 |  |  | 25.08.23 | kannan-p@lntecc.com-04.06.2024-15:39:56
Amritsar | Process | Dewatering pump | LE21M396-P-WS-WT-PR-2223 | LE21M396-P-WS-WT-PR-2223 | Aqua pumps | Sent to BU Operations | 132 |  |  |  |  | 25.07.22 | 11.01.24 | 12.01.24 | [8 empty] | 25.03.24 | 25.03.24 | 25.03.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | Dissolving tray | LE21M396-P-WS-WT-PR-2224 | LE21M396-P-WS-WT-PR-2224 | site procurement | Regret offer | PR Closed | Site procurement |  |  |  | 08.04.22 | [24 empty] | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Trolley | LE21M396-P-WS-WT-PR-2225 | LE21M396-P-WS-WT-PR-2225 | site procurement | Regret offer | PR Closed | Site procurement |  |  |  | 08.04.22 | [24 empty] | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Platform weighing machine | LE21M396-P-WS-WT-PR-2226 | LE21M396-P-WS-WT-PR-2226 | site procurement | Regret offer | PR Closed | Site procurement |  |  |  | 19.03.22 | [24 empty] | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Exhaust fan | LE21M396-P-WS-WT-PR-2227 | LE21M396-P-WS-WT-PR-2227 | site procurement | Regret offer | PR Closed | Site Procurement |  |  |  | 25.07.22 | [24 empty] | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Lab equipment | LE21M396-P-WS-WT-PR-2228 | LE21M396-P-WS-WT-PR-2228 | site procurement | Regret offer | PR Closed | Site procurement |  |  |  | 29.03.22 | [24 empty] | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | Service water pump | LE21M396-P-WS-WT-PR-2229 | LE21M396-P-WS-WT-PR-2229 | Kirloskar | Regret offer | PR Closed | Site procurement |  |  |  | 29.07.22 | [24 empty] | kannan-p@lntecc.com-04.06.2024-15:36:10
Amritsar | Process | GAC | LE21M396-P-WS-WT-PR-2230 | LE21M396-P-WS-WT-PR-2230-A | Ion Asia | Sent to BU Operations | 141 |  |  |  |  | 15.06.23 | 10.10.23 | 17.11.23 | [8 empty] | 16.03.24 | 16.03.24 | 16.03.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:49:22
Amritsar | Process | GAC | LE21M396-P-WS-WT-PR-2230 | LE21M396-P-WS-WT-PR-2230-B | Calgon | Sent to BU Operations | 141 |  |  |  |  | 15.06.23 | 06.11.23 | 07.11.23 | [8 empty] | 16.03.24 | 16.03.24 | 16.03.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:53:02
Amritsar | Process | GAC | LE21M396-P-WS-WT-PR-2230 | LE21M396-P-WS-WT-PR-2230-C | Global adsorbents | Sent to BU Operations | 141 |  |  |  |  | 15.06.23 | 12.12.23 | 19.12.23 | [8 empty] | 16.03.24 | 16.03.24 | 16.03.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:57:15
Amritsar | Process | GAC | LE21M396-P-WS-WT-PR-2230 | LE21M396-P-WS-WT-PR-2230-D | Liqutech | Sent to BU Operations | 141 |  |  |  |  | 15.06.23 | 19.01.24 | 19.01.24 | [8 empty] | 16.03.24 | 16.03.24 | 16.03.24 | Technically cleared | [10 empty] | kannan-p@lntecc.com-10.07.2024-15:57:15
Amritsar | Mechanical | Sluice Gate | LE21M396-M-WS-CW-PR-1506 | LE21M396-M-WS-CW-PR-1506-A | Jash | Post-order technically cleared | 192 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 09.12.23 | 09.12.23 | [8 empty] | 09.12.23 | 09.12.23 | 09.12.23 | T1 | 25.01.24 | Jash | 25.01.24 | 25.01.24 | 25.01.24 | 25.01.24 |  | 09.12.23 | 26.12.23 | 24.02.24 | svcn@lntecc.com-03.07.2024-15:19:12
Amritsar | Mechanical | MS Flanges | LE21M396-M-WS-CW-PR-1510 | LE21M396-M-WS-CW-PR-1510-A | Rajan Metal Fabricators | Pre-order comments issued | 33 |  | SHUBHAM VIJAY MALI | shubham.mali@lntecc.com |  | 20.05.24 | 29.05.24 | 05.06.24 | 25.06.24 | 02.07.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:19:47
Amritsar | Mechanical | OHT Valves | LE21M396-M-WS-PR-DC-1510 | LE21M396-M-WS-PR-DC-1510-A | AVK | Pre-order comments issued | 226 |  |  |  |  | 18.12.23 | 21.12.23 | 22.12.23 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:19:47
Amritsar | Mechanical | OHT Valves | LE21M396-M-WS-PR-DC-1510 | LE21M396-M-WS-PR-DC-1510-B | KBL | Sent to BU Operations | 117 |  |  |  |  | 18.12.23 | 18.01.24 | 18.01.24 | 09.04.24 | 09.04.24 | [6 empty] | 09.04.24 | 09.04.24 | 09.04.24 | T1 | [7 empty] | 09.04.24 | 26.04.24 | 25.06.24 | svcn@lntecc.com-03.07.2024-15:19:12
Amritsar | Mechanical | Pumphouse Valves | LE21M396-M-WS-PR-DC-1501 | LE21M396-M-WS-RW-PR-1501-A | AVK | Pre-order comments issued | 515 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 08.03.23 | 08.03.23 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:19:47
Amritsar | Mechanical | Pumphouse Valves | LE21M396-M-WS-PR-DC-1501 | LE21M396-M-WS-RW-PR-1501-B | VAG | Pre-order comments issued | 401 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 30.06.23 | 30.06.23 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:19:47
Amritsar | Mechanical | Pumphouse Valves | LE21M396-M-WS-PR-DC-1501 | LE21M396-M-WS-RW-PR-1501-C | IVC | Pre-order comments issued | 138 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 12.03.23 | 12.03.23 | 19.03.24 | 19.03.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:19:47
Amritsar | Mechanical | Pumphouse Valves | LE21M396-M-WS-PR-DC-1501 | LE21M396-M-WS-RW-PR-1501-D | Magwen | Pre-order technically cleared | 88 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 04.05.24 | 04.05.24 | [8 empty] | 08.05.24 | 08.05.24 | 08.05.24 | T1 | [7 empty] | 08.05.24 | 25.05.24 | 24.07.24 | svcn@lntecc.com-03.07.2024-15:19:12
Amritsar | Mechanical | Pumphouse Valves | LE21M396-M-WS-PR-DC-1501 | LE21M396-M-WS-RW-PR-1501-E | KBL | Pre-order technically cleared | 275 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 15.03.23 | 15.03.23 | 03.11.23 | 03.11.23 | [6 empty] | 03.11.23 | 03.11.23 | 03.11.23 | T1 | [7 empty] | 03.11.23 | 20.11.23 | 19.01.24 | svcn@lntecc.com-03.07.2024-15:19:12
Amritsar | Mechanical | HSC Pumps | LE21M396-M-WS-RW-PR-1503 | LE21M396-M-WS-RW-PR-1503-A | Willo | Post-order technically cleared | 76 |  |  | manikkandan.pr@wilo.com |  | 17.01.23 | 30.01.23 | 03.02.23 | [8 empty] | 20.05.24 | 20.05.24 | 20.05.24 | T1 | 20.05.24 | Willo | 20.05.24 | 20.05.24 | 20.05.24 | 20.05.24 |  | 20.05.24 | 06.06.24 | 19.07.24 | svcn@lntecc.com-03.07.2024-15:19:12
Amritsar | Mechanical | EOT Cranes | LE21M396-M-WS-RW-PR-1504 | LE21M396-M-WS-RW-PR-1504-A | Bradys | Pre-order comments issued | 227 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 04.02.23 | 04.02.23 | 21.12.23 | 21.12.23 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:19:47
Amritsar | Mechanical | EOT Cranes | LE21M396-M-WS-RW-PR-1504 | LE21M396-M-WS-RW-PR-1504-B | INDEF | Awaiting pre-offer from vendor | 94 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 02.05.24 | 02.05.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:19:47
Amritsar | Mechanical | EOT Cranes | LE21M396-M-WS-RW-PR-1504 | LE21M396-M-WS-RW-PR-1504-C | JAPS | Pre-order comments issued | 536 |  |  | soma.reddy@lntecc.com |  | 17.01.23 | 08.02.23 | 15.02.23 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:19:47
Amritsar | Mechanical | HSC Pumps | LE21M396-M-WS-RW-PR-1507 | LE21M396-M-WS-RW-PR-1507-A | Willo | Post-order technically cleared | 76 |  |  | manikkandan.pr@wilo.com |  | 17.01.23 | 30.01.23 | 03.02.23 | [8 empty] | 20.05.24 | 20.05.24 | 20.05.24 | T1 | 20.05.24 | Willo | 20.05.24 | 20.05.24 | 20.05.24 | 20.05.24 |  | 20.05.24 | 06.06.24 | 19.07.24 | svcn@lntecc.com-03.07.2024-15:19:12
Amritsar | Mechanical | Pipeline Valves | LE21M396-M-WS-PR-DC-1508 | LE21M396-M-WS-RW-PR-1508-A | VAG | Post-order technically cleared | 534 |  |  |  |  | 18.01.23 | 04.02.23 | 04.02.23 | [8 empty] | 04.02.23 | 04.02.23 | 04.02.23 | T1 | 17.02.23 | VAG | 17.02.23 | 17.02.23 | 17.02.23 | 17.02.23 |  | 04.02.23 | 21.02.23 | 18.04.23 | svcn@lntecc.com-03.07.2024-15:19:12
Amritsar | Mechanical | Pipeline Valves | LE21M396-M-WS-PR-DC-1508 | LE21M396-M-WS-RW-PR-1508-B | AVK | Sent to BU Operations | PR Closed |  |  |  |  | 18.01.23 | 09.02.23 | 09.02.23 | [8 empty] | 09.02.23 | 09.02.23 | 09.02.23 | T1 | [7 empty] | 09.02.23 | 26.02.23 | 27.04.23 | svcn@lntecc.com-03.07.2024-15:19:12
Amritsar | Mechanical | Pipeline Valves | LE21M396-M-WS-PR-DC-1508 | LE21M396-M-WS-RW-PR-1508-C | KBL | Post-order technically cleared | 534 |  |  |  |  | 18.01.23 | 10.02.23 | 10.02.23 | [8 empty] | 10.02.23 | 10.02.23 | 10.02.23 | T1 | 17.02.23 | KBL | 17.02.23 | 17.02.23 | 17.02.23 | 17.02.23 |  | 10.02.23 | 27.02.23 | 18.04.23 | svcn@lntecc.com-03.07.2024-15:19:13
Amritsar | Instrumentation | Instrumentation cable | LE21M396-I-WS-PR-CA-5516 | LE21M396-I-WS-PR-CA-5516-A | KEI | Sent to BU Operations | 24 |  | 9355907234 | yogeshwaran.n@kei-ind.com |  | 26.06.24 | 28.06.24 | 11.07.24 | [8 empty] | 11.07.24 | 11.07.24 | 11.07.24 | T1 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Instrumentation Control & signal Cables | LE21M396-I-WS-PR-CA-5516 | LE21M396-I-WS-PR-CA-5516-B | Cords cable | Enquiry yet to float | NA |  | 9849487072 | jus@cordscable.com | [23 empty] | 07.08.24 | 24.08.24 | 23.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | Instrumentation Control & signal Cables | LE21M396-I-WS-PR-CA-5516 | LE21M396-I-WS-PR-CA-5516-C | Thermo cable | Enquiry yet to float | NA |  | 9840038225 | balaji@thermocables.com | [23 empty] | 07.08.24 | 24.08.24 | 23.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | Float & Board Level gauge | LE21M396-I-WS-PR-FB-5503 | LE21M396-I-WS-PR-FB-5503-A | SBEM | Sent to BU Operations | 72 |  | 8681898929 | rajesh.p@sbem.co.in |  | 09.04.24 | 15.05.24 | 17.04.24 | [8 empty] | 24.05.24 | 24.05.24 | 24.05.24 | T1 | [7 empty] | 07.08.24 | 24.08.24 | 23.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:51:48
Amritsar | Instrumentation | Float & Board Level gauge | LE21M396-I-WS-PR-FB-5503 | LE21M396-I-WS-PR-FB-5503-B | Pune Techtrol | Enquiry yet to float | NA |  | 9445565336 | sales.techtrol@measurecon.co.in | [23 empty] | 07.08.24 | 24.08.24 | 23.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | Electromagnectic flow meter | LE21M396-I-WS-PR-FM-5500 | LE21M396-I-WS-PR-FM-5500-A | SBEM | Sent to BU Operations | PR Closed |  | NA | NA |  | 17.05.23 | 24.05.23 | 19.06.23 | [8 empty] | 29.06.23 | 29.06.23 | 29.06.23 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Electromagnetic Flowmeter | LE21M396-I-WS-PR-FM-5500 | LE21M396-I-WS-PR-FM-5500-B | Khrone | Post-order technically cleared | 37 | Awaiting for Client clearance for POD | NA | NA |  | 04.02.23 | 07.02.23 | 09.02.23 | [8 empty] | 22.02.23 | 22.02.23 | 22.02.23 | T1 | 23.01.24 | Khrone | 19.01.24 | 23.01.24 | 23.01.24 | 28.06.24 |  |  |  | 23.03.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Electromagnetic Flowmeter | LE21M396-I-WS-PR-FM-5500 | LE21M396-I-WS-PR-FM-5500-C | Yokogawa | Post-order technically cleared | 24 | Awaiting for Client clearance for POD |  | b.mohan@yokogawa.com |  | 04.02.23 | 07.02.23 | 09.02.23 | [8 empty] | 22.02.23 | 22.02.23 | 22.02.23 | T3 | 23.01.24 | Yokogawa | 19.01.24 | 23.01.24 | 23.01.24 | 11.07.24 |  |  |  | 23.03.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Loss of Head Transmitter | LE21M396-I-WS-PR-LH-5506 | LE21M396-I-WS-PR-LH-5506-A | E&H | Sent to BU Operations | PR Closed |  | 97909 52907 | hari.narayan@endress.com |  | 28.04.23 | 06.06.23 | 09.06.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Loss of Head Transmitter | LE21M396-I-WS-PR-LH-5506 | LE21M396-I-WS-PR-LH-5506-B | Siemens | Post-order comments issued | 26 | Awaiting for Client approval, Vendor to provide compliance to client comments | NA | keerthi.guruswamy.ext@siemens.com |  | 28.04.23 | 10.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T1 | 18.04.23 | Siemens | 04.04.23 | 09.07.24 | 09.07.24 |  |  | 31.07.24 | 17.08.24 | 17.06.23 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Loss of Head Transmitter | LE21M396-I-WS-PR-LH-5506 | LE21M396-I-WS-PR-LH-5506-C | ABB | Sent to BU Operations | PR Closed |  | 99667 75348 | krishna.kishore@in.abb.com |  | 28.04.23 | 04.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Conductivity type Level Switch | LE21M396-I-WS-PR-LS-5503 | LE21M396-I-WS-PR-LS-5503-A | SBEM | Sent to BU Operations | 72 |  | 8681898929 | rajesh.p@sbem.co.in |  | 09.04.24 | 15.05.24 | 17.04.24 | [8 empty] | 24.05.24 | 24.05.24 | 24.05.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Conductivity type Level Switch | LE21M396-I-WS-PR-LS-5503 | LE21M396-I-WS-PR-LS-5503-B | Pune Techtrol | Enquiry yet to float | NA |  | 9445565336 | sales.techtrol@measurecon.co.in | [23 empty] | 21.08.24 | 07.09.24 | 06.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | Turbidity Analyzer | LE21M396-I-WS-PR-NT-5513 | LE21M396-I-WS-PR-NT-5513-A | HACH | Sent to BU Operations | 145 |  | 81236 00656 | mohanraj.elumalai@hach.com |  | 15.12.23 | 13.02.24 | 21.02.24 | [8 empty] | 12.03.24 | 12.03.24 | 12.03.24 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | Turbidity Analyzer | LE21M396-I-WS-PR-NT-5513 | LE21M396-I-WS-PR-NT-5513-B | E&H | Sent to BU Operations | 200 |  | 97909 52907 | hari.narayan@endress.com |  | 15.12.23 | 12.01.24 | 17.01.24 | [8 empty] | 17.01.24 | 17.01.24 | 17.01.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | Turbidity Analyzer | LE21M396-I-WS-PR-NT-5513 | LE21M396-I-WS-PR-NT-5513-C | ABB | Sent to BU Operations | 185 |  | 99667 75348 | krishna.kishore@in.abb.com |  | 15.12.23 | 12.01.24 | 24.01.24 | [8 empty] | 01.02.24 | 01.02.24 | 01.02.24 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M396-I-WS-PR-PC-5519 | LE21M396-I-WS-PR-PC-5519-A | Schneider | Sent to BU Operations | 97 |  | 97009 53031 | rushyendhar.repalli@se.com |  | 14.02.24 | 21.02.24 | 23.02.24 | [8 empty] | 29.04.24 | 29.04.24 | 29.04.24 | T1 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M396-I-WS-PR-PC-5519 | LE21M396-I-WS-PR-PC-5519-B | SIAS | Enquiry yet to float | NA |  | 8012468923 | nandhinik@sias.in | [23 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M396-I-WS-PR-PC-5519 | LE21M396-I-WS-PR-PC-5519-C | SAT | Sent to BU Operations | 117 |  | 7698007206 | meet.makwana@saiapplied.com |  | 14.02.24 | 26.03.24 | 01.04.24 | [8 empty] | 09.04.24 | 09.04.24 | 09.04.24 | T2 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M396-I-WS-PR-PC-5519 | LE21M396-I-WS-PR-PC-5519-D | ICAM | Sent to BU Operations | 159 | Conditional Clearance provided, Awaiting for Finalized Pre-offer. | 9838777959 | isales2@icamsystems.com |  | 02.02.24 | 07.02.24 | 09.02.24 | 13.02.24 | 15.02.24 | 15.02.24 | 27.02.24 |  |  |  |  | 27.02.24 | 27.02.24 | 27.02.24 | T3 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M396-I-WS-PR-PC-5519 | LE21M396-I-WS-PR-PC-5519-E | Autosys | Enquiry yet to float | NA |  | NA | mgrengg@autosysindia.in | [23 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE21M396-I-WS-PR-PG-5501 | LE21M396-I-WS-PR-PG-5501-A | HGuru | Pre-order comments issued | 58 |  | 80233 70300 | info@hgurusouth.com |  | 09.04.24 | 10.04.24 | 07.06.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | pH Meter | LE21M396-I-WS-PR-PH-5512 | LE21M396-I-WS-PR-PH-5512-A | HACH | Sent to BU Operations | 145 |  | 81236 00656 | mohanraj.elumalai@hach.com |  | 15.12.23 | 13.02.24 | 21.02.24 | [8 empty] | 12.03.24 | 12.03.24 | 12.03.24 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | pH Meter | LE21M396-I-WS-PR-PH-5512 | LE21M396-I-WS-PR-PH-5512-B | E&H | Sent to BU Operations | 200 |  | 97909 52907 | hari.narayan@endress.com |  | 15.12.23 | 12.01.24 | 17.01.24 | [8 empty] | 17.01.24 | 17.01.24 | 17.01.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | pH Meter | LE21M396-I-WS-PR-PH-5512 | LE21M396-I-WS-PR-PH-5512-C | ABB | Sent to BU Operations | 185 |  | 99667 75348 | krishna.kishore@in.abb.com |  | 15.12.23 | 12.01.24 | 24.01.24 | [8 empty] | 01.02.24 | 01.02.24 | 01.02.24 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | Pressure Transmitter | LE21M396-I-WS-PR-PT-5502 | LE21M396-I-WS-PR-PT-5502-A | E&H | Sent to BU Operations | PR Closed |  | 97909 52907 | hari.narayan@endress.com |  | 28.04.23 | 06.06.23 | 09.06.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Pressure Transmitter | LE21M396-I-WS-PR-PT-5502 | LE21M396-I-WS-PR-PT-5502-B | Siemens | Post-order comments issued | 26 | Awaiting for Client approval | NA | keerthi.guruswamy.ext@siemens.com |  | 28.04.23 | 10.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T1 | 18.04.23 | Siemens | 04.04.23 | 09.07.24 | 09.07.24 |  |  | 17.07.24 | 03.08.24 | 17.06.23 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Pressure Transmitter | LE21M396-I-WS-PR-PT-5502 | LE21M396-I-WS-PR-PT-5502-C | ABB | Sent to BU Operations | PR Closed |  | 99667 75348 | krishna.kishore@in.abb.com |  | 28.04.23 | 04.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Residual Chlorine analyzer | LE21M396-I-WS-PR-RC-5514 | LE21M396-I-WS-PR-RC-5514-A | HACH | Sent to BU Operations | 145 |  | 81236 00656 | mohanraj.elumalai@hach.com |  | 15.12.23 | 13.02.24 | 21.02.24 | [8 empty] | 12.03.24 | 12.03.24 | 12.03.24 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | Residual Chlorine analyzer | LE21M396-I-WS-PR-RC-5514 | LE21M396-I-WS-PR-RC-5514-B | E&H | Sent to BU Operations | 200 |  | 97909 52907 | hari.narayan@endress.com |  | 15.12.23 | 12.01.24 | 17.01.24 | [8 empty] | 17.01.24 | 17.01.24 | 17.01.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | Residual Chlorine analyzer | LE21M396-I-WS-PR-RC-5514 | LE21M396-I-WS-PR-RC-5514-C | ABB | Sent to BU Operations | 185 |  | 99667 75348 | krishna.kishore@in.abb.com |  | 15.12.23 | 12.01.24 | 24.01.24 | [8 empty] | 01.02.24 | 01.02.24 | 01.02.24 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:42:54
Amritsar | Instrumentation | Rate Of Flow Transmitter | LE21M396-I-WS-PR-RF-5507 | LE21M396-I-WS-PR-RF-5507-A | E&H | Sent to BU Operations | PR Closed |  | 97909 52907 | hari.narayan@endress.com |  | 28.04.23 | 06.06.23 | 09.06.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Rate Of Flow Transmitter | LE21M396-I-WS-PR-RF-5507 | LE21M396-I-WS-PR-RF-5507-B | Siemens | Post-order comments issued | 26 | Awaiting for Client approval | NA | keerthi.guruswamy.ext@siemens.com |  | 28.04.23 | 10.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T1 | 18.04.23 | Siemens | 04.04.23 | 09.07.24 | 09.07.24 |  |  | 17.07.24 | 03.08.24 | 17.06.23 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Rate Of Flow Transmitter | LE21M396-I-WS-PR-RF-5507 | LE21M396-I-WS-PR-RF-5507-C | ABB | Sent to BU Operations | PR Closed |  | 99667 75348 | krishna.kishore@in.abb.com |  | 28.04.23 | 04.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Bypass Rotameter | LE21M396-I-WS-PR-RM-5509 | LE21M396-I-WS-PR-RM-5509 -A | Eureka | Enquiry yet to float | NA |  | 63795 45974 | chennaioffice@eurekaflow.com | [23 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | Bypass Rotameter | LE21M396-I-WS-PR-RM-5509 | LE21M396-I-WS-PR-RM-5509 -B | Scientific Devices | Sent to BU Operations | 19 |  | 80971 39097 | info@scientificdevices.org |  | 12.07.24 | 15.07.24 | 16.07.24 | [8 empty] | 16.07.24 | 16.07.24 | 16.07.24 | T2 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-16.07.2024-11:12:31
Amritsar | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M396-I-WS-PR-UM-5510 | LE21M396-I-WS-PR-UM-5510-A | E&H | Sent to BU Operations | PR Closed |  | 97909 52907 | hari.narayan@endress.com |  | 28.04.23 | 06.06.23 | 09.06.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M396-I-WS-PR-UM-5510 | LE21M396-I-WS-PR-UM-5510-B | Siemens | Post-order comments issued | 26 | Awaiting for Client approval | NA | keerthi.guruswamy.ext@siemens.com |  | 28.04.23 | 10.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T1 | 18.04.23 | Siemens | 04.04.23 | 09.07.24 | 09.07.24 |  |  | 17.07.24 | 03.08.24 | 17.06.23 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M396-I-WS-PR-UM-5510 | LE21M396-I-WS-PR-UM-5510-C | ABB | Sent to BU Operations | PR Closed |  | 99667 75348 | krishna.kishore@in.abb.com |  | 28.04.23 | 04.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | UPS | LE21M396-I-WS-PR-UP-5518 | LE21M396-I-WS-PR-UP-5518-A | Vertiv | Enquiry yet to float | NA |  | 9841974315 | K.Shivakumar@vertiv.com | [23 empty] | 03.09.24 | 20.09.24 | 19.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | UPS | LE21M396-I-WS-PR-UP-5518 | LE21M396-I-WS-PR-UP-5518-B | Hitachi Hirel | Enquiry yet to float | NA |  | 9789979384 | b_ramasamy@hitachi-hirel.com | [23 empty] | 03.09.24 | 20.09.24 | 19.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:22:27
Amritsar | Instrumentation | Ultrasonic level transmitter | LE21M396-I-WS-PR-UT-5505 | LE21M396-I-WS-PR-UT-5505-A | E&H | Sent to BU Operations | PR Closed |  | 97909 52907 | hari.narayan@endress.com |  | 28.04.23 | 06.06.23 | 09.06.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Instrumentation | Ultrasonic level transmitter | LE21M396-I-WS-PR-UT-5505 | LE21M396-I-WS-PR-UT-5505-B | Siemens | Post-order comments issued | 26 | Awaiting for Client approval | NA | keerthi.guruswamy.ext@siemens.com |  | 28.04.23 | 10.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T1 | 18.04.23 | Siemens | 04.04.23 | 09.07.24 | 09.07.24 |  |  | 17.07.24 | 03.08.24 | 17.06.23 | sooryaprakash.t@lntecc.com-11.07.2024-11:50:31
Amritsar | Instrumentation | Ultrasonic level transmitter | LE21M396-I-WS-PR-UT-5505 | LE21M396-I-WS-PR-UT-5505-C | ABB | Sent to BU Operations | PR Closed |  | 99667 75348 | krishna.kishore@in.abb.com |  | 28.04.23 | 04.05.23 | 12.05.23 | [8 empty] | 20.07.23 | 20.07.23 | 20.07.23 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:20:22
Amritsar | Electrical | Transformer | LE21M396-E-WS-WT-PR-4102 | LE21M396-E-WS-WT-PR-4102-A | Crompton Greaves | Awaiting pre-offer from vendor | 117 |  | Vignesh | vignesh.srinivasan@cgglobal.com |  | 09.04.24 | [21 empty] | 31.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | Transformer | LE21M396-E-WS-WT-PR-4102 | LE21M396-E-WS-WT-PR-4102-B | Voltamp | Pre-order comments issued | 29 |  | SASI CHN | sasik_vtlchn@voltamptransformers.com |  | 16.03.24 | 25.03.24 | 05.04.24 | 08.04.24 | 08.05.24 | 18.05.24 | 23.05.24 | 15.06.24 | 06.07.24 | [13 empty] | 26.07.24 | 12.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | Diesel Generator | LE21M396-E-WS-WT-PR-4103 | LE21M396-E-WS-WT-PR-4103-A | Caterpillar | Pre-order comments issued | 138 |  | Aftab Ali | aftab.ali@gainwellindia.com |  | 20.01.24 | 20.01.24 | 03.02.24 | 29.02.24 | 19.03.24 | [17 empty] | 31.07.24 | 17.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | Diesel Generator | LE21M396-E-WS-WT-PR-4103 | LE21M396-E-WS-WT-PR-4103-B | Sudhir Power | Pre-order comments issued | 162 |  | Devesh Singh | deveshsingh@sudhirpower.com |  | 22.01.24 | 13.02.24 | 24.01.24 | 09.02.24 | 24.02.24 | [17 empty] | 31.07.24 | 17.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | HT Switchgear | LE21M396-E-WS-WT-PR-4104 | LE21M396-E-WS-WT-PR-4104-A | Universal | Sent to BU Operations | 23 |  | Deepak Muthu | deepak@upe.co.in |  | 02.03.24 | 04.04.24 | 31.05.24 | 18.06.24 | 06.07.24 | 12.07.24 | 12.07.24 |  |  |  |  | 12.07.24 | 12.07.24 | 12.07.24 | T1 | [7 empty] | 29.07.24 | 15.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:43:34
Amritsar | Electrical | HT Switchgear | LE21M396-E-WS-WT-PR-4104 | LE21M396-E-WS-WT-PR-4104-B | Coronet | Pre-order comments issued | 32 |  | Lakshman singh | laxman@coronet.in |  | 27.05.24 | 13.06.24 | 03.07.24 | [19 empty] | 29.07.24 | 15.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | HT Capacitor | LE21M396-E-WS-WT-PR-4105 | LE21M396-E-WS-WT-PR-4105-A | EPCOS Lecon | Pre-order comments issued | 86 |  | Ashok | ashok.c@tdk-electronics.tdk.com |  | 20.03.24 | 12.04.24 | 10.05.24 | [19 empty] | 25.07.24 | 11.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | HT Capacitor | LE21M396-E-WS-WT-PR-4105 | LE21M396-E-WS-WT-PR-4105-B | CG | Pre-order comments issued | 86 |  | Sivakumar | sivakumar.prakasam@cgglobal.com |  | 20.12.23 | 10.01.24 | 07.02.24 | 22.02.24 | 24.02.24 | 01.03.24 | 06.03.24 | 08.04.24 | 10.05.24 | [13 empty] | 25.07.24 | 11.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | HT Capacitor | LE21M396-E-WS-WT-PR-4105 | LE21M396-E-WS-WT-PR-4105-C | EPCOS Datson | Pre-order comments issued | 86 |  | Ashok | ashok.c@tdk-electronics.tdk.com |  | 20.03.24 | 12.04.24 | 10.05.24 | [19 empty] | 25.07.24 | 11.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | HT VFD | LE21M396-E-WS-WT-PR-4106 | LE21M396-E-WS-WT-PR-4106-A | Schneider | Sent to BU Operations | 139 |  | Anoop - 8976901682 | anoop.satheesh@se.com |  | 20.12.23 | 23.01.24 | 18.03.24 | 23.02.24 | 23.02.24 | [6 empty] | 23.02.24 | 23.02.24 | 23.02.24 | T1 | [7 empty] | 23.02.24 | 11.03.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | HT VFD | LE21M396-E-WS-WT-PR-4106 | LE21M396-E-WS-WT-PR-4106-B | Siemens | Pre-order comments issued | 118 |  | Rajkumar P- 9940270654 | rajkumar.p@siemens.com |  | 22.03.24 | 04.04.24 | 08.04.24 | [19 empty] | 24.07.24 | 10.08.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | LT Switchgear and APFC Panel | LE21M396-E-WS-WT-PR-4107 | LE21M396-E-WS-WT-PR-4107-A | HTS | Sent to BU Operations | 144 |  | Rahul - 7722084474 | rahul.athane@htswitchgears.com |  | 07.12.23 | 09.12.23 | 21.12.23 | 16.12.23 | 21.12.23 | 07.02.24 | 16.02.24 | 02.03.24 | 13.03.24 |  |  | 13.03.24 | 02.03.24 | 13.03.24 | T1 | [7 empty] | 13.03.24 | 30.03.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | LT Switchgear and APFC Panel | LE21M396-E-WS-WT-PR-4107 | LE21M396-E-WS-WT-PR-4107-B | SRCS | Sent to BU Operations | 55 |  | Nivas j | operation@ragavendracontrol.com |  | 09.12.23 | 20.12.23 | 26.12.23 | 08.02.24 | 17.02.24 | 22.02.24 | 08.03.24 | 06.06.24 | 10.06.24 |  |  | 10.06.24 | 06.06.24 | 10.06.24 | T1 | [7 empty] | 10.06.24 | 27.06.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | LT Switchgear and APFC Panel | LE21M396-E-WS-WT-PR-4107 | LE21M396-E-WS-WT-PR-4107-C | UPE | Sent to BU Operations | 38 |  | Deepak - 9500095075 | deepak@upe.co.in |  | 17.02.24 | 24.02.24 | 13.03.24 | 08.04.24 | 17.05.24 | 12.06.24 | 27.06.24 |  |  |  |  | 27.06.24 | 12.06.24 | 27.06.24 | T1 | [7 empty] | 27.06.24 | 14.07.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:58
Amritsar | Electrical | Distribution Boards (DB) | LE21M396-E-WS-WT-PR-4108 | LE21M396-E-WS-WT-PR-4108-A | Monaj Tradings | Sent to BU Operations | 24 |  | +91 9432160680 | monajtrading@gmail.com |  | 09.07.24 | 11.07.24 | 11.07.24 | [8 empty] | 11.07.24 | 09.07.24 | 11.07.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:43:34
Amritsar | Electrical | Distribution Boards (DB) | LE21M396-E-WS-WT-PR-4108 | LE21M396-E-WS-WT-PR-4108-B | Monaj Tradings | Sent to BU Operations | 24 |  | +91 9432160680 | monajtrading@gmail.com |  | 09.07.24 | 11.07.24 | 11.07.24 | [8 empty] | 11.07.24 | 09.07.24 | 11.07.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:43:34
Amritsar | Electrical | Distribution Boards (DB) | LE21M396-E-WS-WT-PR-4108 | LE21M396-E-WS-WT-PR-4108-C | Monaj Tradings | Sent to BU Operations | 24 |  | +91 9432160680 | monajtrading@gmail.com |  | 09.07.24 | 11.07.24 | 11.07.24 | [8 empty] | 11.07.24 | 09.07.24 | 11.07.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:43:34
Amritsar | Electrical | Bus Duct | LE21M396-E-WS-WT-PR-4109 | LE21M396-E-WS-WT-PR-4109-A | CS | Sent to BU Operations | 60 |  | D Ramasamy - 9708063721 | db.ramasamy@cselectric.co.in |  | 18.12.23 | 26.12.23 | 09.01.24 | 15.04.24 | 07.05.24 | 10.05.24 | 23.05.24 | 28.05.24 | 05.06.24 |  |  | 05.06.24 | 28.05.24 | 28.05.24 | T1 | [7 empty] | 05.06.24 | 22.06.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:59
Amritsar | Electrical | Bus Duct | LE21M396-E-WS-WT-PR-4109 | LE21M396-E-WS-WT-PR-4109-B | Star drive | Sent to BU Operations | 60 |  | J.C.Suji Parasuraman - 87544 17065 | suji@stardrive.in |  | 18.12.23 | 26.12.23 | 04.01.24 | 03.04.24 | 07.05.24 | 10.05.24 | 23.05.24 | 28.05.24 | 05.06.24 |  |  | 05.06.24 | 28.05.24 | 28.05.24 | T1 | [7 empty] | 05.06.24 | 22.06.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:59
Amritsar | Electrical | Bus Duct | LE21M396-E-WS-WT-PR-4109 | LE21M396-E-WS-WT-PR-4109-C | Vidyut | Sent to BU Operations | 60 |  | R.MURALI - 8825508480 | karthick@vidyutengg.in |  | 03.04.24 | 04.04.24 | 07.05.24 | 08.05.24 | 28.05.24 | 28.05.24 | 05.06.24 |  |  |  |  | 05.06.24 | 28.05.24 | 05.06.24 | T1 | [7 empty] | 05.06.24 | 22.06.24 |  | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:41:59
Amritsar | Electrical | LPBS and LCP Panels | LE21M396-E-WS-WT-PR-4110 | LE21M396-E-WS-WT-PR-4110-A | Monaj Tradings | Sent to BU Operations | 24 |  | +91 9432160680 | monajtrading@gmail.com |  | 09.07.24 | 11.07.24 | 11.07.24 | [8 empty] | 11.07.24 | 09.07.24 | 11.07.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-15:02:58
Amritsar | Electrical | HT & LT Power Cables and Control Cable and Its accesorries | LE21M396-E-WS-WT-PR-4112 | LE21M396-E-WS-WT-PR-4112-A |  | Enquiry yet to float | NA | [26 empty] | 26.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:21:31
Amritsar | Electrical | Lighting System | LE21M396-E-WS-WT-PR-4114 | LE21M396-E-WS-WT-PR-4114-A | Monaj Tradings | Sent to BU Operations | 24 |  | +91 9432160680 | monajtrading@gmail.com |  | 09.07.24 | 11.07.24 | 11.07.24 | [8 empty] | 11.07.24 | 09.07.24 | 11.07.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:43:34
Amritsar | Electrical | Electrical Safety Items | LE21M396-E-WS-WT-PR-4115 | LE21M396-E-WS-WT-PR-4115-A | Monaj Tradings | Sent to BU Operations | 24 |  | +91 9432160680 | monajtrading@gmail.com |  | 09.07.24 | 11.07.24 | 11.07.24 | [8 empty] | 11.07.24 | 09.07.24 | 11.07.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:43:34
Amritsar | Electrical | Switchyard System | LE21M396-E-WS-WT-PR-4116 | LE21M396-E-WS-WT-PR-4116-A |  | Enquiry yet to float | NA | [26 empty] | 07.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:21:31
Ballia WSP | Process | Clariflocculator Mechanism | LE23M596-P-WS-WT-PR-2102 | LE23M596-P-WS-WT-PR-2102-A | Shivpad | Sent to BU Operations | PR Closed |  |  |  |  | 05.08.23 | 07.12.23 | 20.12.23 | 03.01.24 | 17.01.24 | 09.02.24 | [5 empty] | 09.02.24 | 09.02.24 | 01.03.24 | T1 | [7 empty] | 01.03.24 | 18.03.24 | 17.05.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Clariflocculator Mechanism | LE23M596-P-WS-WT-PR-2102 | LE23M596-P-WS-WT-PR-2102-B | FFP | Pre-order technically rejected | PR Closed |  |  |  |  | 05.08.23 | 03.01.24 | 17.01.24 | 09.02.24 | 01.03.24 | [17 empty] | 01.03.24 | 18.03.24 | 17.05.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Clariflocculator Mechanism | LE23M596-P-WS-WT-PR-2102 | LE23M596-P-WS-WT-PR-2102-C | Sritech | Sent to BU Operations | PR Closed | 1. Observations sent on 20.12.2023 2. Replies received on 28.12.2023 3. Electrical observations sent on 04.01.2024 4. Replies received on 05.01.2024 5. Technically cleared on 17.01.2024 | 94221 11017 | mohan@sritechindia.com |  | 05.08.23 | 29.11.23 | 20.12.23 | 28.12.23 | 04.01.24 | 05.01.24 | [5 empty] | 17.01.24 | 17.01.24 | 01.03.24 | T1 | [7 empty] | 01.03.24 | 18.03.24 | 17.05.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Clariflocculator Mechanism | LE23M596-P-WS-WT-PR-2102 | LE23M596-P-WS-WT-PR-2102-D | Triveni | Post-order pending with EDRC | 54 | 1. Observations (process and electrical) sent on 18.01.2024 2. Reply sent on 20.01.2024 3. Excel copy requested on 22.01.2024 4. Excel copy received on 22.01.2024 5. L&T Observation sent on 12.02.2024 6. Reply received on 21.02.2024 and 26.02.2024 7. Technically Cleared on 27.02.2024 | 98417 31882 | h.sathyanarayanan@projects.trivenigroup.com |  | 05.08.23 | 30.12.23 | 18.01.24 | 22.01.24 | 12.02.24 | 21.02.24 | 27.02.24 |  |  |  |  | 27.02.24 | 27.02.24 | 01.03.24 | T1 | 13.05.24 | Triveni | 10.06.24 | 11.06.24 |  |  |  | 01.03.24 | 18.03.24 | 17.05.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Clariflocculator Mechanism | LE23M596-P-WS-WT-PR-2102 | LE23M596-P-WS-WT-PR-2102-E | Adroit | Sent to BU Operations | PR Closed | 1. Observations sent on 20.12.2023 2. Additional inputs sent on 08.01.2024 3. Replies received on 09.01.2024 4. Observations sent on 20.01.2024 5. Replies received on 12.02.2024 6.Technically cleared on 20.02.2024 | 91790 21490 | shubham@adroitindia.co.in |  | 05.08.23 | 11.12.23 | 20.12.23 | 09.01.24 | 20.01.24 | 12.02.24 | [5 empty] | 20.02.24 | 20.02.24 | 01.03.24 | T1 | [7 empty] | 01.03.24 | 18.03.24 | 17.05.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Air Blower | LE23M596-P-WS-WT-PR-2103 | LE23M596-P-WS-WT-PR-2103-A | Everest | Sent to BU Operations | 52 | 1. L&T Observations (Process and Electrical) sent on 22.01.2024 2. Vendor responded on 13.03.2024 3. Technically cleared on 07.05.2024 | 95826 49157 | Armoghan.Anwar@irco.com |  | 05.08.23 | 05.01.24 | 22.01.24 | 13.03.24 | [7 empty] | 07.05.24 | 07.05.24 | 13.06.24 | T1 | [7 empty] | 13.06.24 | 30.06.24 | 29.08.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Air Blower | LE23M596-P-WS-WT-PR-2103 | LE23M596-P-WS-WT-PR-2103-B | KAY | Sent to BU Operations | 52 | 1. Observations sent on 08.01.2024 2. Part replies received on 08.01.2024 3. Remaining replies received on 17.01.2024 4. Observations sent on 22.01.2024 5. Reminder sent on 14.03.2024 6. Replies received on 15.03.2024 7. Technically cleared on 20.05.24 | 85728 99449 | manish@kayblowers.com |  | 05.08.23 | 29.11.23 | 08.01.24 | 17.01.24 | 22.01.24 | 15.03.24 | [5 empty] | 20.05.24 | 20.05.24 | 13.06.24 | T1 | [7 empty] | 13.06.24 | 30.06.24 | 29.08.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Air Blower | LE23M596-P-WS-WT-PR-2103 | LE23M596-P-WS-WT-PR-2103-C | ACME | Pre-order technically rejected | PR Closed |  | 97263 53221 | jagathees@airequipments.com |  | 05.08.23 | 04.12.23 | [20 empty] | 13.06.24 | 30.06.24 | 29.08.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Air Blower | LE23M596-P-WS-WT-PR-2103 | LE23M596-P-WS-WT-PR-2103-D | AIRVAC | Regret offer | PR Closed | 1. L&T Observations (Process and Electrical) sent on 22.01.2024 2. Reminder sent on 14.03.2024 | 98916 92947 | airvac.ravi@gmail.com |  | 05.08.23 | 05.01.24 | 22.01.24 | [19 empty] | 13.06.24 | 30.06.24 | 29.08.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Agitator | LE23M596-P-WS-WT-PR-2104 | LE23M596-P-WS-WT-PR-2104-A | Shivpad | Sent to BU Operations | PR Closed | 1. Observations sent on 22.12.2023 2. Reply received on 03.01.2024 3. Observations sent on 09.01.2024 4. Reply received on 07.02.2024 5. Mail sent for revised compliance sheet on 01.03.2024 6. Vendor replied on 12.03.2024 7. Technically cleared on 12.03.2024 | 90032 43278 | ragavendar@shivpad.com |  | 23.08.23 | 16.12.23 | 22.12.23 | 03.01.24 | 09.01.24 | 07.02.24 | 01.03.24 | 12.03.24 |  |  |  | 12.03.24 | 12.03.24 | 16.03.24 | T1 | [7 empty] | 16.03.24 | 02.04.24 | 01.06.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Agitator | LE23M596-P-WS-WT-PR-2104 | LE23M596-P-WS-WT-PR-2104-B | FFP | Pre-order technically rejected | PR Closed | 1. L&T asked vendor to provide filled L&T data sheet on 07.12.2023 2. Documents received from Vendor on 03.02.2024 3. L&T provided observations (Process and E&I) on 04.03.2024 4. Vendor replied along with a query to L&T on 05.03.2024 5. L&T provided reply with other observations on 11.03.2024 6. Vendor replied on 12.03.2024 | 81049 82550 | fibrein@gmail.com |  | 23.08.23 | 28.11.23 | 07.12.23 | 03.02.24 | 04.03.24 | 05.03.24 | 11.03.24 | 12.03.24 | [14 empty] | 16.03.24 | 02.04.24 | 01.06.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Agitator | LE23M596-P-WS-WT-PR-2104 | LE23M596-P-WS-WT-PR-2104-C | Sritech | Sent to BU Operations | PR Closed | 1. Observations sent on 01.02.2024 2. Reply received on 06.02.2024 3. Technically cleared on 09.02.2024 | 94221 11017 | mohan@sritechindia.com |  | 23.08.23 | 05.01.24 | 01.02.24 | 06.02.24 | [7 empty] | 09.02.24 | 09.02.24 | 16.03.24 | T1 | [7 empty] | 16.03.24 | 02.04.24 | 01.06.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Agitator | LE23M596-P-WS-WT-PR-2104 | LE23M596-P-WS-WT-PR-2104-D | Adroit | Sent to BU Operations | PR Closed | 1. Observations sent on 22.12.2023 2. Revised offer received on 27.12.2023 3. Observations sent on 04.01.2024 4. Reply received on 20.02.2024 5. Technical Clearance on 01.03.2024 | 91790 21490 | shubham@adroitindia.co.in |  | 23.08.23 | 05.12.23 | 22.12.23 | 27.12.23 | 04.01.24 | 20.02.24 | [5 empty] | 01.03.24 | 01.03.24 | 16.03.24 | T1 | [7 empty] | 16.03.24 | 02.04.24 | 01.06.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Agitator | LE23M596-P-WS-WT-PR-2104 | LE23M596-P-WS-WT-PR-2104-E | Verito | Post-order technically cleared | 32 | 1. Observations sent on 22.12.2023 2. Revised offer received on 23.12.2023 & 25.12.2023 3. Observations sent on 04.01.2024 4. Replies received on 09.01.2024 5. Technically cleared on 23.01.2024 | 98750 18210 | farhin@veritoengineering.com |  | 23.08.23 | 01.12.23 | 22.12.23 | 25.12.23 | 04.01.24 | 20.02.24 | [5 empty] | 01.03.24 | 01.03.24 | 16.03.24 | T1 | 09.05.24 | Verito | 14.05.24 | 29.05.24 | 03.07.24 | 03.07.24 |  | 16.03.24 | 02.04.24 | 01.06.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Sluice Gates | LE23M596-P-WS-WT-PR-2105 | LE23M596-P-WS-WT-PR-2105-A | Jash | Sent to BU Operations | 13 | 1. Vendor requested for editable sheet on 30.11.2023 & 18.12.2023 2. L&T Provided the sheet by 18.12.2023 3. Vendor still not clear. Still requested again on 22.01.2024. 4. L&T provided on 30.01.2024 5. Data sheet received from vendor on 14.02.2024 6. L&T observation sent on 19.02.2024 7. Reply received on 21.02.2024 8. Revised data sheet requested to vendor on 01.03.2024 9. Reminder sent on 04.04.2024 & 16.04.2024 10. Vendor replied on 16.04.2024 11. L&T Observation provided on 07.05.2024 12. Vendor replied on 08.05.2024 13. L&T Observation sent on 08.05.2024 14. Reminder sent on 11.06.2024 15. Reminder sent on 17.07.2024 16. Reminder sent on 20.07.2024 17. Vendor replied on 22.07.2024 and Technical clearance provided on 22.07.2024 | 78699 10452 | robin@jashindia.com |  | 13.09.23 | 14.02.24 | 19.02.24 | 21.02.24 | 01.03.24 | 16.04.24 | 07.05.24 | 08.05.24 | 08.05.24 | 22.07.24 |  | 22.07.24 | 22.07.24 | 22.07.24 | T1 | [7 empty] | 15.07.24 | 01.08.24 | 30.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Sluice Gates | LE23M596-P-WS-WT-PR-2105 | LE23M596-P-WS-WT-PR-2105-B | Oriental Castings | Sent to BU Operations | 13 | 1. L&T observations sent on 01.03.2024 2. Vendor replied on 02.03.2024 3. L&T Observations provided on 07.05.2024 4. Reminder sent on 11.06.2024 5. Vendor replied on 11.07.2024 6. Technically cleared on 11.07.2024 | 98102 05011 | orientalcastings@gmail.com |  | 13.09.23 | 17.01.24 | 01.03.24 | 02.03.24 | 07.05.24 | 11.07.24 | [5 empty] | 11.07.24 | 11.07.24 | 22.07.24 | T1 | [7 empty] | 15.07.24 | 01.08.24 | 30.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Chlorination System | LE23M596-P-WS-WT-PR-2106 | LE23M596-P-WS-WT-PR-2106-A | Verito | Regret offer | PR Closed | 1. Regret mail dated 09.02.2024 | 78598 01358 | jay@veritoengineering.com |  | 16.09.23 | [21 empty] | 22.07.24 | 08.08.24 | 07.10.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Chlorination System | LE23M596-P-WS-WT-PR-2106 | LE23M596-P-WS-WT-PR-2106-B | Toshcon | Sent to BU Operations | 12 | 1. Reminder sent on 20.02.2024 2. L&T requested filled up data sheet on 21.02.2024 3. Filled up data sheet received on 27.02.2024 4. L&T observations sent on 23.05.2024 | 93143 97737 / 93143 97727 | metering1@toshcon.com metering2@toshcon.com |  | 16.09.23 | 27.02.24 | 23.05.24 | 22.07.24 | [7 empty] | 23.07.24 | 23.07.24 | 23.07.24 | T1 | [7 empty] | 22.07.24 | 08.08.24 | 07.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Chlorination System | LE23M596-P-WS-WT-PR-2106 | LE23M596-P-WS-WT-PR-2106-C | FFP | Regret offer | PR Closed | 1. Regret mail - 17.06.24 | 98202 91546 | fibrein@gmail.com |  | 16.09.23 | [21 empty] | 22.07.24 | 08.08.24 | 07.10.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Chlorination System | LE23M596-P-WS-WT-PR-2106 | LE23M596-P-WS-WT-PR-2106-D | Zion | Sent to BU Operations | 12 | 1. L&T Observations (Process and Electrical) sent on 23.01.2024 2. Replies received on 12.02.2024 3. L&T replied on 08.05.2024 4. Vendor replies received on 20.05.24 5. Technically cleared on 21.05.24 | 80945 70996 | deepak@ziontech.in |  | 16.09.23 | 30.11.23 | 23.01.24 | 12.02.24 | 08.05.24 | 20.05.24 | [5 empty] | 21.05.24 | 21.05.24 | 23.07.24 | T1 | [7 empty] | 22.07.24 | 08.08.24 | 07.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Chlorination System | LE23M596-P-WS-WT-PR-2106 | LE23M596-P-WS-WT-PR-2106-E | IEC Fabchem | Sent to BU Operations | 12 | 1. L&T Observations (Process and Electrical) sent on 23.01.2024 2. Replies received on 20.03.2024. 3. Vendor reminded on 27.03.2024 4. L&T replied on 08.05.2024 5. Vendor replied on 13.05.24 6. Technically cleared on 18.05.24 | 75500 13258 | marketing@iecfabchem.in |  | 16.09.23 | 27.11.23 | 23.01.24 | 20.03.24 | 08.05.24 | 13.05.24 | [5 empty] | 18.05.24 | 18.05.24 | 23.07.24 | T1 | [7 empty] | 22.07.24 | 08.08.24 | 07.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Chlorine Tonners | LE23M596-P-WS-WT-PR-2107 | LE23M596-P-WS-WT-PR-2107-A | Verito | Regret offer | PR Closed | 1. Regret mail dated 09.02.2024 | 78598 01358 | jay@veritoengineering.com |  | 16.09.23 | [21 empty] | 29.07.24 | 15.08.24 | 14.10.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Chlorine Tonners | LE23M596-P-WS-WT-PR-2107 | LE23M596-P-WS-WT-PR-2107-B | Toshcon | Regret offer | PR Closed | 1. Reminder sent on 20.02.2024 | 93143 97737 / 93143 97727 | metering1@toshcon.com metering2@toshcon.com |  | 16.09.23 | [21 empty] | 29.07.24 | 15.08.24 | 14.10.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Chlorine Tonners | LE23M596-P-WS-WT-PR-2107 | LE23M596-P-WS-WT-PR-2107-C | FFP | Regret offer | PR Closed |  | 98202 91546 | fibrein@gmail.com |  | 16.09.23 | [21 empty] | 29.07.24 | 15.08.24 | 14.10.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Chlorine Tonners | LE23M596-P-WS-WT-PR-2107 | LE23M596-P-WS-WT-PR-2107-D | Zion | Sent to BU Operations | 12 | 1. Technically cleared on 13.02.2024 | 80945 70996 | deepak@ziontech.in |  | 16.09.23 | 01.12.23 | 13.02.24 | [8 empty] | 13.02.24 | 13.02.24 | 23.07.24 | T1 | [7 empty] | 29.07.24 | 15.08.24 | 14.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Chlorine Tonners | LE23M596-P-WS-WT-PR-2107 | LE23M596-P-WS-WT-PR-2107-E | IEC Fabchem | Sent to BU Operations | 12 | 1. L&T Comments sent on 13.02.2024 2. Vendor replied on 08.05.2024 3. Technically cleared on 13.05.2024 | 75500 13258 | marketing@iecfabchem.in |  | 16.09.23 | 27.11.23 | 13.02.24 | 08.05.24 | [7 empty] | 13.05.24 | 13.05.24 | 23.07.24 | T1 | [7 empty] | 29.07.24 | 15.08.24 | 14.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Sludge Thickener | LE23M596-P-WS-WT-PR-2108 | LE23M596-P-WS-WT-PR-2108-A | Shivpad | Sent to BU Operations | 174 | 1. L&T Observation sent on 18-12-2023 2. Reply received on 03.01.2024 3. Technically cleared on 09.02.2024 | 90032 43278 | ragavendar@shivpad.com |  | 16.08.23 | 07.12.23 | 18.12.23 | 03.01.24 | 17.01.24 | 19.01.24 | 03.02.24 |  |  |  |  | 09.02.24 | 09.02.24 | 12.02.24 | T1 | [7 empty] | 12.02.24 | 29.02.24 | 29.04.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Sludge Thickener | LE23M596-P-WS-WT-PR-2108 | LE23M596-P-WS-WT-PR-2108-B | FFP | Sent to BU Operations | 174 | 1. L&T Observations sent on 20.01.2024 2. Vendor replies received on 03.02.2024 3. Technically cleared on 12.02.2024 | 81049 82550 | fibrein@gmail.com |  | 16.08.23 | 01.01.24 | 20.01.24 | 03.02.24 | 12.02.24 | [6 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T1 | [7 empty] | 12.02.24 | 29.02.24 | 29.04.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Sludge Thickener | LE23M596-P-WS-WT-PR-2108 | LE23M596-P-WS-WT-PR-2108-C | Sritech | Sent to BU Operations | 174 | 1. L&T Observation sent on 18.12.2023 2. Reply received on 19.12.2023 3. L&T Electrical Observation sent on 02.02.2024 4. Reply received on 06.02.2024 5.Technically cleared on 09.02.2024 | 94221 11017 | mohan@sritechindia.com |  | 16.08.23 | 29.11.23 | 18.12.23 | 19.12.23 | 02.02.24 | 06.02.24 | 09.02.24 |  |  |  |  | 09.02.24 | 09.02.24 | 12.02.24 | T1 | [7 empty] | 12.02.24 | 29.02.24 | 29.04.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Nozzles | LE23M596-P-WS-WT-PR-2109 | LE23M596-P-WS-WT-PR-2109-A | Guddi Plastcon | Sent to BU Operations | 23 | 1.Offer received on 04-06-24 2. L&T datasheet asked on 6-6-24 3. Vendor replied on 17-06-24 4. L&T reply sent on 27.06.24 | 022-6157-9393 | sales@guddiindia.com |  | 21.05.24 | 04.06.24 | 06.06.24 | 17.06.24 | 27.06.24 | 11.07.24 | [5 empty] | 11.07.24 | 11.07.24 | 12.07.24 | T1 | [7 empty] | 15.07.24 | 01.08.24 | 30.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Nozzles | LE23M596-P-WS-WT-PR-2109 | LE23M596-P-WS-WT-PR-2109-B | VP Engineers | Sent to BU Operations | 23 | 1.Offer received on 23-05-24 2. L&T observations sent on 06-06-24 3. Vendor replied on 7-6-24 | 94450 03987 | karthik@vpengineers.com |  | 21.05.24 | 23.05.24 | 06.06.24 | 07.06.24 | [7 empty] | 11.06.24 | 11.06.24 | 12.07.24 | T1 | [7 empty] | 15.07.24 | 01.08.24 | 30.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Filter Media | LE23M596-P-WS-WT-PR-2110 | LE23M596-P-WS-WT-PR-2110-A | Global Adsorbents | Pre-order pending with EDRC | 9 |  | 98305 77695 | Paramita@globaladsorbents.com |  | 23.07.24 | 26.07.24 | [20 empty] | 31.10.24 | 17.11.24 | 16.01.25 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Filter Media | LE23M596-P-WS-WT-PR-2110 | LE23M596-P-WS-WT-PR-2110-B | Dalton | Pre-order pending with EDRC | 11 |  | 98187 98540 | Daltonminerals@gmail.com |  | 23.07.24 | 24.07.24 | [23 empty] | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Filter Media | LE23M596-P-WS-WT-PR-2110 | LE23M596-P-WS-WT-PR-2110-C | Kalimati | Pre-order pending with EDRC | 11 |  | 98305 20043 | marketing@kalimaticarbon.com |  | 23.07.24 | 24.07.24 | [23 empty] | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Centrifuge | LE23M596-P-WS-WT-PR-2111 | LE23M596-P-WS-WT-PR-2111-A | Hiller India | Sent to BU Operations | 92 | 1. L&T Observations sent on 01.02.2024 2. Reply received from vendor on 12.03.2024 | 98300 73768 | enquiry@hillerindia.com |  | 16.08.23 | 04.01.24 | 01.02.24 | 12.03.24 | [7 empty] | 04.05.24 | 04.05.24 | 04.05.24 | T1 | [7 empty] | 04.05.24 | 21.05.24 | 20.07.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Centrifuge | LE23M596-P-WS-WT-PR-2111 | LE23M596-P-WS-WT-PR-2111-B | Tega | Sent to BU Operations | 92 |  |  |  |  | 16.08.23 | 04.12.23 | 01.02.24 | 07.02.24 | 20.02.24 | [6 empty] | 04.05.24 | 04.05.24 | 04.05.24 | T1 | [7 empty] | 04.05.24 | 21.05.24 | 20.07.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Screw Pumps | LE23M596-P-WS-WT-PR-2112 | LE23M596-P-WS-WT-PR-2112-A | Tushaco | Pre-order pending with EDRC | 25 | 1. Offer received on 09.05.24 2. L&T observations sent on 22.05.24 3. Vendor replied on 27.05.24 4. L&T reply sent on 03.06.24 5. Vendor replied on 19.06.24 | 99404 26343 | Gowtham@tapengineering.com |  | 04.05.24 | 09.05.24 | 22.05.24 | 27.05.24 | 03.06.24 | 19.06.24 | 29.06.24 | 10.07.24 | [14 empty] | 22.07.24 | 08.08.24 | 07.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Screw Pumps | LE23M596-P-WS-WT-PR-2112 | LE23M596-P-WS-WT-PR-2112-B | Roto Pumps | Pre-order technically cleared | 10 | 1. Offer received on 08.05.24 2. L&T observations sent on 22.05.24 | 93762 28251 93800 11464 | manish@rotopumps.com; chn1@rotopumps.com |  | 04.05.24 | 08.05.24 | 22.05.24 | 22.07.24 | [7 empty] | 25.07.24 | 25.07.24 | [9 empty] | 22.07.24 | 08.08.24 | 07.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Screw Pumps | LE23M596-P-WS-WT-PR-2112 | LE23M596-P-WS-WT-PR-2112-C | Flosys | Pre-order comments issued | 74 | 1. Offer received on 07.05.24 2. L&T observations sent on 22.05.24 | 93613 03055 | sales@flosys.in |  | 04.05.24 | 07.05.24 | 22.05.24 | [19 empty] | 22.07.24 | 08.08.24 | 07.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Backwash Pumps | LE23M596-P-WS-WT-PR-2113 | LE23M596-P-WS-WT-PR-2113-A | WPIL | Sent to BU Operations | 9 | 1. L&T Observations sent on 21.05.2024 2. Vendor replied on 21.06.2024 3. Technically cleared on 29.06.2024 | 91473 32553 | r.chandramohan@wpil.co.in |  | 05.08.23 | 07.02.24 | 21.05.24 | 21.06.24 | [7 empty] | 29.06.24 | 29.06.24 | 26.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Backwash Pumps | LE23M596-P-WS-WT-PR-2113 | LE23M596-P-WS-WT-PR-2113-B | WILO | Sent to BU Operations | 9 | 1. L&T asked vendor to provide filled L&T data sheet on 03.02.2024 2. Reminder sent on 08.05.2024 3. Vendor replied on 18.06.2024 4. L&T Observation sent on 03.07.2024 5. Reminder sent on 12.07.2024 6. Vendor replied on 24.07.2024 7. Technically cleared on 25.07.2024 | 86800 68301 | manikkandan.pr@wilo.com |  | 05.08.23 | 11.01.24 | 03.02.24 | 18.06.24 | 03.07.24 | 24.07.24 | [5 empty] | 25.07.24 | 25.07.24 | 26.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Backwash Pumps | LE23M596-P-WS-WT-PR-2113 | LE23M596-P-WS-WT-PR-2113-C | MBH | Sent to BU Operations | 9 | 1. L&T Observation sent on 02.02.2024 2. Replies received on 12.02.2024 3. Technically cleared on 04.05.2024 | 99200 13772 | northindustrial@mbhpumps.com |  | 05.08.23 | 01.12.23 | 02.02.24 | 12.02.24 | [7 empty] | 04.05.24 | 04.05.24 | 26.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Submersible Pumps | LE23M596-P-WS-WT-PR-2114 | LE23M596-P-WS-WT-PR-2114-A | Grundfos | Regret offer | PR Closed |  | 98403 20809 | ramesh.sivasubramanian@gmail.com |  | 05.08.23 | [21 empty] | 12.08.24 | 29.08.24 | 28.10.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Submersible Pumps | LE23M596-P-WS-WT-PR-2114 | LE23M596-P-WS-WT-PR-2114-B | MBH | Pre-order technically cleared | 89 | 1.Observation sent on 02.02.2024 2. Replies received on 12-02-2024 3. Technically cleared on 07.05.2024 | 99200 13772 | northindustrial@mbhpumps.com |  | 05.08.23 | 01.12.23 | 02.02.24 | 12.02.24 | [7 empty] | 07.05.24 | 07.05.24 | [9 empty] | 12.08.24 | 29.08.24 | 28.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Submersible Pumps | LE23M596-P-WS-WT-PR-2114 | LE23M596-P-WS-WT-PR-2114-C | Aqua | Regret offer | PR Closed |  | 81440 03131 | chennai@aquapumps.com |  | 05.08.23 | [21 empty] | 12.08.24 | 29.08.24 | 28.10.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Submersible Pumps | LE23M596-P-WS-WT-PR-2114 | LE23M596-P-WS-WT-PR-2114-D | KSB | Pre-order comments issued | 184 | 1.Observation sent on 02.02.2024 |  | Dhananjay.Bidnur@ksb.com |  | 05.08.23 | 11.12.23 | 02.02.24 | [19 empty] | 12.08.24 | 29.08.24 | 28.10.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Submersible Pumps | LE23M596-P-WS-WT-PR-2114 | LE23M596-P-WS-WT-PR-2114-E | WPIL | Regret offer | PR Closed |  | 87540 00930 | r.chandramohan@wpil.co.in |  | 05.08.23 | [21 empty] | 12.08.24 | 29.08.24 | 28.10.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Electrical Hoist | LE23M596-P-WS-WT-PR-2115 | LE23M596-P-WS-WT-PR-2115-A | Japs | Sent to BU Operations | 23 | 1. Query asked by vendor on 29.11.2023 2. Clarification sent to vendor on 01.12.2023 3. Revised offer received from vendor on 07.12.2023 4. L&T observations sent on 18.05.24 5. Vendor comments received on 04.06.24 | 99789 00589 | sales.japs@gmail.com |  | 17.08.23 | 07.12.23 | 18.05.24 | 04.06.24 | [7 empty] | 27.06.24 | 27.06.24 | 12.07.24 | T1 | [7 empty] | 08.07.24 | 25.07.24 | 23.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Electrical Hoist | LE23M596-P-WS-WT-PR-2115 | LE23M596-P-WS-WT-PR-2115-B | Reva | Sent to BU Operations | 23 | 1. L&T asked vendor to provide fill L&T data sheet on 03.02.2024 2. Vendor requested for blank format on 03.02.2024, given to vendor on 03.02.2024 3. Documents received from vendor on 12.02.2024 4. L&T observations sent on 18.05.24 5. Vendor replied on 20.05.24 6. L&T replied on 21.05.24 7. Vendor sent compliance sheet on 22.05.24 | 98994 84751 | south@revacranes.com |  | 17.08.23 | 01.12.23 | 03.02.24 | 12.02.24 | 18.05.24 | 20.05.24 | 21.05.24 | 22.05.24 |  |  |  | 27.06.24 | 27.06.24 | 12.07.24 | T1 | [7 empty] | 08.07.24 | 25.07.24 | 23.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Electrical Hoist | LE23M596-P-WS-WT-PR-2115 | LE23M596-P-WS-WT-PR-2115-C | Indef | Sent to BU Operations | 23 | 1. Documents received from vendor on 18.01.24 2. L&T observations sent on 18.05.24 | 81211 74337 | mkm@indef.com |  | 17.08.23 | 18.01.24 | 18.05.24 | 24.06.24 | [7 empty] | 29.06.24 | 29.06.24 | 12.07.24 | T1 | [7 empty] | 08.07.24 | 25.07.24 | 23.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Chain Pulley Block | LE23M596-P-WS-WT-PR-2116 | LE23M596-P-WS-WT-PR-2116-A | Japs | Sent to BU Operations | 23 | 1. Query asked by vendor on 29.11.2023 2. Clarification sent to vendor on 01.12.2023 3. Revised offer received from vendor on 07.12.2023 4. L&T observations sent on 18.05.24 | 99789 00589 | sales.japs@gmail.com |  | 16.08.23 | 28.11.23 | 18.05.24 | 04.06.24 | [7 empty] | 27.06.24 | 27.06.24 | 12.07.24 | T1 | [7 empty] | 08.07.24 | 25.07.24 | 23.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Chain Pulley Block | LE23M596-P-WS-WT-PR-2116 | LE23M596-P-WS-WT-PR-2116-B | Reva | Sent to BU Operations | 23 | 1. L&T asked vendor to provide filled L&T data sheet on 03.02.2024 2. Reply received from vendor on 12.02.2024 | 98994 84751 | south@revacranes.com |  | 16.08.23 | 05.01.24 | 03.02.24 | 12.02.24 | 18.05.24 | 20.05.24 | 21.05.24 | 22.05.24 |  |  |  | 27.06.24 | 27.06.24 | 12.07.24 | T1 | [7 empty] | 08.07.24 | 25.07.24 | 23.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Chain Pulley Block | LE23M596-P-WS-WT-PR-2116 | LE23M596-P-WS-WT-PR-2116-C | Indef | Sent to BU Operations | 23 | 1. Documents received from vendor on 18.01.24 2. L&T observations sent on 18.05.24 3. Vendor replied on 24.06.24 | 81211 74337 | mkm@indef.com |  | 16.08.23 | 18.01.24 | 18.05.24 | 24.06.24 | [7 empty] | 29.06.24 | 29.06.24 | 12.07.24 | T1 | [7 empty] | 08.07.24 | 25.07.24 | 23.09.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Dosing Pumps | LE23M596-P-WS-WT-PR-2117 | LE23M596-P-WS-WT-PR-2117-A | Verito | Sent to BU Operations | 207 | 1. Observations sent on 19.12.2023 2. Technical offer received on 20.12.2023 3. Observations sent on 21.12.2023 4. Revised offer received on 21.12.2023 5. Electrical Observations sent on 26.12.2023 6. Electrical replies received on 03.01.2023 7. Motor signed document received on 05.01.2024 8. Technically Accepted 08.01.2024 | 78598 01358 | jay@veritoengineering.com |  | 16.08.23 | 01.12.23 | 19.12.23 | 20.12.23 | 21.12.23 | 21.12.23 | 26.12.23 | 03.01.24 |  |  |  | 08.01.24 | 08.01.24 | 10.01.24 | T1 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Dosing Pumps | LE23M596-P-WS-WT-PR-2117 | LE23M596-P-WS-WT-PR-2117-B | Positive metering | Sent to BU Operations | 207 | 1. Observations sent on 07.12.2023 2. Revised offer received on 09.12.2023 3. Observations sent on 19.12.2023 4. Revised offer received on 21.12.2023 5. Observations sent on 22.12.2023 6. Revised offer received on 05.01.2024 7. Few Electrical confirmation requested on 05.01.2024 8. Replies received on 06.01.2024 9. Technically Accepted 08.01.2024 | 99229 49549 | muthurai@positivemetering.com |  | 16.08.23 | 02.12.23 | 07.12.23 | 09.12.23 | 19.12.23 | 21.12.23 | 22.12.23 | 05.01.24 |  |  |  | 08.01.24 | 08.01.24 | 10.01.24 | T1 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Dosing Pumps | LE23M596-P-WS-WT-PR-2117 | LE23M596-P-WS-WT-PR-2117-C | SR metering | Sent to BU Operations | 207 | 1. Observations sent on 19.12.2023 2. Technical offer received on 26.12.2023 3. Observations sent on 26.12.2023 4. Revised offer & reply received on 04.01.2024 5. Technically Accepted 08.01.2024 | 88888 65119 | sr1@srmetering.com |  | 16.08.23 | 12.12.23 | 19.12.23 | 26.12.23 | 26.12.23 | 04.01.24 | [5 empty] | 08.01.24 | 08.01.24 | 10.01.24 | T1 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | DWPE Tanks | LE23M596-P-WS-WT-PR-2118 | LE23M596-P-WS-WT-PR-2118-A | Site Procurement | Sent to BU Operations | 9 |  |  |  |  | 26.07.24 | 26.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [7 empty] | 30.09.24 | 17.10.24 | 16.12.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | DWPE Tanks | LE23M596-P-WS-WT-PR-2118 | LE23M596-P-WS-WT-PR-2118-B | Verito | Regret offer | PR Closed |  | 78598 01358 | jay@veritoengineering.com |  | 04.05.24 | [21 empty] | 30.09.24 | 17.10.24 | 16.12.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Sampling Pumps | LE23M596-P-WS-WT-PR-2119 | LE23M596-P-WS-WT-PR-2119-A | Site Procurement | Sent to BU Operations | 9 |  |  |  |  | 26.07.24 | 26.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [7 empty] | 31.10.24 | 17.11.24 | 16.01.25 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Submersible Mixer | LE23M596-P-WS-WT-PR-2120 | LE23M596-P-WS-WT-PR-2120-A | Grundfos | Regret offer | PR Closed | 1. Reminder sent on 26.03.2024 | 98403 20809 | ramesh.sivasubramanian@gmail.com |  | 05.08.23 | [21 empty] | 13.05.24 | 30.05.24 | 29.07.24 | THENNARASU@lntecc.com-01.07.2024-16:53:04
Ballia WSP | Process | Submersible Mixer | LE23M596-P-WS-WT-PR-2120 | LE23M596-P-WS-WT-PR-2120-B | FFP | Sent to BU Operations | 13 | 1. L&T observation sent on 20.02.2024 2. Vendor replied on 20.03.2024 3. L&T Observation sent on 07.05.2024 4. Vendor replied on 09.05.2024. 5. Technically cleared on 13.05.2024 | 81049 82550 | fibrein@gmail.com |  | 05.08.23 | 09.02.24 | 20.02.24 | 20.03.24 | 07.05.24 | 09.05.24 | [5 empty] | 13.05.24 | 13.05.24 | 22.07.24 | T1 | [7 empty] | 13.05.24 | 30.05.24 | 29.07.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Submersible Mixer | LE23M596-P-WS-WT-PR-2120 | LE23M596-P-WS-WT-PR-2120-C | ABS sulzer | Sent to BU Operations | 13 | 1. L&T Observation sent on 07.05.2024 2. Vendor replied on 10.05.2024. 3. Technically cleared on 13.05.2024 | 93190 94421 | wwtechennai@gmail.com |  | 05.08.23 | 30.11.23 | 07.05.24 | 10.05.24 | [7 empty] | 13.05.24 | 13.05.24 | 22.07.24 | T1 | [7 empty] | 13.05.24 | 30.05.24 | 29.07.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Dewatering Pump | LE23M596-P-WS-WT-PR-2121 | LE23M596-P-WS-WT-PR-2121-A | MBH | Pre-order technically cleared | 13 |  | 99200 13772 | northindustrial@mbhpumps.com |  | 20.02.24 | 04.03.24 | 12.07.24 | 17.07.24 | [7 empty] | 22.07.24 | 22.07.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Dewatering Pump | LE23M596-P-WS-WT-PR-2121 | LE23M596-P-WS-WT-PR-2121-B | Jasco | Pre-order pending with EDRC | 19 | 1. Reminder sent on 05.03.2024 & 16.04.2024 | 70690 99037 | info@jascopump.com |  | 20.02.24 | 17.04.24 | 12.07.24 | 16.07.24 | [18 empty] | 31.08.24 | 17.09.24 | 16.11.24 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Hand Driven Trolley | LE23M596-P-WS-WT-PR-2123 | LE23M596-P-WS-WT-PR-2123-A | Site Procurement | Sent to BU Operations | 9 |  |  |  |  | 26.07.24 | 26.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [7 empty] | 31.10.24 | 17.11.24 | 16.01.25 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Platform Weighing Machine | LE23M596-P-WS-WT-PR-2124 | LE23M596-P-WS-WT-PR-2124-A | Site Procurement | Sent to BU Operations | 9 |  |  |  |  | 26.07.24 | 26.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [7 empty] | 31.10.24 | 17.11.24 | 16.01.25 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:31
Ballia WSP | Process | Lab Equipments | LE23M596-P-WS-WT-PR-2126 | LE23M596-P-WS-WT-PR-2126-A | Site Procurement | Sent to BU Operations | 9 |  |  |  |  | 26.07.24 | 26.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [7 empty] | 31.10.24 | 17.11.24 | 16.01.25 | aishwarya.nair1@lntecc.com-29.07.2024-10:47:32
Ballia WSP | Mechanical | HSC Pumps | LE23M596-M-WS-CW-PR-1001 | LE23M596-M-WS-CW-PR-1001-A | Wilo | Pre-order pending with EDRC | 166 | 1. Revised BOQ sent to Vendor on 11.01.2024 2. Reminder sent on 23.01.2024 3. Query from vendor on VT pump on 31.01.2024 4. Query replied to vendor on 31.01.2024 5. Revised BOQ sent on 07.02.2024 6. Rev-03 BOQ sent for WTP-4 and WTP-5 Pumps on 14.02.2024 7. Revised offer received on 20.02.2024 | 86800 68301 | manikkandan.pr@wilo.com |  | 01.07.23 | 20.02.24 | [23 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | HSC Pumps | LE23M596-M-WS-CW-PR-1001 | LE23M596-M-WS-CW-PR-1001-B | Flowmore | Pre-order pending with EDRC | 211 | 1. Revised BOQ sent to Vendor on 11.01.2024 2. Reminder sent on 23.01.2024 3. Received revised offer on 26.01.2024 4. Query sent for VT pump motor on 03.02.2024 5. Reply received on 05.02.2024 6. Revised BOQ sent on 07.02.2024 7. Rev-02 Performance curve received on 14.02.2024 8. Rev-03 BOQ sent for WTP-4 and WTP-5 Pumps on 14.02.2024 9. Revised offer received for WTP-4 and WTP-5 Pumps on 15.02.2024 | 93828 69518 | mkannan@flowmoregroup.co.in |  | 01.07.23 | 06.01.24 | [23 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | HSC Pumps | LE23M596-M-WS-CW-PR-1001 | LE23M596-M-WS-CW-PR-1001-C | WPIL | Pre-order pending with EDRC | 165 | 1. Revised BOQ sent to Vendor 2. Revised BOQ sent on 07.02.2024 3. Query from vendor for VT pump on 07.02.2024 4. Query replied on 07.02.2024 5. Vendor requested for Motor specs on 12.02.2024 6. Motor specs and revised BOQ sent on 15.02.2024 7. Revised offer received on 21.02.2024 | 87540 00930 | r.chandramohan@wpil.co.in |  | 01.07.23 | 21.02.24 | [23 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | HSC Pumps | LE23M596-M-WS-CW-PR-1001 | LE23M596-M-WS-CW-PR-1001-D | KBL | Pre-order pending with EDRC | 148 | 1. Reminder sent on 18.01.2024 2. Revised BOQ sent on 07.02.2024 3. Rev-03 BOQ sent for WTP-4 and WTP-5 Pumps on 14.02.2024 4. Offer received on 09.03.2024 | 86696 64820 | azharuddin.tamboli@kbl.co.in |  | 01.07.23 | 09.03.24 | [23 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | HSC Pumps | LE23M596-M-WS-CW-PR-1001 | LE23M596-M-WS-CW-PR-1001-E | Andritz | Pre-order pending with EDRC | 74 |  |  |  |  | 16.05.24 | 22.05.24 | [23 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | HSC Pumps | LE23M596-M-WS-CW-PR-1001 | LE23M596-M-WS-CW-PR-1001-F | Xylem | Pre-order pending with EDRC | 40 |  |  |  |  | 10.06.24 | 25.06.24 | [23 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | VT Pumps | LE23M596-M-WS-CW-PR-1002 | LE23M596-M-WS-CW-PR-1002-A | Wilo | Sent to BU Operations | PR Closed | 1. Revised BOQ sent to Vendor on 11.01.2024 2. Reminder sent on 23.01.2024 3. Query from vendor on VT pump on 31.01.2024 4. Query replied to vendor on 31.01.2024 5. Revised BOQ sent on 07.02.2024 6. Rev-03 BOQ sent for WTP-4 and WTP-5 Pumps | 86800 68301 | manikkandan.pr@wilo.com |  | 01.07.23 | 20.02.24 | 17.05.24 | 21.05.24 | 21.05.24 | 31.05.24 | 31.05.24 |  |  |  |  | 31.05.24 | 31.05.24 | 31.05.24 | T1 | [10 empty] | srb@lntecc.com-19.06.2024-16:39:26
Ballia WSP | Mechanical | VT Pumps | LE23M596-M-WS-CW-PR-1002 | LE23M596-M-WS-CW-PR-1002-B | WPIL | Post-order pending with EDRC | 36 | 1. Revised BOQ sent to Vendor 2. Revised BOQ sent on 07.02.2024 3. Query from vendor for VT pump on 07.02.2024 4. Query replied on 07.02.2024 5. Vendor requested for Motor specs on 12.02.2024 6. Motor specs and revised BOQ sent on 15.02.2024 7. Revised offer received on 21.02.2024 |  | r.chandramohan@wpil.co.in |  | 01.07.23 | 21.02.24 | 17.05.24 | 28.05.24 | 06.06.24 | 06.06.24 | 06.06.24 |  |  |  |  | 31.05.24 | 31.05.24 | 31.05.24 | T1 | 17.06.24 | WPIL | 29.06.24 | [6 empty] | 16.08.24 | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | VT Pumps | LE23M596-M-WS-CW-PR-1002 | LE23M596-M-WS-CW-PR-1002-C | KBL | Pre-order technically rejected | PR Closed | 1. Reminder sent on 18.01.2024 2. Revised BOQ sent on 07.02.2024 3. Rev-03 BOQ sent for WTP-4 and WTP-5 Pumps on 14.02.2024 4. Offer received on 09.03.2024 | 86696 64820 | azharuddin.tamboli@kbl.co.in |  | 01.07.23 | 09.03.24 | 17.05.24 | 17.05.24 | 18.05.24 | 20.05.24 | 20.05.24 | 21.05.24 | 21.05.24 |  |  | 31.05.24 | 31.05.24 | 31.05.24 | T1 | [10 empty] | gopal.samarth@lntecc.com-18.06.2024-10:15:45
Ballia WSP | Mechanical | VT Pumps | LE23M596-M-WS-CW-PR-1002 | LE23M596-M-WS-CW-PR-1002-D | Flowmore | Pre-order technically rejected | PR Closed | 1. Revised BOQ sent to Vendor on 11.01.2024 2. Reminder sent on 23.01.2024 3. Received revised offer on 26.01.2024 4. Query sent for VT pump motor on 03.02.2024 5. Reply received on 05.02.2024 6. Revised BOQ sent on 07.02.2024 7. Rev-02 Performance curve received on 14.02.2024 8. Rev-03 BOQ sent for WTP-4 and WTP-5 Pumps | 93828 69518 | mkannan@flowmoregroup.co.in |  | 01.07.23 | 26.01.24 | 17.05.24 | 25.05.24 | [21 empty] | gopal.samarth@lntecc.com-18.06.2024-17:14:26
Ballia WSP | Mechanical | EOT Crane | LE23M596-M-WS-CW-PR-1003 | LE23M596-M-WS-CW-PR-1003-A | Japs | Pre-order technically cleared | 27 | 1. L&T Observation sent on 03.02.2024 2. Vendor reply received on 05.02.2024 3. E&I observations sent on 16.02.2024 4. Reply from vendor received on 20.02.2024 5. Mechanical Observations sent on 06.03.2024 6. Reply received on 07.03.2024 | 99789 00589 | sales.japs@gmail.com |  | 25.01.24 | 30.01.24 | 02.03.24 | 05.03.24 | 06.03.24 | 06.07.24 | 06.07.24 | 08.07.24 |  |  |  | 08.07.24 | 08.07.24 | 08.07.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | EOT Crane | LE23M596-M-WS-CW-PR-1003 | LE23M596-M-WS-CW-PR-1003-B | Reva | Regret offer | PR Closed | 1. Reminder sent on 21.02.2024 2. Reminder sent on 02.03.2024 3. Technical offer received on 05.03.2024 | 98994 84751 | south@revacranes.com |  | 25.01.24 | 05.03.24 | [23 empty] | gopal.samarth@lntecc.com-09.07.2024-10:07:20
Ballia WSP | Mechanical | EOT Crane | LE23M596-M-WS-CW-PR-1003 | LE23M596-M-WS-CW-PR-1003-C | Indef | Pre-order pending with EDRC | 93 | 1. Query raised by vendor on 25.01.2024 2. L&T Reply sent on 31.01.2024 | 81211 74337 | mkm@indef.com |  | 25.01.24 | 03.05.24 | [23 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Dismantling Joints | LE23M596-M-WS-CW-PR-1004 | LE23M596-M-WS-CW-PR-1004-A | Qualitech | Sent to BU Operations | 120 | 1. Observations sent on 20.01.2024 2. Replies received on 25.01.2024 3. Observations sent on 16.02.2024 4. Replies received on 17.02.2024 5. Technically cleared on 23.02.2024 |  | kamal.mehta@qualitechgroup.in |  | 01.07.23 | 20.01.24 | 20.01.24 | 25.01.24 | 16.02.24 | 17.02.24 | [5 empty] | 23.02.24 | 23.02.24 | 06.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Dismantling Joints | LE23M596-M-WS-CW-PR-1004 | LE23M596-M-WS-CW-PR-1004-B | Surind | Sent to BU Operations | 120 |  |  |  |  | 01.07.23 | 20.01.24 | 20.01.24 | 25.01.24 | 16.02.24 | 17.02.24 | [5 empty] | 23.02.24 | 23.02.24 | 06.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Dismantling Joints | LE23M596-M-WS-CW-PR-1004 | LE23M596-M-WS-CW-PR-1004-B1 | Surind | Awaiting pre-offer from vendor | 125 |  |  |  |  | 01.04.24 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Dismantling Joints | LE23M596-M-WS-CW-PR-1004 | LE23M596-M-WS-CW-PR-1004-C | Sigmaflow | Sent to BU Operations | 120 | 1. Observation sent on 16.02.2024 2. Reply received on 17.02.2024 3. Technically cleared on 23.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 01.07.23 | 30.11.23 | 16.02.24 | 17.02.24 | [7 empty] | 23.02.24 | 23.02.24 | 06.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Dismantling Joints | LE23M596-M-WS-CW-PR-1004 | LE23M596-M-WS-CW-PR-1004-D | Hawle | Sent to BU Operations | 118 | 1. Reminder mail sent on 03.02.2024 2. Reminder mail sent on 16.02.2024 3. Technical offer sent by vendor on 26.02.2024 4. Revised data sheet sent by vendor on 29.02.2024 5. Comment sent to vendor on 02.04.2024 6. reply from vendor on 03.04.2024 7. comment sent to vendor on 03.04.2024 8. Reply received on 06.04.2024 9. Technical clearance on 06.04.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 01.07.23 | 26.02.24 | 02.04.24 | 03.04.24 | 03.04.24 | 06.04.24 | [5 empty] | 06.04.24 | 06.04.24 | 08.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Dismantling Joints | LE23M596-M-WS-CW-PR-1004 | LE23M596-M-WS-CW-PR-1004-E | Orbit Engineers | Regret offer | PR Closed | DJ not in scope | 78791 45143 | yogesh.orbitengineers@gmail.com |  | 01.07.23 | 19.12.23 | [23 empty] | srb@lntecc.com-21.05.2024-16:54:17
Ballia WSP | Mechanical | Sluice Gates | LE23M596-M-WS-CW-PR-1005 | LE23M596-M-WS-CW-PR-1005-A | Jash | Post-order technically cleared | 61 | 1. R1 observations sent on 14.02.2024 2.Elect. and inst. Observations sent on 16.02.2024 3. Vendor replied on 27.02.2024 4. L&T Observations sent on 06.04.2024 5. Vendor replied on 08.04.2024 6. Technical clearance given on 08.04.2024 | 78699 10452 | robin@jashindia.com |  | 06.02.24 | 14.02.24 | 16.02.24 | 27.02.24 | 06.04.24 | 08.04.24 | [5 empty] | 08.04.24 | 08.04.24 | 08.04.24 | T1 | 18.04.24 | Jash | 04.06.24 | 04.06.24 | 04.06.24 | 04.06.24 |  |  |  | 17.06.24 | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Sluice Gates | LE23M596-M-WS-CW-PR-1005 | LE23M596-M-WS-CW-PR-1005-B | Oriental Castings | Sent to BU Operations | PR Closed | 1. L&T Observations sent on 16.02.2024 2. Reminder sent on 04.04.2024 3. Reminder sent on 05.04.2024 4. Vendor reply received on 08.04.2024 5. Technical clearance given on 08.04.2024 | 98102 05011 | orientalcastings@gmail.com |  | 06.02.24 | 08.02.24 | 16.02.24 | 08.04.24 | [7 empty] | 08.04.24 | 08.04.24 | 08.04.24 | T1 | [10 empty] | srb@lntecc.com-21.05.2024-16:54:17
Ballia WSP | Mechanical | Sluice Valves | LE23M596-M-WS-CW-PR-1006 | LE23M596-M-WS-CW-PR-1006-A | Hawle | Sent to BU Operations | PR Closed | 1. Observations sent on 08.01.2024 2. Electrical and instrumentation observations sent on 23.02.24 3. Vendor replied on 11.03.2024 4. Technical clearance provided on 05.04.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 01.07.23 | 12.12.23 | 23.02.24 | 11.03.24 | [7 empty] | 05.04.24 | 05.04.24 | 16.04.24 | T1 | [10 empty] | srb@lntecc.com-21.06.2024-14:38:23
Ballia WSP | Mechanical | Sluice Valves | LE23M596-M-WS-CW-PR-1006 | LE23M596-M-WS-CW-PR-1006-B | AVK | Post-order pending with EDRC | 48 | 1. Observations sent on 29.11.2023 2. Compliance received on 04.12.2023 3. Observations sent on 07.12.2023 4. Compliance received on 04.01.2024 5. Observations sent on 04.01.2024 6. Observation sent on 16.02.2024 7. Vendor reply on 23.02.24 8. Technically cleared on 04.03.2024 | 91769 66455 | subhash@avkindia.com |  | 01.07.23 | 28.11.23 | 29.11.23 | 04.12.23 | 07.12.23 | 04.01.24 | 16.02.24 | 23.02.24 |  |  |  | 04.03.24 | 04.03.24 | 16.04.24 | T1 | 11.06.24 | AVK | 17.06.24 | [6 empty] | 10.08.24 | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Sluice Valves | LE23M596-M-WS-CW-PR-1006 | LE23M596-M-WS-CW-PR-1006-C | VAG | Sent to BU Operations | PR Closed | 1. Observations sent on 22.01.2024 2. Reminder sent on 05.03.2024 3. Technical compliance received on 08.03.2024 4. Observations sent on 06.04.2024 5. Vendor replied on 10.04.2024 6. L&T Observation sent on 10.04.2024 7. Vendor replied on 12.04.2024 8. Technically cleared on 16.04.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 01.07.23 | 09.01.24 | 22.01.24 | 08.03.24 | 06.04.24 | 10.04.24 | 10.04.24 | 12.04.24 |  |  |  | 16.04.24 | 16.04.24 | 16.04.24 | T1 | [10 empty] | srb@lntecc.com-21.06.2024-14:38:23
Ballia WSP | Mechanical | Sluice Valves | LE23M596-M-WS-CW-PR-1006 | LE23M596-M-WS-CW-PR-1006-D | Sigmaflow | Sent to BU Operations | PR Closed | 1. L&T Observation sent on 10.01.2024 2. Reply received on 12.01.2024 3. Electrical observation sent for Acutator on 08.02.2024 4. Vendor replied on electrical points on 15.02.2024 5. Instrumentation query sent on 16.02.2024 6. Vendor replied on 28.02.2024 7. Technical Clearance on 29.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 01.07.23 | 30.11.23 | 10.01.24 | 12.01.24 | 08.02.24 | 15.02.24 | 16.02.24 | 28.02.24 |  |  |  | 29.02.24 | 29.02.24 | 16.04.24 | T1 | [10 empty] | srb@lntecc.com-21.06.2024-14:38:23
Ballia WSP | Mechanical | Sluice Valves | LE23M596-M-WS-CW-PR-1006 | LE23M596-M-WS-CW-PR-1006-E | Orbit Engineers | Sent to BU Operations | PR Closed | 1. Observations sent on 05.01.2024 2. Replies received on 11.01.2024 3. GA and QAP received on 19.01.2024 4. Electrical observation sent on 08.02.2024 5. Inst. Comments sent on 22.02.2024 6. Wiring diagram for actuators received on 04.03.2024 7. E&I Observations sent on 27.03.2024 8. Vendor replied on 09.04.2024 & 10.04.2024 9.Technically Cleared on 16.04.2024 | 78791 45143 | yogesh.orbitengineers@gmail.com |  | 01.07.23 | 23.12.23 | 05.01.24 | 11.01.24 | 08.02.24 | 04.03.24 | 27.03.24 | 10.04.24 |  |  |  | 16.04.24 | 16.04.24 | 16.04.24 | T1 | [10 empty] | srb@lntecc.com-21.06.2024-14:38:23
Ballia WSP | Mechanical | Sluice Valves | LE23M596-M-WS-CW-PR-1006 | LE23M596-M-WS-CW-PR-1006-F | MAGWEN | Sent to BU Operations | PR Closed |  |  |  |  | 27.05.24 | 29.05.24 | 05.06.24 | 10.06.24 | [7 empty] | 11.06.24 | 11.06.24 | 14.06.24 | T1 | [10 empty] | srb@lntecc.com-19.06.2024-16:40:11
Ballia WSP | Mechanical | Butterfly Valves | LE23M596-M-WS-CW-PR-1007 | LE23M596-M-WS-CW-PR-1007-A | Hawle | Sent to BU Operations | 106 | 1. Observations sent on 08.01.2024 2. Electrical and instrumentation observations sent on 23.02.24 3. Vendor replied on 11.03.2024 4. Technical clearance provided on 05.04.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 01.07.23 | 12.12.23 | 23.02.24 | 11.03.24 | [7 empty] | 05.04.24 | 05.04.24 | 20.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Butterfly Valves | LE23M596-M-WS-CW-PR-1007 | LE23M596-M-WS-CW-PR-1007-B | AVK | Sent to BU Operations | 106 | 1. Observations sent on 29.11.2023 2. Compliance received on 04.12.2023 3. Observations sent on 07-12-2023 4. Compliance received on 04.01.2024 5. Observations sent on 04.01.2024 6. Observation sent on 16.02.2024 7. Vendor reply on 23.02.24 8. Technical clearance on 04.03.2024 | 91769 66455 | subhash@avkindia.com |  | 01.07.23 | 28.11.23 | 29.11.23 | 04.12.23 | 07.12.23 | 04.01.24 | 16.02.24 | 23.02.24 |  |  |  | 04.03.24 | 04.03.24 | 20.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Butterfly Valves | LE23M596-M-WS-CW-PR-1007 | LE23M596-M-WS-CW-PR-1007-C | VAG | Sent to BU Operations | 106 | 1. Observations sent on 22.01.2024 2. Reminder sent on 05.03.2024 3. Technical compliance received on 08.03.2024 4. Observations sent on 06.04.2024 5. Vendor replied on 10.04.2024 6. L&T Observation sent on 10.04.2024 7. Vendor replied on 12.04.2024 8. Technical clearance given on 16.04.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 01.07.23 | 09.01.24 | 22.01.24 | 08.03.24 | 06.04.24 | 10.04.24 | 10.04.24 | 12.04.24 |  |  |  | 16.04.24 | 16.04.24 | 20.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Butterfly Valves | LE23M596-M-WS-CW-PR-1007 | LE23M596-M-WS-CW-PR-1007-D | Sigmaflow | Sent to BU Operations | 106 | 1. L&T Observation sent on 10.01.2024 2. Reply received on 12.01.2024 3. Electrical observation sent for Acutator on 08.02.2024 4. Vendor replied on electrical points on 15.02.2024 5. Instrumentation query sent on 16.02.2024 6. Technical Clearance on 29.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 01.07.23 | 30.11.23 | 10.01.24 | 12.01.24 | 08.02.24 | 15.02.24 | [5 empty] | 29.02.24 | 29.02.24 | 20.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Butterfly Valves | LE23M596-M-WS-CW-PR-1007 | LE23M596-M-WS-CW-PR-1007-E | Orbit Engineers | Sent to BU Operations | 106 | 1. Observations sent on 05.01.2024 2. Replies received on 11.01.2024 3. GA and QAP received on 19.01.2024 4. Electrical observation sent on 08.02.2024 5. Inst. Comments sent on 22.02.2024 6. Wiring diagram for actuators received on 04.03.2024 7. E&I Observations sent on 27.03.2024 8. Vendor replied on 09.04.2024 & 10.04.2024 9. Technical clearance given on 16.04.2024 | 78791 45143 | yogesh.orbitengineers@gmail.com |  | 01.07.23 | 23.12.23 | 05.01.24 | 11.01.24 | 08.02.24 | 04.03.24 | 27.03.24 | 09.04.24 |  |  |  | 16.04.24 | 16.04.24 | 20.04.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Butterfly Valves | LE23M596-M-WS-CW-PR-1007 | LE23M596-M-WS-CW-PR-1007-F | MAGWEN | Sent to BU Operations | 51 |  |  |  |  | 27.05.24 | 29.05.24 | 06.06.24 | 10.06.24 | [7 empty] | 11.06.24 | 11.06.24 | 14.06.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Dual Plate Check Valves | LE23M596-M-WS-CW-PR-1008 | LE23M596-M-WS-CW-PR-1008-A | Hawle | Regret offer | PR Closed | not in scope | 99440 74005 | sagaya.prabhu@hawle.in |  | 01.07.23 | [24 empty] | srb@lntecc.com-21.05.2024-16:54:17
Ballia WSP | Mechanical | Dual Plate Check Valves | LE23M596-M-WS-CW-PR-1008 | LE23M596-M-WS-CW-PR-1008-B | AVK | Sent to BU Operations | PR Closed | 1. Observations sent on 29.11.2023 2. Compliance received on 04.12.2023 3. Observations sent on 07-12-2023 4. Compliance received on 04.01.2024 5. Observations sent on 04.01.2024 6. Observation sent on 16.02.2024 7. Vendor replied on 23.02.24 8. Technical clearance sent on 27.02.2024 | 91769 66455 | subhash@avkindia.com |  | 01.07.23 | 28.11.23 | 29.11.23 | 04.12.23 | 07.12.23 | 04.01.24 | 16.02.24 | 23.02.24 |  |  |  | 27.02.24 | 27.02.24 | 07.03.24 | T1 | [10 empty] | srb@lntecc.com-10.06.2024-18:04:05
Ballia WSP | Mechanical | Dual Plate Check Valves | LE23M596-M-WS-CW-PR-1008 | LE23M596-M-WS-CW-PR-1008-C | VAG | Post-order technically cleared | 48 | 1. Observations sent on 22.01.2024 2. Reminder sent on 05.03.2024 3. Technical compliance received on 08.03.2024 4. Technically cleared on 15.03.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 01.07.23 | 09.01.24 | 22.01.24 | 08.03.24 | [7 empty] | 15.03.24 | 15.03.24 | 15.03.24 | T1 | 03.06.24 | VAG | 07.06.24 | 14.06.24 | 17.06.24 | 17.06.24 |  |  |  | 02.08.24 | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Dual Plate Check Valves | LE23M596-M-WS-CW-PR-1008 | LE23M596-M-WS-CW-PR-1008-D | Sigmaflow | Sent to BU Operations | PR Closed | 1. L&T Observation sent on 10.01.2024 2. Reply received on 12.01.2024 3. Electrical observation sent for Acutator on 08.02.2024 4. Vendor replied on electrical points on 15.02.2024 5. Instrumentation query sent on 16.02.2024 6. Technical clearance on 27.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 01.07.23 | 30.11.23 | 10.01.24 | 12.01.24 | 08.02.24 | 15.02.24 | [5 empty] | 27.02.24 | 27.02.24 | 07.03.24 | T1 | [10 empty] | srb@lntecc.com-10.06.2024-18:04:05
Ballia WSP | Mechanical | Dual Plate Check Valves | LE23M596-M-WS-CW-PR-1008 | LE23M596-M-WS-CW-PR-1008-E | Orbit Engineers | Sent to BU Operations | PR Closed | 1. Observations sent on 05.01.2024 2. Replies received on 11.01.2024 3. GA and QAP received on 19.01.2024 4. Electrical observation sent on 08.02.2024 5. Technical Clearance on 27.02.2024 | 78791 45143 | yogesh.orbitengineers@gmail.com |  | 01.07.23 | 23.12.23 | 05.01.24 | 19.01.24 | 08.02.24 | 27.02.24 | [5 empty] | 27.02.24 | 27.02.24 | 07.03.24 | T1 | [10 empty] | srb@lntecc.com-10.06.2024-18:04:05
Ballia WSP | Mechanical | Dual Plate Check Valves | LE23M596-M-WS-CW-PR-1008 | LE23M596-M-WS-CW-PR-1008-F | MAGWEN | Sent to BU Operations | PR Closed |  |  |  |  | 07.05.24 | 10.05.24 | 10.05.24 | [8 empty] | 13.05.24 | 13.05.24 | 13.05.24 | T2 | [10 empty] | srb@lntecc.com-10.06.2024-18:04:05
Ballia WSP | Mechanical | Air Valves with Isolation valve | LE23M596-M-WS-CW-PR-1009 | LE23M596-M-WS-CW-PR-1009-A | Hawle | Sent to BU Operations | PR Closed | 1. Observations sent on 08.01.2024 2. Observations sent on 23.02.24 3. Vendor replied on 11.03.2024 4. Technical clearance on 05.04.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 01.07.23 | 12.12.23 | 23.02.24 | 11.03.24 | [7 empty] | 05.04.24 | 05.04.24 | 15.04.24 | T1 | [10 empty] | srb@lntecc.com-21.06.2024-14:38:23
Ballia WSP | Mechanical | Air Valves with Isolation valve | LE23M596-M-WS-CW-PR-1009 | LE23M596-M-WS-CW-PR-1009-B | AVK | Post-order pending with EDRC | 48 | 1. Observations sent on 29.11.2023 2. Compliance received on 04.12.2023 3. Observations sent on 07-12-2023 4. Compliance received on 04.01.2024 5. Observations sent on 04.01.2024 6. Observation sent on 16.02.2024 7. Vendor reply received on 23.02.24 8. Technically cleared on 27.02.2024 | 91769 66455 | subhash@avkindia.com |  | 01.07.23 | 28.11.23 | 29.11.23 | 04.12.23 | 07.12.23 | 04.01.24 | 16.02.24 | 23.02.24 |  |  |  | 27.02.24 | 27.02.24 | 15.04.24 | T1 | 11.06.24 | AVK | 17.06.24 | [6 empty] | 10.08.24 | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Air Valves with Isolation valve | LE23M596-M-WS-CW-PR-1009 | LE23M596-M-WS-CW-PR-1009-C | VAG | Sent to BU Operations | PR Closed | 1. Observations sent on 22.01.2024 2. Reminder sent on 05.03.2024 3. Technical compliance received on 08.03.2024 4. Observations sent on 06.04.2024 5. Vendor replied on 10.04.2024 6. L&T Observation sent on 10.04.2024 7. Vendor replied on 12.04.2024 8. technically cleared on 15.04.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 01.07.23 | 09.01.24 | 22.01.24 | 08.03.24 | 06.04.24 | 10.04.24 | 10.04.24 | 12.04.24 |  |  |  | 15.04.24 | 15.04.24 | 15.04.24 | T1 | [10 empty] | srb@lntecc.com-21.06.2024-14:38:23
Ballia WSP | Mechanical | Air Valves with Isolation valve | LE23M596-M-WS-CW-PR-1009 | LE23M596-M-WS-CW-PR-1009-D | Sigmaflow | Sent to BU Operations | PR Closed | 1. L&T Observation sent on 10.01.2024 2. Reply received on 12.01.2024 3. Electrical observation sent for Acutator on 08.02.2024 4. Vendor replied on electrical points on 15.02.2024 5. Instrumentation query sent on 16.02.2024 6. Technical clearance on 27.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 01.07.23 | 30.11.23 | 10.01.24 | 12.01.24 | 15.02.24 | [6 empty] | 27.02.24 | 27.02.24 | 15.04.24 | T1 | [10 empty] | srb@lntecc.com-21.06.2024-14:38:23
Ballia WSP | Mechanical | Air Valves with Isolation valve | LE23M596-M-WS-CW-PR-1009 | LE23M596-M-WS-CW-PR-1009-E | Orbit Engineers | Sent to BU Operations | PR Closed | 1. Observations sent on 05.01.2024 2. Replies received on 11.01.2024 3. GA and QAP received on 19.01.2024 4. Electrical observation sent on 08.02.2024 5. Technical Clearance on 27.02.2024 | 78791 45143 | yogesh.orbitengineers@gmail.com |  | 01.07.23 | 23.12.23 | 05.01.24 | 11.01.24 | 08.02.24 | 27.02.24 | [5 empty] | 27.02.24 | 27.02.24 | 15.04.24 | T1 | [10 empty] | srb@lntecc.com-21.06.2024-14:38:23
Ballia WSP | Mechanical | Air Valves with Isolation valve | LE23M596-M-WS-CW-PR-1009 | LE23M596-M-WS-CW-PR-1009-F | MAGWEN | Sent to BU Operations | PR Closed |  |  |  |  | 27.05.24 | 29.05.24 | 06.06.24 | 10.06.24 | [7 empty] | 11.06.24 | 11.06.24 | 14.06.24 | T1 | [10 empty] | srb@lntecc.com-19.06.2024-16:40:11
Ballia WSP | Mechanical | Dewatering Pump | LE23M596-M-WS-CW-PR-1010 | LE23M596-M-WS-CW-PR-1010-A | Kishor Pumps | Regret offer | PR Closed | 1. Reminder sent on 04.03.2024 | 91766 10938 | P.Dixon@kishorpumps.com |  | 30.01.24 | [24 empty] | srb@lntecc.com-03.06.2024-15:05:02
Ballia WSP | Mechanical | Dewatering Pump | LE23M596-M-WS-CW-PR-1010 | LE23M596-M-WS-CW-PR-1010-B | MBH Pumps | Sent to BU Operations | PR Closed | 1. Elect. and inst. comments sent on 21.03.2024 2. Vendor reply received on 27.03.2024 & 28.03.2024 | 98254 67472 99200 13772 | Parth@mbhpumps.com |  | 30.01.24 | 06.02.24 | 21.03.24 | [8 empty] | 22.03.24 | 22.03.24 | 10.05.24 | T3 | [10 empty] | gopal.samarth@lntecc.com-04.06.2024-12:04:17
Ballia WSP | Mechanical | Dewatering Pump | LE23M596-M-WS-CW-PR-1010 | LE23M596-M-WS-CW-PR-1010-C | Jasco Pump | Post-order technically cleared | 62 | 1. Electrical motor specifications and observations sent on 16.02.2024 2. Revised offer received on 10.03.2024 | 70690 99037 | info@jascopump.com |  | 30.01.24 | 03.02.24 | 16.02.24 | [8 empty] | 22.03.24 | 22.03.24 | 10.05.24 | T3 | 28.05.24 | Jasco Pump | 03.06.24 | 03.06.24 | 03.06.24 | 03.06.24 |  |  |  | 27.07.24 | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Mechanical | Surge Equipments | LE23M596-M-WS-CW-PR-1011 | LE23M596-M-WS-CW-PR-1011-A |  | Enquiry yet to float | NA | [29 empty] | srb@lntecc.com-21.05.2024-16:54:18
Ballia WSP | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE23M596-I-WS-WT-PR-5501 | LE23M596-I-WS-WT-PR-5501-A | H Guru | Pre-order comments issued | 33 |  |  |  |  | 29.11.23 | 17.05.24 | 24.05.24 | 25.05.24 | 02.07.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE23M596-I-WS-WT-PR-5501 | LE23M596-I-WS-WT-PR-5501-B | General instruments | Pre-order comments issued | 33 |  |  |  |  | 29.11.23 | 17.05.24 | 24.05.24 | 24.05.24 | 02.07.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Pressure Switch | LE23M596-I-WS-WT-PR-5502 | LE23M596-I-WS-WT-PR-5502-A | General instruments | Pre-order comments issued | 33 |  |  |  |  | 29.11.23 | 17.05.24 | 24.05.24 | 24.05.24 | 02.07.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Pressure Switch | LE23M596-I-WS-WT-PR-5502 | LE23M596-I-WS-WT-PR-5502-B | H Guru | Pre-order pending with EDRC | 32 |  |  |  |  | 29.11.23 | 17.05.24 | 24.05.24 | 25.05.24 | 02.07.24 | 03.07.24 | [19 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Pressure transmitter | LE23M596-I-WS-WT-PR-5503 | LE23M596-I-WS-WT-PR-5503-A | Siemens | Pre-order comments issued | 30 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 17.05.24 | 05.07.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Pressure transmitter | LE23M596-I-WS-WT-PR-5503 | LE23M596-I-WS-WT-PR-5503-B | E&H | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Pressure transmitter | LE23M596-I-WS-WT-PR-5503 | LE23M596-I-WS-WT-PR-5503-C | Vega | Pre-order comments issued | 33 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 14.12.23 | 24.05.24 | 27.05.24 | 02.07.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Pressure transmitter | LE23M596-I-WS-WT-PR-5503 | LE23M596-I-WS-WT-PR-5503-D | SBEM | Pre-order comments issued | 72 |  |  |  |  | 29.11.23 | 17.05.24 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Pressure transmitter | LE23M596-I-WS-WT-PR-5503 | LE23M596-I-WS-WT-PR-5503-E | EIP Enviro | Pre-order comments issued | 61 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 05.12.23 | 22.05.24 | 25.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Float & Board Level gauge | LE23M596-I-WS-WT-PR-5504 | LE23M596-I-WS-WT-PR-5504-A | SBEM | Pre-order comments issued | 90 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 04.12.23 | 06.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:06
Ballia WSP | Instrumentation | Float & Board Level gauge | LE23M596-I-WS-WT-PR-5504 | LE23M596-I-WS-WT-PR-5504-B | Pune techtrol | Pre-order comments issued | 68 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 25.12.23 | 28.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Level switch - Conductivity type | LE23M596-I-WS-WT-PR-5505 | LE23M596-I-WS-WT-PR-5505-A | Vega | Regret offer | PR Closed |  |  |  |  | 29.11.23 | [24 empty] | rajesh.muthuraj@lntecc.com-24.05.2024-16:47:15
Ballia WSP | Instrumentation | Level switch - Conductivity type | LE23M596-I-WS-WT-PR-5505 | LE23M596-I-WS-WT-PR-5505-B | SBEM | Pre-order comments issued | 94 | Awaiting electrode length finalisation |  |  |  | 29.11.23 | 12.12.23 | 02.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Level switch - Conductivity type | LE23M596-I-WS-WT-PR-5505 | LE23M596-I-WS-WT-PR-5505-C | EIP Enviro | Regret offer | PR Closed |  |  |  |  | 29.11.23 | [24 empty] | justin.v@lntecc.com-24.05.2024-11:26:00
Ballia WSP | Instrumentation | Ultrasonic level transmitter | LE23M596-I-WS-WT-PR-5506 | LE23M596-I-WS-WT-PR-5506-A | Mirrant | Pre-order comments issued | 61 | Awaiting OHT details from Mech |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic level transmitter | LE23M596-I-WS-WT-PR-5506 | LE23M596-I-WS-WT-PR-5506-B | Siemens | Pre-order comments issued | 72 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 20.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic level transmitter | LE23M596-I-WS-WT-PR-5506 | LE23M596-I-WS-WT-PR-5506-C | E&H | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic level transmitter | LE23M596-I-WS-WT-PR-5506 | LE23M596-I-WS-WT-PR-5506-D | Vega | Pre-order comments issued | 61 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 14.12.23 | 24.05.24 | 27.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic level transmitter | LE23M596-I-WS-WT-PR-5506 | LE23M596-I-WS-WT-PR-5506-E | SBEM | Pre-order comments issued | 72 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 12.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic level transmitter | LE23M596-I-WS-WT-PR-5506 | LE23M596-I-WS-WT-PR-5506-F | EIP Enviro | Pre-order comments issued | 61 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 05.12.23 | 22.05.24 | 25.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Radar level transmitter | LE23M596-I-WS-WT-PR-5507 | LE23M596-I-WS-WT-PR-5507-A | Mirrant | Pre-order comments issued | 61 |  |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Radar level transmitter | LE23M596-I-WS-WT-PR-5507 | LE23M596-I-WS-WT-PR-5507-B | Siemens | Pre-order comments issued | 72 |  |  |  |  | 29.11.23 | 20.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Radar level transmitter | LE23M596-I-WS-WT-PR-5507 | LE23M596-I-WS-WT-PR-5507-C | E&H | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Radar level transmitter | LE23M596-I-WS-WT-PR-5507 | LE23M596-I-WS-WT-PR-5507-D | Vega | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 14.12.23 | 24.05.24 | 27.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Radar level transmitter | LE23M596-I-WS-WT-PR-5507 | LE23M596-I-WS-WT-PR-5507-E | SBEM | Pre-order comments issued | 72 |  |  |  |  | 29.11.23 | 12.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Radar level transmitter | LE23M596-I-WS-WT-PR-5507 | LE23M596-I-WS-WT-PR-5507-F | EIP Enviro | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 05.12.23 | 22.05.24 | 25.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Loss of head transmitter | LE23M596-I-WS-WT-PR-5508 | LE23M596-I-WS-WT-PR-5508-A | Siemens | Pre-order comments issued | 72 |  |  |  |  | 29.11.23 | 20.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Loss of head transmitter | LE23M596-I-WS-WT-PR-5508 | LE23M596-I-WS-WT-PR-5508-B | E&H | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Loss of head transmitter | LE23M596-I-WS-WT-PR-5508 | LE23M596-I-WS-WT-PR-5508-C | Vega | Regret offer | PR Closed |  |  |  |  | 29.11.23 | [24 empty] | rajesh.muthuraj@lntecc.com-24.05.2024-16:08:07
Ballia WSP | Instrumentation | Loss of head transmitter | LE23M596-I-WS-WT-PR-5508 | LE23M596-I-WS-WT-PR-5508-D | SBEM | Pre-order comments issued | 72 |  |  |  |  | 29.11.23 | 12.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Loss of head transmitter | LE23M596-I-WS-WT-PR-5508 | LE23M596-I-WS-WT-PR-5508-E | EIP Enviro | Regret offer | PR Closed |  |  |  |  | 29.11.23 | [24 empty] | justin.v@lntecc.com-17.05.2024-18:12:00
Ballia WSP | Instrumentation | Rate for flow transmitter | LE23M596-I-WS-WT-PR-5509 | LE23M596-I-WS-WT-PR-5509-A | Mirrant | Pre-order comments issued | 61 |  |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Rate for flow transmitter | LE23M596-I-WS-WT-PR-5509 | LE23M596-I-WS-WT-PR-5509-B | SBEM | Pre-order comments issued | 72 |  |  |  |  | 29.11.23 | 04.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Rate for flow transmitter | LE23M596-I-WS-WT-PR-5509 | LE23M596-I-WS-WT-PR-5509-C | Pune techtrol | Pre-order comments issued | 90 |  |  |  |  | 29.11.23 | 25.12.23 | 06.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Rate for flow transmitter | LE23M596-I-WS-WT-PR-5509 | LE23M596-I-WS-WT-PR-5509-D | H Guru | Regret offer | PR Closed |  |  |  |  | 29.11.23 | [24 empty] | justin.v@lntecc.com-17.05.2024-18:12:00
Ballia WSP | Instrumentation | Rate for flow transmitter | LE23M596-I-WS-WT-PR-5509 | LE23M596-I-WS-WT-PR-5509-E | Siemens | Pre-order comments issued | 72 |  |  |  |  | 29.11.23 | 04.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Rate for flow transmitter | LE23M596-I-WS-WT-PR-5509 | LE23M596-I-WS-WT-PR-5509-F | Pune techtrol | Pre-order comments issued | 90 |  |  |  |  | 29.11.23 | 25.12.23 | 06.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Bypass Rotameter | LE23M596-I-WS-WT-PR-5510 | LE23M596-I-WS-WT-PR-5510-A | Scientific Devices | Pre-order comments issued | 73 |  |  |  |  | 29.11.23 | 05.12.23 | 23.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Bypass Rotameter | LE23M596-I-WS-WT-PR-5510 | LE23M596-I-WS-WT-PR-5510-B | Eureka Forbes | Pre-order comments issued | 87 |  |  |  |  | 29.11.23 | 01.12.23 | 09.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Bypass Rotameter | LE23M596-I-WS-WT-PR-5510 | LE23M596-I-WS-WT-PR-5510-C | Mirrant | Pre-order comments issued | 61 |  |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Electromagnectic flow meter | LE23M596-I-WS-WT-PR-5511 | LE23M596-I-WS-WT-PR-5511-A | Krohne | Pre-order comments issued | 61 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 02.12.23 | 24.05.24 | 27.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Electromagnectic flow meter | LE23M596-I-WS-WT-PR-5511 | LE23M596-I-WS-WT-PR-5511-B | ABB | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Electromagnectic flow meter | LE23M596-I-WS-WT-PR-5511 | LE23M596-I-WS-WT-PR-5511-C | E&H | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Electromagnectic flow meter | LE23M596-I-WS-WT-PR-5511 | LE23M596-I-WS-WT-PR-5511-D | Siemens | Pre-order comments issued | 72 | Awaiting OHT details from Mech |  |  |  | 29.11.23 | 30.11.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Electromagnectic flow meter | LE23M596-I-WS-WT-PR-5511 | LE23M596-I-WS-WT-PR-5511-E | Mirrant | Pre-order comments issued | 61 | Awaiting OHT details from Mech |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Electromagnectic flow meter | LE23M596-I-WS-WT-PR-5511 | LE23M596-I-WS-WT-PR-5511-F | SBEM | Pre-order comments issued | 72 | Awaiting OHT details from Mech |  |  |  | 14.12.23 | 20.12.23 | 24.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic type Open channel flow transmitter | LE23M596-I-WS-WT-PR-5512 | LE23M596-I-WS-WT-PR-5512-A | Krohne | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic type Open channel flow transmitter | LE23M596-I-WS-WT-PR-5512 | LE23M596-I-WS-WT-PR-5512-B | ABB | Pre-order comments issued | 68 |  |  |  |  | 29.11.23 | 05.12.23 | 28.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic type Open channel flow transmitter | LE23M596-I-WS-WT-PR-5512 | LE23M596-I-WS-WT-PR-5512-C | E&H | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic type Open channel flow transmitter | LE23M596-I-WS-WT-PR-5512 | LE23M596-I-WS-WT-PR-5512-D | Mirrant | Pre-order comments issued | 61 |  |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic type Open channel flow transmitter | LE23M596-I-WS-WT-PR-5512 | LE23M596-I-WS-WT-PR-5512-E | EIP Enviro | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 05.12.23 | 22.05.24 | 25.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Ultrasonic type Open channel flow transmitter | LE23M596-I-WS-WT-PR-5512 | LE23M596-I-WS-WT-PR-5512-F | SBEM | Pre-order comments issued | 61 |  |  |  |  | 14.12.23 | 20.12.23 | 24.05.24 | 04.06.24 | [21 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | pH Meter | LE23M596-I-WS-WT-PR-5513 | LE23M596-I-WS-WT-PR-5513-A | Hach | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 21.05.24 | 04.06.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | pH Meter | LE23M596-I-WS-WT-PR-5513 | LE23M596-I-WS-WT-PR-5513-B | E&H | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | pH Meter | LE23M596-I-WS-WT-PR-5513 | LE23M596-I-WS-WT-PR-5513-C | Emerson | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 21.05.24 | 04.06.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | pH Meter | LE23M596-I-WS-WT-PR-5513 | LE23M596-I-WS-WT-PR-5513-D | Mirrant | Pre-order comments issued | 61 |  |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Turbidity meter | LE23M596-I-WS-WT-PR-5514 | LE23M596-I-WS-WT-PR-5514-A | Hach | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 21.05.24 | 04.06.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Turbidity meter | LE23M596-I-WS-WT-PR-5514 | LE23M596-I-WS-WT-PR-5514-B | E&H | Awaiting pre-offer from vendor | 75 |  |  |  |  | 29.11.23 |  | 21.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Turbidity meter | LE23M596-I-WS-WT-PR-5514 | LE23M596-I-WS-WT-PR-5514-C | Emerson | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 21.05.24 | 04.06.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Turbidity meter | LE23M596-I-WS-WT-PR-5514 | LE23M596-I-WS-WT-PR-5514-D | Mirrant | Pre-order comments issued | 61 |  |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Residual Chlorine Analyzer | LE23M596-I-WS-WT-PR-5515 | LE23M596-I-WS-WT-PR-5515-A | Hach | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 21.05.24 | 04.06.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Residual Chlorine Analyzer | LE23M596-I-WS-WT-PR-5515 | LE23M596-I-WS-WT-PR-5515-B | E&H | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Residual Chlorine Analyzer | LE23M596-I-WS-WT-PR-5515 | LE23M596-I-WS-WT-PR-5515-C | Emerson | Pre-order comments issued | 61 |  |  |  |  | 29.11.23 | 21.05.24 | 04.06.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Residual Chlorine Analyzer | LE23M596-I-WS-WT-PR-5515 | LE23M596-I-WS-WT-PR-5515-D | Mirrant | Pre-order comments issued | 61 |  |  |  |  | 01.12.23 | 13.12.23 | 20.05.24 | 22.05.24 | 04.06.24 | [20 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M596-I-WS-WT-PR-5516 | LE23M596-I-WS-WT-PR-5516-A | SIAS | Pre-order comments issued | 61 | Awaiting finalisation of PLC I/O |  |  |  | 29.11.23 | 13.05.23 | 06.05.24 | 04.06.24 | [21 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M596-I-WS-WT-PR-5516 | LE23M596-I-WS-WT-PR-5516-B | Mitsubishi | Pre-order comments issued | 90 | Awaiting finalisation of PLC I/O |  |  |  | 29.11.23 | 04.12.23 | 06.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M596-I-WS-WT-PR-5516 | LE23M596-I-WS-WT-PR-5516-C | Schneider | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M596-I-WS-WT-PR-5516 | LE23M596-I-WS-WT-PR-5516-D | Autosys | Awaiting pre-offer from vendor | 249 |  |  |  |  | 29.11.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M596-I-WS-WT-PR-5516 | LE23M596-I-WS-WT-PR-5516-E | Mirrant | Pre-order comments issued | 90 | Awaiting finalisation of PLC I/O |  |  |  | 01.12.23 | 13.12.23 | 06.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Instrumentation Control & signal Cables | LE23M596-I-WS-WT-PR-5517 | LE23M596-I-WS-WT-PR-5517-A | Axelon | Pre-order comments issued | 75 |  |  |  |  | 29.11.23 | 02.12.23 | 21.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Instrumentation Control & signal Cables | LE23M596-I-WS-WT-PR-5517 | LE23M596-I-WS-WT-PR-5517-B | Cords | Pre-order comments issued | 79 |  |  |  |  | 29.11.23 | 14.12.23 | 17.05.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | UPS | LE23M596-I-WS-WT-PR-5518 | LE23M596-I-WS-WT-PR-5518-A | Hitachi | Pre-order comments issued | 61 | Awaiting load sizing finalisation |  |  |  | 29.11.23 | 07.12.23 | 06.05.24 | 04.06.24 | [21 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | UPS | LE23M596-I-WS-WT-PR-5518 | LE23M596-I-WS-WT-PR-5518-B | Vertiv | Pre-order comments issued | 96 | Awaiting load sizing finalisation |  |  |  | 29.11.23 | 06.02.24 | 30.04.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | UPS | LE23M596-I-WS-WT-PR-5518 | LE23M596-I-WS-WT-PR-5518-C | Liveline | Pre-order comments issued | 61 | Awaiting load sizing finalisation |  |  |  | 29.11.23 | 07.12.23 | 06.05.24 | 04.06.24 | [21 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Instrumentation | Solar and Battery system | LE23M596-I-WS-WT-PR-5519 | LE23M596-I-WS-WT-PR-5519-A | SIAS | Pre-order comments issued | 61 | Awaiting load sizing finalisation |  |  |  | 29.11.23 | 13.05.24 | 04.06.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Electrical | Motors | LE23M596-E-WS-CW-PR-4001 | LE23M596-E-WS-CW-PR-4001-A | CGL | Awaiting pre-offer from vendor | 400 |  |  |  |  | 01.07.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Electrical | Motors | LE23M596-E-WS-CW-PR-4001 | LE23M596-E-WS-CW-PR-4001-B | ABB | Awaiting pre-offer from vendor | 400 |  |  |  |  | 01.07.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Electrical | Motors | LE23M596-E-WS-CW-PR-4001 | LE23M596-E-WS-CW-PR-4001-C | Siemens | Awaiting pre-offer from vendor | 400 |  |  |  |  | 01.07.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Electrical | Transformers | LE23M596-E-WS-CW-PR-4002 | LE23M596-E-WS-CW-PR-4002-A | ITE | Sent to BU Operations | 155 | 1. Clarification sent on 21.12.2023 2. Reminder sent on 11.01.2024 3. Reminder sent on 03.02.2024 4. Technical Offer received on 05.02.2024 5. Replies received from vendor on 12.02.2024 6. M/s ITE will visit chennai on 15.02.2024 (Ballia & Firozabad) 6. Vendor follow up mail received on 16.02.2024 7. Vendor revised technical offer received on 16.02.2024 (under review) 8. Vendor follow up mail received on 26.02.2024 9. L&T Observations sent on 26.02.2024 10. Vendor replied on 29.02.2024 11. Vendor follow up mail received on 01.03.2024 12. Technical Clearance given on 02.03.2024 | 98991 33500 | sales@indiantransformers.com |  | 01.12.23 | 17.08.23 | 21.12.23 | 05.02.24 | 26.02.24 | 29.02.24 | [5 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Electrical | Transformers | LE23M596-E-WS-CW-PR-4002 | LE23M596-E-WS-CW-PR-4002-B | Uttam Bharat | Regret offer | PR Closed | 1. Vendor asked clarification on 07.12.2023 2. L&T sent clarification on 19.12.2023 3. Reminder sent on 11.01.2024 4. Reminder sent on 23.01.2024 5. Query raised by vendor on 24.01.2024 6. Bidder Regretted Level-2 T/F. (closed) | 88249 10561 | marketing@uttam-bharat.com |  | 01.12.23 | [24 empty] | karthik.ajithkumar@lntecc.com-17.05.2024-09:34:25
Ballia WSP | Electrical | Transformers | LE23M596-E-WS-CW-PR-4002 | LE23M596-E-WS-CW-PR-4002-C | Voltech | Sent to BU Operations | 155 | 1. Observations sent on 27.12.2023 2. Replies received on 03.01.2024 3. Reminder sent to get vendor's reply on 31.01.2024 4. Vendor resent same replies again on 31.01.2024 5. Technical meeting scheduled on 05.02.2024 6. Meeting happened at 05.02.2024 7.MOM sent to Vendor on 21.02.2024, awaiting revised offer 8. Revised offer sent by vendor on 27.02.2024 9.Technical Clearance given on 02.03.2024 | 96000 95932 | ragu.g@voltechgroup.com |  | 01.12.23 | 08.12.23 | 27.12.23 | 03.01.24 | 21.02.24 | 27.02.24 | [5 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:07
Ballia WSP | Electrical | Transformers | LE23M596-E-WS-CW-PR-4002 | LE23M596-E-WS-CW-PR-4002-D | Voltamp | Sent to BU Operations | 146 | 1. Vendor asked clarification for bid submission on 03.01.2024 2. Provided clarification on 14.01.2024 3. Reminder on 20.01.2024 4. Reminder on 23.01.2024 5. Technical offer received on 23.01.2024 6. Meeting scheduled on 08.02.2024 7. MOM sent to Bidder on 21.02.2024, awaiting revised offer 8. Revised offer received on 24.02.2024 9. Mail sent to vendor for final consolidation on 02.03.2024 10. Reminder sent on 05.03.2024 9 (final confirmation) 11. Vendor replied on 07.03.2024 12. Technical clearance given on 11.03.2024 | 78618 14751 | ks_vtlchn@voltamptransformers.com |  | 01.12.23 | 23.01.24 | 21.02.24 | 24.02.24 | 02.03.24 | 07.03.24 | [5 empty] | 11.03.24 | 11.03.24 | 11.03.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Switchgear, Switchyard | LE23M596-E-WS-CW-PR-4003 | LE23M596-E-WS-CW-PR-4003-A | Universal Power | Sent to BU Operations | 87 | 1. Meeting arranged on 14.02.2024 2. MOM and revised SLD will send on 20.02.2024 (motor rating changed) 3.Revised SLD, sent on 12.03.2024 (motor rating, trafo rating changed) 4. Reminder sent on 20.03.2024 5. Reminder sent on 27.03.2024 6. Reminder sent on 30.03.2024 7. Revised offer received on 04.04.2024 8. Comments sent on 15.04.2024 9. Reminder sent on 22.04.2024 10. Reminder sent on 23.04.2024 11. Revised offer received on 23.04.2024 & 26.04.2024 12. pre-order cleared on 09.05.2024 | 95000 95075 | deepak@upe.co.in |  | 01.12.23 | 03.02.24 | 12.03.24 | 04.04.24 | 15.04.24 | 26.04.24 | [5 empty] | 09.05.24 | 09.05.24 | 09.05.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Switchgear, Switchyard | LE23M596-E-WS-CW-PR-4003 | LE23M596-E-WS-CW-PR-4003-B | Kontact | Sent to BU Operations | 87 | 1. Meeting arranged on 13.02.2024 2. vendor follow up on 19.02.2024 3. Revised SLD, sent on 12.03.2024 (motor rating, trafo rating changed) 4. Reminder sent on 27.03.2024 5. Reminder sent on 30.03.2024 6. Offer received on 04.04.2024 7. Comments sent on 15.04.2024 8. Reminder sent on 22.04.2024 9. Revised technical offer received on 24.04.2024 10. Revised offer for Option 2 requested on 29.04.2024 11.Recived offer on 30.04.24 12. Pre order clearance given on 9.5.24 | 90878 40000 | vijendra@kontact.in |  | 01.12.23 | 4.4.24 | 15.4.24 | 24.4.24 | 29.4.24 | 30.4.24 | 9.5.24 |  |  |  |  | 30.4.24 | 9.5.24 | 9.5.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Switchgear, Switchyard | LE23M596-E-WS-CW-PR-4003 | LE23M596-E-WS-CW-PR-4003-C | Vivid Electromech | Sent to BU Operations | 87 | 1. L&T Observations sent on 03.02.2024, meeting proposed on 12.02.2024 2. Revised technical offer with replies sent on 13.02.2024 3. Updated SLD shared with vendor for obtaining revised offer on 15.02.2024 (revised offer awating)_ 4. Revised offer received on 17.02.2024 5.Revised SLD, sent on 12.03.2024 (motor rating, trafo rating changed) 6. Revised offer received on 16.03.2024 7. Comments sent on 30.03.2024 8. Vendor replied on 09.04.2024 9. L&T Observations sent on 15.04.2024 10. Revised offer sent on 22.04.2024 11. Comments sent on 23.04.2024 12. Reminder sent on 29.04.2024 13. Vendor replied on 29.04.2024 14. Pre order clearance given on 9.5.24 | 91679 80556 | chennai.sales@vividgroup.in |  | 01.12.23 | 13.2.24 | 15.2.24 | 17.2.24 | 12.3.24 | 16.3.24 | 30.3.24 | 29.4.24 | 9.5.24 |  |  | 29.4.24 | 9.5.24 | 9.5.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M596-E-WS-CW-PR-4004 | LE23M596-E-WS-CW-PR-4004-A | Sri Ragavendra Controls | Pre-order pending with EDRC | 121 | 1. Revised SLD sent on 19.02.2024 (motor rating changed) 2. meeting arranged on 22.02.2024 (vendor not visited) 3. Revised SLD sent on 12.03.2024 (motor rating, trafo rating changed) 4. Offer received on 15.03.2024 5. Comments sent to vendor on 03.04.2024 6. Vendor replied on 05.04.2024 7. L&T Observation sent on 05.04.2024 | 98947 13024 | ashok@ragavendracontrol.com |  | 01.12.23 | 5.4.24 | [23 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M596-E-WS-CW-PR-4004 | LE23M596-E-WS-CW-PR-4004-B | Universal Power | Pre-order comments issued | 66 | 1. Meeting arranged on 14.02.2024 2. Revised SLD, sent on 12.03.2024 (motor rating, trafo rating changed) 3. Reminder sent on 27.03.2024 4.revised offer received on 09.04.24 5. Comments sent on 30.5.24 | 95000 95075 | deepak@upe.co.in |  | 01.12.23 | 9.4.24 | 30.5.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M596-E-WS-CW-PR-4004 | LE23M596-E-WS-CW-PR-4004-C | Kontact | Pre-order comments issued | 65 | 1. Meeting arranged on 13.02.2024 2. Technical offer awiting from vendor 3. Revised SLD, sent on 12.03.2024 (motor rating, trafo rating changed) 4. Reminder sent on 27.03.2024 5. Offer received on 28.03.2024 6. revised offer received on 4.04.24 7.Comments sent on 31.5.24 | 90878 40000 | vijendra@kontact.in |  | 01.12.23 | 4.4.24 | 31.5.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M596-E-WS-CW-PR-4004 | LE23M596-E-WS-CW-PR-4004-D | Stambh | Pre-order pending with EDRC | 25 | 1. Revised SLD, will be provided on 06.03.24 (motor rating, trafo rating changed) 2. Revised SLD, sent on 12.03.24 (motor rating, trafo rating changed) 3. Revised offer received on 20.03.2024 4. Index for drawings sent by vendor on 21.03.2024 | 97920 01030 | rupali@stambhindia.com |  | 01.12.23 | 21.3.24 | 02.07.24 | 10.7.24 | [21 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M596-E-WS-CW-PR-4004 | LE23M596-E-WS-CW-PR-4004-E | Vivid Electromech | Pre-order pending with EDRC | 38 | 1. Query raised by vendor on 26.02.2024 2. Query resonded by L&T on 26.02.2024 3. Revised Technical offer received on 28.02.2024 4. Revised SLD, sent on 12.03.24 (motor rating, trafo rating changed) 5. Dimensions requested by L&T on 14.03.2024 6. Vendor responded on 19.03.2024 (regarding dimension) 7. Reminder sent on 27.03.2024 8. Vendor replied on 09.04.2024 9. Comments sent on 1.6.24 | 91679 80556 | chennai.sales@vividgroup.in |  | 07.12.23 | 9.4.24 | 1.6.24 | 27.06.24 | [21 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | DG Sets | LE23M596-E-WS-CW-PR-4005 | LE23M596-E-WS-CW-PR-4005-A | IEC | Regret offer | PR Closed | 1. Observations sent on 14.01.2024 2. Reminder sent on 20.01.2024 3. Reminder sent on 23.01.2024 4. Reminder sent on 31.01.2024 5. Reminder sent on 06.02.2024 6. Regretted for CPCB II norms on 06.02.2024 | 98105 59597 | rajnish.sharma@iecgensets.com |  | 01.12.23 | 07.08.23 | 6.2.24 | [22 empty] | karthik.ajithkumar@lntecc.com-17.05.2024-09:34:25
Ballia WSP | Electrical | DG Sets | LE23M596-E-WS-CW-PR-4005 | LE23M596-E-WS-CW-PR-4005-B | Jakson | Sent to BU Operations | 130 | 1. Observations sent on 14.01.2024 2. Replies received on 15.01.2024 3. Reminder sent on 23.01.2024 4. CRS and Reply received on 24.01.2024. 5. Revised offer requested as per CPCB-II norms for <1000 kVA sets on 31.01.2024 6. Technical meeting scheduled on 08.02.2024 7.MOM sent to Bidder on 15.02.2024, awaiting revised offer 8. Revised offer received on 23.02.2024 9. Vendor to revise the documents as per CPCB-II only, CPCB-IV not acceptable.L&T Observations given on 13.03.2024 10. Meeting conducted on 15.03.2024 with all technical requirement and MOM sent to vendor on 16.03.2024 to adhere the MOM after po. | 98369 63737 | ayan.das@jakson.com |  | 01.12.23 | 11.12.23 | 14.01.24 | 15.01.24 | 31.01.24 | 08.02.24 | 15.02.24 | 23.02.24 | 15.03.24 | 27.03.24 |  | 27.03.24 | 27.03.24 | 27.03.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | DG Sets | LE23M596-E-WS-CW-PR-4005 | LE23M596-E-WS-CW-PR-4005-C | Greaves Cotton | Sent to BU Operations | 130 | Not Started Bidder- plan to will visit chennai on 14/02/24 1. MOM sent to vendor on 16.02.2024 for their revised offer. 2. Vendor queried on 19.02.2024 3. L&T responded on 20.02.2024 4. Reminder sent on 22.02.2024 5. Reminder sent on 23.02.2024 6. Reminder sent on 01.03.2024 7. Revised offer received on 02.03.2024 8. L&T Observations sent on 14.03.2024 9. Reminder sent on 19.03.2024 10. Meeting conducted on 19.03.2024 with all technical requirement and MOM sent to vendor on 20.03.2024 to adhere the MOM after po. 11 Revised offer and reply received from Vendor on 31.03.2024 | 70303 11775 | s.banerjee@greavescotton.com |  | 01.12.23 | 09.02.24 | 16.02.24 | 19.02.24 | 20.02.24 | 02.03.24 | 14.03.24 | 19.03.24 | 20.03.24 | 27.03.24 |  | 27.03.24 | 27.03.24 | 27.03.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | DG Sets | LE23M596-E-WS-CW-PR-4005 | LE23M596-E-WS-CW-PR-4005-D | Prime Powergenerators | Sent to BU Operations | 130 | 1. Observations sent on 14.01.2024 2. Reminder sent on 20.01.2024 3. Replies received on 23.01.2024 4. MOM sent to vendor for final confirmation on 30.01.2024 5. Vendor sent additional docs on 05.02.2024 6. Meeting scheduled on 14/02/24, sync panel scope, insulation level 7. Additional information sent by vendor on 17.02.2024 8. L&T observations to fill in data sheet was sent on 20.02.2024 9. Meeting fixed on 23.02.2024 10. Reminder mail sent on 01.03.2024 11. Vendor replied on 02.03.2024 12. MOM and further comments sent on 13.03.2024 13. Vendor comments on the MOM sent by vendor on 13.03.2024 14. Technically cleared on 13.03.24 | 91001 55773 | chitendar@primepowergen.com |  | 01.12.23 | 05.08.23 | 14.01.24 | 23.01.24 | 30.01.24 | 05.02.24 | 20.02.24 | 02.03.24 | 13.03.24 | 13.03.24 |  | 13.03.24 | 13.03.24 | 27.03.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | Local Push Button Stations (LPBS) | LE23M596-E-WS-CW-PR-4006 | LE23M596-E-WS-CW-PR-4006-A | Sri Ragavendra Controls | Sent to BU Operations | 82 | Revised SLD sent on 12.03.24 Technical clearance given on 14.05.24 | 98947 13024 | ashok@ragavendracontrol.com |  | 01.12.23 | 05.12.23 | 14.5.24 | [8 empty] | 9.4.24 | 14.5.24 | 14.5.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | Local Push Button Stations (LPBS) | LE23M596-E-WS-CW-PR-4006 | LE23M596-E-WS-CW-PR-4006-B | Universal Power | Sent to BU Operations | 82 | 1. Revised SLD sent on 12.03.2024 2. Revised Vendor offer received on 09.04.2024 3.Technical clearance given on 14.05.24 | 95000 95075 | deepak@upe.co.in |  | 01.12.23 | 9.4.24 | 14.5.24 | [8 empty] | 9.4.24 | 14.5.24 | 14.5.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT/LT Power and Control Cable | LE23M596-E-WS-CW-PR-4008 | LE23M596-E-WS-CW-PR-4008-A | Havells | Awaiting pre-offer from vendor | 247 |  | 94377 68522 | santosh.swain@havells.com |  | 01.12.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT/LT Power and Control Cable | LE23M596-E-WS-CW-PR-4008 | LE23M596-E-WS-CW-PR-4008-B | KEI | Pre-order comments issued | 87 |  | 89291 60605 | vincent.kallen@kei-ind.com |  | 01.12.23 | 02.12.23 | 9.5.24 | [22 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT/LT Power and Control Cable | LE23M596-E-WS-CW-PR-4008 | LE23M596-E-WS-CW-PR-4008-C | Axelon | Awaiting pre-offer from vendor | 247 |  | 98677 69603 | hardik@axeloninternational.com |  | 01.12.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT/LT Power and Control Cable | LE23M596-E-WS-CW-PR-4008 | LE23M596-E-WS-CW-PR-4008-D | Monaj Trading | Awaiting pre-offer from vendor | 247 |  | 98305 69644 | monajtrading@gmail.com |  | 01.12.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT/LT Power and Control Cable | LE23M596-E-WS-CW-PR-4008 | LE23M596-E-WS-CW-PR-4008-E | Stokes | Regret offer | PR Closed |  | 98401 52061 | sales@stokesglands.com |  | 01.12.23 | 02.12.23 | [23 empty] | srb@lntecc.com-21.05.2024-16:54:18
Ballia WSP | Electrical | HT/LT Power and Control Cable | LE23M596-E-WS-CW-PR-4008 | LE23M596-E-WS-CW-PR-4008-F | Govind Electricals | Awaiting pre-offer from vendor | 247 |  | 98401 89014 | sgovindele@gmail.com |  | 01.12.23 | [24 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Cable Termination Kit (Glands & Lugs) | LE23M596-E-WS-CW-PR-4009 | LE23M596-E-WS-CW-PR-4009-A | Monaj Trading | Sent to BU Operations | 247 |  | 98305 69644 | monajtrading@gmail.com |  | 01.12.23 | 01.12.23 | 01.12.23 | [8 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Cable Termination Kit (Glands & Lugs) | LE23M596-E-WS-CW-PR-4009 | LE23M596-E-WS-CW-PR-4009-B | Stokes | Sent to BU Operations | 247 |  | 98401 52061 | sales@stokesglands.com |  | 01.12.23 | 01.12.23 | 01.12.23 | [8 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Cable Termination Kit (Glands & Lugs) | LE23M596-E-WS-CW-PR-4009 | LE23M596-E-WS-CW-PR-4009-C | Govind Electricals | Sent to BU Operations | 247 |  | 98401 89014 | sgovindele@gmail.com |  | 01.12.23 | 01.12.23 | 01.12.23 | [8 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Cable Termination Kit (Glands & Lugs) | LE23M596-E-WS-CW-PR-4009 | LE23M596-E-WS-CW-PR-4009-D | Havells | Sent to BU Operations | 247 |  | 94377 68522 |  |  | 01.12.23 | 01.12.23 | 01.12.23 | [8 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Cable Termination Kit (Glands & Lugs) | LE23M596-E-WS-CW-PR-4009 | LE23M596-E-WS-CW-PR-4009-E | KEI | Sent to BU Operations | 247 |  | 89291 60605 | vincent.kallen@kei-ind.com |  | 01.12.23 | 01.12.23 | 01.12.23 | [8 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | HT Cable Termination Kit (Glands & Lugs) | LE23M596-E-WS-CW-PR-4009 | LE23M596-E-WS-CW-PR-4009-F | Axelon | Sent to BU Operations | 183 |  | 98677 69603 | hardik@axeloninternational.com |  | 01.12.23 | 03.02.24 | 03.02.24 | [8 empty] | 03.02.24 | 03.02.24 | 03.02.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | Cable Tray & Supports | LE23M596-E-WS-CW-PR-4010 | LE23M596-E-WS-CW-PR-4010-A | Monaj Trading | Enquiry yet to float | NA |  | 98305 69644 | monajtrading@gmail.com | [26 empty] | karthik.ajithkumar@lntecc.com-17.05.2024-09:34:26
Ballia WSP | Electrical | Cable Tray & Supports | LE23M596-E-WS-CW-PR-4010 | LE23M596-E-WS-CW-PR-4010-B | Stokes | Enquiry yet to float | NA |  | 98401 52061 | sales@stokesglands.com | [26 empty] | karthik.ajithkumar@lntecc.com-17.05.2024-09:34:26
Ballia WSP | Electrical | Cable Tray & Supports | LE23M596-E-WS-CW-PR-4010 | LE23M596-E-WS-CW-PR-4010-C | Govind Electricals | Enquiry yet to float | NA |  | 98401 89014 | sgovindele@gmail.com | [26 empty] | karthik.ajithkumar@lntecc.com-17.05.2024-09:34:26
Ballia WSP | Electrical | Earthing & Lightning Protection | LE23M596-E-WS-CW-PR-4012 | LE23M596-E-WS-CW-PR-4012-A | Monaj Trading | Sent to BU Operations | 228 | Technical clearance provided | 98305 69644 | monajtrading@gmail.com |  | 14.12.23 | 20.12.23 | 20.12.23 | [8 empty] | 20.12.23 | 20.12.23 | 20.12.23 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | Earthing & Lightning Protection | LE23M596-E-WS-CW-PR-4012 | LE23M596-E-WS-CW-PR-4012-B | Stokes | Sent to BU Operations | 234 |  | 98401 52061 | sales@stokesglands.com |  | 14.12.23 | 14.12.23 | 14.12.23 | [8 empty] | 14.12.23 | 14.12.23 | 14.12.23 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | Earthing & Lightning Protection | LE23M596-E-WS-CW-PR-4012 | LE23M596-E-WS-CW-PR-4012-C | Govind Electricals | Sent to BU Operations | 234 |  | 98401 89014 | sgovindele@gmail.com |  | 14.12.23 | 14.12.23 | 14.12.23 | [8 empty] | 14.12.23 | 14.12.23 | 14.12.23 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Ballia WSP | Electrical | Illumination | LE23M596-E-WS-CW-PR-4013 | LE23M596-E-WS-CW-PR-4013-A | ACE Engineering | Enquiry yet to float | NA |  | 99400 29850 | mhnviswanathan@yahoo.co.in | [26 empty] | karthik.ajithkumar@lntecc.com-17.05.2024-09:34:26
Ballia WSP | Electrical | Illumination | LE23M596-E-WS-CW-PR-4013 | LE23M596-E-WS-CW-PR-4013-B | Wipro | Enquiry yet to float | NA |  | 70771 00980 | vipul.kumar35@wipro.com | [26 empty] | karthik.ajithkumar@lntecc.com-17.05.2024-09:34:26
Ballia WSP | Electrical | Electrical Safety | LE23M596-E-WS-CW-PR-4014 | LE23M596-E-WS-CW-PR-4014-A | Site Procurement | Sent to BU Operations | 171 | Technical clearance provided |  |  |  | 15.02.24 | 15.02.24 | 15.02.24 | [8 empty] | 15.02.24 | 15.02.24 | 15.02.24 | T1 | [10 empty] | srb@lntecc.com-26.07.2024-10:52:08
Bandra | Process | MBR System | LE22M508-P-001 | LE22M508-P-001-A | Suez | Sent to BU Operations | 709 |  |  |  | 15.06.22 | 15.06.22 | 30.06.22 | 26.08.22 | [8 empty] | 24.08.22 | 26.08.22 | 26.08.22 | T1 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-10:57:00
Bandra | Process | RAS Pumps | LE22M508-P-002 | LE22M508-P-002-A | Grundfos | Post-order comments issued | 36 |  |  |  | 16.06.22 | 16.06.22 | 30.06.22 | 29.03.23 | [8 empty] | 24.03.23 | 30.03.23 | 30.03.23 | T1 | 07.06.24 | Grundfos | 28.06.24 | 29.06.24 | [5 empty] | 06.08.24 | a-saurabh@lntecc.com-01.07.2024-12:14:52
Bandra | Process | RAS Pumps | LE22M508-P-002 | LE22M508-P-002-B | Aqua | Pre-order technically rejected | PR Closed |  |  |  | 16.06.22 | 16.06.22 | 09.07.22 | 31.01.23 | [8 empty] | 22.02.23 | 22.02.23 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | RAS Pumps | LE22M508-P-002 | LE22M508-P-002-C | Sulzer | Sent to BU Operations | PR Closed |  |  |  | 16.06.22 | 16.06.22 | 13.07.22 | 28.03.23 | [8 empty] | 29.03.23 | 30.03.23 | 30.03.23 | T3 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:14:52
Bandra | Process | RAS Pumps | LE22M508-P-002 | LE22M508-P-002-D | Xylem | Sent to BU Operations | PR Closed |  |  |  | 16.06.22 | 16.06.22 | 12.07.22 | 24.03.23 | [8 empty] | 20.03.23 | 24.03.23 | 24.03.23 | T2 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:14:52
Bandra | Process | RAS Pumps | LE22M508-P-002 | LE22M508-P-002-E | Wilo | Pre-order technically rejected | PR Closed |  |  |  | 16.06.22 | 16.06.22 | 04.09.22 | 20.06.23 | [8 empty] | 23.06.23 | 27.06.23 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | RAS Pumps | LE22M508-P-002 | LE22M508-P-002-F | KSB | Pre-order technically rejected | PR Closed |  |  |  | 16.06.22 | 16.06.22 | 20.02.23 | 07.08.23 | [8 empty] | 19.08.23 | 23.08.23 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | RAS Pumps | LE22M508-P-002 | LE22M508-P-002-G | KBL | Pre-order technically rejected | PR Closed |  |  |  | 16.06.22 | 16.06.22 | 14.04.23 | 20.06.23 | [8 empty] | 01.07.23 | 05.07.23 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Fine Screen | LE22M508-P-003 | LE22M508-P-003-A | Huber | Sent to BU Operations | PR Closed |  |  |  | 22.06.22 | 22.06.22 | 03.08.22 | 20.10.22 | [8 empty] | 18.11.22 | 23.11.22 | 23.11.22 | T1 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:18:06
Bandra | Process | Fine Screen | LE22M508-P-003 | LE22M508-P-003-B | Jash | Approved by Client | PR Closed |  |  |  | 22.06.22 | 22.06.22 | 20.07.22 | 18.11.22 | [8 empty] | 11.11.22 | 19.11.22 | 18.11.22 | T3 | 10.04.23 | Jash | 04.05.23 | 07.07.23 | 21.07.23 | 04.08.23 | 14.03.24 |  |  | 09.06.23 | a-saurabh@lntecc.com-01.07.2024-12:18:06
Bandra | Process | Fine Screen | LE22M508-P-003 | LE22M508-P-003-C | Johnson | Sent to BU Operations | PR Closed |  |  |  | 22.06.22 | 22.06.22 | 30.06.22 | 20.11.22 | [8 empty] | 16.11.22 | 21.11.22 | 22.11.22 | T2 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:18:06
Bandra | Process | Fine Screen | LE22M508-P-003 | LE22M508-P-003-D | Fundamental | Pre-order technically rejected | PR Closed |  |  |  | 22.06.22 | 22.06.22 | 09.07.22 | 11.11.22 | [8 empty] | 01.12.22 | 01.12.22 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-11:12:02
Bandra | Process | Fine Screen | LE22M508-P-003 | LE22M508-P-003-E | WAM | Sent to BU Operations | PR Closed |  |  |  | 22.06.22 | 22.06.22 | 30.06.22 | 18.11.22 | [8 empty] | 13.11.22 | 19.11.22 | 01.12.22 | T4 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:18:06
Bandra | Process | Vortex Grit System | LE22M508-P-004 | LE22M508-P-004-A | Huber | Post-order comments issued | 36 |  |  |  | 04.07.22 | 04.07.22 | 24.07.22 | 25.10.22 | [8 empty] | 14.11.22 | 16.11.22 | 17.11.22 | T1 | 08.06.24 | Huber | 18.06.24 | 29.06.24 | [5 empty] | 07.08.24 | a-saurabh@lntecc.com-01.07.2024-12:20:41
Bandra | Process | Vortex Grit System | LE22M508-P-004 | LE22M508-P-004-B | Ovivo | Sent to BU Operations | PR Closed |  |  |  | 04.07.22 | 04.07.22 | 03.08.22 | 20.11.22 | [8 empty] | 18.11.22 | 22.11.22 | 23.11.22 | T2 | 19.04.23 |  |  |  | 30.06.23 | 01.07.23 |  |  |  | 18.06.23 | a-saurabh@lntecc.com-01.07.2024-12:20:41
Bandra | Process | Vortex Grit System | LE22M508-P-004 | LE22M508-P-004-C | S&L | Sent to BU Operations | PR Closed |  |  |  | 04.07.22 | 04.07.22 | 23.07.22 | 17.11.22 | [8 empty] | 18.11.22 | 21.11.22 | 22.11.22 | T3 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:20:41
Bandra | Process | Vortex Grit System | LE22M508-P-004 | LE22M508-P-004-D | WAM | Sent to BU Operations | PR Closed |  |  |  | 04.07.22 | 04.07.22 | 02.09.22 | 18.11.22 | [8 empty] | 18.11.22 | 19.11.22 | 21.11.22 | T4 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:20:41
Bandra | Process | Primary Clarifier Mechanism | LE22M508-P-005 | LE22M508-P-005-A | Filsep | Sent to BU Operations | PR Closed |  |  |  | 20.06.22 | 20.06.22 | 15.07.22 | 19.11.22 | [8 empty] | 29.11.22 | 29.11.22 | 29.11.22 | T1 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:22:05
Bandra | Process | Primary Clarifier Mechanism | LE22M508-P-005 | LE22M508-P-005-B | Indofab | Pre-order technically rejected | PR Closed |  |  |  | 20.06.22 | 20.06.22 | 18.07.22 | 01.09.22 | [8 empty] | 16.11.22 | 16.11.22 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Primary Clarifier Mechanism | LE22M508-P-005 | LE22M508-P-005-C | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 20.06.22 | 20.06.22 | 26.07.22 | 16.02.22 | [8 empty] | 14.02.23 | 18.02.23 | 18.02.23 | T3 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:22:05
Bandra | Process | Primary Clarifier Mechanism | LE22M508-P-005 | LE22M508-P-005-D | Voltas | Sent to BU Operations | PR Closed |  |  |  | 20.06.22 | 20.06.22 | 08.09.22 | 15.02.23 | [8 empty] | 13.02.23 | 18.02.23 | 18.02.23 | T1 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:22:05
Bandra | Process | Primary Clarifier Mechanism | LE22M508-P-005 | LE22M508-P-005-E | K Pack | Post-order comments issued | 41 |  |  |  | 20.06.22 | 20.06.22 | 10.09.22 | 13.02.23 | [8 empty] | 13.02.23 | 15.02.23 | 15.02.23 | T2 | 10.04.24 | K Pack | 20.06.24 | 24.06.24 | [5 empty] | 09.06.24 | a-saurabh@lntecc.com-01.07.2024-12:22:05
Bandra | Process | Primary Clarifier Mechanism | LE22M508-P-005 | LE22M508-P-005-F | Krofta | Pre-order technically rejected | PR Closed |  |  |  | 20.06.22 | 20.06.22 | 05.08.22 | 14.02.23 | [8 empty] | 14.02.23 | 17.02.23 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Gas Holders(2 Nos) | LE22M508-P-006 | LE22M508-P-006-A | GGE | Sent to BU Operations | PR Closed |  |  |  | 27.06.22 | 14.06.23 | 26.05.23 | 05.07.23 | [8 empty] | 06.07.23 | 06.07.23 | 06.07.23 | T3 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:23:48
Bandra | Process | Gas Holders(2 Nos) | LE22M508-P-006 | LE22M508-P-006-B | Biogas Tech | Sent to BU Operations | PR Closed |  |  |  | 27.06.22 | 14.06.23 | 25.05.23 | 04.07.23 | [8 empty] | 08.07.23 | 08.07.23 | 06.07.23 | T2 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:23:48
Bandra | Process | Gas Holders(2 Nos) | LE22M508-P-006 | LE22M508-P-006-C | Sattler | Pre-order technically rejected | PR Closed |  |  |  | 27.06.22 | 14.06.23 | 08.06.23 | 09.08.23 | [8 empty] | 10.08.23 | 10.08.23 | 06.07.23 | [11 empty] | a-saurabh@lntecc.com-01.07.2024-11:22:18
Bandra | Process | Gas Holders(2 Nos) | LE22M508-P-006 | LE22M508-P-006-D | Inventive | Post-order pending with EDRC | 48 |  |  |  | 27.06.22 | 14.06.23 | 12.06.23 | 02.08.23 | [8 empty] | 08.08.23 | 08.08.23 | 06.07.23 | T1 | 17.04.24 | Inventive | 17.06.24 | [6 empty] | 16.06.24 | a-saurabh@lntecc.com-01.07.2024-12:23:48
Bandra | Process | Rotary Drum Screen | LE22M508-P-007 | LE22M508-P-007-A | Johnson | Sent to BU Operations | PR Closed |  |  |  | 27.06.22 | 27.06.22 | 25.07.22 | 25.07.22 | [8 empty] | 08.09.22 | 10.09.22 | 25.03.24 | T3 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:25:01
Bandra | Process | Rotary Drum Screen | LE22M508-P-007 | LE22M508-P-007-B | WAM | Post-order comments issued | 39 |  |  |  | 27.06.22 | 27.06.22 | 20.07.22 | 16.11.22 | [8 empty] | 22.11.22 | 24.11.22 | 24.11.22 | T2 | 25.05.24 | WAM | 20.06.24 | 26.06.24 | [5 empty] | 24.07.24 | a-saurabh@lntecc.com-01.07.2024-12:25:01
Bandra | Process | Rotary Drum Screen | LE22M508-P-007 | LE22M508-P-007-C | Jash | Pre-order technically rejected | PR Closed |  |  |  | 27.06.22 | 27.06.22 | 02.09.22 | 25.11.22 | [8 empty] | 02.12.22 | 05.12.22 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-11:39:00
Bandra | Process | Rotary Drum Screen | LE22M508-P-007 | LE22M508-P-007-D | Huber | Sent to BU Operations | PR Closed |  |  |  | 27.06.22 | 27.06.22 | 05.09.22 | 22.11.22 | [8 empty] | 23.11.22 | 25.11.22 | 25.11.22 | T2 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:25:01
Bandra | Process | Digesters Mixing System | LE22M508-P-008 | LE22M508-P-008-A | Ovivo | Sent to BU Operations | 620 |  |  |  | 18.06.22 | 18.06.22 | 19.07.22 | 18.11.22 | [8 empty] | 23.11.22 | 23.11.22 | 23.11.22 | T1 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-11:43:39
Bandra | Process | Digesters Mixing System | LE22M508-P-008 | LE22M508-P-008-B | Voltas | Pre-order technically rejected | PR Closed |  |  |  | 18.06.22 | 18.06.22 | 26.06.23 | 26.06.23 | [8 empty] | 27.06.23 | 29.06.23 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Submersible Mixers | LE22M508-P-009 | LE22M508-P-009-A | Sulzer | Sent to BU Operations | PR Closed |  |  |  | 11.07.22 | 11.07.22 | 28.08.22 | 08.04.23 | [8 empty] | 10.04.23 | 10.04.23 | 10.04.23 | T1 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:28:16
Bandra | Process | Submersible Mixers | LE22M508-P-009 | LE22M508-P-009-B | Ebara | Pre-order technically rejected | PR Closed |  |  |  | 11.07.22 | 11.07.22 | 25.08.22 | 01.09.22 | [8 empty] | 01.09.22 | 01.09.22 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Submersible Mixers | LE22M508-P-009 | LE22M508-P-009-C | Xylem | Post-order comments issued | 36 |  |  |  | 11.07.22 | 11.07.22 | 30.03.23 | 05.04.23 | [8 empty] | 08.04.23 | 08.04.23 | 08.04.23 | T2 | 16.04.24 | Xylem | 28.06.24 | 29.06.24 | [5 empty] | 15.06.24 | a-saurabh@lntecc.com-01.07.2024-12:28:16
Bandra | Process | Submersible Mixers | LE22M508-P-009 | LE22M508-P-009-D | Grundfos | Sent to BU Operations | PR Closed |  |  |  | 11.07.22 | 11.07.22 | 28.03.23 | 04.04.23 | [8 empty] | 05.04.23 | 10.04.23 | 10.04.23 | T3 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-12:28:16
Bandra | Process | Submersible Mixers | LE22M508-P-009 | LE22M508-P-009-E | Wilo | Pre-order technically rejected | PR Closed |  |  |  | 11.07.22 | 11.07.22 | 03.06.23 | 22.03.23 | [8 empty] | 06.04.23 | 10.04.23 | 10.04.23 | [11 empty] | a-saurabh@lntecc.com-01.07.2024-11:47:10
Bandra | Process | Air Diffuser System | LE22M508-P-010 | LE22M508-P-010-A | EDI | Sent to BU Operations | PR Closed |  |  |  | 04.07.23 | 04.07.22 | 09.07.22 | 16.12.22 | [8 empty] | 20.12.22 | 21.12.22 | 21.12.22 | T2 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-13:40:04
Bandra | Process | Air Diffuser System | LE22M508-P-010 | LE22M508-P-010-B | SSI | Approved by Client | PR Closed |  |  |  | 04.07.23 | 04.07.22 | 08.07.22 | 18.12.22 | [8 empty] | 20.12.22 | 21.12.22 | 21.12.22 | T1 | 15.05.24 | SSI | 20.06.23 | 30.06.23 | 06.07.23 | 11.07.23 | 03.06.24 |  |  | 14.07.24 | a-saurabh@lntecc.com-01.07.2024-13:40:04
Bandra | Process | Air Diffuser System | LE22M508-P-010 | LE22M508-P-010-C | OTT | Sent to BU Operations | PR Closed |  |  |  | 04.07.23 | 04.07.22 | 14.07.22 | 27.12.22 | [8 empty] | 20.01.23 | 23.01.23 | 21.12.22 | T3 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-13:40:04
Bandra | Process | Air Diffuser System | LE22M508-P-010 | LE22M508-P-010-D | Supratec | Pre-order technically rejected | PR Closed |  |  |  | 04.07.23 | 04.07.22 | 11.07.22 | 21.11.22 | [8 empty] | 23.11.22 | 28.11.22 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Air Diffuser System | LE22M508-P-010 | LE22M508-P-010-E | SBS enviro | Pre-order technically rejected | PR Closed |  |  |  | 04.07.23 | 04.07.22 | 05.08.22 | 14.12.22 | [8 empty] | 18.12.22 | 23.12.22 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Air Diffuser System | LE22M508-P-010 | LE22M508-P-010-F | Premiertech | Pre-order technically rejected | PR Closed |  |  |  | 04.07.23 | 04.07.22 | 09.08.22 | 11.08.22 | [8 empty] | 11.08.22 | 11.08.22 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Sluice Gates | LE22M508-P-011 | LE22M508-P-011-A | Jash | Sent to BU Operations | 464 |  |  |  | 29.08.22 | 29.08.22 | 16.03.23 | 21.04.23 | [8 empty] | 20.04.23 | 28.04.23 | 28.04.23 | T1 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-11:47:10
Bandra | Process | Sluice Gates | LE22M508-P-011 | LE22M508-P-011-B | DVPL | Sent to BU Operations | 442 |  |  |  | 29.08.22 | 29.08.22 | 20.03.23 | 23.04.23 | [8 empty] | 18.05.23 | 20.05.23 | 20.05.23 | T2 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-11:47:10
Bandra | Process | Sluice Gates | LE22M508-P-011 | LE22M508-P-011-C | AVK | Pre-order technically rejected | PR Closed |  |  |  | 29.08.22 | 29.08.22 | 21.03.23 | 16.05.23 | [8 empty] | 16.05.23 | 20.05.23 | 20.05.23 | [11 empty] | a-saurabh@lntecc.com-01.07.2024-11:50:11
Bandra | Process | Air Blower | LE22M508-P-012 | LE22M508-P-012-A | Garden denver | Sent to BU Operations | 117 |  |  |  | 21.06.22 | 21.06.22 | 02.04.24 | 03.04.24 | [8 empty] | 09.04.24 | 09.04.24 | 09.04.24 | T2 |  |  |  |  | 09.04.24 | 09.04.24 |  |  |  |  | a-saurabh@lntecc.com-01.07.2024-11:47:10
Bandra | Process | Air Blower | LE22M508-P-012 | LE22M508-P-012-B | Howden | Pre-order technically rejected | PR Closed | Technically Rejected |  |  | 21.06.22 | 21.06.22 | 21.06.22 | [10 empty] | 16.09.23 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Air Blower | LE22M508-P-012 | LE22M508-P-012-C | Everest | Pre-order technically rejected | PR Closed |  |  |  | 21.06.22 | 21.06.22 | 28.11.23 | 21.12.23 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Air Blower | LE22M508-P-012 | LE22M508-P-012-D | Neuros | Sent to BU Operations | 117 | Technically Clearaed |  |  | 21.06.22 | 21.06.22 | 04.08.22 | 05.10.23 | [8 empty] | 09.04.24 | 09.04.24 | 09.04.24 | T1 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-11:47:10
Bandra | Process | Air Blower | LE22M508-P-012 | LE22M508-P-012-E | Turbomax | Sent to BU Operations | 117 | Not under review as vendor is not approved make- offer closed |  |  | 21.06.22 | 21.06.22 | 11.03.24 | 21.03.24 | [8 empty] | 09.04.24 | 09.04.24 | 09.04.24 | T3 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-11:47:10
Bandra | Process | Air Blower | LE22M508-P-012 | LE22M508-P-012-F | Atlas copco | Pre-order technically rejected | PR Closed |  |  |  | 21.06.22 | 21.06.22 | 28.11.23 | 07.02.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Air Blower | LE22M508-P-012 | LE22M508-P-012-G | Turbowin | Pre-order technically rejected | PR Closed | Turbowin |  |  | 21.06.22 | 21.06.22 | 02.04.24 | 02.04.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Rotary Drum Thickener | LE22M508-P-013 | LE22M508-P-013-A | Shree Techno | Pre-order technically rejected | PR Closed |  |  |  | 16.06.22 | 16.06.22 | 29.03.24 | 05.04.24 | [8 empty] | 05.04.24 | 05.04.24 | [12 empty] | a-saurabh@lntecc.com-01.07.2024-11:54:43
Bandra | Process | Rotary Drum Thickener | LE22M508-P-013 | LE22M508-P-013-B | Andrtiz | Sent to BU Operations | 90 |  |  |  | 16.06.22 | 16.06.22 | 14.03.24 | 23.04.24 | [8 empty] | 06.05.24 | 06.05.24 | 06.05.24 | T2 | [10 empty] | a-saurabh@lntecc.com-01.07.2024-11:54:43
Bandra | Process | Rotary Drum Thickener | LE22M508-P-013 | LE22M508-P-013-C | EMO | Sent to BU Operations | 121 | Technically Clearaed |  |  | 16.06.22 | 16.06.22 | 12.02.24 | 12.02.24 | [8 empty] | 12.02.24 | 12.02.24 | 05.04.24 | T1 | [5 empty] | 12.02.24 |  |  |  |  | a-saurabh@lntecc.com-01.07.2024-11:50:11
Bandra | Process | Rotary Drum Thickener | LE22M508-P-013 | LE22M508-P-013-D | Jagtap | Pre-order technically rejected | PR Closed |  |  |  | 16.06.22 | 16.06.22 | 27.12.23 | 08.02.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Rotary Drum Thickener | LE22M508-P-013 | LE22M508-P-013-E | Auricent | Pre-order technically rejected | PR Closed | Technically Rejected- offer closed |  |  | 16.06.22 | 16.06.22 | 16.06.22 | [23 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | UV System | LE22M508-P-014 | LE22M508-P-014-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | UV System | LE22M508-P-014 | LE22M508-P-014-B |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | UV System | LE22M508-P-014 | LE22M508-P-014-C |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | UV System | LE22M508-P-014 | LE22M508-P-014-D |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Dewatering Screw Press | LE22M508-P-015 | LE22M508-P-015-A | Krofta | Pre-order comments issued | 38 |  |  |  | 27.06.22 | 27.06.22 | 23.03.24 | 23.04.24 | 26.06.24 | 27.06.24 | [20 empty] | a-saurabh@lntecc.com-01.07.2024-11:56:21
Bandra | Process | Dewatering Screw Press | LE22M508-P-015 | LE22M508-P-015-B | Auric | Pre-order technically rejected | PR Closed |  |  |  | 27.06.22 | 27.06.22 | 18.07.22 | 20.03.23 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Dewatering Screw Press | LE22M508-P-015 | LE22M508-P-015-C | SBS | Pre-order comments issued | 69 |  |  |  | 27.06.22 | 27.06.22 | 02.04.24 | 22.04.24 | 24.05.24 | 27.05.24 | [20 empty] | a-saurabh@lntecc.com-01.07.2024-11:58:28
Bandra | Process | Dewatering Screw Press | LE22M508-P-015 | LE22M508-P-015-D | Huber | Pre-order technically rejected | PR Closed |  |  |  | 27.06.22 | 27.06.22 | 28.02.24 | 04.03.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Dewatering Screw Press | LE22M508-P-015 | LE22M508-P-015-E | Andritz | Pre-order comments issued | 79 | PR released on 14-02-2024 |  |  | 27.06.22 | 27.06.22 | 04.03.24 | 07.03.24 | 16.05.24 | 17.05.24 | [20 empty] | a-saurabh@lntecc.com-01.07.2024-11:57:05
Bandra | Process | Dewatering Screw Press | LE22M508-P-015 | LE22M508-P-015-F | Micro transmission | Pre-order technically rejected | PR Closed |  |  |  | 27.06.22 | 27.06.22 | 15.03.24 | 16.03.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-11:56:21
Bandra | Process | Dewatering Screw Press | LE22M508-P-015 | LE22M508-P-015-G | EMO | Pre-order comments issued | 41 |  |  |  | 27.06.22 | 27.06.22 | 06.06.24 | 24.06.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-11:56:21
Bandra | Process | Heat Exchanger | LE22M508-P-016 | LE22M508-P-016-A |  | Enquiry yet to float | NA |  |  |  | 27.06.22 | [25 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Heat Exchanger | LE22M508-P-016 | LE22M508-P-016-B |  | Enquiry yet to float | NA |  |  |  | 27.06.22 | [25 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Heat Exchanger | LE22M508-P-016 | LE22M508-P-016-C |  | Enquiry yet to float | NA |  |  |  | 27.06.22 | [25 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Heat Exchanger | LE22M508-P-016 | LE22M508-P-016-D |  | Enquiry yet to float | NA |  |  |  | 27.06.22 | [25 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | CHP engine | LE22M508-P-017 | LE22M508-P-017-A |  | Enquiry yet to float | NA |  |  |  | 22.07.22 | [25 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Autopolymer dosing System | LE22M508-P-018 | LE22M508-P-018-A | PSG Dover | Pre-order comments issued | 173 |  |  |  |  | 13.07.22 | 04.11.22 | 13.02.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Autopolymer dosing System | LE22M508-P-018 | LE22M508-P-018-B | Fluidoze Milton Roy | Pre-order comments issued | 150 |  |  |  |  | 13.07.22 | 05.03.24 | 07.03.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Autopolymer dosing System | LE22M508-P-018 | LE22M508-P-018-C | Neev fluidex | Pre-order comments issued | 169 |  |  |  |  | 13.07.22 | 16.02.24 | 17.02.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Autopolymer dosing System | LE22M508-P-018 | LE22M508-P-018-D | Positive Metering Pump | Pre-order comments issued | 173 |  |  |  |  | 13.07.22 | 17.04.23 | 13.02.24 | [22 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Biogas Scrubbing system | LE22M508-P-019 | LE22M508-P-019-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Biogas Scrubbing system | LE22M508-P-019 | LE22M508-P-019-B |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Biogas engine feed blower | LE22M508-P-020 | LE22M508-P-020-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Biogas engine feed blower | LE22M508-P-020 | LE22M508-P-020-B |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Submersible drain pump | LE22M508-P-021 | LE22M508-P-021-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | HCP Pump- MBR system | LE22M508-P-022 | LE22M508-P-022-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | HCP Pump- STP | LE22M508-P-023 | LE22M508-P-023-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Screw Pump for Sludge system | LE22M508-P-024 | LE22M508-P-024-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Biogas Flare | LE22M508-P-025 | LE22M508-P-025-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Dewatered Sludge Conveyors | LE22M508-P-026 | LE22M508-P-026-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Dewatering Pumps | LE22M508-P-027 | LE22M508-P-027-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Motorized Hoist for Buildings | LE22M508-P-028 | LE22M508-P-028-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | EOT Crane for Buildings | LE22M508-P-029 | LE22M508-P-029-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | EOT Crane for MBR tank | LE22M508-P-030 | LE22M508-P-030-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Monorail & Chain Pulley Block | LE22M508-P-031 | LE22M508-P-031-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Chemical Dosing Tanks | LE22M508-P-032 | LE22M508-P-032-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Chemical Dosing Tank Agitators | LE22M508-P-033 | LE22M508-P-033-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Chemical Dosing Pumps | LE22M508-P-034 | LE22M508-P-034-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Air Compressor for MBR System | LE22M508-P-035 | LE22M508-P-035-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Bulk Storage Tank for Chemicals | LE22M508-P-036 | LE22M508-P-036-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Peristaltic Pumps for Sampling and Service Application | LE22M508-P-037 | LE22M508-P-037-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Process | Laboratory Equipment | LE22M508-P-038 | LE22M508-P-038-A |  | Enquiry yet to float | NA | [29 empty] | a-saurabh@lntecc.com-01.07.2024-10:54:57
Bandra | Mechanical | Trash Racks for IIPS | LE22M508-M-001 | LE22M508-M-001-A | WAM | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 19.09.22 | 19.09.22 | 07.10.22 | 07.10.22 | 02.11.22 | 04.11.22 |  |  |  |  | 02.11.22 | 04.11.22 | 25.01.23 | T1 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Trash Racks for IIPS | LE22M508-M-001 | LE22M508-M-001-B | HUBER | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 14.09.22 | 19.09.22 | 07.10.22 | 07.10.22 | 21.10.22 | 21.10.22 |  |  |  |  | 21.10.22 | 21.10.22 | 25.01.23 | T3 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Trash Racks for IIPS | LE22M508-M-001 | LE22M508-M-001-C | Johnson | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 27.07.22 | 29.10.22 | 07.10.22 | 07.10.22 | 21.10.22 | 21.10.22 |  |  |  |  | 21.10.22 | 21.10.22 | 25.01.23 | T2 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Trash Racks for IIPS | LE22M508-M-001 | LE22M508-M-001-D | Jash | Approved by Client | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 15.09.22 | 29.09.22 | 07.10.22 | 07.10.22 | 21.10.22 | 21.10.22 |  |  |  |  | 21.10.22 | 21.10.22 | 25.01.23 | T4 | 23.03.23 | Jash | 21.04.23 | 08.05.23 | 22.05.23 | 02.06.23 | 14.03.24 |  |  | 22.05.23 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Trash Racks for IIPS | LE22M508-M-001 | LE22M508-M-001-E | Fundametal | Pre-order technically rejected | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 06.12.22 | 06.12.22 | 12.12.22 | 13.12.22 | [6 empty] | 12.12.22 | 13.12.22 | [12 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Coarse Screen for IIPS | LE22M508-M-002 | LE22M508-M-002-A | WAM | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 27.07.22 | 12.08.22 | 19.09.22 | 30.09.22 | 08.11.22 | 10.11.22 | 17.11.22 | 17.11.22 | 19.11.22 | 19.11.22 | 19.11.22 | 19.11.22 | 25.01.23 | T1 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Coarse Screen for IIPS | LE22M508-M-002 | LE22M508-M-002-B | HUBER | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 23.08.22 | 02.09.22 | 14.09.22 | 14.09.22 | 08.11.22 | 09.11.22 | 17.11.22 | 17.11.23 | 19.11.22 | 19.11.22 | 19.11.22 | 19.11.22 | 25.01.23 | T2 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Coarse Screen for IIPS | LE22M508-M-002 | LE22M508-M-002-C | Johnson | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 25.07.22 | 27.07.22 | 16.08.22 | 08.09.22 | 01.10.22 | 11.10.22 | 17.11.22 | 29.11.22 | 02.12.22 | 02.12.22 | 02.12.22 | 02.12.22 | 25.01.23 | T3 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Coarse Screen for IIPS | LE22M508-M-002 | LE22M508-M-002-D | Jash | Approved by Client | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 06.09.22 | 08.09.22 | 15.09.22 | 30.09.22 | 10.10.22 | 08.11.22 | 17.11.22 | 17.11.22 | 19.11.22 | 19.11.22 | 19.11.22 | 19.11.22 | 25.01.23 | T4 | 23.03.23 | Jash | 21.04.23 | 09.05.23 | 15.07.23 | 20.07.23 | 14.03.24 |  |  | 22.05.23 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Coarse Screen for IIPS | LE22M508-M-002 | LE22M508-M-002-E | Fundametal | Pre-order technically rejected | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 06.12.22 | 06.12.22 | 12.12.22 | 13.12.22 | [6 empty] | 12.12.22 | 13.12.22 | [12 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Submersible Non-Clog Pump-IIPS | LE22M508-M-003 | LE22M508-M-003-A | Aqua | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 09.07.22 | 21.07.22 | 17.02.23 | 17.02.23 | [6 empty] | 17.02.23 | 17.02.23 | 27.02.24 | T5 | [10 empty] | gokul.c@lntecc.com-05.06.2024-09:26:26
Bandra | Mechanical | Submersible Non-Clog Pump-IIPS | LE22M508-M-003 | LE22M508-M-003-B | Wilo | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 08.08.22 | 15.08.22 | 29.11.22 | 20.12.22 | 04.02.23 | 04.02.23 |  |  |  |  | 04.02.23 | 04.02.23 | 27.02.24 | T1 | [10 empty] | gokul.c@lntecc.com-05.06.2024-09:26:26
Bandra | Mechanical | Submersible Non-Clog Pump-IIPS | LE22M508-M-003 | LE22M508-M-003-C | Xylem | Post-order comments issued | 64 |  |  |  | 01.07.22 | 01.07.22 | 13.07.22 | 20.07.22 | 23.08.22 | 05.09.22 | 13.09.22 | 13.09.22 | 30.12.22 | 31.12.22 | 01.02.23 | 01.02.23 | 01.02.23 | 01.02.23 | 27.02.24 | T3 | 26.04.24 | Xylem | 29.05.24 | 01.06.24 | [5 empty] | 25.06.24 | jeevan.a@lntecc.com-01.07.2024-14:26:00
Bandra | Mechanical | Submersible Non-Clog Pump-IIPS | LE22M508-M-003 | LE22M508-M-003-D | KBL | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 12.05.23 | 15.05.23 | 19.05.23 | 19.05.23 | 21.05.23 | 22.05.23 |  |  |  |  | 21.05.23 | 22.05.23 | 27.02.24 | T6 | [10 empty] | gokul.c@lntecc.com-05.06.2024-09:26:26
Bandra | Mechanical | Submersible Non-Clog Pump-IIPS | LE22M508-M-003 | LE22M508-M-003-E | KSB | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 20.02.23 | 21.02.23 | 30.05.23 | 31.05.23 | 16.02.24 | 18.02.24 | 20.02.24 | 22.02.24 | 27.02.24 | 28.02.24 | 27.02.24 | 28.02.24 | 27.02.24 | T4 | [10 empty] | gokul.c@lntecc.com-05.06.2024-09:26:26
Bandra | Mechanical | Submersible Non-Clog Pump-IIPS | LE22M508-M-003 | LE22M508-M-003-F | Grundfos | Sent to BU Operations | PR Closed |  |  |  | 01.07.22 | 01.07.22 | 15.07.22 | 20.07.22 | 09.09.22 | 20.12.22 | 02.02.23 | 03.02.23 | 08.03.23 | 09.03.23 | 24.03.23 | 24.03.23 | 24.03.23 | 24.03.23 | 27.02.24 | T2 | [10 empty] | gokul.c@lntecc.com-05.06.2024-09:26:26
Bandra | Mechanical | Submersible Axial Flow pump-EPS | LE22M508-M-004 | LE22M508-M-004-A | Aqua | Sent to BU Operations | PR Closed |  |  |  | 06.07.22 | 06.07.22 | 02.01.23 | 02.01.23 | 20.01.23 | 07.02.23 | 17.02.23 | 17.02.23 | 20.02.23 | 23.02.23 |  |  | 20.02.23 | 23.02.23 | 12.03.24 | T6 | [10 empty] | jeevan.a@lntecc.com-08.07.2024-15:57:14
Bandra | Mechanical | Submersible Axial Flow pump-EPS | LE22M508-M-004 | LE22M508-M-004-B | Wilo | Sent to BU Operations | PR Closed |  |  |  | 06.07.22 | 06.07.22 | 20.12.22 | 30.12.22 | 15.02.23 | 15.02.23 | 28.02.23 | 28.02.23 | 07.03.23 | 10.03.23 |  |  | 07.03.23 | 10.03.23 | 12.03.24 | T1 | [10 empty] | jeevan.a@lntecc.com-08.07.2024-15:57:14
Bandra | Mechanical | Submersible Axial Flow pump-EPS | LE22M508-M-004 | LE22M508-M-004-C | Xylem | Sent to BU Operations | PR Closed |  |  |  | 06.07.22 | 06.07.22 | 14.07.22 | 23.08.22 | 05.09.22 | 05.09.22 | 10.10.22 | 10.10.22 | 29.12.22 | 31.12.22 | 08.02.23 | 09.02.23 | 08.02.23 | 09.02.23 | 12.03.24 | T2 | [10 empty] | jeevan.a@lntecc.com-08.07.2024-15:57:14
Bandra | Mechanical | Submersible Axial Flow pump-EPS | LE22M508-M-004 | LE22M508-M-004-D | Suzler | Sent to BU Operations | PR Closed |  |  |  | 06.07.22 | 06.07.22 | 14.07.22 | 16.07.22 | 23.08.22 | 23.08.22 | 20.12.22 | 20.12.22 | 18.02.23 | 23.02.23 | 04.03.23 | 14.03.23 | 04.03.23 | 14.03.23 | 12.03.24 | T4 | [10 empty] | jeevan.a@lntecc.com-08.07.2024-15:57:14
Bandra | Mechanical | Submersible Axial Flow pump-EPS | LE22M508-M-004 | LE22M508-M-004-E | Grunfos | Post-order comments issued | 41 |  |  |  | 06.07.22 | 06.07.22 | 18.08.22 | 07.10.22 | 01.03.23 | 02.03.23 | 09.03.23 | 10.03.23 | 24.03.23 | 28.03.23 |  |  | 24.03.23 | 28.03.23 | 12.03.24 | T2 | 04.06.24 | Grunfos | 19.06.24 | 24.06.24 | [5 empty] | 03.08.24 | jeevan.a@lntecc.com-08.07.2024-15:57:14
Bandra | Mechanical | Submersible Axial Flow pump-EPS | LE22M508-M-004 | LE22M508-M-004-F | KBL | Sent to BU Operations | PR Closed |  |  |  | 06.07.22 | 06.07.22 | 14.04.22 | 18.04.22 | 24.04.23 | 27.04.23 | 18.05.23 | 20.05.23 | 22.05.23 | 22.05.23 |  |  | 22.05.23 | 22.05.23 | 12.03.24 | T7 | [10 empty] | jeevan.a@lntecc.com-08.07.2024-15:57:14
Bandra | Mechanical | Submersible Axial Flow pump-EPS | LE22M508-M-004 | LE22M508-M-004-G | KSB | Sent to BU Operations | PR Closed |  |  |  | 06.07.22 | 06.07.22 | 20.02.23 | 21.02.23 | 24.04.23 | 25.04.23 | 30.05.23 | 31.05.23 | 29.02.24 | 05.03.24 |  |  | 29.02.24 | 05.03.24 | 12.03.24 | T5 | [10 empty] | jeevan.a@lntecc.com-08.07.2024-15:57:14
Bandra | Mechanical | Valves for Knife Gate Valve | LE22M508-M-005 | LE22M508-M-005-A | Fouress | Pre-order comments issued | 92 |  |  |  | 14.09.22 | 14.09.22 | 28.02.23 | 22.03.23 | 28.03.23 | 29.03.23 | 04.04.23 | 06.04.23 | 16.05.23 | 01.06.23 | 25.04.24 | 04.05.24 | [14 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Knife Gate Valve | LE22M508-M-005 | LE22M508-M-005-B | Vag | Regret offer | PR Closed |  |  |  | 15.09.22 | 14.09.22 | 21.03.23 | 23.03.23 | 24.03.23 | 29.03.23 | 30.03.23 | 31.03.23 | 07.04.23 | 10.04.23 | 12.04.23 | [15 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Knife Gate Valve | LE22M508-M-005 | LE22M508-M-005-C | AVK | Pre-order comments issued | 92 |  |  |  | 16.09.22 | 14.09.22 | 09.03.23 | 24.03.23 | 31.03.23 | 31.03.23 | 04.04.23 | 06.04.23 | 21.04.24 | 23.04.24 | 26.04.24 | 04.05.24 | [14 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Knife Gate Valve | LE22M508-M-005 | LE22M508-M-005-D | DVPL | Regret offer | PR Closed |  |  |  | 17.09.22 | 14.09.22 | 17.03.23 | 26.04.23 | 26.04.23 | 26.04.23 | [20 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Knife Gate Valve | LE22M508-M-005 | LE22M508-M-005-E | Jash | Pre-order comments issued | 94 |  |  |  | 18.09.22 | 14.09.22 | 03.03.23 | 23.03.23 | 12.05.23 | 15.05.23 | 20.06.23 | 21.06.23 | 19.04.24 | 19.04.24 | 25.04.24 | 02.05.24 | [14 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Knife Gate Valve | LE22M508-M-005 | LE22M508-M-005-F | Sigma Flow | Regret offer | PR Closed |  |  |  | 19.09.22 | 14.09.22 | 16.03.23 | 23.03.23 | 26.04.23 | 26.04.23 | 29.04.23 | 08.05.23 | 10.06.23 | 12.06.23 | [16 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Knife Gate Valve | LE22M508-M-005 | LE22M508-M-005-G | R&D Multiples | Regret offer | PR Closed |  |  |  | 20.09.22 | 14.09.22 | 31.03.23 | 06.05.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Knife Gate Valve | LE22M508-M-005 | LE22M508-M-005-H | H Sarker | Regret offer | PR Closed |  |  |  | 21.09.22 | 14.09.22 | 28.03.23 | 06.05.23 | 15.05.23 | 16.05.23 | 20.05.23 | 07.06.23 | 30.06.23 | 03.07.23 | [16 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-A | Vag | Regret offer | PR Closed |  |  |  | 22.09.22 | 14.09.22 | 21.03.23 | 23.03.23 | 24.03.23 | 29.03.23 | 30.03.23 | 31.03.23 | 07.04.23 | 10.04.23 | 12.04.23 | 12.04.23 | [14 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-B | AVK | Sent to BU Operations | 88 |  |  |  | 23.09.22 | 14.09.22 | 09.03.23 | 24.03.23 | 31.03.23 | 31.03.23 | 04.04.23 | 06.04.23 | 07.04.23 | 10.04.23 | 08.04.24 | 18.04.24 | 18.04.24 | 18.04.24 | 08.05.24 | T3 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-C | KBL | Sent to BU Operations | 88 |  |  |  | 24.09.22 | 14.09.22 | 09.03.23 | 22.03.23 | 30.03.23 | 31.03.23 | 10.04.23 | 10.04.23 | 04.04.24 | 17.04.24 | 24.04.24 | 24.04.24 | 24.04.24 | 24.04.24 | 08.05.24 | T4 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-D | DVPL | Regret offer | PR Closed |  |  |  | 25.09.22 | 14.09.22 | 17.03.23 | 21.04.23 | 25.04.23 | 25.04.23 | 01.04.24 | 17.04.24 | [18 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-E | Sigma Flow | Regret offer | PR Closed |  |  |  | 26.09.22 | 14.09.22 | 16.03.23 | 23.03.23 | 26.04.23 | 26.04.23 | [20 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-F | McWane | Regret offer | PR Closed |  |  |  | 27.09.22 | 14.09.22 | 17.03.23 | 22.03.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-G | Venus | Regret offer | PR Closed |  |  |  | 28.09.22 | 14.09.22 | 17.03.23 | 22.03.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-H | R&D Multiples | Sent to BU Operations | 88 |  |  |  | 29.09.22 | 14.09.22 | 31.03.23 | 06.05.23 | 11.04.24 | 17.04.24 | 23.04.24 | 23.04.24 | 24.04.24 | 24.04.24 |  |  | 24.04.24 | 24.04.24 | 08.05.24 | T1 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-I | IVC | Sent to BU Operations | 88 |  |  |  | 30.09.22 | 14.09.22 | 25.03.23 | 21.04.23 | 29.04.23 | 09.06.23 | 04.04.24 | 17.04.24 | 23.04.24 | 23.04.24 | 24.04.24 | 24.04.24 | 24.04.24 | 24.04.24 | 08.05.24 | T2 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Non Return Valve | LE22M508-M-006 | LE22M508-M-006-J | H Sarker | Regret offer | PR Closed |  |  |  | 01.10.22 | 14.09.22 | 28.03.23 | 21.04.23 | 26.04.23 | 26.04.23 | [20 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-A | Vag | Regret offer | PR Closed |  |  |  | 02.10.22 | 14.09.22 | 21.03.23 | 23.03.23 | 24.03.23 | 29.03.23 | 30.03.23 | 31.03.23 | 07.04.23 | 10.04.23 | 12.04.23 | [15 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-B | AVK | Sent to BU Operations | 88 |  |  |  | 03.10.22 | 14.09.22 | 09.03.23 | 24.03.23 | 31.03.23 | 31.03.23 | 04.04.23 | 06.04.23 | 23.04.23 | 25.04.23 | 02.05.24 | 03.05.24 | 03.05.24 | 03.05.24 | 08.05.24 | T1 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-C | KBL | Sent to BU Operations | 88 |  |  |  | 04.10.22 | 14.09.22 | 09.03.23 | 22.03.23 | 30.03.23 | 31.03.23 | 10.04.23 | 10.04.23 | 24.04.24 | 25.04.24 | 29.04.24 | 03.05.24 | 03.05.24 | 03.05.24 | 08.05.24 | T3 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-D | DVPL | Regret offer | PR Closed |  |  |  | 05.10.22 | 14.09.22 | 17.03.23 | 10.04.23 | 01.04.24 | 17.04.24 | [20 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-E | Sigma Flow | Regret offer | PR Closed |  |  |  | 06.10.22 | 14.09.22 | 16.03.23 | 23.03.23 | 26.04.23 | 26.04.23 | [20 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-F | McWane | Regret offer | PR Closed |  |  |  | 07.10.22 | 14.09.22 | 17.03.23 | 22.03.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-G | Venus | Regret offer | PR Closed |  |  |  | 08.10.22 | 14.09.22 | 17.03.23 | 22.03.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-H | R&D Multiples | Sent to BU Operations | 88 |  |  |  | 09.10.22 | 14.09.22 | 31.03.23 | 06.05.23 | 11.04.24 | 17.04.24 | 23.04.24 | 25.04.24 | 25.04.24 |  |  |  | 25.04.24 | 25.04.24 | 08.05.24 | T4 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-I | IVC | Sent to BU Operations | 88 |  |  |  | 10.10.22 | 14.09.22 | 25.03.23 | 28.04.23 | 29.04.23 | 09.06.23 | 04.04.24 | 17.04.24 | 24.04.24 | 24.04.24 |  |  | 24.04.24 | 24.04.24 | 08.05.24 | T2 | [10 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Sluice gate Valve | LE22M508-M-007 | LE22M508-M-007-J | H Sarker | Regret offer | PR Closed |  |  |  | 11.10.22 | 14.09.22 | 08.05.23 | 12.05.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-A | Fouress | Awaiting pre-offer from vendor | 305 | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 12.10.22 | 14.09.22 | 28.03.23 | 30.03.23 | 08.04.23 | 04.10.23 | 07.07.23 | [19 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-B | Vag | Awaiting pre-offer from vendor | 75 | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 13.10.22 | 16.05.24 | 21.05.24 | [23 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-C | AVK | Awaiting pre-offer from vendor | 75 | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 14.10.22 | 16.05.24 | 21.05.24 | [23 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-D | KBL | Awaiting pre-offer from vendor | 75 | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 15.10.22 | 16.05.24 | 21.05.24 | [23 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-E | DVPL | Regret offer | PR Closed | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 16.10.22 | 14.09.22 | 17.03.23 | 10.04.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-F | McWane | Regret offer | PR Closed | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 17.10.22 | 14.09.22 | 17.03.23 | 22.03.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-G | Venus | Regret offer | PR Closed | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 18.10.22 | 14.09.22 | 17.03.23 | 22.03.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-H | R&D Multiples | Regret offer | PR Closed | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 19.10.22 | 14.09.22 | 31.03.23 | 06.05.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-I | IVC | Regret offer | PR Closed | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 20.10.22 | 14.09.22 | 25.03.23 | 28.04.23 | 29.04.23 | 09.06.23 | [20 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-J | H Sarker | Regret offer | PR Closed | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  | 21.10.22 | 14.09.22 | 08.05.23 | 12.05.23 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Valves for Butterfly Valve | LE22M508-M-008 | LE22M508-M-008-K | Magwen | Regret offer | PR Closed | Awaiting MBR Vendor Finalization. Revised PR yet to float. |  |  |  | 14.09.22 | 01.12.23 | 08.02.24 | 21.02.24 | 27.02.24 | 08.03.24 | [19 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Sluice Gate | LE22M508-M-009 | LE22M508-M-009-A | AVK | Pre-order technically cleared | 116 |  |  |  | 06.07.22 | 06.07.22 | 16.03.23 | 29.03.23 | 14.04.23 | 21.04.23 | 10.05.23 | 16.05.23 | 02.04.24 | 05.04.24 | 09.04.24 | 10.04.24 | 10.04.24 | 10.04.24 | [12 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Sluice Gate | LE22M508-M-009 | LE22M508-M-009-A | AVK | Pre-order technically cleared | 116 |  |  |  | 06.07.22 | 06.07.22 | 16.03.23 | 29.03.23 | 14.04.23 | 21.04.23 | 10.05.23 | 16.05.23 | 02.04.24 | 05.04.24 | 09.04.24 | 10.04.24 | 10.04.24 | 10.04.24 | [12 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Sluice Gate | LE22M508-M-009 | LE22M508-M-009-B | DVPL | Pre-order technically cleared | 116 |  |  |  | 06.07.22 | 06.07.22 | 01.03.23 | 20.03.23 | 22.03.23 | 28.03.23 | 15.04.23 | 15.04.23 | 04.04.24 | 05.04.24 | 09.04.24 | 10.04.24 | 10.04.24 | 10.04.24 | [12 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Sluice Gate | LE22M508-M-009 | LE22M508-M-009-B | DVPL | Pre-order technically cleared | 116 |  |  |  | 06.07.22 | 06.07.22 | 01.03.23 | 20.03.23 | 22.03.23 | 28.03.23 | 15.04.23 | 15.04.23 | 04.04.24 | 05.04.24 | 09.04.24 | 10.04.24 | 10.04.24 | 10.04.24 | [12 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Sluice Gate | LE22M508-M-009 | LE22M508-M-009-C | Jash | Pre-order technically cleared | 118 |  |  |  | 06.07.22 | 06.07.22 | 21.03.23 | 29.03.23 | 31.03.23 | 11.04.23 | 25.04.23 | 29.04.23 | 02.04.24 | 04.04.24 | 06.04.24 | 08.04.24 | 08.04.24 | 08.04.24 | [12 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Sluice Gate | LE22M508-M-009 | LE22M508-M-009-C | Jash | Pre-order technically cleared | 118 |  |  |  | 06.07.22 | 06.07.22 | 21.03.23 | 29.03.23 | 31.03.23 | 11.04.23 | 25.04.23 | 29.04.23 | 02.04.24 | 04.04.24 | 06.04.24 | 08.04.24 | 08.04.24 | 08.04.24 | [12 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Sluice Gate | LE22M508-M-009 | LE22M508-M-009-D | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 06.07.22 | [25 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Sluice Gate | LE22M508-M-009 | LE22M508-M-009-E | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 06.07.22 | [25 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Odour Control Unit | LE22M508-M-010 | LE22M508-M-010-A | AZZURO | Pre-order comments issued | 101 |  |  |  | 06.08.22 | 22.02.24 | 01.03.24 | 05.03.24 | 28.03.24 | 25.04.24 | [20 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Odour Control Unit | LE22M508-M-010 | LE22M508-M-010-B | BioAir | Pre-order comments issued | 101 |  |  |  | 07.08.22 | 22.02.24 | 07.03.24 | 25.04.24 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Odour Control Unit | LE22M508-M-010 | LE22M508-M-010-C | Neev Fluidex | Pre-order comments issued | 101 |  |  |  | 08.08.22 | 22.02.24 | 25.03.24 | 25.04.24 | [22 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Odour Control Unit | LE22M508-M-010 | LE22M508-M-010-D | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 09.08.22 | 22.02.24 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Odour Control Unit | LE22M508-M-010 | LE22M508-M-010-E | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 10.08.22 | 22.02.24 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Firefighting System | LE22M508-M-011 | LE22M508-M-011-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 14.02.23 | 14.02.23 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Firefighting System | LE22M508-M-011 | LE22M508-M-011-B | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 15.02.23 | 14.02.23 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Firefighting System | LE22M508-M-011 | LE22M508-M-011-C | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.02.23 | 14.02.23 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Firefighting System | LE22M508-M-011 | LE22M508-M-011-D | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 17.02.23 | 14.02.23 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Firefighting System | LE22M508-M-011 | LE22M508-M-011-E | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 18.02.23 | 14.02.23 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Lifting Arrangement | LE22M508-M-012 | LE22M508-M-012-A | Vendor Name yet to provide | Enquiry yet to float | NA | Supply Target 2025-2026 |  |  | 06.07.22 | 06.07.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Lifting Arrangement | LE22M508-M-012 | LE22M508-M-012-B | Vendor Name yet to provide | Enquiry yet to float | NA | Supply Target 2025-2026 |  |  | 07.07.22 | 06.07.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Lifting Arrangement | LE22M508-M-012 | LE22M508-M-012-C | Vendor Name yet to provide | Enquiry yet to float | NA | Supply Target 2025-2026 |  |  | 08.07.22 | 06.07.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Lifting Arrangement | LE22M508-M-012 | LE22M508-M-012-D | Vendor Name yet to provide | Enquiry yet to float | NA | Supply Target 2025-2026 |  |  | 09.07.22 | 06.07.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Mechanical | Lifting Arrangement | LE22M508-M-012 | LE22M508-M-012-E | Vendor Name yet to provide | Enquiry yet to float | NA | Supply Target 2025-2026 |  |  | 10.07.22 | 06.07.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Electromagnetic Type Flow Transmitter | LE22M508-I-001 | LE22M508-I-001-A | E&H | Enquiry yet to float | NA | [29 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Electromagnetic Type Flow Transmitter | LE22M508-I-002 | LE22M508-I-001-B | Krohne | Enquiry yet to float | NA | [29 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Electromagnetic Type Flow Transmitter | LE22M508-I-003 | LE22M508-I-001-C | Emerson | Enquiry yet to float | NA | [29 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Thermal Mass Flowmeter | LE22M508-I-002 | LE22M508-I-002-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Ultrasonic Type Flowmeter | LE22M508-I-003 | LE22M508-I-003-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Orifice Flow Meter with DPT | LE22M508-I-004 | LE22M508-I-004-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Area Velocity Flow meter | LE22M508-I-005 | LE22M508-I-005-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Rotameter | LE22M508-I-006 | LE22M508-I-006-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Pressure Transmitter | LE22M508-I-007 | LE22M508-I-007-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Pressure Switch | LE22M508-I-008 | LE22M508-I-008-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Pressure Gauge | LE22M508-I-009 | LE22M508-I-009-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Ultrasonic Type Level Transmitter | LE22M508-I-010 | LE22M508-I-010-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Hydrostatic Type Level Transmitter | LE22M508-I-011 | LE22M508-I-011-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Radar Type Level Transmitter | LE22M508-I-012 | LE22M508-I-012-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Level Switch | LE22M508-I-013 | LE22M508-I-013-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | 08.10.23 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Level Gauge | LE22M508-I-014 | LE22M508-I-014-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | 08.10.23 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Temperature Indicating Transmitter | LE22M508-I-015 | LE22M508-I-015-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.10.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Weight Indicating Transmitter | LE22M508-I-016 | LE22M508-I-016-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | [25 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Auto Sampler | LE22M508-I-017 | LE22M508-I-017-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Online Analyzers | LE22M508-I-018 | LE22M508-I-018-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | PLC / RIO Panel | LE22M508-I-019 | LE22M508-I-019-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | 29.12.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | SCADA Software & Hardware Equipment | LE22M508-I-020 | LE22M508-I-020-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | 29.12.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | UPS Panel | LE22M508-I-021 | LE22M508-I-021-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | 28.11.22 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | I&C Cable | LE22M508-I-022 | LE22M508-I-022-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | 08.09.23 | [24 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | CCTV System | LE22M508-I-023 | LE22M508-I-023-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | [25 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | Fire Alarm and Detection System | LE22M508-I-024 | LE22M508-I-024-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | [25 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | PA System | LE22M508-I-025 | LE22M508-I-025-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | [25 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Instrumentation | EPABX System | LE22M508-I-026 | LE22M508-I-026-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 16.11.22 | [25 empty] | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | 6.6 kV MV Switchboard | LE22M508-E-001 | LE22M508-E-001-A | ABB | Sent to BU Operations | 231 |  |  |  | 30.08.22 | 30.08.22 | 18.10.22 | 20.10.22 | 17.12.23 | 30.12.22 | 21.01.23 | 12.02.23 | 18.02.23 |  |  |  | 10.02.23 | 18.02.23 | 18.02.23 | T1 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | 6.6 kV MV Switchboard | LE22M508-E-001 | LE22M508-E-001-B | Schneider L&T | Sent to BU Operations | 542 |  |  |  | 30.08.22 | 30.08.22 | 07.10.22 | 25.10.22 | 08.12.22 | 10.01.23 | 09.02.23 | [5 empty] | 12.01.23 | 18.01.23 | 18.01.23 | T1 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:02:52
Bandra | Electrical | 6.6 kV MV Switchboard | LE22M508-E-001 | LE22M508-E-001-C | Simens Symatic | Sent to BU Operations | 543 |  |  |  | 30.08.22 | 30.08.22 | 20.10.22 | 11.11.22 | 15.12.22 | 30.12.22 | 21.01.23 | 01.02.23 | 08.02.23 |  |  |  | 01.02.23 | 03.02.23 | 03.02.23 | T2 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:02:52
Bandra | Electrical | 6.6 kV MV Switchboard | LE22M508-E-001 | LE22M508-E-001-D | HT Switchgears | Sent to BU Operations | 534 |  |  |  | 30.08.22 | 30.08.22 | 15.12.22 | 16.12.22 | 17.12.22 | 30.12.22 | 21.01.23 | 01.02.23 | 17.02.23 |  |  |  | 08.02.23 | 16.02.23 | 16.02.23 | T3 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:02:52
Bandra | Electrical | 6.6 kV MV Switchboard | LE22M508-E-001 | LE22M508-E-001-E | CGL | Sent to BU Operations | 125 |  |  |  | 30.08.22 | 30.08.22 | 10.10.22 | 25.10.22 | 08.12.22 | 10.01.23 | 18.02.23 | 01.04.24 |  |  |  |  | 04.02.23 | 14.02.23 | 14.02.23 | T2 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:02:52
Bandra | Electrical | 6.6 kV MV Switchboard | LE22M508-E-001 | LE22M508-E-001-F | Technocraft | Sent to BU Operations | 533 |  |  |  | 30.08.22 | 30.08.22 | 05.12.22 | 07.12.22 | 08.12.22 | 10.01.23 | 18.02.23 | [5 empty] | 11.02.23 | 17.02.23 | 17.02.23 | T3 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:02:52
Bandra | Electrical | 6.6 kV MV Switchboard | LE22M508-E-001 | LE22M508-E-001-G | UPE | Sent to BU Operations | 543 |  |  |  | 30.08.22 | 30.08.22 | 21.10.22 | 26.10.22 | 07.11.22 |  | 08.02.23 | [5 empty] | 20.01.23 | 22.01.23 | 22.01.23 | T3 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:02:52
Bandra | Electrical | 6.6 kV MV Switchboard | LE22M508-E-001 | LE22M508-E-001-H | Popular Switchgear | Sent to BU Operations | 37 |  |  |  |  | 03.06.24 | 05.06.24 | 10.06.24 | 14.06.24 | [7 empty] | 14.06.24 | 14.06.24 | 14.06.24 | T1 | 28.06.24 | [8 empty] | 27.08.24 | syuvaraj@lntecc.com-08.07.2024-17:02:52
Bandra | Electrical | Solar PV Module | LE22M508-E-002 | LE22M508-E-002-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 01.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | Solar PV Module | LE22M508-E-002 | LE22M508-E-002-B | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 01.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | Solar PV Module | LE22M508-E-002 | LE22M508-E-002-C | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 01.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-B | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-C | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-D | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-E | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-F | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:02
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-G | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-H | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-I | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-J | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT Switchboard ( PMCC & MCC) Panels | LE22M508-E-003 | LE22M508-E-003-K | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-B | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-C | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-D | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-E | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-F | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-G | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-H | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-I | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-J | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT VFD Panels | LE22M508-E-004 | LE22M508-E-004-K | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-B | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-C | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-D | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-E | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-F | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-G | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-H | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-I | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-J | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT APFC Panels | LE22M508-E-005 | LE22M508-E-005-K | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 08.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | 415V LT Non Segregated Busduct | LE22M508-E-006 | LE22M508-E-006-A | C&S | Sent to BU Operations | 544 |  |  |  | 13.09.22 | 23.09.22 | 16.12.22 | 07.11.22 | 08.11.22 | 16.12.22 | 16.12.22 | 07.01.23 | 07.02.23 |  |  |  | 02.02.23 | 07.02.23 | 07.02.23 | T2 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:31:46
Bandra | Electrical | 415V LT Non Segregated Busduct | LE22M508-E-006 | LE22M508-E-006-B | Star Drive | Sent to BU Operations | 544 |  |  |  | 13.09.22 | 23.09.22 | 06.10.22 | 07.11.22 | 07.02.23 | [7 empty] | 03.02.23 | 07.02.23 | 07.02.23 | T1 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:31:46
Bandra | Electrical | 415V LT Non Segregated Busduct | LE22M508-E-006 | LE22M508-E-006-C | Schneider | Sent to BU Operations | 31 |  |  |  | 13.09.22 | 23.09.22 | 02.01.23 | 29.11.22 | 02.01.23 | 22.01.23 | 15.02.23 | [5 empty] | 12.02.23 | 15.02.23 | 15.02.23 | T1 | 04.07.24 | Schneider | [7 empty] | 02.09.24 | syuvaraj@lntecc.com-08.07.2024-17:31:46
Bandra | Electrical | 415V LT Non Segregated Busduct | LE22M508-E-006 | LE22M508-E-006-D | Godrej | Sent to BU Operations | 544 |  |  |  | 13.09.22 | 23.09.22 | 09.12.22 | 09.12.22 | 07.02.23 | [7 empty] | 01.02.23 | 07.02.23 | 07.02.23 | T1 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:31:46
Bandra | Electrical | 415V LT Non Segregated Busduct | LE22M508-E-006 | LE22M508-E-006-E | Sun Automat | Sent to BU Operations | 541 |  |  |  | 13.09.22 | 23.09.22 | 14.10.22 | 07.11.22 | 10.02.23 | [7 empty] | 03.02.23 | 10.02.23 | 10.02.23 | T2 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:31:46
Bandra | Electrical | 415V LT Non Segregated Busduct | LE22M508-E-006 | LE22M508-E-006-F | Nitya Electricals | Sent to BU Operations | 541 |  |  |  | 13.09.22 | 23.09.22 | 31.12.22 | 16.12.22 | 31.12.22 | 22.01.23 | 10.02.23 | [5 empty] | 04.02.23 | 10.02.23 | 10.02.23 | T2 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:31:46
Bandra | Electrical | Distribution Transformer (Electrical Substation -1 ) | LE22M508-E-007 | LE22M508-E-007-A | Hitachi | Pre-order technically cleared | 541 |  |  |  | 16.09.22 | 03.09.22 | 08.10.22 | 20.10.22 | 28.10.22 | 21.01.23 | 10.02.23 | [5 empty] | 07.02.23 | 10.02.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Distribution Transformer (Electrical Substation -1 ) | LE22M508-E-007 | LE22M508-E-007-B | Indcoil | Pre-order technically cleared | 537 |  |  |  | 16.09.22 | 03.09.22 | 25.01.23 | 17.10.22 | 28.10.22 | 21.01.23 | 14.02.23 | [5 empty] | 10.02.23 | 14.02.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Distribution Transformer (Electrical Substation -1 ) | LE22M508-E-007 | LE22M508-E-007-C | Voltech | Pre-order technically cleared | 538 |  |  |  | 16.09.22 | 03.09.22 | 11.10.22 | 15.01.23 | 13.02.23 | [7 empty] | 03.02.23 | 13.02.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Distribution Transformer (Electrical Substation -1 ) | LE22M508-E-007 | LE22M508-E-007-D | Telewane | Pre-order technically cleared | 538 |  |  |  | 16.09.22 | 03.09.22 | 06.01.23 | 15.01.23 | 23.01.23 | 01.02.23 | 13.02.23 | [5 empty] | 10.02.23 | 13.02.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Distribution Transformer (Electrical Substation -1 ) | LE22M508-E-007 | LE22M508-E-007-E | SGB | Pre-order technically cleared | 552 |  |  |  | 16.09.22 | 03.09.22 | 18.12.22 | 22.11.22 | 02.12.22 | 29.12.22 | 30.01.23 | [5 empty] | 23.01.23 | 30.01.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Active Harmonic Filters | LE22M508-E-008 | LE22M508-E-008-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 17.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | Battery Charger | LE22M508-E-009 | LE22M508-E-009-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 24.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | Distribution Transformer (Electrical Substation -2 ) | LE22M508-E-010 | LE22M508-E-010-A | Hitachi | Pre-order technically cleared | 541 |  |  |  | 16.09.22 | 03.09.22 | 08.10.22 | 20.10.22 | 28.10.22 | 21.01.23 | 10.02.23 | [5 empty] | 07.02.23 | 10.02.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Distribution Transformer (Electrical Substation -2 ) | LE22M508-E-010 | LE22M508-E-010-B | Indcoil | Pre-order technically cleared | 537 |  |  |  | 16.09.22 | 03.09.22 | 25.01.23 | 17.10.22 | 28.10.22 | 21.01.23 | 14.02.23 | [5 empty] | 10.02.23 | 14.02.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Distribution Transformer (Electrical Substation -2 ) | LE22M508-E-010 | LE22M508-E-010-C | Voltech | Pre-order technically cleared | 538 |  |  |  | 16.09.22 | 03.09.22 | 11.10.22 | 15.01.23 | 13.02.23 | [7 empty] | 03.02.23 | 13.02.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Distribution Transformer (Electrical Substation -2 ) | LE22M508-E-010 | LE22M508-E-010-D | Telewane | Pre-order technically cleared | 538 |  |  |  | 16.09.22 | 03.09.22 | 06.01.23 | 15.01.23 | 23.01.23 | 01.02.23 | 13.02.23 | [5 empty] | 10.02.23 | 13.02.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | Distribution Transformer (Electrical Substation -2 ) | LE22M508-E-010 | LE22M508-E-010-E | SGB | Pre-order technically cleared | 552 |  |  |  | 16.09.22 | 03.09.22 | 18.12.22 | 22.11.22 | 02.12.22 | 29.12.22 | 30.01.23 | [5 empty] | 23.01.23 | 30.01.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | HT Cables | LE22M508-E-011 | LE22M508-E-011-A | Universal | Sent to BU Operations | 30 |  |  |  | 16.09.22 | 23.09.22 | 06.02.23 | 21.03.23 | 27.03.23 | [7 empty] | 20.03.23 | 22.03.23 | 22.03.23 | T1 | 05.07.24 | Universal | [7 empty] | 03.09.24 | syuvaraj@lntecc.com-08.07.2024-17:29:11
Bandra | Electrical | HT Cables | LE22M508-E-011 | LE22M508-E-011-B | KEC | Sent to BU Operations | 496 |  |  |  | 16.09.22 | 23.09.22 | 25.01.23 | 23.03.23 | 27.03.23 | [7 empty] | 18.03.23 | 19.03.23 | 19.03.23 | T1 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:27:43
Bandra | Electrical | HT Cables | LE22M508-E-011 | LE22M508-E-011-C | Polycab | Sent to BU Operations | 496 |  |  |  | 16.09.22 | 23.09.22 | 25.02.22 | 26.03.23 | 27.03.23 | [7 empty] | 20.03.23 | 23.03.23 | 23.03.23 | T2 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:27:43
Bandra | Electrical | HT Cables | LE22M508-E-011 | LE22M508-E-011-D | Dynamic Cables | Sent to BU Operations | 496 |  |  |  | 16.09.22 | 23.09.22 | 18.10.22 | 12.01.23 | 27.01.23 | 12.02.23 | 27.02.23 | 26.03.23 | 27.03.23 |  |  |  | 18.03.23 | 25.03.23 | 25.03.23 | T1 | [10 empty] | syuvaraj@lntecc.com-08.07.2024-17:27:43
Bandra | Electrical | Battery System | LE22M508-E-012 | LE22M508-E-012-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 24.09.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | Power Distribution Boards | LE22M508-E-013 | LE22M508-E-013-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 01.10.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | Lighting System | LE22M508-E-014 | LE22M508-E-014-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 11.10.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | Earthing & Lightning Materials | LE22M508-E-015 | LE22M508-E-015-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 11.10.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | Safety Accessories | LE22M508-E-016 | LE22M508-E-016-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 11.10.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | Local Push Button Station | LE22M508-E-017 | LE22M508-E-017-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 13.10.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | Cable Tray & Accessories | LE22M508-E-018 | LE22M508-E-018-A | Vendor Name yet to provide | Enquiry yet to float | NA | This Equipment planned in Q4. Revised Enquiry Yet to Float. |  |  | 15.10.22 | [22 empty] | 31.03.25 | 17.04.25 | 16.06.25 | prabhakaranm@lntecc.com-01.07.2024-14:47:03
Bandra | Electrical | LT Cables | LE22M508-E-019 | LE22M508-E-019-A | Avocab | Pre-order technically cleared | 503 |  |  |  | 15.10.22 | 07.11.22 | 21.11.22 | 15.03.23 | 20.03.23 | [7 empty] | 18.03.23 | 19.03.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:09
Bandra | Electrical | LT Cables | LE22M508-E-019 | LE22M508-E-019-B | Axelon | Pre-order technically cleared | 503 |  |  |  | 15.10.22 | 07.11.22 | 01.12.22 | 14.03.23 | 20.03.23 | [7 empty] | 15.03.23 | 19.03.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:10
Bandra | Electrical | LT Cables | LE22M508-E-019 | LE22M508-E-019-C | Delton | Pre-order technically cleared | 503 |  |  |  | 15.10.22 | 07.11.22 | 01.12.22 | 19.03.23 | 20.03.23 | [7 empty] | 15.03.23 | 19.03.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:10
Bandra | Electrical | LT Cables | LE22M508-E-019 | LE22M508-E-019-D | Grandlay | Pre-order technically cleared | 503 |  |  |  | 15.10.22 | 07.11.22 | 01.12.22 | 10.03.23 | 20.03.23 | [7 empty] | 15.03.23 | 19.03.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:10
Bandra | Electrical | LT Cables | LE22M508-E-019 | LE22M508-E-019-E | Prime Cables | Pre-order technically cleared | 503 |  |  |  | 15.10.22 | 07.11.22 | 01.12.22 | 20.03.23 | 20.03.23 | [7 empty] | 10.03.23 | 12.03.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:10
Bandra | Electrical | LT Cables | LE22M508-E-019 | LE22M508-E-019-F | Cords | Pre-order technically cleared | 424 |  |  |  | 15.10.22 | 07.11.22 | 05.05.23 | 01.01.23 | 07.06.23 | [7 empty] | 15.03.23 | 19.03.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:10
Bandra | Electrical | LT Cables | LE22M508-E-019 | LE22M508-E-019-G | Universal | Pre-order technically cleared | 424 |  |  |  | 15.10.22 | 07.11.22 | 30.05.23 | 01.01.23 | 07.06.23 | [7 empty] | 15.03.23 | 19.03.23 | [12 empty] | syuvaraj@lntecc.com-08.07.2024-16:59:10
Bankura 2A | Mechanical | Ventilation fans | LE190278-004-M | LE190278-004-M-A | BAJAJ | Enquiry yet to float | NA | [26 empty] | 18.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:04:39
Bankura 2A | Mechanical | Ventilation fans | LE190278-004-M | LE190278-004-M-B | EPC | Enquiry yet to float | NA | [26 empty] | 18.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:04:39
Bankura 2A | Mechanical | Ventilation fans | LE190278-004-M | LE190278-004-M-C | Havells | Enquiry yet to float | NA | [26 empty] | 18.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:04:39
Bankura 2A | Mechanical | SLUICE GATE | LE190278-M-001 | LE190278-M-001-A | IVC | Pre-order comments issued | 233 |  |  |  | 13.09.23 | 13.09.23 | 20.11.23 | 15.12.23 | [19 empty] | 19.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:04:39
Bankura 2A | Mechanical | SLUICE GATE | LE190278-M-001 | LE190278-M-001-B | JASH | Pre-order comments issued | 233 |  |  |  | 13.09.23 | 13.09.23 | 20.11.23 | 15.12.23 | [19 empty] | 19.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:04:39
Bankura 2A | Mechanical | SLUICE GATE | LE190278-M-001 | LE190278-M-001-C | ORIENTAL CASTING | Pre-order comments issued | 233 |  |  |  | 13.09.23 | 13.09.23 | 20.11.23 | 15.12.23 | [19 empty] | 19.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:04:39
Bankura 2A | Mechanical | VALVES | LE190278-M-002 | LE190278-M-002-A | AVK | Approved by Client | PR Closed |  |  |  | 13.09.23 | 13.09.23 | 08.04.24 | 15.04.24 | [8 empty] | 30.04.24 | 30.04.24 | 01.05.24 | T1 | 06.05.24 | AVK | 01.05.24 | 02.05.24 | 04.05.24 | 06.05.24 | 01.07.24 | 31.03.24 | 17.04.24 | 16.06.24 | gopal.samarth@lntecc.com-10.07.2024-15:03:12
Bankura 2A | Mechanical | VALVES | LE190278-M-002 | LE190278-M-002-B | KBL | Sent to BU Operations | PR Closed |  |  |  | 13.09.23 | 13.09.23 | 13.10.23 | 15.12.23 | [8 empty] | 30.04.24 | 30.04.24 | 01.05.24 | T1 | [7 empty] | 31.03.24 | 17.04.24 | 16.06.24 | gopal.samarth@lntecc.com-10.07.2024-14:11:50
Bankura 2A | Mechanical | VALVES | LE190278-M-002 | LE190278-M-002-C | VAG | Sent to BU Operations | PR Closed |  |  |  | 13.09.23 | 13.09.23 | 13.10.23 | 15.12.23 | [8 empty] | 30.04.24 | 30.04.24 | 01.05.24 | T1 | [7 empty] | 31.03.24 | 17.04.24 | 16.06.24 | gopal.samarth@lntecc.com-10.07.2024-14:11:50
Bankura 2A | Mechanical | HSC-pump | LE190278-M-003 | LE190278-M-003-1 | WILO | Approved by Client | PR Closed | GOBINDPUR-HSC_pump Doc. pending with Client |  |  |  | 08.01.24 | 15.01.24 | 17.01.24 | [8 empty] | 22.01.24 | 23.01.24 | 23.01.24 | T1 | 24.01.24 | WILO | 24.01.24 | 24.01.24 | 25.01.24 | 25.01.24 | 29.01.24 | 23.01.24 | 09.02.24 | 24.03.24 | gopal.samarth@lntecc.com-03.07.2024-17:17:51
Bankura 2A | Instrumentation | Epabx systen | LE190278-I-002 | LE190278-I-00-A2 | Telsonetwork | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:28:44
Bankura 2A | Instrumentation | Epabx systen | LE190278-I-002 | LE190278-I-00-A3 | Int Tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:28:44
Bankura 2A | Instrumentation | UPS | LE190278-I-001 | LE190278-I-001-A | Hitachi Hirel | Sent to BU Operations | 56 |  |  |  | 05.01.24 | 05.01.24 | 08.01.24 | 18.01.24 | 09.06.24 | [7 empty] | 19.01.24 | 31.01.24 | 09.06.24 | T1 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-09.07.2024-17:04:55
Bankura 2A | Instrumentation | UPS | LE190278-I-001 | LE190278-I-001-B | Liveline | Sent to BU Operations | 56 |  |  |  | 05.01.24 | 05.01.24 | 08.01.24 | 18.01.24 | 09.06.24 | [7 empty] | 27.01.24 | 31.01.24 | 09.06.24 | T2 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-09.07.2024-17:04:55
Bankura 2A | Instrumentation | PA systen | LE190278-I-003 | LE190278-I-003-A | Telsonetwork | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:28:44
Bankura 2A | Instrumentation | PA systen | LE190278-I-003 | LE190278-I-003-B | Int Tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:28:44
Bankura 2A | Instrumentation | CCTV systen | LE190278-I-004 | LE190278-I-004-A | Telsonetwork | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:28:44
Bankura 2A | Instrumentation | CCTV systen | LE190278-I-004 | LE190278-I-004-B | Int Tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:28:44
Bankura 2A | Instrumentation | Battery operated Electro Magnetic Flow meter | LE190278-I-WS-PR-BP-5509 | LE190278-I-WS-PR-BP-5509-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Instrumentation Cables | LE190278-I-WS-PR-BP-5515 | LE190278-I-WS-PR-BP-5515-A | KEI | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | KEI | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | AC operated Electro Magnetic Flow meter | LE190278-I-WS-PR-EF-5508 | LE190278-I-WS-PR-EF-5508-A | Adept | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Adept | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Float & Dial Type Level indicator | LE190278-I-WS-PR-LI-5506 | LE190278-I-WS-PR-LI-5506-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Conductivity Type Level Swtch | LE190278-I-WS-PR-LS-5507 | LE190278-I-WS-PR-LS-5507-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Radar Type Level Transmitter | LE190278-I-WS-PR-LT-5504 | LE190278-I-WS-PR-LT-5504-A | siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Ultrasonic Type Level Transmitter | LE190278-I-WS-PR-LT-5505 | LE190278-I-WS-PR-LT-5505-A | siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Pressure Gauge/Compound Pressure Gauge | LE190278-I-WS-PR-PG-5501 | LE190278-I-WS-PR-PG-5501-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | AN Instruments | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Ph Analyzer | LE190278-I-WS-PR-PH-5510 | LE190278-I-WS-PR-PH-5510-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | PLC\SCADA | LE190278-I-WS-PR-PL-5513 | LE190278-I-WS-PR-PL-5513-A | Autosys | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Autosys | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Pressure Switch | LE190278-I-WS-PR-PS-5502 | LE190278-I-WS-PR-PS-5502-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | AN Instruments | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Pressure Transmitter | LE190278-I-WS-PR-PT-5503 | LE190278-I-WS-PR-PT-5503-A | siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Residual Chlroine Analyzer | LE190278-I-WS-PR-RC-5511 | LE190278-I-WS-PR-RC-5511-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Instrumentation | Turbidity Analyzer | LE190278-I-WS-PR-TU-5512 | LE190278-I-WS-PR-TU-5512-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | SURENDHAR@lntecc.com-01.06.2024-11:25:00
Bankura 2A | Electrical | LT Cables | LE-190278-E-WS-WT-PR-4106 | LE-190278-E-WS-WT-PR-4106-A | KEI | Pre-order comments issued | 408 | Compliance given |  |  |  | 11.09.20 | 21.12.22 | 26.12.22 | [8 empty] | 23.06.23 | 23.06.23 | 23.06.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:08
Bankura 2A | Electrical | Cable trays | LE-190278-E-WS-WT-PR-4107 | LE-190278-E-WS-WT-PR-4107-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:40
Bankura 2A | Electrical | Lighting Fixtures | LE-190278-E-WS-WT-PR-4108 | LE-190278-E-WS-WT-PR-4108-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:40
Bankura 2A | Electrical | HT Cable and termination | LE-190278-E-WS-WT-PR-4117 | LE-190278-E-WS-WT-PR-4117-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:40
Bankura 2A | Electrical | LT Panel | LE190278-E-001 | LE190278-E-001-B | BCH | Sent to BU Operations | 215 |  |  |  | 26.9.22 | 26.09.22 | 16.12.23 | 16.12.23 | [8 empty] | 16.12.23 | 02.01.24 | 02.01.24 | T2 | [10 empty] | rawabi.c@lntecc.com-22.07.2024-17:31:49
Bankura 2A | Electrical | Transformer | LE190278-E-002 | LE190278-E-002-A | Essenar | Sent to BU Operations | PR Closed |  |  |  | 14.2.20 | 14.02.20 | 14.12.23 | 22.12.23 | [8 empty] | 22.12.23 | 22.12.23 | 22.12.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:40
Bankura 2A | Electrical | Transformer | LE190278-E-002 | LE190278-E-002-B | Kirlosker | Post-order technically cleared | 106 |  |  |  | 14.2.20 | 14.02.20 | 19.12.23 | 22.12.23 | [8 empty] | 01.02.24 | 01.02.24 | 01.02.24 | T2 | 1.2.24 | Kirlosker | 11.3.24 | 16.3.24 | 16.4.24 | 20.4.24 |  |  |  | 01.04.24 | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:08
Bankura 2A | Electrical | Transformer | LE190278-E-002 | LE190278-E-002-C | Voltamp | Sent to BU Operations | PR Closed |  |  |  | 14.2.20 | 14.02.20 | 21.12.23 | 01.01.24 | [8 empty] | 02.01.24 | 02.01.24 | 02.01.24 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:40
Bankura 2A | Electrical | Transformer | LE190278-E-002 | LE190278-E-002-D | Sai Electrical | Sent to BU Operations | PR Closed |  |  |  | 14.2.20 | 14.02.20 | 21.02.24 | 21.02.24 | [8 empty] | 21.02.24 | 21.02.24 | 22.2.24 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:40
Bankura 2A | Electrical | AVR | LE190278-E-WS-CW-PR-4104 | LE190278-E-WS-CW-PR-4104-A | ICON | Post-order comments issued | 65 |  |  |  | 7.12.22 | 07.12.22 | 17.01.24 | 14.02.24 | 19.02.24 | 20.02.24 | [6 empty] | 29.02.24 | 29.02.24 | 29.02.24 | T2 | 15.5.24 | ICON | 16.5.24 | 31.5.24 | [5 empty] | 14.07.24 | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:08
Bankura 2A | Electrical | AVR | LE190278-E-WS-CW-PR-4104 | LE190278-E-WS-CW-PR-4104-B | Reliable | Sent to BU Operations | PR Closed |  |  |  | 7.12.22 | 07.12.22 | 05.02.24 | 06.02.24 | [8 empty] | 6.2.24 | 6.2.24 | 6.2.24 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:08
Bankura 2A | Electrical | LT Panel | LE190278-E-WS-CW-PR-4105 | LE190278-E-WS-CW-PR-4105-A | EAP | Post-order technically cleared | 157 |  |  |  | 26.9.22 | 26.09.22 | 29.09.22 | 05.10.22 | [8 empty] | 08.10.22 | 08.10.22 | 08.10.22 | T1 | 16.10.23 | EAP | 30.01.24 | 23.02.24 | 26.02.24 | 29.02.24 |  |  |  | 15.12.23 | rawabi.c@lntecc.com-22.07.2024-17:31:49
Bankura 2A | Electrical | LT Panel | LE190278-E-WS-CW-PR-4105 | LE190278-E-WS-CW-PR-4105-B | PCE | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 26.09.22 | 28.10.22 | 02.11.22 | [8 empty] | 22.05.23 | 22.05.23 | 22.05.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:41
Bankura 2A | Electrical | LT Panel | LE190278-E-WS-CW-PR-4105 | LE190278-E-WS-CW-PR-4105-C | Prayaas | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 26.09.22 | 28.10.22 | 11.11.22 | [8 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:41
Bankura 2A | Electrical | Cable glands and lugs | LE190278-E-WS-CW-PR-4112 | LE190278-E-WS-CW-PR-4112-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:41
Bankura 2A | Electrical | Diesel Generators | LE190278-E-WS-WT-PR-4103 | LE190278-E-WS-WT-PR-4103-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:41
Bankura 2A | Electrical | Earthing and Lightning | LE190278-E-WS-WT-PR-4109 | LE190278-E-WS-WT-PR-4109-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:41
Bankura 2A | Electrical | Electrical Safety Items | LE190278-E-WS-WT-PR-4110 | LE190278-E-WS-WT-PR-4110-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:41
Bankura 2A | Electrical | Local Push Button Station | LE190278-E-WS-WT-PR-4111 | LE190278-E-WS-WT-PR-4111-A | SRCS | Pre-order comments issued | 86 | LPBS& LDB |  |  |  | 10.4.24 | 23.4.24 | 24.4.24 | 3.5.24 | 6.5.24 | 6.5.24 | 10.5.24 | [18 empty] | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:08
Bankura 2A | Electrical | Local Push Button Station | LE190278-E-WS-WT-PR-4111 | LE190278-E-WS-WT-PR-4111-B | EAP | Pre-order comments issued | 86 | LPBS & LDB |  |  |  | 10.4.24 | 30.4.24 | 2.5.24 | 3.5.24 | 7.5.24 | 7.5.24 | 10.5.24 | [18 empty] | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:08
Bankura 2A | Electrical | HT Panel | LE190278-E-WS-WT-PR-4116 | LE190278-E-WS-WT-PR-4116-A | ABB | Approved by Client | PR Closed |  |  |  | 8.6.22 | 08.06.22 | 10.06.22 | 15.06.22 | [8 empty] | 25.06.22 | 25.06.22 | 25.06.22 | T1 | 25.06.23 | ABB | 27.06.23 | 27.12.23 | 28.12.23 | 28.12.23 | 28.12.23 |  |  | 24.08.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:52:41
Bankura 2A | Electrical | BUS DUCT | LE190278-E-WS-WT-PR-4118 | LE190278-E-WS-WT-PR-4118-A | PCE | Sent to BU Operations | PR Closed |  |  |  | 18.11.22 | 18.11.22 | 14.12.22 | 14.12.22 | [8 empty] | 14.12.22 | 14.12.22 | 14.12.22 | T2 | [10 empty] | rawabi.c@lntecc.com-22.07.2024-17:30:39
Bankura 2A | Electrical | BUS DUCT | LE190278-E-WS-WT-PR-4118 | LE190278-E-WS-WT-PR-4118-B | C &S | Post-order technically cleared | 121 |  |  |  | 18.11.22 | 01.09.22 | 18.10.23 | 31.10.23 | [8 empty] | 21.12.23 | 25.12.23 | 25.12.23 | T1 | 12.02.24 | C &S | 18.02.24 | 23.02.24 | 05.04.24 | 05.04.24 |  |  |  |  | rawabi.c@lntecc.com-22.07.2024-17:30:39
Bankura 2B | Mechanical | SLUICE GATE | LE190280-M-001 | LE190280-M-001-A | IVC | Pre-order comments issued | 233 |  |  |  | 13.09.23 | 13.09.23 | 20.11.23 | 15.12.23 | [19 empty] | 19.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:05:38
Bankura 2B | Mechanical | SLUICE GATE | LE190280-M-001 | LE190280-M-001-B | JASH | Pre-order comments issued | 233 |  |  |  | 13.09.23 | 13.09.23 | 20.11.23 | 15.12.23 | [19 empty] | 19.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:05:38
Bankura 2B | Mechanical | SLUICE GATE | LE190280-M-001 | LE190280-M-001-C | ORIENTAL CASTING | Pre-order comments issued | 233 |  |  |  | 13.09.23 | 13.09.23 | 20.11.23 | 15.12.23 | [19 empty] | 19.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:05:38
Bankura 2B | Mechanical | VALVES | LE190280-M-002 | LE190280-M-002-A | AVK | Approved by Client | PR Closed |  |  |  | 13.09.23 | 11.03.24 | 04.04.24 | 09.04.24 | 12.04.24 | 14.04.24 | [6 empty] | 15.04.24 | 15.04.24 | 17.04.24 | T1 | 29.04.24 | AVK | 30.04.24 | 02.05.24 | 03.05.24 | 06.05.24 | 24.06.24 | 17.04.24 | 04.05.24 | 28.06.24 | gopal.samarth@lntecc.com-10.07.2024-15:05:38
Bankura 2B | Mechanical | VALVES | LE190280-M-002 | LE190280-M-002-B | KBL | Sent to BU Operations | PR Closed |  |  |  | 13.09.23 | 13.09.23 | 13.10.23 | 15.12.23 | 12.04.24 | 14.04.24 | [6 empty] | 15.04.24 | 15.04.24 | 17.04.24 | T1 | [7 empty] | 17.04.24 | 04.05.24 | 03.07.24 | gopal.samarth@lntecc.com-05.07.2024-16:27:14
Bankura 2B | Mechanical | VALVES | LE190280-M-002 | LE190280-M-002-C | VAG | Sent to BU Operations | PR Closed |  |  |  | 13.09.23 | 13.09.23 | 13.10.23 | 15.12.23 | 12.04.24 | 14.04.24 | [6 empty] | 15.04.24 | 15.04.24 | 17.04.24 | T1 | [7 empty] | 17.04.24 | 04.05.24 | 03.07.24 | gopal.samarth@lntecc.com-05.07.2024-16:27:14
Bankura 2B | Mechanical | HSC-pump | LE190280-M-003 | LE190280-M-003-A | WILO | Approved by Client | PR Closed |  |  |  |  | 04.10.23 | 17.10.23 | 21.10.23 | 23.10.23 | 24.10.23 | [6 empty] | 26.10.23 | 01.11.23 | 01.11.23 | T1 | 15.11.23 | WILO | 17.11.23 | 17.11.23 | 20.11.23 | 20.11.23 | 20.12.23 | 17.04.24 | 04.05.24 | 14.01.24 | gopal.samarth@lntecc.com-05.07.2024-16:27:14
Bankura 2B | Mechanical | EOT-crane | LE190280-M-004 | LE190280-M-004-A | Hercules hoists limited | Post-order technically cleared | 88 |  |  |  |  | 01.02.24 | 01.03.24 | 04.03.24 | 07.03.24 | 12.03.24 | [6 empty] | 25.03.24 | 26.03.24 | 01.04.24 | T1 | 22.04.24 | Hercules hoists limited | 26.04.24 | 30.04.24 | 02.05.24 | 08.05.24 |  | 17.04.24 | 04.05.24 | 21.06.24 | gopal.samarth@lntecc.com-10.07.2024-14:12:55
Bankura 2B | Mechanical | EOT-Crane | LE190280-M-004 | LE190280-M-004-B | REVA | Sent to BU Operations | PR Closed |  |  |  |  | 01.02.24 | 01.03.24 | 04.03.24 | 07.03.24 | 12.03.24 | [6 empty] | 25.03.24 | 26.03.24 | 01.04.24 | T1 | [7 empty] | 17.04.24 | 04.05.24 | 03.07.24 | gopal.samarth@lntecc.com-05.07.2024-16:27:14
Bankura 2B | Mechanical | EOT-Crane | LE190280-M-004 | LE190280-M-004-C | Sureka Teknik | Sent to BU Operations | PR Closed |  |  |  |  | 01.02.24 | 01.03.24 | 04.03.24 | 07.03.24 | 12.03.24 | [6 empty] | 25.03.24 | 26.03.24 | 01.04.24 | T1 | [7 empty] | 19.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:05:38
Bankura 2B | Mechanical | Ventilation fans | LE190280-M-005 | LE190280-M-005-A | Bajaj | Enquiry yet to float | NA | [26 empty] | 20.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:05:38
Bankura 2B | Mechanical | Ventilation fans | LE190280-M-005 | LE190280-M-005-B | Havells | Enquiry yet to float | NA | [26 empty] | 20.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:05:38
Bankura 2B | Mechanical | Ventilation fans | LE190280-M-005 | LE190280-M-005-C | EPC | Enquiry yet to float | NA | [26 empty] | 20.07.24 |  |  | gopal.samarth@lntecc.com-10.07.2024-15:05:38
Bankura 2B | Instrumentation | UPS | LE190278-I-001 | LE190278-I-001-B | Liveline | Sent to BU Operations | 56 |  |  |  | 05.01.24 | 05.01.24 | 08.01.24 | 18.01.24 | [8 empty] | 21.01.24 | 31.01.24 | 09.06.24 | T1 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Epabx systen | LE190280-I-002 | LE190280-I-00-A2 | Telso network | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:36:56
Bankura 2B | Instrumentation | Epabx systen | LE190280-I-002 | LE190280-I-00-A3 | Int tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:36:56
Bankura 2B | Instrumentation | UPS | LE190280-I-001 | LE190280-I-001-A | Hitachi Hirel | Sent to BU Operations | 56 |  |  |  | 05.01.24 | 05.01.24 | 08.01.24 | 18.01.24 | [8 empty] | 25.01.24 | 31.01.24 | 09.06.24 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | PA systen | LE190280-I-003 | LE190280-I-003-A | Telso network | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:36:56
Bankura 2B | Instrumentation | PA systen | LE190280-I-003 | LE190280-I-003-B | Int tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:36:56
Bankura 2B | Instrumentation | CCTV systen | LE190280-I-004 | LE190280-I-004-A | Telso network | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:36:56
Bankura 2B | Instrumentation | CCTV systen | LE190280-I-004 | LE190280-I-004-B | Int tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:36:56
Bankura 2B | Instrumentation | Battery operated Electro Magnetic Flow meter | LE190280-I-WS-PR-BP-5509 | LE190280-I-WS-PR-BP-5509-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Instrumentation Cables | LE190280-I-WS-PR-BP-5515 | LE190280-I-WS-PR-BP-5515-A | KEI | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | KEI | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | AC operated Electro Magnetic Flow meter | LE190280-I-WS-PR-EF-5508 | LE190280-I-WS-PR-EF-5508-A | Adept | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Adept | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Float & Dial Type Level indicator | LE190280-I-WS-PR-LI-5506 | LE190280-I-WS-PR-LI-5506-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Conductivity Type Level Swtch | LE190280-I-WS-PR-LS-5507 | LE190280-I-WS-PR-LS-5507-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Radar Type Level Transmitter | LE190280-I-WS-PR-LT-5504 | LE190280-I-WS-PR-LT-5504-A | siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Ultrasonic Type Level Transmitter | LE190280-I-WS-PR-LT-5505 | LE190280-I-WS-PR-LT-5505-A | siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Pressure Gauge/Compound Pressure Gauge | LE190280-I-WS-PR-PG-5501 | LE190280-I-WS-PR-PG-5501-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | AN Instruments | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Ph Analyzer | LE190280-I-WS-PR-PH-5510 | LE190280-I-WS-PR-PH-5510-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | PLC\SCADA | LE190280-I-WS-PR-PL-5513 | LE190280-I-WS-PR-PL-5513-A | Autosys | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Autosys | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Pressure Switch | LE190280-I-WS-PR-PS-5502 | LE190280-I-WS-PR-PS-5502-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | AN Instruments | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Pressure Transmitter | LE190280-I-WS-PR-PT-5503 | LE190280-I-WS-PR-PT-5503-A | siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Residual Chlroine Analyzer | LE190280-I-WS-PR-RC-5511 | LE190280-I-WS-PR-RC-5511-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Instrumentation | Turbidity Analyzer | LE190280-I-WS-PR-TU-5512 | LE190280-I-WS-PR-TU-5512-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 10.10.23 | 27.10.23 | 09.12.23 | SURENDHAR@lntecc.com-09.07.2024-17:30:04
Bankura 2B | Electrical | Cable trays | LE-190280-E-WS-WT-PR-4107 | LE-190280-E-WS-WT-PR-4107-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | Lighting fixtures | LE-190280-E-WS-WT-PR-4108 | LE-190280-E-WS-WT-PR-4108-A | Not yet decided | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | Cable glands and lugs | LE-190280-E-WS-WT-PR-4112 | LE-190280-E-WS-WT-PR-4112-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | Lighting pole and junction box | LE-190280-E-WS-WT-PR-4114 | LE-190280-E-WS-WT-PR-4114-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | Battery & Charger | LE-190280-E-WS-WT-PR-4119 | LE-190280-E-WS-WT-PR-4119-A | Liveline | Post-order technically cleared | 127 |  |  |  |  | 20.02.23 | 16.10.23 | 04.11.23 | 06.11.23 | 15.11.23 | [6 empty] | 15.12.23 | 15.12.23 | 15.12.23 | T1 | 18.12.23 | Liveline | 14.03.24 | 14.03.24 | 30.03.24 | 30.03.24 |  |  |  | 16.02.24 | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:40
Bankura 2B | Electrical | LT panels | LE190280-E-001 | LE190280-E-001-A | EAP | Post-order technically cleared | 122 |  |  |  | 26.9.22 | 26.09.22 | 21.04.23 | 26.04.23 | [8 empty] | 16.06.23 | 16.06.23 | 16.06.23 | T1 | 31.10.23 | EAP | 02.04.24 | 03.04.24 | 04.04.24 | 04.04.24 |  |  |  | 30.12.23 | rawabi.c@lntecc.com-22.07.2024-17:33:41
Bankura 2B | Electrical | LT Panel | LE190280-E-001 | LE190280-E-001-B | BCH | Sent to BU Operations | PR Closed |  |  |  | 11.3.20 | 11.03.20 | 16.12.23 | 16.12.23 | [8 empty] | 16.12.23 | 02.01.24 | 02.01.24 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | Transformer | LE190280-E-002 | LE190280-E-002-A | Essenar | Sent to BU Operations | PR Closed |  |  |  | 12.2.20 | 12.02.20 | 14.12.23 | 22.12.23 | [8 empty] | 14.12.23 | 22.12.23 | 22.12.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | Transformer | LE190280-E-002 | LE190280-E-002-B | Kirloskar | Post-order technically cleared | 106 |  |  |  | 12.2.20 | 12.02.20 | 19.12.23 | 22.12.23 | [8 empty] | 01.02.24 | 01.02.24 | 01.02.24 | T2 | 21.02.24 | Kirloskar | 16.4.24 | 20.4.24 | 16.4.24 | 20.4.24 |  |  |  | 21.04.24 | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:40
Bankura 2B | Electrical | Transformer | LE190280-E-002 | LE190280-E-002-C | Voltamp | Sent to BU Operations | PR Closed |  |  |  | 12.2.20 | 12.02.20 | 21.12.23 | 22.01.24 | [8 empty] | 02.02.24 | 02.02.24 | 02.02.24 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | Transformer | LE190280-E-002 | LE190280-E-002-D | Sai electrical | Sent to BU Operations | PR Closed |  |  |  | 12.2.20 | 12.02.20 | 21.02.24 | 21.02.24 | [8 empty] | 21.02.24 | 21.02.24 | 22.2.24 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | AVR | LE190280-E-WS-CE-PR-4104 | LE190280-E-WS-CE-PR-4104-A | ICON | Post-order comments issued | 65 |  |  |  | 7.12.22 | 07.12.22 | 17.01.24 | 07.02.24 | 14.02.24 | 19.02.24 | [6 empty] | 29.02.24 | 29.02.24 | 29.2.24 | T2 | 15.5.24 | ICON | 16.5.24 | 31.5.24 | [5 empty] | 14.07.24 | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:40
Bankura 2B | Electrical | AVR | LE190280-E-WS-CE-PR-4104 | LE190280-E-WS-CE-PR-4104-B | Reliable | Sent to BU Operations | PR Closed |  |  |  | 7.12.22 | 07.12.22 | 05.02.24 | 06.02.24 | [8 empty] | 6.2.24 | 6.2.24 | 6.2.24 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:40
Bankura 2B | Electrical | Earthing & Lightning | LE190280-E-WS-WT-PR-4109 | LE190280-E-WS-WT-PR-4109-A | Not yet decided | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | Electrical safety items | LE190280-E-WS-WT-PR-4110 | LE190280-E-WS-WT-PR-4110-A | Not yet decided | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | LPBS | LE190280-E-WS-WT-PR-4111 | LE190280-E-WS-WT-PR-4111-A | SRCS | Pre-order comments issued | 86 |  |  |  |  | 10.4.24 | 23.4.24 | 24.4.24 | 3.5.24 | 6.5.24 | 6.5.24 | 10.5.24 | [18 empty] | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:40
Bankura 2B | Electrical | LPBS | LE190280-E-WS-WT-PR-4111 | LE190280-E-WS-WT-PR-4111-B | EAP | Pre-order comments issued | 86 |  |  |  |  | 10.4.24 | 30.4.24 | 2.5.24 | 3.5.24 | 7.5.24 | 7.5.24 | 10.5.24 | [18 empty] | karthik.ajithkumar@lntecc.com-05.06.2024-15:55:40
Bankura 2B | Electrical | HT Panel | LE190280-E-WS-WT-PR-4116 | LE190280-E-WS-WT-PR-4116-A | ABB | Approved by Client | PR Closed |  |  |  | 8.6.22 | 08.06.22 | 05.07.22 | 06.07.22 | 11.07.22 | 13.07.22 | [6 empty] | 08.08.22 | 08.08.22 | 08.08.22 | T1 | 13.07.23 | ABB | 21.12.23 | 21.12.23 | 21.12.23 | 28.12.23 | 28.12.23 |  |  | 11.09.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:55:33
Bankura 2B | Electrical | LT Panel | LE190280-E-WS-WT-PR-4150 | LE190280-E-WS-WT-PR-4150-C | PCE | Sent to BU Operations | 608 |  |  |  | 26.9.22 | 26.09.22 | 29.10.22 | 02.11.22 | [8 empty] | 05.12.22 | 05.12.22 | 05.12.22 | T2 | [10 empty] | rawabi.c@lntecc.com-22.07.2024-17:33:41
Bankura 2B | Electrical | LT Panel | LE190280-E-WS-WT-PR-4150 | LE190280-E-WS-WT-PR-4150-D | Prayaas | Sent to BU Operations | 597 |  |  |  | 26.9.22 | 26.09.22 | 29.10.22 | 02.11.22 | [8 empty] | 16.12.22 | 16.12.22 | 16.12.22 | T2 | [10 empty] | rawabi.c@lntecc.com-22.07.2024-17:33:41
Bankura 3 | Process | Inclined plate settler & flocculator paddles | LE190276-P-001 | LE190276-P-001-A | Filsep | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 24.02.21 | 24.02.21 | [8 empty] | 24.02.21 | 24.02.21 | 24.02.21 | T3 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Inclined plate settler & flocculator paddles | LE190276-P-001 | LE190276-P-001-B | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 18.05.21 | 25.05.21 | [8 empty] | 25.05.21 | 25.05.21 | 25.05.21 | T2 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Inclined plate settler & flocculator paddles | LE190276-P-001 | LE190276-P-001-C | SRI TECH | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 22.02.21 | 22.02.21 | [8 empty] | 22.02.21 | 22.02.21 | 27.12.21 | T1 | 31.03.22 | SRI TECH | 22.04.22 | 18.05.22 | 18.05.22 | 18.05.22 | 18.05.22 |  |  | 30.05.22 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | HSC Pumps | LE190276-P-002 | LE190276-P-002-A | KSB | Pre-order comments issued | 286 |  |  |  | 10.09.20 | 10.09.20 | 23.10.23 | 23.10.23 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Air Blower | LE190276-P-003 | LE190276-P-003-A | ACME | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 27.03.23 | 04.04.23 | [8 empty] | 25.08.23 | 25.08.23 | 14.09.23 | T1 | [6 empty] | 24.09.23 |  |  |  | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Air Blower | LE190276-P-003 | LE190276-P-003-B | Everest | Approved by Client | PR Closed |  | 9582649157 | Armoghan.Anwar@irco.com | 10.09.20 | 10.09.20 | 29.04.21 | 15.06.23 | [8 empty] | 19.06.23 | 19.06.23 | 10.08.23 | T1 | 30.11.23 | Everest | 08.02.24 | 12.02.24 | 12.03.24 | 16.04.24 | 17.04.24 |  |  | 29.01.24 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Air Blower | LE190276-P-003 | LE190276-P-003-C | Swam | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 27.03.23 | 01.05.21 | [8 empty] | 20.07.21 | 20.07.21 | 09.08.21 | T2 | [6 empty] | 19.08.21 |  |  |  | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Air Blower | LE190276-P-003 | LE190276-P-003-D | Aivac | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 02.06.23 | 02.06.23 | [8 empty] | 02.06.23 | 02.06.23 | 06.06.23 | T3 | [6 empty] | 02.07.23 |  |  |  | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | WTP Sluice gates | LE190276-P-004 | LE190276-P-004-A | Jash | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 10.10.20 | 12.10.20 | [8 empty] | 25.04.21 | 30.09.21 | 19.11.21 | T1 | 23.11.21 | Jash | 06.12.21 | 06.12.21 | 10.12.21 | 05.01.22 | 05.01.22 |  |  | 22.01.22 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | WTP Sluice gates | LE190276-P-004 | LE190276-P-004-B | Oriental | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 21.05.21 | 24.05.21 | [8 empty] | 10.06.21 | 22.06.21 | 22.06.21 | T2 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Agitator | LE190276-P-005 | LE190276-P-005-A | Triveni | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 27.05.21 | 26.06.21 | [11 empty] | T3 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Agitator | LE190276-P-005 | LE190276-P-005-B | Sritech | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 25.04.23 | 03.05.23 | [8 empty] | 03.05.23 | 03.05.23 | 03.05.23 | T2 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Agitator | LE190276-P-005 | LE190276-P-005-C | Shivpad | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 22.05.23 | 23.05.23 | [8 empty] | 23.05.23 | 23.05.23 | 03.10.23 | T1 | 08.10.23 | Shivpad | 01.11.23 | 09.11.23 | 23.11.23 | 21.12.23 | 21.12.23 |  |  | 07.12.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Dosing pump | LE190276-P-006 | LE190276-P-006-A | Positive Metering | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 06.06.23 | 07.06.23 | [8 empty] | 10.07.23 | 24.07.23 | 10.09.23 | t1 | 10.10.23 | Positive Metering | 31.10.23 | 07.11.23 | 07.11.23 | 22.12.23 | 22.12.23 |  |  | 09.12.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Dosing pump | LE190276-P-006 | LE190276-P-006-B | Verito | Pre-order technically rejected | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 24.03.23 | 07.04.23 | [22 empty] | premkumar.nagarajan@lntecc.com-30.05.2024-12:16:55
Bankura 3 | Process | Dosing pump | LE190276-P-006 | LE190276-P-006-C | Swelore | Pre-order technically rejected | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 07.08.23 | 08.08.23 | [22 empty] | premkumar.nagarajan@lntecc.com-30.05.2024-12:16:55
Bankura 3 | Process | Electrical hoist | LE190276-P-007 | LE190276-P-007-A | Indef | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 06.02.23 | 20.02.23 | [8 empty] | 20.02.23 | 20.02.23 | 20.02.23 | T2 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Electrical hoist | LE190276-P-007 | LE190276-P-007-B | Reva | Approved by Client | PR Closed | Cleared By Mechanical team |  |  | 10.09.20 | 10.09.20 | 16.05.23 | 19.05.23 | [8 empty] | 19.05.23 | 19.05.23 | 19.05.23 | T1 | 19.05.23 | Reva | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 | 05.06.23 | 18.07.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Electrical hoist | LE190276-P-007 | LE190276-P-007-C | Japs | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 09.05.23 | 11.05.23 | [8 empty] | 15.05.23 | 16.05.23 | 16.05.23 | T2 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Manual chain pulley block | LE190276-P-008 | LE190276-P-008-A | Indef | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 06.02.23 | 20.02.23 | [8 empty] | 20.02.23 | 20.02.23 | 20.02.23 | T3 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Manual chain pulley block | LE190276-P-008 | LE190276-P-008-B | Reva | Approved by Client | PR Closed | Cleared By Mechanical team |  |  | 10.09.20 | 10.09.20 | 16.05.23 | 19.05.23 | [8 empty] | 19.05.23 | 20.02.23 | 20.02.23 | T1 | 20.02.23 | Reva | 20.02.23 | 20.02.23 | 20.02.23 | 20.02.23 | 20.02.23 | 20.02.23 | 09.03.23 | 21.04.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Manual chain pulley block | LE190276-P-008 | LE190276-P-008-C | Japs | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 11.05.23 | 11.05.23 | [8 empty] | 14.05.23 | 19.05.23 | 19.05.23 | T3 | [10 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Filter media | LE190276-P-009 | LE190276-P-009-A | Maa Kalyaneshwari | Approved by Client | PR Closed |  | Manoj K Singh-9832131302 |  | 10.09.20 | 10.09.20 | 29.03.24 | 30.03.24 | [8 empty] | 30.03.24 | 30.03.24 | 30.03.24 | t1 | 30.03.24 | Maa Kalyaneshwari | 29.03.24 | 30.03.24 | 23.04.24 | 24.04.24 | 24.04.24 |  |  | 29.05.24 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Submersible pump | LE190276-P-010 | LE190276-P-010-A | AQUA | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 18.05.23 | 25.05.23 | [8 empty] | 08.06.23 | 24.06.23 | 24.06.23 | t1 | 20.04.24 | AQUA | 08.05.24 | 18.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  |  | 19.06.24 | premkumar.nagarajan@lntecc.com-30.05.2024-12:24:22
Bankura 3 | Process | Submersible pump | LE190276-P-010 | LE190276-P-010-B | MBH | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 24.03.21 | 21.04.23 | [22 empty] | premkumar.nagarajan@lntecc.com-30.05.2024-12:24:22
Bankura 3 | Process | Sludge tranfer pumps | LE190276-P-011 | LE190276-P-011-A | KSB | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 06.10.23 | 13.10.23 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Sludge tranfer pumps | LE190276-P-011 | LE190276-P-011-B | AQUA | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 06.10.23 | 13.10.23 | [8 empty] | 08.06.23 | 24.06.23 | 24.06.23 | t1 | 20.04.24 | AQUA | 08.05.24 | 18.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  |  | 19.06.24 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Chlorination system | LE190276-P-012 | LE190276-P-012-A | Zion | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 02.12.20 | 02.12.20 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Chlorination system | LE190276-P-012 | LE190276-P-012-B | ME Infra | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 18.12.20 | 21.12.20 | [8 empty] | 26.06.21 | 01.07.21 | 29.08.21 | T1 | 01.10.21 | ME Infra | 07.10.21 | 13.10.21 | 13.10.21 | 13.10.21 | 13.10.21 |  |  | 30.11.21 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Chlorination system | LE190276-P-012 | LE190276-P-012-C | IEC Fabchem | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 06.02.21 | 08.02.21 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Chlorination system | LE190276-P-012 | LE190276-P-012-D | Toshcon | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 11.12.20 | 30.12.20 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Trolley | LE190276-P-013 | LE190276-P-013-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 10.09.20 | 10.09.20 | [24 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Submersible mixer | LE190276-P-014 | LE190276-P-014-A | KSB | Pre-order technically cleared | 276 |  |  |  | 10.09.20 | 10.09.20 | 31.10.23 | 02.11.23 | [8 empty] | 02.11.23 | 02.11.23 | [9 empty] | 28.02.24 | 16.03.24 | 15.05.24 | premkumar.nagarajan@lntecc.com-09.07.2024-12:07:12
Bankura 3 | Process | Submersible mixer | LE190276-P-014 | LE190276-P-014-B | Shivpad | Regret offer | PR Closed | No responses from vendor |  |  | 10.09.20 | 10.09.20 | 20.09.23 | 21.09.23 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Submersible mixer | LE190276-P-014 | LE190276-P-014-C | Sulzer World water tech | Pre-order technically cleared | 26 |  | Dawood Badsha 9003031687 | wwtechennai@gmail.com | 10.09.20 | 10.09.20 | 04.07.24 | 06.07.24 | 08.07.24 | 09.07.24 | [6 empty] | 09.07.24 | 09.07.24 | 09.07.24 | [11 empty] | premkumar.nagarajan@lntecc.com-12.07.2024-17:22:20
Bankura 3 | Process | Dewatering pump | LE190276-P-015 | LE190276-P-015-A | AQUA | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 07.11.23 | 17.11.23 | [8 empty] | 17.11.23 | 17.11.23 | 17.11.23 | t1 | 20.04.24 | AQUA | 08.05.24 | 18.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  |  | 19.06.24 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Dewatering pump | LE190276-P-015 | LE190276-P-015-B | Jasco | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 23.08.23 | 28.08.23 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Dewatering pump | LE190276-P-015 | LE190276-P-015-C | KSB | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 02.06.23 | 12.10.23 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Dewatering pump | LE190276-P-015 | LE190276-P-015-D | MBH | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 04.10.21 | 13.10.21 | [8 empty] | 16.10.21 | 20.10.21 | 20.10.21 | t2 | [6 empty] | 12.11.21 |  |  |  | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Unloading pump | LE190276-P-016 | LE190276-P-016-A | MBH | Regret offer | PR Closed | Site Procurement |  |  | 10.09.20 | 10.09.20 | 23.03.23 | 24.04.23 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Sampling pump | LE190276-P-017 | LE190276-P-017-A | KSB | Regret offer | PR Closed | Site Procurement |  |  | 10.09.20 | 10.09.20 | 07.10.23 | 12.10.23 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Sampling pump | LE190276-P-017 | LE190276-P-017-B | MBH | Regret offer | PR Closed | Site Procurement |  |  | 10.09.20 | 10.09.20 | 07.10.23 | 12.10.23 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Exhaust fan | LE190276-P-018 | LE190276-P-018-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 10.09.20 | 10.09.20 | [24 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | lab equipment | LE190276-P-019 | LE190276-P-019-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 10.09.20 | 10.09.20 | [24 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Dissolving Tray | LE190276-P-020 | LE190276-P-020-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 10.09.20 | 10.09.20 | [24 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | PE Tank | LE190276-P-021 | LE190276-P-021-A | FFP Eco | Pre-order comments issued | 38 |  | Namrata S 81049 82550 | fibrein@gmail.com | 10.09.20 | 30.05.24 | 24.06.24 | 27.06.24 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-08.07.2024-12:36:07
Bankura 3 | Process | PE Tank | LE190276-P-021 | LE190276-P-021-B | EPP | Regret offer | PR Closed | SS tank are not manufactured by the vendor | Prasanta 88205 22220 | prasantabose@epp.co.in | 10.09.20 | 30.05.24 | 24.06.24 | 27.06.24 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-08.07.2024-12:36:07
Bankura 3 | Process | Filter Nozzle | LE190276-P-022 | LE190276-P-022-A | GUDDI | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 25.11.22 | 28.11.22 | [8 empty] | 28.11.22 | 08.12.22 | 08.12.22 | T1 | 09.12.22 | GUDDI | 12.12.22 | 15.12.22 | 15.12.22 | 15.12.22 | 15.12.22 |  |  | 07.02.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Filter Nozzle | LE190276-P-022 | LE190276-P-022-B | VP Engineers | Regret offer | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 25.11.22 | 28.11.22 | [22 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Process | Rechlorination system | LE190276-P-023 | LE190276-P-023-A | Supreme | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 07.11.23 | 14.12.23 | [8 empty] | 15.12.23 | 18.12.23 | 18.12.23 | t3 | [10 empty] | premkumar.nagarajan@lntecc.com-30.05.2024-12:18:02
Bankura 3 | Process | Rechlorination system | LE190276-P-023 | LE190276-P-023-B | ME Infra | Sent to BU Operations | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 25.09.23 | 11.10.23 | [8 empty] | 23.10.23 | 26.10.23 | 26.10.23 | t2 | [10 empty] | premkumar.nagarajan@lntecc.com-30.05.2024-12:18:02
Bankura 3 | Process | Rechlorination system | LE190276-P-023 | LE190276-P-023-C | Zion | Approved by Client | PR Closed |  |  |  | 10.09.20 | 10.09.20 | 25.09.23 | 11.10.23 | [8 empty] | 14.10.23 | 26.10.23 | 26.10.23 | t1 | 02.04.24 | Zion | 02.04.24 | 09.04.24 | 11.04.24 | 12.04.24 | 12.04.24 |  |  | 01.06.24 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Mechanical | VT-pumps | LE190276-002 | LE190276-002 | WILO | Approved by Client | PR Closed |  |  |  |  | 08.04.24 | 08.04.24 | 08.04.24 | [8 empty] | 09.04.24 | 09.04.24 | 09.04.24 | T1 | 09.04.24 | WILO | 09.04.24 | 09.04.24 | 09.04.24 | 09.04.24 | 09.04.24 | 10.01.24 | 27.01.24 | 27.03.24 | gopal.samarth@lntecc.com-03.07.2024-17:15:28
Bankura 3 | Mechanical | VALVES | LE190276-M-001 | LE190276-M-001-A | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 02.11.23 | 8.11.23 | 19.12.23 | [8 empty] | 08.01.24 | 08.01.24 | 08.01.24 | T1 | [7 empty] | 08.01.24 | 25.01.24 | 25.03.24 | gopal.samarth@lntecc.com-03.07.2024-17:14:37
Bankura 3 | Mechanical | VALVES | LE190276-M-001 | LE190276-M-001-B | VAG | Sent to BU Operations | PR Closed |  |  |  |  | 02.11.23 | 8.11.23 | 19.12.23 | [8 empty] | 08.01.24 | 08.01.24 | 08.01.24 | T1 | [7 empty] | 08.01.24 | 25.01.24 | 25.03.24 | gopal.samarth@lntecc.com-03.07.2024-17:14:37
Bankura 3 | Mechanical | VALVES | LE190276-M-001 | LE190276-M-001-C | AVK | Approved by Client | PR Closed |  |  |  |  | 02.11.23 | 8.11.23 | 19.12.23 | [8 empty] | 08.01.24 | 08.01.24 | 08.01.24 | T1 | 01.04.24 | AVK | 03.04.24 | 08.04.24 | 08.04.24 | 11.04.24 | 18.04.24 | 08.01.24 | 25.01.24 | 25.03.24 | gopal.samarth@lntecc.com-05.07.2024-14:47:41
Bankura 3 | Mechanical | HSC-pumps | LE190276-M-003 | LE190276-M-003-A | WILO | Approved by Client | PR Closed |  |  |  |  | 08.04.24 | 09.04.24 | 09.04.24 | [8 empty] | 09.04.24 | 09.04.24 | 09.04.24 | T1 | 09.04.24 | WILO | 09.04.24 | 09.04.24 | 09.04.24 | 09.04.24 | 09.04.24 | 09.04.24 | 26.04.24 | 08.06.24 | gopal.samarth@lntecc.com-03.07.2024-14:39:30
Bankura 3 | Mechanical | HSC-pumps-lot-2 | LE190276-M-004 | LE190276-M-004-A | WILO | Approved by Client | PR Closed |  |  |  |  | 08.04.24 | 09.04.24 | 09.04.24 | [8 empty] | 09.04.24 | 09.04.24 | 09.04.24 | T1 | 09.04.24 | WILO | 09.04.24 | 09.04.24 | 09.04.24 | 09.04.24 | 09.04.24 | 09.04.24 | 26.04.24 | 08.06.24 | gopal.samarth@lntecc.com-03.07.2024-14:30:20
Bankura 3 | Mechanical | Sluice gates | LE190276-M-005 | LE190276-M-005-A | JASH | Approved by Client | PR Closed |  |  |  |  | 08.01.24 | 09.01.24 | 10.01.24 | [8 empty] | 11.01.24 | 12.01.24 | 12.01.24 | T1 | 12.01.24 | JASH | 15.01.24 | 15.01.24 | 16.01.24 | 16.01.24 | 17.01.24 | 12.01.24 | 29.01.24 | 12.03.24 | gopal.samarth@lntecc.com-03.07.2024-14:30:20
Bankura 3 | Mechanical | Exhaust fans | LE190276-M-006 | LE190276-M-006-A | CGL | Approved by Client | PR Closed |  |  |  |  | 08.01.24 | 10.01.24 | 10.01.24 | [8 empty] | 15.01.24 | 16.01.24 | 17.01.24 | T1 | 18.01.24 | CGL | 18.01.24 | 19.01.24 | 19.01.24 | 20.01.24 | 23.01.24 | 17.01.24 | 03.02.24 | 18.03.24 | gopal.samarth@lntecc.com-03.07.2024-14:30:20
Bankura 3 | Mechanical | EOT-Crane | LE190276-M-007 | LE190276-M-007-A | REVA | Approved by Client | PR Closed |  |  |  |  | 02.02.24 | 05.02.24 | 08.02.24 | [8 empty] | 12.02.24 | 14.02.24 | 19.02.24 | T1 | 04.03.24 | REVA | 06.03.24 | 07.03.24 | 08.03.24 | 08.03.24 | 13.04.24 | 19.02.24 | 07.03.24 | 03.05.24 | gopal.samarth@lntecc.com-05.07.2024-14:43:54
Bankura 3 | Mechanical | Surge vessel & Equipment | LE190276-M-008 | LE190276-M-008-A | JASH | Post-order technically cleared | 122 |  |  |  |  | 04.12.23 | 19.12.23 | 21.12.23 | [8 empty] | 02.01.24 | 04.01.24 | 04.04.24 | T1 | 05.01.24 | JASH | 08.01.24 | 09.01.24 | 10.01.24 | 10.01.24 |  | 04.04.24 | 21.04.24 | 05.03.24 | gopal.samarth@lntecc.com-05.07.2024-14:50:34
Bankura 3 | Mechanical | Dewatering pumps | LE190276-M-009 | LE190276-M-009-A | Aqua Engineering | Approved by Client | PR Closed |  |  |  |  | 04.03.24 | 06.03.24 | 07.03.24 | [8 empty] | 08.03.24 | 11.03.24 | 12.03.24 | T1 | 12.03.24 | Aqua Engineering | 12.03.24 | 12.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 12.03.24 | 29.03.24 | 11.05.24 | gopal.samarth@lntecc.com-03.07.2024-14:30:20
Bankura 3 | Mechanical | Flow control valve | LE190276-M-010 | LE190276-M-010-A | DURGA | Post-order technically cleared | 32 |  |  |  |  | 02.06.24 | 03.06.24 | 04.06.24 | [8 empty] | 03.06.24 | 03.06.24 | 03.06.24 | T1 | 10.06.24 | DURGA | 27.06.24 | 02.07.24 | 03.07.24 | 03.07.24 |  | 03.06.24 | 20.06.24 | 09.08.24 | gopal.samarth@lntecc.com-05.07.2024-14:50:34
Bankura 3 | Mechanical | Dismantling joint | LE190276-M-011 | LE190276-M-011-A | UMA engineering | Post-order technically cleared | 96 |  |  |  |  | 28.03.24 | 01.04.24 | 02.04.24 | 03.04.24 | 04.04.24 | [6 empty] | 06.04.24 | 08.04.24 | 08.04.24 | T1 | 22.04.24 | UMA engineering | 29.04.24 | 30.04.24 | 30.04.24 | 30.04.24 | 30.04.24 | 08.04.24 | 25.04.24 | 21.06.24 | gopal.samarth@lntecc.com-05.07.2024-14:38:12
Bankura 3 | Instrumentation | UPS | LE190276-I-001 | LE190276-I-001-A | Hitachi Hirel | Sent to BU Operations | 56 |  |  |  | 01.01.24 | 05.01.24 | 08.01.24 | 18.01.24 | [8 empty] | 31.01.24 | 31.01.24 | 09.06.24 | T1 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-09.07.2024-17:31:03
Bankura 3 | Instrumentation | Epabx systen | LE190276-I-002 | LE190276-I-002-A | Telso network | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:37:51
Bankura 3 | Instrumentation | Epabx systen | LE190276-I-002 | LE190276-I-002-B | Int Tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:37:51
Bankura 3 | Instrumentation | PA systen | LE190276-I-003 | LE190276-I-003-A | Telso network | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:37:51
Bankura 3 | Instrumentation | PA systen | LE190276-I-003 | LE190276-I-003-B | Int Tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:37:51
Bankura 3 | Instrumentation | CCTV systen | LE190276-I-004 | LE190276-I-004-A | Telso network | Pre-order pending with EDRC | 13 |  |  | nitanshu@TELSONETWORKS.COM | 7.08.20 | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:37:51
Bankura 3 | Instrumentation | CCTV systen | LE190276-I-004 | LE190276-I-004-B | Int Tech | Pre-order pending with EDRC | 13 |  |  | kl@inttech.in |  | 25.05.24 | 04.07.24 | 06.07.24 | 22.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:37:51
Bankura 3 | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE190276-I-WS-PR-PG-5501 | LE190276-I-WS-PR-PG-5501-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 29.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | AN Instruments | 20.10.23 | 20.10.23 | 20.10.23 | 28.10.23 | 28.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Pressure Switch | LE190276-I-WS-PR-PS-5502 | LE190276-I-WS-PR-PG-5502-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | AN Instruments | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Pressure transmitter | LE190276-I-WS-PR-PT-5503 | LE190276-I-WS-PR-PG-5503-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 29.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | Siemens | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | float & board level gauge | LE190276-I-WS-PR-FB-5504 | LE190276-I-WS-PR-PG-5504-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Siemens | 11.11.23 | 11.11.23 | 11.11.23 | 11.11.23 | 11.11.23 |  |  | 09.12.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Ultrasonic level transmitter | LE190276-I-WS-PR-UL-5505 | LE190276-I-WS-PR-PG-5505-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | Siemens | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Float and Board type level indicator | LE190276-I-WS-PR-LS-5506 | LE190276-I-WS-PR-PG-5506-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 11.11.23 | 11.11.23 | 11.11.23 | 11.11.23 | 11.11.23 |  |  | 09.12.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | level switch - Conductivity type | LE190276-I-WS-PR-FT-5507 | LE190276-I-WS-PR-PG-5507-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | SBEM | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Ultrasonic flow meter (channel) | LE190276-I-WS-PR-LH-5508 | LE190276-I-WS-PR-PG-5508-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | Siemens | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Loss of head transmitter | LE190276-I-WS-PR-RF-5509 | LE190276-I-WS-PR-PG-5509-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | Siemens | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Rate for flow transmitter | LE190276-I-WS-PR-RM-5510 | LE190276-I-WS-PR-PG-5510-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | Siemens | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Rotameter | LE190276-I-WS-PR-RC-5511 | LE190276-I-WS-PR-PG-5511-A | Scientific Device | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | Scientific Device | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | pH Meter | LE190276-I-WS-PR-TM-5512 | LE190276-I-WS-PR-PG-5512-A | ABB | Approved by Client | PR Closed |  |  |  |  | 20.06.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | ABB | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Turbidity meter | LE190276-I-WS-PR-RC-5513 | LE190276-I-WS-PR-PG-5513-A | ABB | Approved by Client | PR Closed |  |  |  |  | 20.06.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | ABB | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | Residual Chlorine Analyzer | LE190276-I-WS-PR-EF-5514 | LE190276-I-WS-PR-PG-5514-A | ABB | Approved by Client | PR Closed |  |  |  |  | 20.06.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | ABB | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | AC operated Electromagnectic flow meter | LE190276-I-WS-PR-PL-5515 | LE190276-I-WS-PR-PG-5515-A | Adept | Approved by Client | PR Closed |  |  |  |  | 29.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Adept | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE190276-I-WS-PR-CB-5516 | LE190276-I-WS-PR-PG-5516-A | SATPL | Approved by Client | PR Closed |  |  |  |  | 29.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SATPL | 13.02.24 | 14.02.24 | 21.02.24 | 21.02.24 | 20.03.24 |  |  | 09.12.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | instrumentation Control & signal Cables | LE190276-I-WS-PR-UP-5517 | LE190276-I-WS-PR-PG-5517-A | KEI | Approved by Client | PR Closed |  |  |  |  | 29.04.22 | 29.04.22 | 29.04.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 29.08.23 | KEI | 29.08.23 | 29.08.23 | 29.08.23 | 29.08.23 | 31.08.23 |  |  | 28.10.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Instrumentation | UPS | LE190278-I-001 | LE190278-I-001-B | Liveline | Sent to BU Operations | 56 |  |  |  | 05.01.24 | 05.01.24 | 08.01.24 | 18.01.24 | [8 empty] | 31.01.24 | 31.01.24 | 09.06.24 | T2 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SURENDHAR@lntecc.com-09.07.2024-17:31:03
Bankura 3 | Electrical | Cable trays | LE-190276-E-WS-WT-PR-4106 | LE-190276-E-WS-WT-PR-4106-A | Manoj Trading | Awaiting pre-offer from vendor | 608 |  |  |  |  | 05.12.22 | [24 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Electrical | Lighting fixtures | LE-190276-E-WS-WT-PR-4107 | LE-190276-E-WS-WT-PR-4107-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Cable lugs and glands | LE-190276-E-WS-WT-PR-4111 | LE-190276-E-WS-WT-PR-4111-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | LDB | LE-190276-E-WS-WT-PR-4112 | LE-190276-E-WS-WT-PR-4112-A | SRCS | Pre-order comments issued | 86 |  |  |  |  | 10.4.24 | 23.4.24 | 23.4.24 | 3.5.24 | 6.5.24 | 6.5.24 | 10.5.24 | [18 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Electrical | LDB | LE-190276-E-WS-WT-PR-4112 | LE-190276-E-WS-WT-PR-4112-B | EAP | Pre-order comments issued | 86 |  |  |  |  | 10.4.24 | 15.4.24 | 20.4.24 | 23.4.24 | 2.5.24 | 3.5.24 | 7.5.24 | 7.5.24 | 10.5.24 | [16 empty] | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Electrical | Lighting poles and junction box | LE-190276-E-WS-WT-PR-4113 | LE-190276-E-WS-WT-PR-4113-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Switchboards | LE-190276-E-WS-WT-PR-4114 | LE-190276-E-WS-WT-PR-4114-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Transformer | LE190276-E-WS-WT-PR-4101 | LE190276-E-WS-WT-PR-4101-A | Voltamp | Approved by Client | PR Closed |  |  |  | 8.2.20 | 08.02.20 | 12.06.23 | 12.06.23 | [8 empty] | 15.06.23 | 15.06.23 | 15.06.23 | T1 | 09.07.23 | Voltamp | 12.07.23 | 12.07.23 | 11.08.23 | 17.10.23 | 17.10.23 |  |  | 07.09.23 | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Transformer | LE190276-E-WS-WT-PR-4101 | LE190276-E-WS-WT-PR-4101-B | AEG | Sent to BU Operations | PR Closed |  |  |  | 7.2.20 | 07.02.20 | 07.12.22 | 07.12.22 | [8 empty] | 02.01.23 | 02.01.23 | 02.01.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Transformer | LE190276-E-WS-WT-PR-4101 | LE190276-E-WS-WT-PR-4101-C | KECL | Sent to BU Operations | PR Closed |  |  |  | 7.2.20 | 07.02.20 | 05.12.22 | 22.12.22 | [8 empty] | 18.01.23 | 27.01.23 | 27.01.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Transformer | LE190276-E-WS-WT-PR-4101 | LE190276-E-WS-WT-PR-4101-D | KOTSONS | Sent to BU Operations | PR Closed |  |  |  | 7.2.20 | 07.02.20 | 07.01.21 | 07.01.21 | [8 empty] | 07.01.21 | 07.01.21 | 07.01.21 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Transformer | LE190276-E-WS-WT-PR-4101 | LE190276-E-WS-WT-PR-4101-E | VOLTECH | Sent to BU Operations | PR Closed |  |  |  | 7.2.20 | 07.02.20 | 07.01.21 | 07.01.21 | [8 empty] | 07.01.21 | 07.01.21 | 07.01.21 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | DG Set | LE190276-E-WS-WT-PR-4103 | LE190276-E-WS-WT-PR-4103-A | Goel | Sent to BU Operations | PR Closed |  |  |  | 7.9.19 | 07.09.19 | 02.03.20 | 05.03.20 | [8 empty] | 25.05.20 | 25.05.20 | 25.05.20 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | DG Set | LE190276-E-WS-WT-PR-4103 | LE190276-E-WS-WT-PR-4103-B | IEC | Approved by Client | PR Closed |  |  |  | 7.9.21 | 15.01.20 | 26.05.20 | 26.05.20 | [8 empty] | 02.06.20 | 02.06.20 | 02.06.20 | T1 | 06.06.20 | IEC | 05.08.20 | 05.08.20 | 07.12.23 | 07.12.23 | 7.12.23 |  |  | 05.08.20 | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | LT Panel | LE190276-E-WS-WT-PR-4104 | LE190276-E-WS-WT-PR-4104-A | PCE | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 26.09.22 | 07.11.22 | 17.12.22 | [8 empty] | 04.01.23 | 01.02.23 | 01.02.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | LT Panel | LE190276-E-WS-WT-PR-4104 | LE190276-E-WS-WT-PR-4104-B | Prayass | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 26.09.22 | 28.11.22 | 17.12.22 | [8 empty] | 03.02.23 | 03.02.23 | 03.02.23 | T1 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | LT Panel | LE190276-E-WS-WT-PR-4104 | LE190276-E-WS-WT-PR-4104-C | EAP | Approved by Client | PR Closed |  |  |  | 26.9.22 | 26.09.22 | 19.12.22 | 20.12.22 | [8 empty] | 31.12.22 | 18.02.23 | 18.02.23 | T1 | 13.03.23 | EAP | 19.05.23 | 01.07.23 | 30.11.23 | 30.11.23 | 30.11.23 |  |  | 12.05.23 | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Cable | LE190276-E-WS-WT-PR-4105 | LE190276-E-WS-WT-PR-4105-A | KEI | Post-order technically cleared | 290 | Compliance given |  |  | 30.11.22 | 30.11.22 | 26.12.22 | 02.01.23 | [8 empty] | 03.01.23 | 03.01.23 | 03.01.23 | T1 | 06.07.23 | KEI | 04.10.23 | 04.10.23 | 04.10.23 | 19.10.23 |  |  |  | 04.09.23 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Electrical | Earthing and Lightning | LE190276-E-WS-WT-PR-4108 | LE190276-E-WS-WT-PR-4108-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Electrical Safety Items | LE190276-E-WS-WT-PR-4109 | LE190276-E-WS-WT-PR-4109-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | HT Panel | LE190276-E-WS-WT-PR-4115 | LE190276-E-WS-WT-PR-4115-A | Schnider | Sent to BU Operations | PR Closed |  |  |  | 8.6.22 | 08.06.22 | 16.12.22 | 21.12.22 | [8 empty] | 25.01.23 | 08.02.23 | 08.02.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | HT Panel | LE190276-E-WS-WT-PR-4115 | LE190276-E-WS-WT-PR-4115-B | ABB | Approved by Client | PR Closed |  |  |  | 8.6.22 | 08.06.22 | 19.12.22 | 06.02.23 | [8 empty] | 21.02.23 | 23.02.23 | 23.02.23 | T1 | 31.03.23 | ABB | 28.06.23 | 03.11.23 | 06.12.23 | 06.12.23 | 6.12.23 |  |  | 30.05.23 | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | HT Panel | LE190276-E-WS-WT-PR-4115 | LE190276-E-WS-WT-PR-4115-C | Lntebg | Sent to BU Operations | PR Closed |  |  |  | 8.6.22 | 08.06.22 | 12.12.22 | 14.12.22 | [8 empty] | 24.12.22 | 18.02.23 | 18.02.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | BUS DUCT | LE190276-E-WS-WT-PR-4116 | LE190276-E-WS-WT-PR-4116-A | PCE | Sent to BU Operations | PR Closed |  |  |  | 18.11.22 | 18.11.22 | 14.12.22 | 17.02.23 | [8 empty] | 21.02.23 | 21.02.23 | 21.02.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | BUS DUCT | LE190276-E-WS-WT-PR-4116 | LE190276-E-WS-WT-PR-4116-B | Prayaas | Sent to BU Operations | PR Closed |  |  |  | 18.11.22 | 18.11.22 | 17.12.22 | 23.01.23 | [8 empty] | 17.02.23 | 17.02.23 | 17.02.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | BUS DUCT | LE190276-E-WS-WT-PR-4116 | LE190276-E-WS-WT-PR-4116-C | Godrej & Boyce | Sent to BU Operations | PR Closed |  |  |  | 18.11.22 | 18.11.22 | 20.04.23 | 25.04.23 | [8 empty] | 27.04.23 | 27.04.23 | 27.04.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | BUS DUCT | LE190276-E-WS-WT-PR-4116 | LE190276-E-WS-WT-PR-4116-D | C&S | Post-order technically cleared | 90 | Technical clearance given on 4.4.24 Revised as per consultant comments and given technical clearance on 7.5.24 |  |  | 18.11.22 | 18.11.22 | 18.10.23 | 30.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T1 | 08.11.23 | C&S | 09.02.24 | 02.03.24 | 5.4.24 | 6.5.24 |  |  |  | 07.01.24 | karthiga@lntecc.com-03.07.2024-17:06:57
Bankura 3 | Electrical | Battery & Battery Charger | LE190276-E-WS-WT-PR-4118 | LE190276-E-WS-WT-PR-4118-A | Liveline | Approved by Client | PR Closed |  |  |  | 20.2.23 | 20.02.23 | 31.03.23 | 01.04.23 | [8 empty] | 05.05.23 | 05.05.23 | 05.05.23 | T1 | 09.08.23 | Liveline | 16.10.23 | 15.11.23 | 15.11.23 | 24.11.23 | 24.11.23 |  |  | 08.10.23 | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Soft Starter | LE190276-E-WS-WT-PR-4130 | LE190276-E-WS-WT-PR-4130-A | Lecon | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 26.09.22 | 13.03.23 | 18.05.23 | [8 empty] | 30.05.23 | 30.05.23 | 30.05.23 | T2 | [10 empty] | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 3 | Electrical | Soft Starter | LE190276-E-WS-WT-PR-4130 | LE190276-E-WS-WT-PR-4130-B | Jayashree | Approved by Client | PR Closed |  |  |  | 26.9.22 | 26.09.22 | 26.05.23 | 19.06.23 | [8 empty] | 29.06.23 | 29.06.23 | 29.06.23 | T1 | 05.08.23 | Jayashree | 17.08.23 | 11.10.23 | 16.12.23 | 16.12.23 | 16.12.23 |  |  | 04.10.23 | duppalapudi.raviteja@lntecc.com-26.06.2024-18:17:20
Bankura 4 | Instrumentation | UPS | LE190279-I-001 | LE190279-I-001-A | Hitachi Hirel | Sent to BU Operations | 56 |  |  |  | 6.01.24 | 06.01.24 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 09.06.24 | T1 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-17:35:40
Bankura 4 | Instrumentation | Battery operated Electro Magnetic Flow meter | LE190279-I-WS-PR-BP-5508 | LE190279-I-WS-PR-BP-5508-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Instrumentation Cables | LE190279-I-WS-PR-CB-5512 | LE190279-I-WS-PR-CB-5512-A | KEI | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | KEI | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | AC operated Electro Magnetic Flow meter | LE190279-I-WS-PR-EF-5507 | LE190279-I-WS-PR-EF-5507-A | Adept | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Adept | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Float & Dial Type Level indicator | LE190279-I-WS-PR-LI-5505 | LE190279-I-WS-PR-LI-5505-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 30.10.23 | 16.11.23 | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Conductivity Type Level Swtch | LE190279-I-WS-PR-LS-5506 | LE190279-I-WS-PR-LS-5506-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | SBEM | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 | 30.10.23 | 16.11.23 | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Radar Type Level Transmitter | LE190279-I-WS-PR-LT-5503 | LE190279-I-WS-PR-LT-5503-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Ultrasonic Type Level Transmitter | LE190279-I-WS-PR-LT-5504 | LE190279-I-WS-PR-LT-5504-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Pressure Gauge/Compound Pressure Gauge | LE190279-I-WS-PR-PG-5501 | LE190279-I-WS-PR-PG-5501-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | AN Instruments | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Ph Analyzer | LE190279-I-WS-PR-PH-5509 | LE190279-I-WS-PR-PH-5509-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Pressure Transmitter | LE190279-I-WS-PR-PT-5502 | LE190279-I-WS-PR-PT-5502-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | Siemens | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Residual Chlroine Analyzer | LE190279-I-WS-PR-RC-5510 | LE190279-I-WS-PR-RC-5510-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Instrumentation | Turbidity Analyzer | LE190279-I-WS-PR-TU-5511 | LE190279-I-WS-PR-TU-5511-A | ABB | Approved by Client | PR Closed |  |  |  |  | 24.04.22 | 30.04.22 | 05.05.22 | [8 empty] | 31.05.23 | 31.05.23 | 31.05.23 | T1 | 10.10.23 | ABB | 20.10.23 | 20.10.23 | 20.10.23 | 20.10.23 | 30.10.23 |  |  | 09.12.23 | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Electrical | Lighting | LE19027-E-WS-WT-PR-4104 | LE19027-E-WS-WT-PR-4104-A |  | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-01.06.2024-11:51:07
Bankura 4 | Electrical | Earthing and Lightning | LE190279-E-WS-WT-PR-4101 | LE190279-E-WS-WT-PR-4101-A |  | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-01.06.2024-11:51:07
Bargarh | Process | Clariflocculator | LE20M144-P-001 | LE20M144-P-001-A | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 19.07.21 | 19.07.21 | 14.09.22 | 14.09.22 | [8 empty] | 14.09.22 | 14.09.22 | 04.10.22 | T1 | [6 empty] | 14.10.22 | 04.10.22 | 21.10.22 | 20.12.22 | SNEHA-S@lntecc.com-02.07.2024-11:32:03
Bargarh | Process | Clariflocculator | LE20M144-P-001 | LE20M144-P-001-B | Triveni | Sent to BU Operations | PR Closed |  |  |  | 19.07.21 | 19.07.21 | 22.09.22 | 22.09.22 | [8 empty] | 22.09.22 | 22.09.22 | 13.10.22 | T2 | [6 empty] | 22.10.22 | 13.10.22 | 30.10.22 | 29.12.22 | SNEHA-S@lntecc.com-02.07.2024-11:32:03
Bargarh | Process | Clariflocculator | LE20M144-P-001 | LE20M144-P-001-C | Sritech | Approved by Client | PR Closed |  |  |  | 19.07.21 | 19.07.21 | 26.10.22 | 26.10.22 | [8 empty] | 26.10.22 | 26.10.22 | 04.01.23 | T3 | 03.02.23 | Sritech | 15.02.23 | 18.02.23 | 01.03.23 | 09.03.23 | 20.03.23 | 04.01.23 | 21.01.23 | 22.03.23 | SNEHA-S@lntecc.com-02.07.2024-11:32:03
Bargarh | Process | Air blowers | LE20M144-P-002 | LE20M144-P-002-A | Swam | Sent to BU Operations | PR Closed |  |  |  | 19.07.21 | 19.07.21 | 14.09.22 | 20.09.22 | [8 empty] | 23.02.24 | 26.02.24 | 29.02.24 | T1 | [7 empty] | 29.02.24 | 17.03.24 | 16.05.24 | SNEHA-S@lntecc.com-02.07.2024-11:32:03
Bargarh | Process | Air blowers | LE20M144-P-002 | LE20M144-P-002-B | Kay | Post-order technically cleared | 20 |  |  |  | 19.07.21 | 19.07.21 | 09.10.23 | 09.10.23 | [8 empty] | 09.10.23 | 09.10.23 | 29.02.24 | T2 | 16.02.24 | Kay | 05.06.24 | 15.06.24 | 12.07.24 | 15.07.24 |  | 29.02.24 | 17.03.24 | 16.04.24 | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Air blowers | LE20M144-P-002 | LE20M144-P-002-C | ACME | Regret offer | PR Closed | Technically rejected |  |  | 19.07.21 | 19.07.21 | 20.11.23 | 21.11.23 | [22 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Agitators | LE20M144-P-003 | LE20M144-P-003-A | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 7.08.21 | 07.08.21 | 06.09.22 | 06.09.22 | [8 empty] | 06.09.22 | 06.09.22 | 02.10.22 | T1 | [6 empty] | 06.10.22 | 02.10.22 | 19.10.22 | 18.12.22 | SNEHA-S@lntecc.com-02.07.2024-11:32:03
Bargarh | Process | Agitators | LE20M144-P-003 | LE20M144-P-003-B | Triveni | Sent to BU Operations | PR Closed |  |  |  | 7.08.21 | 07.08.21 | 15.09.22 | 22.09.22 | [8 empty] | 26.09.22 | 14.10.22 | 17.10.22 | T2 | [6 empty] | 22.10.22 | 17.10.22 | 03.11.22 | 02.01.23 | SNEHA-S@lntecc.com-02.07.2024-11:32:03
Bargarh | Process | Agitators | LE20M144-P-003 | LE20M144-P-003-C | Sritech | Approved by Client | PR Closed |  |  |  | 7.08.21 | 07.08.21 | 16.11.22 | 21.11.22 | [8 empty] | 21.11.22 | 21.11.22 | 02.03.23 | T3 | 18.03.23 | Sritech | 31.03.23 | 01.04.23 | 24.04.23 | 26.04.23 | 01.05.23 | 02.03.23 | 19.03.23 | 17.05.23 | SNEHA-S@lntecc.com-02.07.2024-11:32:03
Bargarh | Process | Sluice gate | LE20M144-P-004 | LE20M144-P-004-A | FCE | Regret offer | PR Closed | Technically rejected |  |  | 31.08.21 | 31.08.21 | 30.08.22 | 19.09.22 | [22 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Sluice gate | LE20M144-P-004 | LE20M144-P-004-B | Jash | Post-order comments issued | 48 | Vendor not responding. |  |  | 31.08.21 | 31.08.21 | 22.11.23 | 24.11.23 | [8 empty] | 09.02.24 | 09.02.24 | 07.03.24 | T2 | 22.04.24 | Jash | 03.06.24 | 17.06.24 |  |  |  | 07.03.24 | 24.03.24 | 23.05.24 | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Sluice gate | LE20M144-P-004 | LE20M144-P-004-C | Oriental | Sent to BU Operations | PR Closed |  |  |  | 31.08.21 | 31.08.21 | 28.07.22 | 01.08.22 | [8 empty] | 01.08.22 | 01.08.22 | 07.03.24 | T1 | [7 empty] | 07.03.24 | 24.03.24 | 23.05.24 | SNEHA-S@lntecc.com-02.07.2024-11:32:04
Bargarh | Process | Chlorination system | LE20M144-P-005 | LE20M144-P-005-A | Zion | Post-order technically cleared | 15 |  |  |  | 7.08.21 | 07.08.21 | 05.09.23 | 05.09.23 | [8 empty] | 05.09.23 | 05.09.23 | 05.09.23 | T1 | 12.06.24 | Zion | 01.07.24 | 02.07.24 | 20.07.24 | 20.07.24 |  | 09.10.23 | 26.10.23 | 25.12.23 | SNEHA-S@lntecc.com-22.07.2024-14:22:02
Bargarh | Process | Chlorination system | LE20M144-P-005 | LE20M144-P-005-B | IEC | Sent to BU Operations | PR Closed |  |  |  | 7.08.21 | 07.08.21 | 07.10.23 | 09.10.23 | [8 empty] | 09.10.23 | 09.10.23 | 09.10.23 | T3 | [7 empty] | 09.10.23 | 26.10.23 | 25.12.23 | SNEHA-S@lntecc.com-02.07.2024-18:48:27
Bargarh | Process | Chlorination system | LE20M144-P-005 | LE20M144-P-005-C | Chlorotech | Sent to BU Operations | PR Closed |  |  |  | 7.08.21 | 07.08.21 | 03.10.23 | 03.10.23 | [8 empty] | 03.10.23 | 03.10.23 | 03.10.23 | T3 | [7 empty] | 09.10.23 | 26.10.23 | 25.12.23 | SNEHA-S@lntecc.com-02.07.2024-18:48:27
Bargarh | Process | Sludge thickener | LE20M144-P-006 | LE20M144-P-006-A | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 10.07.22 | 02.08.22 | [8 empty] | 02.08.22 | 02.08.22 | 19.08.22 | T1 | [6 empty] | 01.09.22 | 19.08.22 | 05.09.22 | 04.11.22 | SNEHA-S@lntecc.com-02.07.2024-11:32:04
Bargarh | Process | Sludge thickener | LE20M144-P-006 | LE20M144-P-006-B | Triveni | Sent to BU Operations | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 04.11.22 | 09.11.22 | [8 empty] | 09.11.22 | 09.11.22 | 07.12.22 | T2 | [6 empty] | 09.12.22 | 07.12.22 | 24.12.22 | 22.02.23 | SNEHA-S@lntecc.com-02.07.2024-11:32:04
Bargarh | Process | Sludge thickener | LE20M144-P-006 | LE20M144-P-006-C | Sritech | Approved by Client | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 26.10.22 | 26.10.22 | [8 empty] | 26.10.22 | 26.10.22 | 19.02.23 | T3 | 23.02.23 | Sritech | 14.03.23 | 16.03.23 | 16.03.23 | 05.04.23 | 15.04.23 | 19.02.23 | 08.03.23 | 24.04.23 | SNEHA-S@lntecc.com-02.07.2024-11:32:04
Bargarh | Process | Filter media | LE20M144-P-007 | LE20M144-P-007-A | Maa Kalyaneshwari | Awaiting post-offer from vendor | 1082 | Cluster SCM released PO |  |  | 19.07.21 | 19.07.21 | 02.08.21 | 11.08.21 | [8 empty] | 17.08.21 | 17.08.21 | 17.08.21 | T1 | 17.08.21 | Maa Kalyaneshwari |  |  |  |  | 18.08.21 |  |  | 16.10.21 | SNEHA-S@lntecc.com-16.07.2024-12:53:19
Bargarh | Process | Centrifuge | LE20M144-P-008 | LE20M144-P-008-A | Hiller | Post-order technically cleared | 40 |  |  |  | 08.02.24 | 08.02.24 | 10.02.24 | 12.02.24 | [8 empty] | 26.02.24 | 02.03.24 | 04.03.24 | T1 | 22.04.24 | Hiller | 24.05.24 | 28.05.24 | 25.06.24 | 25.06.24 |  | 04.03.24 | 21.03.24 | 20.05.24 | SNEHA-S@lntecc.com-16.07.2024-12:53:19
Bargarh | Process | Centrifuge | LE20M144-P-008 | LE20M144-P-008-B | Humbolt | Sent to BU Operations | PR Closed |  |  |  | 08.02.24 | 08.02.24 | 09.02.24 | 13.02.24 | [8 empty] | 17.02.24 | 21.02.24 | 27.02.24 | T2 | [7 empty] | 27.02.24 | 15.03.24 | 14.05.24 | SNEHA-S@lntecc.com-02.07.2024-11:32:04
Bargarh | Process | Centrifuge | LE20M144-P-008 | LE20M144-P-008-C | Alfa | Regret offer | PR Closed |  |  |  | 08.02.24 | 08.02.24 | 19.02.24 | 26.02.24 | [8 empty] | 26.02.24 | 26.02.24 | [12 empty] | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Centrifuge | LE20M144-P-008 | LE20M144-P-008-D | GEA | Regret offer | PR Closed |  |  |  | 08.02.24 | 08.02.24 | 15.02.24 | 17.02.24 | [8 empty] | 26.02.24 | 26.02.24 | [12 empty] | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | screw pump | LE20M144-P-009 | LE20M144-P-009-A | Tap Engineering | Regret offer | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 24.01.24 | 30.01.24 | [8 empty] | 04.02.24 | 12.03.24 | 13.03.24 | T2 | 23.05.24 | Tap Engineering | 18.06.24 | 25.06.24 | 01.07.24 |  |  | 31.07.24 | 17.08.24 | 22.07.24 | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | screw pump | LE20M144-P-009 | LE20M144-P-009-B | Flosys | Sent to BU Operations | 26 |  |  |  | 23.07.21 | 23.07.21 | 06.07.24 | 08.07.24 | [8 empty] | 08.07.24 | 09.07.24 | 09.07.24 | T1 | [10 empty] | SNEHA-S@lntecc.com-16.07.2024-12:53:19
Bargarh | Process | Backwash Reservoir pump | LE20M144-P-010 | LE20M144-P-010-A | Wilo | Post-order technically cleared | 37 |  |  |  | 08.02.24 | 08.02.24 | 09.04.24 | 09.04.24 | 11.04.24 | 11.04.24 | [6 empty] | 20.04.24 | 20.04.24 | 20.04.24 | T2 | 30.05.24 | Wilo | 18.06.24 | 25.06.24 | 25.06.24 | 28.06.24 |  | 20.04.24 | 07.05.24 | 06.07.24 | SNEHA-S@lntecc.com-16.07.2024-12:53:19
Bargarh | Process | Backwash Reservoir pump | LE20M144-P-010 | LE20M144-P-010-B | WPIL | Regret offer | PR Closed |  |  |  | 08.02.24 | 08.02.24 | 11.03.24 | 18.03.24 | [22 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Backwash Reservoir pump | LE20M144-P-010 | LE20M144-P-010-C | Xylem | Pre-order technically rejected | PR Closed |  |  |  | 08.02.24 | 08.02.24 | 10.02.24 | 15.02.24 | [8 empty] | 15.02.24 | [13 empty] | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Backwash Reservoir pump | LE20M144-P-010 | LE20M144-P-010-D | Kirloskar | Sent to BU Operations | PR Closed |  |  |  | 13.02.24 | 13.02.24 | 12.03.24 | 18.03.24 | [8 empty] | 06.04.24 | 06.04.24 | 20.04.24 | T1 | [10 empty] | SNEHA-S@lntecc.com-25.06.2024-12:55:27
Bargarh | Process | Submersible pump | LE20M144-P-011 | LE20M144-P-011-A | MBH Pump | Approved by Client | PR Closed |  |  |  | 08.02.24 | 08.02.24 | 09.02.24 | 12.02.24 | [8 empty] | 14.02.24 | 23.02.24 | 26.02.24 | T1 | 23.05.24 | MBH Pump | 18.06.24 | 20.06.24 | 24.06.24 | 24.06.24 | 01.07.24 | 26.02.24 | 14.03.24 | 13.05.24 | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Submersible pump | LE20M144-P-011 | LE20M144-P-011-B | Kishor Pump | Regret offer | PR Closed | No response from vendor |  |  | 13.02.24 | 13.02.24 | [24 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Submersible pump | LE20M144-P-011 | LE20M144-P-011-C | Aqua Pump | Pre-order technically rejected | PR Closed | No response from vendor |  |  | 13.02.24 | 13.02.24 | 27.02.24 | 05.03.24 | [22 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Submersible pump | LE20M144-P-011 | LE20M144-P-011-D | Anala Pump | Pre-order technically rejected | PR Closed |  |  |  | 16.02.24 | 16.02.24 | 11.03.24 | 13.03.24 | [22 empty] | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Electrical hoist | LE20M144-P-012 | LE20M144-P-012-A | W H Brady&co Ltd | Regret offer | PR Closed | No response from vendor |  |  | 09.02.24 | 09.02.24 | [24 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Electrical hoist | LE20M144-P-012 | LE20M144-P-012-B | JAPS | Post-order technically cleared | 45 |  |  |  | 09.02.24 | 09.02.24 | 13.02.24 | 15.02.24 | [8 empty] | 19.02.24 | 01.03.24 | 01.03.24 | T1 | 23.05.24 | JAPS | 14.06.24 | 15.06.24 | 20.06.24 | 20.06.24 |  | 01.03.24 | 18.03.24 | 17.05.24 | SNEHA-S@lntecc.com-16.07.2024-12:53:19
Bargarh | Process | Electrical hoist | LE20M144-P-012 | LE20M144-P-012-C | Indef | Pre-order technically rejected | PR Closed |  |  |  | 14.02.24 | 14.02.24 | 15.03.24 | 20.03.24 | [22 empty] | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Manual chain pulley block | LE20M144-P-013 | LE20M144-P-013-A | W H Brady&co Ltd | Regret offer | PR Closed | No response from vendor |  |  | 09.02.24 | 09.02.24 | [24 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Manual chain pulley block | LE20M144-P-013 | LE20M144-P-013-B | JAPS | Post-order technically cleared | 45 |  |  |  | 09.02.24 | 09.02.24 | 13.02.24 | 15.02.24 | [8 empty] | 19.02.24 | 19.02.24 | 01.03.24 | T1 | 23.05.24 | JAPS | 14.06.24 | 15.06.24 | 20.06.24 | 20.06.24 |  |  |  | 22.07.24 | SNEHA-S@lntecc.com-16.07.2024-12:53:19
Bargarh | Process | Manual chain pulley block | LE20M144-P-013 | LE20M144-P-013-C | Indef | Pre-order technically rejected | PR Closed |  |  |  | 14.02.24 | 14.02.24 | 15.03.24 | 21.03.24 | [22 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Dosing pump | LE20M144-P-014 | LE20M144-P-014-A | SJ Industries | Pre-order technically rejected | PR Closed |  |  |  | 31.08.21 | 31.08.21 | 19.01.24 | 14.02.24 | [8 empty] | 17.02.24 | [13 empty] | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Dosing pump | LE20M144-P-014 | LE20M144-P-014-B | Positive metering Pumps | Post-order technically cleared | 30 |  |  |  | 13.02.24 | 13.02.24 | 19.02.24 | 22.02.24 | [8 empty] | 27.03.24 | 27.03.24 | 28.03.24 | T1 | 17.05.24 | Positive metering Pumps | 13.06.24 | 15.06.24 | 28.06.24 | 05.07.24 |  | 28.03.24 | 14.04.24 | 13.06.24 | SNEHA-S@lntecc.com-16.07.2024-12:56:48
Bargarh | Process | Dosing pump | LE20M144-P-014 | LE20M144-P-014-C | SR Metering | Sent to BU Operations | PR Closed |  |  |  | 13.02.24 | 13.02.24 | 15.02.24 | 17.02.24 | [8 empty] | 27.02.24 | 28.02.24 | 28.03.24 | T2 | [7 empty] | 28.03.24 | 14.04.24 | 13.06.24 | SNEHA-S@lntecc.com-10.07.2024-10:13:50
Bargarh | Process | HDPE tanks | LE20M144-P-015 | LE20M144-P-015-A | FFP | Sent to BU Operations | 123 |  |  |  | 7.08.21 | 07.08.21 | 11.12.23 | 19.12.23 | 21.03.24 | 28.03.24 | 02.04.24 | 02.04.24 |  |  |  |  | 02.04.24 | 03.04.24 | 03.04.24 | T1 | [7 empty] | 03.04.24 | 20.04.24 | 19.06.24 | SNEHA-S@lntecc.com-16.07.2024-12:53:19
Bargarh | Process | DWPE tank Agitators | LE20M144-P-016 | LE20M144-P-016-A | FFP | Sent to BU Operations | 116 | To be floated to FFP. |  |  | 7.08.21 | 07.08.21 | 09.04.24 | 10.04.24 | [8 empty] | 10.04.24 | 10.04.24 | 10.04.24 | T1 | [7 empty] | 10.04.24 | 27.04.24 | 26.06.24 | SNEHA-S@lntecc.com-16.07.2024-12:53:19
Bargarh | Process | Sampling pump | LE20M144-P-017 | LE20M144-P-017-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 31.01.24 | 31.01.24 | [24 empty] | SNEHA-S@lntecc.com-25.06.2024-15:22:47
Bargarh | Process | Submersible mixer | LE20M144-P-018 | LE20M144-P-018-A | World water tech | Pre-order pending with EDRC | 20 | Process cleared. Pending with electrical |  |  | 13.08.21 | 13.08.21 | 11.07.24 | 12.07.24 | 15.07.24 | [7 empty] | 12.07.24 | 15.07.24 | [12 empty] | SNEHA-S@lntecc.com-18.07.2024-17:02:09
Bargarh | Process | Submersible mixer | LE20M144-P-018 | LE20M144-P-018-B | FFP | Pre-order pending with EDRC | 19 | Process cleared. Pending with electrical |  |  | 13.08.21 | 13.08.21 | 15.07.24 | 16.07.24 | 16.07.24 | [7 empty] | 12.07.24 | 15.07.24 | [12 empty] | SNEHA-S@lntecc.com-18.07.2024-17:07:40
Bargarh | Process | Dewatering pump | LE20M144-P-019 | LE20M144-P-019-A | MBH Pump | Approved by Client | PR Closed | File sent to SCM |  |  | 13.02.24 | 13.02.24 | 03.04.24 | 03.04.24 | [8 empty] | 06.04.24 | 06.04.24 | 06.04.24 | T1 | 23.05.24 | MBH Pump | 18.06.24 | 20.06.24 | 24.06.24 | 24.06.24 | 01.07.24 | 06.04.24 | 23.04.24 | 22.06.24 | SNEHA-S@lntecc.com-02.07.2024-18:40:26
Bargarh | Process | Dewatering pump | LE20M144-P-019 | LE20M144-P-019-B | Kishor Pump | Regret offer | PR Closed | No response from vendor |  |  | 13.02.24 | 13.02.24 | [24 empty] | SNEHA-S@lntecc.com-25.06.2024-15:22:47
Bargarh | Process | Dewatering pump | LE20M144-P-019 | LE20M144-P-019-C | Aqua Pump | Pre-order technically rejected | PR Closed | No response from vendor |  |  | 13.02.24 | 13.02.24 | 27.02.24 | 05.03.24 | [22 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Dewatering pump | LE20M144-P-019 | LE20M144-P-019-D | Anala Pump | Pre-order technically rejected | PR Closed | Pump model does not suit L&T requirement. |  |  | 16.02.24 | 16.02.24 | 11.03.24 | [23 empty] | SNEHA-S@lntecc.com-13.06.2024-17:40:54
Bargarh | Process | Dissolving tray | LE20M144-P-020 | LE20M144-P-020-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 31.01.24 | 31.01.24 | [24 empty] | SNEHA-S@lntecc.com-25.06.2024-15:22:47
Bargarh | Process | Trolley | LE20M144-P-021 | LE20M144-P-021-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 31.01.24 | 31.01.24 | [24 empty] | SNEHA-S@lntecc.com-25.06.2024-15:22:47
Bargarh | Process | Platform weighing machine | LE20M144-P-022 | LE20M144-P-022-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 31.01.24 | 31.01.24 | [24 empty] | SNEHA-S@lntecc.com-25.06.2024-15:22:48
Bargarh | Process | Exhaust fan | LE20M144-P-023 | LE20M144-P-023-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 31.01.24 | 31.01.24 | [24 empty] | SNEHA-S@lntecc.com-25.06.2024-15:22:48
Bargarh | Process | lab equipment | LE20M144-P-024 | LE20M144-P-024-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 31.01.24 | 31.01.24 | [24 empty] | SNEHA-S@lntecc.com-25.06.2024-15:22:48
Bargarh | Process | Service water Pump | LE20M144-P-025 | LE20M144-P-025-A | Anala Pumps | Pre-order technically rejected | PR Closed | Model not available |  |  | 13.02.24 | 13.02.24 | 17.02.24 | 27.02.24 | [8 empty] | 04.03.24 | 04.03.24 | [12 empty] | SNEHA-S@lntecc.com-27.05.2024-11:16:41
Bargarh | Process | Service water Pump | LE20M144-P-025 | LE20M144-P-025-B | KSB | Pre-order technically cleared | 39 |  |  |  | 13.02.24 | 13.02.24 | 27.05.24 | 13.06.24 | [8 empty] | 24.06.24 | 24.06.24 | 26.06.24 | T1 | [10 empty] | SNEHA-S@lntecc.com-16.07.2024-12:53:20
Bargarh | Process | Chemical Unloading pumps | LE20M144-P-WS-WT-PR-2128 | LE20M144-P-WS-WT-PR-2128-A | Fabriken | Pre-order technically cleared | 17 |  |  |  |  | 24.06.24 | 02.07.24 | 03.07.24 | [8 empty] | 18.07.24 | 18.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | SNEHA-S@lntecc.com-18.07.2024-16:40:15
Bargarh | Mechanical | EOT crane | LE20M144-M-001 | LE20M144-M-001-A | Reva | Sent to BU Operations | PR Closed |  |  |  | 19.01.23 | 19.01.23 | 16.08.23 | 16.08.23 | [8 empty] | 04.09.23 | 04.09.23 | 15.10.23 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | EOT crane | LE20M144-M-001 | LE20M144-M-001-B | Bradys | Sent to BU Operations | PR Closed |  |  |  | 19.01.23 | 19.01.23 | 16.08.23 | 16.08.23 | [8 empty] | 02.09.23 | 02.09.23 | 15.10.23 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | EOT crane | LE20M144-M-001 | LE20M144-M-001-C | Indef | Post-order technically cleared | 239 |  |  |  | 19.01.23 | 19.01.23 | 28.08.23 | 28.08.23 | [8 empty] | 11.09.23 | 11.09.23 | 15.10.23 | T1 | 05.11.23 | Indef | 05.12.23 | 05.12.23 | 09.12.23 | 09.12.23 |  |  |  | 04.01.24 | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | Sluice Gates | LE20M144-M-002 | LE20M144-M-002-A | Oriental casting | Sent to BU Operations | 110 |  |  |  | 19.01.23 | 19.01.23 | 17.07.23 | 17.07.23 | 16.04.24 | 16.04.24 | [6 empty] | 16.04.24 | 16.04.24 | 16.04.24 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | Sluice Gates | LE20M144-M-002 | LE20M144-M-002-B | Jash | Sent to BU Operations | 139 |  |  |  | 09.02.24 | 09.02.24 | 21.02.24 | 28.02.24 | 13.03.24 | 18.03.24 | [6 empty] | 18.04.24 | 18.03.24 | 18.03.24 | T1 |  | Jash | [8 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | Sluice Gates | LE20M144-M-002 | LE20M144-M-002-C | Fluid Control | Sent to BU Operations | 140 |  |  |  | 09.02.24 | 09.02.24 | 13.02.24 | 04.03.24 | [8 empty] | 04.03.24 | 17.03.24 | 17.03.24 | T1 | [6 empty] | 17.03.24 |  |  |  | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | HSC Pumps | LE20M144-M-003 | LE20M144-M-003-A | Wilo | Sent to BU Operations | 353 |  |  |  | 19.01.23 | 19.01.23 | 31.01.23 | 31.01.23 | [8 empty] | 10.07.23 | 10.07.23 | 29.07.23 | T1 | 29.07.23 | Wilo | 08.08.23 | 08.08.23 | 17.08.23 | 17.08.23 |  |  |  | 27.09.23 | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | HSC Pumps | LE20M144-M-003 | LE20M144-M-003-B | KBL | Sent to BU Operations | 372 |  |  |  | 30.12.23 | 11.05.22 | 30.01.23 | 30.01.23 | [8 empty] | 31.01.23 | 09.02.23 | 29.07.23 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | HSC Pumps | LE20M144-M-003 | LE20M144-M-003-C | KSB | Sent to BU Operations | 372 |  |  |  | 30.12.23 | 11.12.22 | 19.04.23 | 19.04.23 | [8 empty] | 14.05.23 | 18.05.23 | 29.07.23 | T1 |  | KSB | [8 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | HSC Pumps | LE20M144-M-003 | LE20M144-M-003-D | WPIL | Sent to BU Operations | 372 |  |  |  | 30.12.23 | 17.02.23 | 24.04.23 | 24.04.23 | [8 empty] | 15.05.23 | 20.05.23 | 29.07.23 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | Surge Valves | LE20M144-M-004 | LE20M144-M-004-A | JASH | Pre-order comments issued | 320 |  |  |  | 19.01.23 | 19.01.23 | 19.09.23 | 19.09.23 | [22 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | Pump House Valves (intake) | LE20M144-M-005 | LE20M144-M-005-A | Indian Valves | Sent to BU Operations | 283 |  |  |  | 19.01.23 | 19.01.23 | 27.09.23 | 27.09.23 | [8 empty] | 21.10.23 | 26.10.23 | 26.10.23 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | Pump House Valves (intake) | LE20M144-M-005 | LE20M144-M-005-B | AVK | Regret offer | PR Closed | Reply delayed so regret offer |  |  | 19.01.23 | 19.01.23 | 27.09.23 | 27.09.23 | [22 empty] | deepak.sabnani@lntecc.com-01.07.2024-11:38:15
Bargarh | Mechanical | Pump House Valves (intake) | LE20M144-M-005 | LE20M144-M-005-C | Y Cube | Sent to BU Operations | 301 |  |  |  | 19.01.23 | 19.01.23 | 27.09.23 | 27.09.23 | [8 empty] | 30.09.23 | 08.10.23 | 08.10.23 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | Pump House Valves (intake) | LE20M144-M-005 | LE20M144-M-005-D | VAG | Sent to BU Operations | 292 |  |  |  | 19.01.23 | 19.01.23 | 29.09.23 | 29.09.23 | [8 empty] | 05.10.23 | 17.10.23 | 17.10.23 | T1 |  | VAG | [8 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | CWPH and IBPS valves | LE20M144-M-006 | LE20M144-M-006-A | IVC | Sent to BU Operations | 240 |  |  |  | 19.01.23 | 19.01.23 | 27.09.23 | 27.09.23 | [8 empty] | 08.12.23 | 08.12.23 | 08.12.23 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | CWPH and IBPS valves | LE20M144-M-006 | LE20M144-M-006-B | Y CUBE | Sent to BU Operations | 240 |  |  |  | 19.01.23 | 19.01.23 | 27.09.23 | 27.09.23 | [8 empty] | 08.12.23 | 08.12.23 | 08.12.23 | T1 | [10 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | CWPH and IBPS valves | LE20M144-M-006 | LE20M144-M-006-C | VAG | Sent to BU Operations | 240 |  |  |  | 19.01.23 | 19.01.23 | 29.09.23 | 29.09.23 | [8 empty] | 08.12.23 | 08.12.23 | 08.12.23 | T1 |  | VAG | [8 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Mechanical | exhaust fan ( clear water pump house) | LE20M144-M-007 | LE20M144-M-007-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 337 | Site procurement |  |  | 2.09.23 | 02.09.23 | [24 empty] | rallabandi.bharadwaj@lntecc.com-22.07.2024-14:50:07
Bargarh | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M144-I-WS-WT-PR-5101 | LE20M144-I-WS-WT-PR-5101-A | AN instruments | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 31.12.23 | 01.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 07.01.24 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M144-I-WS-WT-PR-5101 | LE20M144-I-WS-WT-PR-5101-B | Hguru South | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 31.12.23 | 01.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 07.01.24 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M144-I-WS-WT-PR-5101 | LE20M144-I-WS-WT-PR-5101-C | Measurecal | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 31.12.23 | 01.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 07.01.24 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M144-I-WS-WT-PR-5101 | LE20M144-I-WS-WT-PR-5101-D | Hguru | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 31.12.23 | 01.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 07.01.24 | T1 | 20.01.24 | H guru Instruments | 22.01.24 | 27.01.24 | 30.01.24 | 01.02.24 | 02.02.24 |  |  | 20.03.24 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Pressure Switch | LE20M144-I-WS-WT-PR-5102 | LE20M144-I-WS-WT-PR-5102-A | AN instruments | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 31.12.23 | 01.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 07.01.24 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Pressure Switch | LE20M144-I-WS-WT-PR-5102 | LE20M144-I-WS-WT-PR-5102-B | Hguru South | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 31.12.23 | 01.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 07.01.24 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Pressure Switch | LE20M144-I-WS-WT-PR-5102 | LE20M144-I-WS-WT-PR-5102-C | Measurecal | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 31.12.23 | 01.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 07.01.24 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Pressure Switch | LE20M144-I-WS-WT-PR-5102 | LE20M144-I-WS-WT-PR-5102-D | H guru Instruments | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 31.12.23 | 01.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 07.01.24 | T1 | 16.01.24 | H guru Instruments | 22.01.24 | 27.01.24 | 31.01.24 | 01.02.24 | 02.02.24 |  |  | 16.03.24 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Pressure transmitter | LE20M144-I-WS-WT-PR-5103 | LE20M144-I-WS-WT-PR-5103-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Pressure transmitter | LE20M144-I-WS-WT-PR-5103 | LE20M144-I-WS-WT-PR-5103-B | E&H | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Pressure transmitter | LE20M144-I-WS-WT-PR-5103 | LE20M144-I-WS-WT-PR-5103-C | Siemens | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T1 | 29.12.22 | Siemens | 09.01.23 | 14.01.23 | 18.01.23 | 19.01.23 | 20.01.23 |  |  | 27.02.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Float & Board Level gauge | LE20M144-I-WS-WT-PR-5104 | LE20M144-I-WS-WT-PR-5104-A | SBEM | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 09.02.23 | 10.02.23 | [8 empty] | 15.02.23 | 15.02.23 | 16.02.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Float & Board Level gauge | LE20M144-I-WS-WT-PR-5104 | LE20M144-I-WS-WT-PR-5104-B | Techtrol | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 09.02.23 | 10.02.23 | [8 empty] | 15.02.23 | 15.02.23 | 16.02.23 | T1 | 19.02.23 | Techtrol | 03.03.23 | 08.03.23 | 08.03.23 | 13.03.23 | 20.03.23 |  |  | 20.04.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | level switch - Conductivity type | LE20M144-I-WS-WT-PR-5105 | LE20M144-I-WS-WT-PR-5105-A | SBEM | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 09.02.23 | 10.02.23 | [8 empty] | 15.02.23 | 15.02.23 | 16.02.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | level switch - Conductivity type | LE20M144-I-WS-WT-PR-5105 | LE20M144-I-WS-WT-PR-5105-B | Pune Techtrol | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 09.02.23 | 10.02.23 | [8 empty] | 15.02.23 | 15.02.23 | 16.02.23 | T1 | 17.02.23 | Pune Techtrol | 03.03.23 | 08.03.23 | 08.03.23 | 13.03.23 | 14.03.23 |  |  | 18.04.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Ultrasonic level Transmitter | LE20M144-I-WS-WT-PR-5106 | LE20M144-I-WS-WT-PR-5106-A | eip enviro | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Ultrasonic level Transmitter | LE20M144-I-WS-WT-PR-5106 | LE20M144-I-WS-WT-PR-5106-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Ultrasonic level Transmitter | LE20M144-I-WS-WT-PR-5106 | LE20M144-I-WS-WT-PR-5106-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Ultrasonic level Transmitter | LE20M144-I-WS-WT-PR-5106 | LE20M144-I-WS-WT-PR-5106-D | siemens | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T1 | 31.12.22 | siemens | 09.01.23 | 14.01.23 | 17.01.23 | 19.01.23 | 20.01.23 |  |  | 01.03.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Radar Level Transmitter | LE20M144-I-WS-WT-PR-5107 | LE20M144-I-WS-WT-PR-5107-A | eip enviro | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Radar Level Transmitter | LE20M144-I-WS-WT-PR-5107 | LE20M144-I-WS-WT-PR-5107-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Radar Level Transmitter | LE20M144-I-WS-WT-PR-5107 | LE20M144-I-WS-WT-PR-5107-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Radar Level Transmitter | LE20M144-I-WS-WT-PR-5107 | LE20M144-I-WS-WT-PR-5107-D | Siemens | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T1 | 30.12.22 | Siemens | 09.01.23 | 14.01.23 | 14.01.23 | 19.01.23 | 20.01.23 |  |  | 28.02.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Loss of head transmitter | LE20M144-I-WS-WT-PR-5108 | LE20M144-I-WS-WT-PR-5108-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Loss of head transmitter | LE20M144-I-WS-WT-PR-5108 | LE20M144-I-WS-WT-PR-5108-B | E&H | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Loss of head transmitter | LE20M144-I-WS-WT-PR-5108 | LE20M144-I-WS-WT-PR-5108-C | Siemens | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T1 | 03.01.23 | Siemens | 09.01.23 | 14.01.23 | 16.01.23 | 19.01.23 | 20.01.23 |  |  | 04.03.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Rate for flow transmitter | LE20M144-I-WS-WT-PR-5109 | LE20M144-I-WS-WT-PR-5109-A | eip enviro | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Rate for flow transmitter | LE20M144-I-WS-WT-PR-5109 | LE20M144-I-WS-WT-PR-5109-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Rate for flow transmitter | LE20M144-I-WS-WT-PR-5109 | LE20M144-I-WS-WT-PR-5109-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Rate for flow transmitter | LE20M144-I-WS-WT-PR-5109 | LE20M144-I-WS-WT-PR-5109-D | Siemens | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T1 | 27.12.22 | Siemens | 09.01.23 | 14.01.23 | 15.01.23 | 19.01.23 | 20.01.23 |  |  | 25.02.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Bypass Rotameter | LE20M144-I-WS-WT-PR-5110 | LE20M144-I-WS-WT-PR-5110-A | Eureka | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 12.10.23 | 13.10.23 | [8 empty] | 18.10.23 | 18.10.23 | 19.10.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Bypass Rotameter | LE20M144-I-WS-WT-PR-5110 | LE20M144-I-WS-WT-PR-5110-B | Scientific devices | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 12.10.23 | 13.10.23 | [8 empty] | 18.10.23 | 18.10.23 | 19.10.23 | T1 | 23.10.23 | Scientific devices | 03.11.23 | 08.11.23 | 12.11.23 | 13.11.23 | 14.11.23 |  |  | 22.12.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Electromagnectic flow meter | LE20M144-I-WS-WT-PR-5111 | LE20M144-I-WS-WT-PR-5111-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.10.22 | 09.10.22 | [8 empty] | 14.10.22 | 14.10.22 | 15.10.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Electromagnectic flow meter | LE20M144-I-WS-WT-PR-5111 | LE20M144-I-WS-WT-PR-5111-B | Khrone | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.10.22 | 09.10.22 | [8 empty] | 14.10.22 | 14.10.22 | 15.10.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Electromagnectic flow meter | LE20M144-I-WS-WT-PR-5111 | LE20M144-I-WS-WT-PR-5111-C | siemens | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.10.22 | 09.10.22 | [8 empty] | 14.10.22 | 14.10.22 | 15.10.22 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Electromagnectic flow meter | LE20M144-I-WS-WT-PR-5111 | LE20M144-I-WS-WT-PR-5111-D | SBEM | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.10.22 | 09.10.22 | [8 empty] | 14.10.22 | 14.10.22 | 15.10.22 | T1 | 28.10.22 | SBEM | 30.10.22 | 04.11.22 | 08.11.22 | 09.11.22 | 10.11.22 |  |  | 27.12.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M144-I-WS-WT-PR-5112 | LE20M144-I-WS-WT-PR-5112-A | Eip enviro | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M144-I-WS-WT-PR-5112 | LE20M144-I-WS-WT-PR-5112-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M144-I-WS-WT-PR-5112 | LE20M144-I-WS-WT-PR-5112-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M144-I-WS-WT-PR-5112 | LE20M144-I-WS-WT-PR-5112-D | Siemens | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.12.22 | 19.12.22 | [8 empty] | 24.12.22 | 24.12.22 | 25.12.22 | T1 | 30.12.22 | Siemens | 09.01.23 | 14.01.23 | 17.01.23 | 19.01.23 | 20.01.23 |  |  | 28.02.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Battery Operated Flow Meter | LE20M144-I-WS-WT-PR-5113 | LE20M144-I-WS-WT-PR-5113-A | Zenner | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 02.11.22 | 03.11.22 | [8 empty] | 08.11.22 | 08.11.22 | 09.11.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Battery Operated Flow Meter | LE20M144-I-WS-WT-PR-5113 | LE20M144-I-WS-WT-PR-5113-B | SBEM | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 02.11.22 | 03.11.22 | [8 empty] | 08.11.22 | 08.11.22 | 09.11.22 | T1 | 19.11.22 | SBEM | 24.11.22 | 29.11.22 | 03.12.22 | 04.12.22 | 05.12.22 |  |  | 18.01.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | pH Meter | LE20M144-I-WS-WT-PR-5114 | LE20M144-I-WS-WT-PR-5114-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | pH Meter | LE20M144-I-WS-WT-PR-5114 | LE20M144-I-WS-WT-PR-5114-B | ABB | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T1 | 01.10.23 | ABB | 10.10.23 | 15.10.23 | 18.10.23 | 20.10.23 | 21.10.23 |  |  | 30.11.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | pH Meter | LE20M144-I-WS-WT-PR-5114 | LE20M144-I-WS-WT-PR-5114-C | Emerson | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | pH Meter | LE20M144-I-WS-WT-PR-5114 | LE20M144-I-WS-WT-PR-5114-D | HACH | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Turbidity meter | LE20M144-I-WS-WT-PR-5115 | LE20M144-I-WS-WT-PR-5115-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Turbidity meter | LE20M144-I-WS-WT-PR-5115 | LE20M144-I-WS-WT-PR-5115-B | ABB | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T1 | 25.09.23 | ABB | 10.10.23 | 15.10.23 | 18.10.23 | 20.10.23 | 21.10.23 |  |  | 24.11.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Turbidity meter | LE20M144-I-WS-WT-PR-5115 | LE20M144-I-WS-WT-PR-5115-C | Emerson | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Turbidity meter | LE20M144-I-WS-WT-PR-5115 | LE20M144-I-WS-WT-PR-5115-D | HACH | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Residual Chlorine Analyzer | LE20M144-I-WS-WT-PR-5116 | LE20M144-I-WS-WT-PR-5116-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Residual Chlorine Analyzer | LE20M144-I-WS-WT-PR-5116 | LE20M144-I-WS-WT-PR-5116-B | ABB | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T1 | 25.09.23 | ABB | 10.10.23 | 15.10.23 | 17.10.23 | 20.10.23 | 21.10.23 |  |  | 24.11.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Residual Chlorine Analyzer | LE20M144-I-WS-WT-PR-5116 | LE20M144-I-WS-WT-PR-5116-C | Emerson | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | Residual Chlorine Analyzer | LE20M144-I-WS-WT-PR-5116 | LE20M144-I-WS-WT-PR-5116-D | HACH | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 18.09.23 | 19.09.23 | [8 empty] | 24.09.23 | 24.09.23 | 25.09.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M144-I-WS-WT-PR-5117 | LE20M144-I-WS-WT-PR-5117-A | Mitsubishi | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.07.23 | 09.07.23 | [8 empty] | 14.07.23 | 14.07.23 | 15.07.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M144-I-WS-WT-PR-5117 | LE20M144-I-WS-WT-PR-5117-B | Autosys | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.07.23 | 09.07.23 | [8 empty] | 14.07.23 | 14.07.23 | 15.07.23 | T1 | 19.07.23 | Autosys | 30.07.23 | 04.08.23 | 07.08.23 | 09.08.23 | 10.08.23 |  |  | 17.09.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M144-I-WS-WT-PR-5117 | LE20M144-I-WS-WT-PR-5117-C | Sai applied | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.07.23 | 09.07.23 | [8 empty] | 14.07.23 | 14.07.23 | 15.07.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M144-I-WS-WT-PR-5117 | LE20M144-I-WS-WT-PR-5117-D | SIAS | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.07.23 | 09.07.23 | [8 empty] | 14.07.23 | 14.07.23 | 15.07.23 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M144-I-WS-WT-PR-5117 | LE20M144-I-WS-WT-PR-5117-E | COTMAC | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 08.07.23 | 09.07.23 | [8 empty] | 14.07.23 | 14.07.23 | 15.07.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | instrumentation Control & signal Cables | LE20M144-I-WS-WT-PR-5118 | LE20M144-I-WS-WT-PR-5118-A | Delton | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 09.07.22 | 10.07.22 | [8 empty] | 15.07.22 | 15.07.22 | 16.07.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | instrumentation Control & signal Cables | LE20M144-I-WS-WT-PR-5118 | LE20M144-I-WS-WT-PR-5118-B | Thermo | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 09.07.22 | 10.07.22 | [8 empty] | 15.07.22 | 15.07.22 | 16.07.22 | T1 | 28.07.22 | Thermo | 31.07.22 | 05.08.22 | 08.08.22 | 10.08.22 | 11.08.22 |  |  | 26.09.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | instrumentation Control & signal Cables | LE20M144-I-WS-WT-PR-5118 | LE20M144-I-WS-WT-PR-5118-C | Axelon | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 09.07.22 | 10.07.22 | [8 empty] | 15.07.22 | 15.07.22 | 16.07.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | instrumentation Control & signal Cables | LE20M144-I-WS-WT-PR-5118 | LE20M144-I-WS-WT-PR-5118-D | Cords | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 09.07.22 | 10.07.22 | [8 empty] | 15.07.22 | 15.07.22 | 16.07.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | UPS | LE20M144-I-WS-WT-PR-5119 | LE20M144-I-WS-WT-PR-5119-A | Vertiv | Sent to BU Operations | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 12.10.23 | 13.10.23 | [8 empty] | 18.10.23 | 18.10.23 | 19.10.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Instrumentation | UPS | LE20M144-I-WS-WT-PR-5119 | LE20M144-I-WS-WT-PR-5119-B | Live Line | Approved by Client | PR Closed |  |  |  | 12.01.22 | 12.01.22 | 12.10.23 | 13.10.23 | [8 empty] | 18.10.23 | 18.10.23 | 19.10.23 | T1 | 30.10.23 | Live Line | 03.11.23 | 08.11.23 | 12.11.23 | 13.11.23 | 14.11.23 |  |  | 29.12.23 | sooryaprakash.t@lntecc.com-03.05.2024-12:13:08
Bargarh | Electrical | CRP panels | LE20M144-E-001 | LE20M144-E-001-A | HT switchgears | Pre-order comments issued | 213 |  |  |  | 3.12.21 | 03.12.21 | 14.11.23 | 04.01.24 | [22 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | Transformer | LE20M144-E-WS-PR-4004 | LE20M144-E-WS-PR-4004-C | TBEA | Approved by Client | PR Closed |  |  |  | 7.9.21 | 07.09.21 | 19.12.22 | 19.12.22 | [8 empty] | 19.12.22 | 19.12.22 | 19.12.22 | T2 | 24.02.23 | TBEA | 28.05.23 | 20.06.23 | 26.06.23 | 26.06.23 | 26.6.23 |  |  | 25.04.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | Transformer | LE20M144-E-WS-WT-PR-4007 | LE20M144-E-WS-WT-PR-4004-A | Voltech | Sent to BU Operations | PR Closed |  |  |  | 7.9.21 | 07.09.21 | 19.12.22 | 28.02.23 | [8 empty] | 28.02.23 | 28.02.23 | 28.02.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | Transformer | LE20M144-E-WS-WT-PR-4004 | LE20M144-E-WS-WT-PR-4004-B | Uttam Bharat | Sent to BU Operations | 527 |  |  |  | 7.9.21 | 07.09.21 | 19.12.22 | 24.02.23 | [8 empty] | 24.02.23 | 24.02.23 | 24.02.23 | T | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | HT Panel | LE20M144-E-WS-WT-PR-4005 | LE20M144-E-WS-WT-PR-4005-A | Popular | Approved by Client | PR Closed |  |  |  | 04.12.21 | 04.12.21 | 28.01.22 | 24.01.23 | [8 empty] | 24.02.23 | 24.02.23 | 24.02.23 | T2 | 25.07.23 | Popular | 25.08.23 | 25.08.23 | 13.09.23 | 13.09.23 | 13.9.23 |  |  | 23.09.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | HT Panel | LE20M144-E-WS-WT-PR-4005 | LE20M144-E-WS-WT-PR-4005-B | HTS | Sent to BU Operations | PR Closed |  |  |  | 04.12.21 | 04.12.21 | 24.02.23 | 16.03.23 | [8 empty] | 16.03.23 | 16.03.23 | 16.03.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | HT Panel | LE20M144-E-WS-WT-PR-4005 | LE20M144-E-WS-WT-PR-4005-C | Universal | Sent to BU Operations | PR Closed |  |  |  | 04.12.21 | 04.12.21 | 02.12.22 | 23.01.23 | [8 empty] | 16.03.23 | 16.03.23 | 16.03.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | DG Set | LE20M144-E-WS-WT-PR-4006 | LE20M144-E-WS-WT-PR-4006-A | Gainwell | Sent to BU Operations | PR Closed |  |  |  | 3.12.21 | 03.12.21 | 19.12.22 | 06.02.23 | [8 empty] | 14.02.23 | 14.02.23 | 14.02.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | DG Set | LE20M144-E-WS-WT-PR-4006 | LE20M144-E-WS-WT-PR-4006-B | Supernova | Sent to BU Operations | PR Closed |  |  |  | 3.12.21 | 03.12.21 | 19.12.22 | 01.02.23 | [8 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | DG Set | LE20M144-E-WS-WT-PR-4006 | LE20M144-E-WS-WT-PR-4006-C | Jackson | Approved by Client | PR Closed |  |  |  | 3.12.21 | 03.12.21 | 06.12.22 | 31.01.23 | [8 empty] | 04.02.23 | 04.02.23 | 04.02.23 | T2 | 25.02.23 | Jackson | 13.10.23 | 16.10.23 | 21.10.23 | 30.10.23 | 30.10.23 |  |  | 26.04.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | DG Set | LE20M144-E-WS-WT-PR-4006 | LE20M144-E-WS-WT-PR-4006-D | Prime Power | Sent to BU Operations | PR Closed |  |  |  | 3.12.21 | 03.12.21 | 08.12.22 | 01.02.23 | [8 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | DG Set | LE20M144-E-WS-WT-PR-4006 | LE20M144-E-WS-WT-PR-4006-E | IEC | Sent to BU Operations | PR Closed |  |  |  | 03.12.21 | 03.12.21 | 11.09.23 | 11.09.23 | [8 empty] | 11.09.23 | 15.09.23 | 15.09.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | LT Panel | LE20M144-E-WS-WT-PR-4007 | LE20M144-E-WS-WT-PR-4007-A | EAP | Sent to BU Operations | PR Closed |  |  |  | 7.7.22 | 07.07.22 | 18.10.22 | 02.02.23 | [8 empty] | 10.03.23 | 10.03.23 | 10.03.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | LT Panel | LE20M144-E-WS-WT-PR-4007 | LE20M144-E-WS-WT-PR-4007-B | SRCS | Approved by Client | PR Closed |  |  |  | 7.7.22 | 07.07.22 | 02.08.22 | 23.01.23 | [8 empty] | 28.02.23 | 28.02.23 | 28.02.23 | T2 | 07.04.23 | SRCS | 07.06.23 | 08.06.23 | 28.06.23 | 28.06.23 | 28.6.23 |  |  | 06.06.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | LT Panel | LE20M144-E-WS-WT-PR-4007 | LE20M144-E-WS-WT-PR-4007-C | Universal | Sent to BU Operations | PR Closed |  |  |  | 7.7.22 | 07.07.22 | 21.07.22 | 21.01.23 | [8 empty] | 29.03.23 | 29.03.23 | 29.03.23 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | LPBS | LE20M144-E-WS-WT-PR-4011 | LE20M144-E-WS-WT-PR-4011-A | SRCS | Post-order comments issued | 250 |  |  |  | 26.7.23 | 26.07.23 | 28.08.23 | 30.08.23 | [8 empty] | 05.09.23 | 05.09.23 | 05.09.23 | T2 | 01.10.23 | SRCS | 28.11.23 | 28.11.23 | [5 empty] | 30.11.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | Lighting Fixtures | LE20M144-E-WS-WT-PR-4013 | LE20M144-E-WS-WT-PR-4013-A | Crompton | Approved by Client | PR Closed |  |  |  | 16.7.22 | 16.07.22 | 18.08.22 | 20.08.22 | [8 empty] | 25.09.22 | 25.09.22 | 25.09.22 | T2 | 26.12.22 | Crompton | 03.04.23 | 07.04.23 | 20.05.23 | 20.05.23 | 20.5.23 |  |  | 24.02.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | HT Cable | LE20M144-E-WS-WT-PR-4016 | LE20M144-E-WS-WT-PR-4016-A | Havells | Approved by Client | PR Closed |  |  |  | 29.7.22 | 29.07.22 | 13.07.23 | 13.07.23 | [8 empty] | 13.07.23 | 13.07.23 | 13.07.23 | T2 | 13.08.23 | Havells | 18.08.23 | 18.08.23 | 18.08.23 | 18.08.23 | 18.8.23 |  |  | 12.10.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | Bus Duct | LE20M144-E-WS-WT-PR-4017 | LE20M144-E-WS-WT-PR-4017-A | Vidyut | Post-order technically cleared | 101 |  |  |  | 25.7.23 | 25.07.23 | 28.08.23 | 29.08.23 | [8 empty] | 01.09.23 | 01.09.23 | 01.09.23 | T1 | 01.01.24 | Vidyut | 11.01.24 | 31.01.24 | 23.4.24 | 25.4.24 |  |  |  | 01.03.24 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Bargarh | Electrical | LT Panel | LE20M144-E-WS-WT-PR-4030 | LE20M144-E-WS-WT-PR-4030-A | Universal | Approved by Client | PR Closed |  |  |  | 7.7.22 | 07.07.22 | 21.07.22 | 21.01.23 | [8 empty] | 29.03.23 | 29.03.23 | 29.03.23 | T2 | 16.04.23 | Universal | 28.09.23 | 09.01.24 | 05.02.24 | 16.02.24 | 23.2.24 |  |  | 15.06.23 | karthik.ajithkumar@lntecc.com-20.05.2024-09:47:23
Belgavi | Process | Flocculator and IPS Mechanism | LE200357-P-WS-WT-PR-2252 | LE200357-P-WS-WT-PR-2252-A | Sritech | Post-order technically cleared | 103 |  |  |  |  | 04.02.24 | 05.02.24 | 19.02.24 | 22.02.24 | 28.02.24 | 11.03.24 | 26.03.24 |  |  |  |  | 28.03.24 | 27.03.24 | 28.03.24 | T1 | 10.04.24 | Sritech | 11.04.24 | 20.04.24 | 25.04.24 | 23.04.24 |  |  |  | 09.06.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | Flocculator and IPS Mechanism | LE200357-P-WS-WT-PR-2252 | LE200357-P-WS-WT-PR-2252-B | Shivpad | Sent to BU Operations | PR Closed |  |  |  |  | 03.03.24 | 04.03.24 | 08.03.24 | 25.03.24 | 26.03.24 | 27.03.24 | 28.03.24 |  |  |  |  | 28.03.24 | 27.03.24 | 28.03.24 | T2 | [10 empty] | PVVKSG@lntecc.com-20.05.2024-17:22:35
Belgavi | Process | Flocculator and IPS Mechanism | LE200357-P-WS-WT-PR-2252 | LE200357-P-WS-WT-PR-2252-C | Triveni | Regret offer | PR Closed |  |  |  |  | 05.04.24 | 06.04.24 | 11.04.24 | [22 empty] | niyali.sen@lntecc.com-16.05.2024-17:16:52
Belgavi | Process | Air Blower | LE200357-P-WS-WT-PR-2253 | LE200357-P-WS-WT-PR-2253-A | Everest | Post-order technically cleared | 60 |  |  |  |  | 28.08.23 | 29.08.23 | 07.09.23 | 05.10.23 | 31.10.23 | [6 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T1 | 03.04.24 | Everest | 04.04.24 | 30.04.24 | 18.06.24 | 05.06.24 |  |  |  | 02.06.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | Agitator | LE200357-P-WS-WT-PR-2254 | LE200357-P-WS-WT-PR-2254-A | Verito Engineering | Post-order technically cleared | 178 |  |  |  |  | 18.10.23 | 19.10.23 | 06.11.23 | 13.11.23 | 22.11.23 | 30.11.23 | 27.12.23 |  |  |  |  | 27.12.23 | 30.11.23 | 27.12.23 | T1 | 30.12.23 | Verito Engineering | 01.01.24 | 08.02.24 | 22.02.24 | 08.02.24 |  |  |  | 28.02.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | WTP Sluice gates | LE200357-P-WS-WT-PR-2255 | LE200357-P-WS-WT-PR-2255-A | IVC | Regret offer | PR Closed |  |  |  |  | 23.11.23 | 24.11.23 | 15.12.23 | 30.01.24 | 08.02.24 | 12.02.24 | 23.02.24 | [18 empty] | PVVKSG@lntecc.com-25.06.2024-12:18:55
Belgavi | Process | WTP Sluice gates | LE200357-P-WS-WT-PR-2255 | LE200357-P-WS-WT-PR-2255-B | Jash | Pre-order technically cleared | 23 |  |  |  |  | 01.04.24 | 02.04.24 | 29.04.24 | 01.06.24 | 07.06.24 | 13.06.24 | 18.06.24 |  |  |  |  | 12.07.24 | 03.07.24 | 12.07.24 | T1 | [7 empty] | 11.07.24 | 28.07.24 | 26.09.24 | PVVKSG@lntecc.com-23.07.2024-09:49:46
Belgavi | Process | WTP Sluice gates | LE200357-P-WS-WT-PR-2255 | LE200357-P-WS-WT-PR-2255-C | Oriental | Pre-order pending with EDRC | 12 |  |  |  |  | 14.04.24 | 15.04.24 | 30.04.24 | 24.06.24 | 24.06.24 | 02.07.24 | 03.07.24 | 23.07.24 | [14 empty] | 08.07.24 | 25.07.24 | 23.09.24 | PVVKSG@lntecc.com-23.07.2024-09:49:46
Belgavi | Process | Chlorination system | LE200357-P-WS-WT-PR-2256 | LE200357-P-WS-WT-PR-2256-A | Chennai Chloro system | Regret offer | PR Closed |  |  |  |  | 16.01.24 | 17.01.24 | 19.02.24 | 27.03.24 | 30.04.24 | 15.06.24 | 17.06.24 | [18 empty] | PVVKSG@lntecc.com-16.07.2024-09:57:30
Belgavi | Process | Chlorination system | LE200357-P-WS-WT-PR-2256 | LE200357-P-WS-WT-PR-2256-B | Zion | Post-order pending with EDRC | 20 |  |  |  |  | 26.02.24 | 27.02.24 | 07.03.24 | 11.03.24 | 11.03.24 | 12.03.24 | 30.04.24 | 27.05.24 | 07.06.24 |  |  | 17.06.24 | 08.06.24 | 17.06.24 | T1 | 25.06.24 | Zion | 15.07.24 | [7 empty] | PVVKSG@lntecc.com-16.07.2024-10:08:57
Belgavi | Process | Chlorination system | LE200357-P-WS-WT-PR-2256 | LE200357-P-WS-WT-PR-2256-C | Toschon | Regret offer | PR Closed |  |  |  |  | 01.04.24 | 02.04.24 | 30.04.24 | 15.06.24 | 19.06.24 | [20 empty] | PVVKSG@lntecc.com-16.07.2024-09:57:30
Belgavi | Process | Chlorine tonners | LE200357-P-WS-WT-PR-2257 | LE200357-P-WS-WT-PR-2257-A | Zion | Post-order pending with EDRC | 20 |  |  |  |  | 26.02.24 | 27.02.24 | 07.03.24 | 11.03.24 | 11.03.24 | 12.03.24 | 30.04.24 | 27.05.24 | 07.06.24 | 08.06.24 |  | 17.06.24 | 08.06.24 | 17.06.24 | T1 | 25.06.24 | Zion | 15.07.24 | [7 empty] | PVVKSG@lntecc.com-16.07.2024-10:08:57
Belgavi | Process | Filter media | LE200357-P-WS-WT-PR-2258 | LE200357-P-WS-WT-PR-2258-A | Kalimati | Sent to BU Operations | 160 |  |  |  |  | 16.02.24 | 17.02.24 | 26.02.24 | [8 empty] | 26.02.24 | 17.02.24 | 26.02.24 | T1 | [10 empty] | PVVKSG@lntecc.com-10.07.2024-12:03:56
Belgavi | Process | Filter media | LE200357-P-WS-WT-PR-2258 | LE200357-P-WS-WT-PR-2258-B | Dalton | Sent to BU Operations | 109 |  |  |  |  | 19.03.24 | 20.03.24 | 17.04.24 | [8 empty] | 17.04.24 | 20.03.24 | 17.04.24 | T3 | [10 empty] | PVVKSG@lntecc.com-10.07.2024-12:03:56
Belgavi | Process | Filter media | LE200357-P-WS-WT-PR-2258 | LE200357-P-WS-WT-PR-2258-C | Shakun minerals | Sent to BU Operations | 54 |  | Mr HN Patel Mob. No. +91 9552470726/ 8780043361/ 9773206161 | smpl5253@gmail.com |  | 09.02.24 | 27.05.24 | 31.05.24 | [8 empty] | 11.06.24 | 08.06.24 | 11.06.24 | T2 | [10 empty] | PVVKSG@lntecc.com-10.07.2024-12:03:56
Belgavi | Process | Filter Nozzles | LE200357-P-WS-WT-PR-2259 | LE200357-P-WS-WT-PR-2259-A | Guddi Plastcon | Approved by Client | PR Closed |  |  |  |  | 25.09.23 | 26.09.23 | 12.10.23 | 31.10.23 | 01.11.23 | [6 empty] | 20.11.23 | 20.11.23 | 20.11.23 | T1 | 06.12.23 | Guddi Plastcon | 08.12.23 | 09.12.23 | 14.12.23 | 13.12.23 | 15.02.24 |  |  | 04.02.24 | PVVKSG@lntecc.com-05.06.2024-14:39:26
Belgavi | Process | Sludge drying bed media | LE200357-P-WS-WT-PR-2260 | LE200357-P-WS-WT-PR-2260-A | Kalimati | Sent to BU Operations | 149 |  |  |  |  | 15.02.24 | 16.02.24 | 26.02.24 | 04.03.24 | 08.03.24 | [6 empty] | 26.02.24 | 04.03.24 | 26.02.24 | T1 | [10 empty] | PVVKSG@lntecc.com-10.07.2024-12:03:56
Belgavi | Process | Sludge drying bed media | LE200357-P-WS-WT-PR-2260 | LE200357-P-WS-WT-PR-2260-B | Dalton | Sent to BU Operations | 109 |  |  |  |  | 19.03.24 | 20.03.24 | 17.04.24 | [8 empty] | 17.04.24 | 20.03.24 | 17.04.24 | T3 | [10 empty] | PVVKSG@lntecc.com-10.07.2024-12:03:56
Belgavi | Process | Sludge drying bed media | LE200357-P-WS-WT-PR-2260 | LE200357-P-WS-WT-PR-2260-C | Shakun minerals | Sent to BU Operations | 54 |  | Mr HN Patel Mob. No. +91 9552470726/ 8780043361/ 9773206161 | smpl5253@gmail.com |  | 09.02.24 | 27.05.24 | 31.05.24 | [8 empty] | 11.06.24 | 08.06.24 | 11.06.24 | T2 | [10 empty] | PVVKSG@lntecc.com-10.07.2024-12:03:56
Belgavi | Process | Backwash pump | LE200357-P-WS-WT-PR-2261 | LE200357-P-WS-WT-PR-2261-A | MBH | Post-order technically cleared | 109 |  |  |  |  | 17.08.23 | 18.08.23 | 19.08.23 | 25.08.23 | 25.08.23 | 25.09.23 | 27.09.23 | 11.10.23 | 01.11.23 |  |  | 01.11.23 | 11.10.23 | 01.11.23 | T1 | 20.03.24 | MBH | 21.03.24 | 16.04.24 | 17.04.24 | 17.04.24 |  |  |  | 19.05.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | Backwash pump | LE200357-P-WS-WT-PR-2261 | LE200357-P-WS-WT-PR-2261-B | WILO | Regret offer | PR Closed |  |  |  |  | 20.08.23 | 21.08.23 | 23.08.23 | [22 empty] | niyali.sen@lntecc.com-17.05.2024-09:53:05
Belgavi | Process | Submersible pump | LE200357-P-WS-WT-PR-2262 | LE200357-P-WS-WT-PR-2262-A | Andritz | Regret offer | PR Closed |  |  |  |  | 04.04.24 | 05.04.24 | 29.04.24 | [22 empty] | PVVKSG@lntecc.com-25.06.2024-12:18:55
Belgavi | Process | Submersible pump | LE200357-P-WS-WT-PR-2262 | LE200357-P-WS-WT-PR-2262-B | MBH | Sent to BU Operations | 48 |  |  |  |  | 01.05.24 | 02.05.24 | 06.05.24 | 16.05.24 | 03.06.24 | [6 empty] | 17.06.24 | 08.06.24 | 17.06.24 | T1 | [10 empty] | PVVKSG@lntecc.com-29.07.2024-11:20:54
Belgavi | Process | Submersible pump | LE200357-P-WS-WT-PR-2262 | LE200357-P-WS-WT-PR-2262-C | Jasco | Pre-order comments issued | 6 |  |  |  |  | 29.06.24 | 09.07.24 | 29.07.24 | [22 empty] | PVVKSG@lntecc.com-29.07.2024-11:20:54
Belgavi | Process | Electrical hoist | LE200357-P-WS-WT-PR-2263 | LE200357-P-WS-WT-PR-2263-A | JAPS | Post-order technically cleared | 87 |  |  |  |  | 25.09.23 | 26.09.23 | 19.10.23 | [8 empty] | 19.10.23 | 26.09.23 | 19.10.23 | T1 | 03.04.24 | JAPS | 04.04.24 | 30.04.24 | 30.05.24 | 09.05.24 |  |  |  | 02.06.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | Manual chain pulley block | LE200357-P-WS-WT-PR-2264 | LE200357-P-WS-WT-PR-2264-A | JAPS | Post-order technically cleared | 60 |  |  |  |  | 25.09.23 | 26.09.23 | 19.10.23 | [8 empty] | 19.10.23 | 26.09.23 | 19.10.23 | T1 | 03.04.24 | JAPS | 04.04.24 | 30.04.24 | 07.06.24 | 05.06.24 |  |  |  | 02.06.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | Dosing pump | LE200357-P-WS-WT-PR-2265 | LE200357-P-WS-WT-PR-2265-A | SR Metering | Post-order technically cleared | 186 |  |  |  |  | 20.08.23 | 21.08.23 | 25.08.23 | 30.08.23 | 30.08.23 | [6 empty] | 01.09.23 | 01.09.23 | 01.09.23 | T1 | 12.11.23 | SR Metering | 13.11.23 | 30.01.24 | 01.02.24 | 31.01.24 |  |  |  | 11.01.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | Sampling pump | LE200357-P-WS-WT-PR-2266 | LE200357-P-WS-WT-PR-2266-A | Andritz | Regret offer | PR Closed | Site Procurement |  |  |  | 16.04.24 | 17.04.24 | [23 empty] | PVVKSG@lntecc.com-07.06.2024-14:13:56
Belgavi | Process | Submersible mixer | LE200357-P-WS-WT-PR-2267 | LE200357-P-WS-WT-PR-2267-A | WWTE | Post-order technically cleared | 44 |  |  |  |  | 10.12.23 | 11.12.23 | 15.12.23 | 19.12.23 | 12.02.24 | [6 empty] | 27.02.24 | 22.02.24 | 27.02.24 | T1 | 17.05.24 | WWTE | 20.05.24 | 03.06.24 | 24.06.24 | 21.06.24 |  |  |  | 16.07.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | Submersible mixer | LE200357-P-WS-WT-PR-2267 | LE200357-P-WS-WT-PR-2267-B | FFP | Regret offer | PR Closed |  |  |  |  | 12.03.24 | 13.03.24 | 03.04.24 | [22 empty] | PVVKSG@lntecc.com-20.05.2024-17:22:35
Belgavi | Process | Dewatering pump | LE200357-P-WS-WT-PR-2268 | LE200357-P-WS-WT-PR-2268-A | MBH | Post-order technically cleared | 59 |  |  |  |  | 30.10.23 | 31.10.23 | 10.11.23 | 17.01.24 | 09.02.24 | 12.02.24 | 22.02.24 | 28.02.24 | 06.03.24 |  |  | 22.02.24 | 28.02.24 | 22.02.24 | T1 | 24.05.24 | MBH | 27.05.24 | 04.06.24 | 07.06.24 | 06.06.24 |  |  |  | 23.07.24 | PVVKSG@lntecc.com-25.06.2024-12:16:57
Belgavi | Process | Dissolving Tray | LE200357-P-WS-WT-PR-2269 | LE200357-P-WS-WT-PR-2269-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 13.11.20 | [24 empty] | PVVKSG@lntecc.com-20.05.2024-17:22:35
Belgavi | Process | Trolley | LE200357-P-WS-WT-PR-2270 | LE200357-P-WS-WT-PR-2270-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 13.11.20 | [24 empty] | PVVKSG@lntecc.com-20.05.2024-17:13:56
Belgavi | Process | Platform weighing machine | LE200357-P-WS-WT-PR-2271 | LE200357-P-WS-WT-PR-2271-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 19.11.20 | [24 empty] | PVVKSG@lntecc.com-20.05.2024-17:22:36
Belgavi | Process | Exhaust fan | LE200357-P-WS-WT-PR-2272 | LE200357-P-WS-WT-PR-2272-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 05.12.20 | [24 empty] | PVVKSG@lntecc.com-20.05.2024-17:22:36
Belgavi | Process | Lab equipment | LE200357-P-WS-WT-PR-2273 | LE200357-P-WS-WT-PR-2273-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 19.09.20 | [24 empty] | PVVKSG@lntecc.com-20.05.2024-17:22:36
Belgavi | Process | Rate of Flow Controller | LE200357-P-WS-WT-PR-2274 | LE200357-P-WS-WT-PR-2274-A | Reliable | Pre-order comments issued | 23 |  | Pradip Kumar Dutt PH: +91 9830030126 | reliable522@yahoo.in |  | 17.06.24 | 03.07.24 | 12.07.24 | [19 empty] | 26.07.24 | 12.08.24 | 11.10.24 | PVVKSG@lntecc.com-12.07.2024-19:14:06
Belgavi | Mechanical | Chain pulley | LE200357-M-WS-CR-PR-1198 | LE200357-M-WS-CR-PR-1198-A | JAPS | Pre-order comments issued | 55 |  | 9825019138 | sales.japs@gmail.com |  | 04.11.23 | 22.03.24 | 10.06.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | Submersible Pumps | LE200357-M-WS-DW-PR-1196 | LE200357-M-WS-DW-PR-1196-A | WPIL | Regret offer | PR Closed |  | 33 4052 6000 | s.sen@wpil.co.in |  | 30.09.20 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | Submersible Pumps | LE200357-M-WS-DW-PR-1196 | LE200357-M-WS-DW-PR-1196-B | Aqua | Pre-order technically cleared | 10 |  | S.T.Sambandam 8144003131 | chennai@aquapumps.com |  | 05.07.24 | 23.07.24 | 25.07.24 | [8 empty] | 25.07.24 | 25.07.24 | 25.07.24 | T2 | [10 empty] | svcn@lntecc.com-26.07.2024-17:11:56
Belgavi | Mechanical | Submersible Pumps | LE200357-M-WS-DW-PR-1196 | LE200357-M-WS-DW-PR-1196-C | JASCO | Pre-order technically cleared | 9 |  | Arvish Modi 7069099037 | mailto:hyd@jascopump.com |  | 29.06.24 | 09.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [10 empty] | svcn@lntecc.com-26.07.2024-17:11:56
Belgavi | Mechanical | Exhaust Fans | LE200357-M-WS-EF-PR-1197 | LE200357-M-WS-EF-PR-1197-A |  | Enquiry yet to float | NA | [26 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-02.07.2024-10:56:59
Belgavi | Mechanical | HSC Pumps | LE200357-M-WS-HS-PR-1195 | LE200357-M-WS-HS-PR-1195-A | WPIL | Post-order technically cleared | 256 |  | 33 4052 6000 | s.sen@wpil.co.in |  | 31.03.21 | 16.08.23 | 24.08.23 | [8 empty] | 30.08.23 | 30.08.23 | 30.08.23 | T1 | 30.08.23 | WPIL | 07.10.23 | 16.10.23 | 22.11.23 | 22.11.23 |  | 30.08.23 | 16.09.23 | 29.10.23 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | Sluice Gate | LE200357-M-WS-SG-PR-1199 | LE200357-M-WS-SG-PR-1199-A | Jash | Pre-order technically cleared | 58 |  | 91-72900 40772 | lpgsouth2@jashindia.com |  | 02.11.20 | 28.03.24 | 07.06.24 | [8 empty] | 07.06.24 | 07.03.24 | 07.06.24 | T1 | [7 empty] | 07.06.24 | 24.06.24 | 23.08.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | Sluice Gate | LE200357-M-WS-SG-PR-1199 | LE200357-M-WS-SG-PR-1199-B | IVC | Regret offer | PR Closed |  | Sudip Ghosh | sudip.ghosh@ivc-valves.com |  | 02.11.20 | [21 empty] | 02.11.20 | 19.11.20 | 18.01.21 | svcn@lntecc.com-02.07.2024-10:57:17
Belgavi | Mechanical | Surge Equipments | LE200357-M-WS-SP-PR-1204 | LE200357-M-WS-SP-PR-1204-A | Jash | Post-order technically cleared | 144 |  | 91-72900 40772 | lpgsouth2@jashindia.com |  | 24.06.20 | 12.02.24 | 04.03.24 | [8 empty] | 04.03.24 | 04.03.24 | 04.03.24 | T1 | 06.03.24 | Jash | 12.03.24 | 13.03.24 | 13.03.24 | 13.03.24 |  | 04.03.24 | 21.03.24 | 05.05.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | Surge Equipments | LE200357-M-WS-SP-PR-1204 | LE200357-M-WS-SP-PR-1204-B | Sigmaflow | Sent to BU Operations | PR Closed |  | Jagadesh | jagadesh@sigmaflow.in |  | 24.06.20 | 31.01.24 | 08.02.24 | [8 empty] | 08.02.24 | 08.02.24 | 08.02.24 | T3 | [7 empty] | 08.02.24 | 25.02.24 | 25.04.24 | svcn@lntecc.com-03.07.2024-14:57:18
Belgavi | Mechanical | Surge Equipments | LE200357-M-WS-SP-PR-1204 | LE200357-M-WS-SP-PR-1204-C | AVK | Post-order technically cleared | 135 |  | 91769 66455 | subhash@avkindia.com |  | 24.06.20 | 31.01.24 | 08.02.24 | [8 empty] | 08.02.24 | 08.02.24 | 08.02.24 | T2 | 12.03.24 | AVK | 13.03.24 | 22.03.24 | 22.03.24 | 22.03.24 |  | 08.02.24 | 25.02.24 | 25.04.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | PRV | LE200357-M-WS-SP-PR-1205 | LE200357-M-WS-SP-PR-1205-A | Dorot | Post-order technically cleared | 123 |  | 91769 66464 | abhishek.mathur@aquestia.com |  | 06.11.23 | 18.12.23 | 22.12.23 | [8 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T1 | 07.03.24 | Dorot | 02.04.24 | 03.04.24 | 03.04.24 | 03.04.24 |  | 02.03.24 | 19.03.24 | 06.05.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | Dewatering Pumps | LE200357-M-WS-SP-PR-1206 | LE200357-M-WS-SP-PR-1206-A | Aqua | Pre-order technically cleared | 10 |  | S.T.Sambandam 8144003131 | chennai@aquapumps.com |  | 05.07.24 | 23.07.24 | 25.07.24 | [8 empty] | 25.07.24 | 25.07.24 | 25.07.24 | T2 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:09:01
Belgavi | Mechanical | Dewatering Pumps | LE200357-M-WS-SP-PR-1206 | LE200357-M-WS-SP-PR-1206-B | JASCO | Pre-order technically cleared | 9 |  | Arvish Modi 7069099037 | mailto:hyd@jascopump.com |  | 29.06.24 | 09.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [10 empty] | svcn@lntecc.com-26.07.2024-17:11:38
Belgavi | Mechanical | FCV | LE200357-M-WS-SP-PR-1207 | LE200357-M-WS-SP-PR-1207-A | AVK | Post-order technically cleared | 177 |  | 91769 66455 | subhash@avkindia.com |  | 10.07.23 | 03.07.23 | 03.07.23 | [8 empty] | 09.02.24 | 09.02.24 | 09.02.24 | T1 | 01.08.23 | AVK | 04.08.23 | 09.08.23 | 09.08.23 | 09.08.23 |  | 09.02.24 | 26.02.24 | 30.09.23 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | Pump house valves | LE200357-M-WS-VL-PR-1200 | LE200357-M-WS-VL-PR-1200-A | AVK | Post-order technically cleared | 78 |  | 91769 66455 | subhash@avkindia.com |  | 02.11.20 | 30.10.23 | 08.11.23 | [8 empty] | 08.11.23 | 08.11.23 | 08.11.23 | T1 | 08.12.23 | AVK | 09.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  | 08.11.23 | 25.11.23 | 24.01.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | DJ | LE200357-M-WS-VL-PR-1200 | LE200357-M-WS-VL-PR-1200-B | Electrosteel | Post-order technically cleared | 78 |  |  | satyendra.kumar@electrosteel.com; anujkr.maurya@electrosteel.com; animikh.banerjee@electrosteel.com; soumayajit.mukherjee@electrosteel.com |  | 02.11.20 | 30.10.23 | 08.11.23 | [8 empty] | 08.11.23 | 08.11.23 | 08.11.23 | T1 | 08.12.23 | Electrosteel | 09.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  | 08.11.23 | 25.11.23 | 24.01.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | DPCV | LE200357-M-WS-VL-PR-1200 | LE200357-M-WS-VL-PR-1200-C | R&D | Post-order technically cleared | 240 |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 02.11.20 | 17.06.23 | 20.06.23 | [8 empty] | 05.08.23 | 05.08.23 | 05.08.23 | T1 | 30.09.23 | R&D | 30.11.23 | 07.12.23 | 08.12.23 | 08.12.23 |  | 05.08.23 | 22.08.23 | 21.10.23 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Mechanical | ELSR valves | LE200357-M-WS-VL-PR-1202 | LE200357-M-WS-VL-PR-1202-A | R&D | Post-order technically cleared | 92 |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 12.12.20 | 09.02.24 | 12.02.24 | [8 empty] | 17.04.24 | 17.04.24 | 17.04.24 | T1 | 20.04.24 | R&D | 04.05.24 | 04.05.24 | 04.05.24 | 04.05.24 |  | 17.04.24 | 04.05.24 | 19.06.24 | svcn@lntecc.com-26.07.2024-17:07:09
Belgavi | Instrumentation | Electromagnetic Flowmeter | LE200357-I-WS-PR-EF-5505 | LE200357-I-WS-PR-EF-5505-A | Khrone | Approved by Client | PR Closed |  | Diliban | dilibanr@forbesmarshall.com | 02.03.22 | 02.03.22 | 07.03.22 | 14.03.22 | 18.03.22 | [7 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T1 | 21.05.24 | Khrone | 06.08.22 | 18.08.22 | 18.08.22 | 18.08.22 | 10.04.24 | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-16:49:00
Belgavi | Instrumentation | Electromagnetic Flowmeter | LE200357-I-WS-PR-EF-5505 | LE200357-I-WS-PR-EF-5505-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 02.03.22 | 02.03.22 | 15.03.22 | 15.03.22 | 16.06.22 | [7 empty] | 16.06.22 | 16.06.22 | 20.03.22 | T2 | [7 empty] | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-16:49:00
Belgavi | Instrumentation | Electromagnetic Flowmeter | LE200357-I-WS-PR-EF-5505 | LE200357-I-WS-PR-EF-5505-C | ABB | Sent to BU Operations | PR Closed |  | Krishnakishore | krishna.kishore@in.abb.com | 02.03.22 | 02.03.22 | 07.03.22 | 14.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-16:49:00
Belgavi | Instrumentation | Electromagnetic Flowmeter | LE200357-I-WS-PR-EF-5505 | LE200357-I-WS-PR-EF-5505-D | Siemens | Sent to BU Operations | PR Closed |  | Guruswamy Keerthi | keerthi.guruswamy.ext@siemens.com | 02.03.22 | 02.03.22 | 08.03.22 | 14.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T4 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-16:49:00
Belgavi | Instrumentation | Float and Board Level Indicator | LE200357-I-WS-PR-FB-5504 | LE200357-I-WS-PR-FB-5504-A | SBEM | Sent to BU Operations | 40 |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 05.03.22 | 29.09.23 | 25.03.24 | 08.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T1 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Float and Board Level Indicator | LE200357-I-WS-PR-FB-5504 | LE200357-I-WS-PR-FB-5504-B | Pune Techtrol | Pre-order technically rejected | PR Closed |  | Shanmugasundari | sales.techtrol@measurecon.co.in | 01.01.22 | 05.03.22 | 19.02.24 | 25.03.24 | [22 empty] | mehernani@lntecc.com-01.07.2024-16:49:39
Belgavi | Instrumentation | Float and Board Level Indicator | LE200357-I-WS-PR-FB-5504 | LE200357-I-WS-PR-FB-5504-C | Scientific Devices | Sent to BU Operations | 40 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 05.03.22 | 16.11.23 | 25.03.24 | 10.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T2 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | PLC & SCADA | LE200357-I-WS-PR-PL-5516 | LE200357-I-WS-PR-PL-5516-A | Schnedier | Sent to BU Operations | 317 |  | Rusheyandr | rushyendhar.repalli@se.com | 01.01.22 | 30.07.22 | 30.06.23 | 01.07.23 | 10.08.23 | [7 empty] | 22.09.23 | 22.09.23 | 22.09.23 | T1 | [7 empty] | 22.09.23 | 09.10.23 | 08.12.23 | mehernani@lntecc.com-11.07.2024-13:07:14
Belgavi | Instrumentation | PLC & SCADA | LE200357-I-WS-PR-PL-5516 | LE200357-I-WS-PR-PL-5516-B | Honeywell | Sent to BU Operations | 258 |  | Vinod Janarthan | vinod.janarthan@Honeywell.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 13.11.23 | [7 empty] | 17.11.23 | 17.11.23 | 20.11.23 | T2 | [7 empty] | 17.11.23 | 04.12.23 | 02.02.24 | mehernani@lntecc.com-11.07.2024-13:07:14
Belgavi | Instrumentation | PLC & SCADA | LE200357-I-WS-PR-PL-5516 | LE200357-I-WS-PR-PL-5516-C | Mitsubushi | Pre-order technically rejected | PR Closed |  | Sudarsan.Gupta | Sudarsan.Gupta@asia.meap.com | 01.01.22 | 30.07.22 | 13.12.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | PLC & SCADA | LE200357-I-WS-PR-PL-5516 | LE200357-I-WS-PR-PL-5516-D | Sai applied technologies pvt limited | Pre-order technically rejected | PR Closed |  | Sweta Parvatiya | mktg@saiapplied.com | 01.01.22 | 30.07.22 | 01.11.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | UPS | LE200357-I-WS-PR-UP-5518 | LE200357-I-WS-PR-UP-5518-A | Liveline | Sent to BU Operations | 49 | Technical clearance given. However final clearance shall be given after PLC vendor finalization | Shilajit Naskar | sales2@livelineindia.com | 01.01.22 | 29.05.24 | 30.05.24 | 30.05.24 | [8 empty] | 10.06.24 | 10.06.24 | 16.06.24 | T1 | [7 empty] | 10.06.24 | 27.06.24 | 26.08.24 | mehernani@lntecc.com-11.07.2024-12:10:30
Belgavi | Instrumentation | UPS | LE200357-I-WS-PR-UP-5518 | LE200357-I-WS-PR-UP-5518-B | Hitachihirel | Sent to BU Operations | 47 | Technical clearance given. However final clearance shall be given after PLC vendor finalization |  | balakumaran_s@hitachi-hirel.com |  | 29.05.24 | 05.06.24 | 05.06.24 | [8 empty] | 08.06.24 | 08.06.24 | 18.06.24 | T2 | [7 empty] | 08.06.24 | 25.06.24 | 24.08.24 | mehernani@lntecc.com-11.07.2024-12:10:30
Belgavi | Instrumentation | UPS | LE200357-I-WS-PR-UP-5518 | LE200357-I-WS-PR-UP-5518-C | Vertiv | Pre-order pending with EDRC | 30 |  |  | K.Shivakumar@vertiv.com |  | 29.11.23 | 05.07.24 | [20 empty] | 12.07.24 | 29.07.24 | 27.09.24 | mehernani@lntecc.com-11.07.2024-12:10:31
Belgavi | Instrumentation | WATER METER | LE200357-I-WS-PR-WT-5523 | LE200357-I-WS-PR-WT-5523-A | Venus | Approved by Client | PR Closed |  | A S JAYARAMA | gm_venusmeters@yahoo.com |  | 20.01.24 | 20.01.24 | 31.01.24 | [8 empty] | 16.02.24 | 16.02.24 | 18.02.24 | T1 | 15.05.24 | Venus | 14.03.24 | 15.03.24 | 15.03.24 | 15.03.24 | 13.05.24 | 16.02.24 | 04.03.24 | 03.05.24 | mehernani@lntecc.com-01.07.2024-17:02:53
Belgavi | Instrumentation | Pressure Gauge | LE200357-I-WS-WT-PR-5501 | LE200357-I-WS-WT-PR-5501-A | Hguru | Sent to BU Operations | 207 |  | H Guru | info@hgurusouth.com | 01.01.22 | 30.07.22 | 08.11.23 | 10.01.24 | [8 empty] | 10.01.24 | 10.01.24 | 10.01.24 | T1 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Pressure Gauge | LE200357-I-WS-WT-PR-5501 | LE200357-I-WS-WT-PR-5501-B | Scientific devices | Sent to BU Operations | 207 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 30.07.22 | 16.11.23 | 10.01.24 | [8 empty] | 10.01.24 | 10.01.24 | 10.01.24 | T2 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Pressure Gauge | LE200357-I-WS-WT-PR-5501 | LE200357-I-WS-WT-PR-5501-C | GIC | Regret offer | PR Closed |  | Dinabandhu Bhatta | gicchennai@general-gauges.com | 01.01.22 | 30.07.22 | 14.11.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Pressure Gauge | LE200357-I-WS-WT-PR-5501 | LE200357-I-WS-WT-PR-5501-D | Forbes marshall | Sent to BU Operations | 132 |  | R, DILIBAN. | dilibanr@forbesmarshall.com | 01.01.22 | 30.07.22 | 20.11.23 | 10.01.24 | 19.02.24 | [7 empty] | 25.03.24 | 25.03.24 | 25.03.24 | T3 | [7 empty] | 25.03.24 | 11.04.24 | 10.06.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Pressure transmitter | LE200357-I-WS-WT-PR-5503 | LE200357-I-WS-WT-PR-5503-A | Eximp | Sent to BU Operations | PR Closed |  | Jayakrishnan Pallath | Jayakrishnan.Pallath@eximpinc.com | 03.03.22 | 03.03.22 | 14.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 17.03.22 | 17.03.22 | 20.03.22 | T1 | [7 empty] | 17.03.22 | 03.04.22 | 02.06.22 | mehernani@lntecc.com-01.07.2024-16:55:04
Belgavi | Instrumentation | Pressure transmitter | LE200357-I-WS-WT-PR-5503 | LE200357-I-WS-WT-PR-5503-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 03.03.22 | 03.03.22 | 09.03.22 | 18.03.22 | [8 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T2 | [7 empty] | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-16:55:04
Belgavi | Instrumentation | Pressure transmitter | LE200357-I-WS-WT-PR-5503 | LE200357-I-WS-WT-PR-5503-C | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 03.03.22 | 03.03.22 | 08.03.22 | 16.03.22 | [8 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-16:55:04
Belgavi | Instrumentation | Pressure transmitter | LE200357-I-WS-WT-PR-5503 | LE200357-I-WS-WT-PR-5503-D | Siemens | Approved by Client | PR Closed |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 03.03.22 | 03.03.22 | 16.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T4 | 14.09.22 | Siemens | 20.09.22 | 21.09.22 | 21.09.22 | 21.09.22 | 01.04.24 | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-08.07.2024-17:54:44
Belgavi | Instrumentation | Ultrasonic Flow transmitter | LE200357-I-WS-WT-PR-5507 | LE200357-I-WS-WT-PR-5507-A | SBEM | Pre-order technically rejected | PR Closed |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 30.07.22 | 29.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Ultrasonic Flow transmitter | LE200357-I-WS-WT-PR-5507 | LE200357-I-WS-WT-PR-5507-B | Siemens | Sent to BU Operations | 132 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 01.01.22 | 30.07.22 | 09.11.23 | 14.12.23 | 25.03.24 | [7 empty] | 25.03.24 | 25.03.24 | 25.03.24 | T1 | [7 empty] | 25.03.24 | 11.04.24 | 10.06.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Rate of flowmeter | LE200357-I-WS-WT-PR-5509 | LE200357-I-WS-WT-PR-5509-A | SBEM | Pre-order technically rejected | PR Closed |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 30.07.22 | 29.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Rate of flowmeter | LE200357-I-WS-WT-PR-5509 | LE200357-I-WS-WT-PR-5509-B | Siemens | Sent to BU Operations | 234 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 01.01.22 | 30.07.22 | 09.11.23 | 14.12.23 | [8 empty] | 14.12.23 | 14.12.23 | 14.12.23 | T1 | [7 empty] | 25.03.24 | 11.04.24 | 10.06.24 | mehernani@lntecc.com-11.07.2024-12:56:52
Belgavi | Instrumentation | Bypass Rotameter | LE200357-I-WS-WT-PR-5510 | LE200357-I-WS-WT-PR-5510-A | Scientific devices | Sent to BU Operations | 211 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 30.07.22 | 16.11.23 | 06.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 06.01.24 | T1 | [7 empty] | 06.01.24 | 23.01.24 | 23.03.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Bypass Rotameter | LE200357-I-WS-WT-PR-5510 | LE200357-I-WS-WT-PR-5510-B | Eureka | Sent to BU Operations | 211 |  | S.Kumar | chennaioffice@eurekaflow.com | 01.01.22 | 30.07.22 | 24.11.23 | 06.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 06.01.24 | T2 | [7 empty] | 06.01.24 | 23.01.24 | 23.03.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Ph Analyser | LE200357-I-WS-WT-PR-5511 | LE200357-I-WS-WT-PR-5511-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-16:52:58
Belgavi | Instrumentation | Ph Analyser | LE200357-I-WS-WT-PR-5511 | LE200357-I-WS-WT-PR-5511-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Ph Analyser | LE200357-I-WS-WT-PR-5511 | LE200357-I-WS-WT-PR-5511-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Ph Analyser | LE200357-I-WS-WT-PR-5511 | LE200357-I-WS-WT-PR-5511-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 01.02.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-08.07.2024-17:54:44
Belgavi | Instrumentation | Ph Analyser | LE200357-I-WS-WT-PR-5511 | LE200357-I-WS-WT-PR-5511-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 20.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-16:52:58
Belgavi | Instrumentation | Ph Analyser | LE200357-I-WS-WT-PR-5511 | LE200357-I-WS-WT-PR-5511-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Turbidity Analyser | LE200357-I-WS-WT-PR-5512 | LE200357-I-WS-WT-PR-5512-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-16:57:31
Belgavi | Instrumentation | Turbidity Analyser | LE200357-I-WS-WT-PR-5512 | LE200357-I-WS-WT-PR-5512-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Turbidity Analyser | LE200357-I-WS-WT-PR-5512 | LE200357-I-WS-WT-PR-5512-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Turbidity Analyser | LE200357-I-WS-WT-PR-5512 | LE200357-I-WS-WT-PR-5512-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 01.02.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-08.07.2024-17:54:44
Belgavi | Instrumentation | Turbidity Analyser | LE200357-I-WS-WT-PR-5512 | LE200357-I-WS-WT-PR-5512-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 20.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-16:57:31
Belgavi | Instrumentation | Turbidity Analyser | LE200357-I-WS-WT-PR-5512 | LE200357-I-WS-WT-PR-5512-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | RCL Analyser | LE200357-I-WS-WT-PR-5513 | LE200357-I-WS-WT-PR-5513-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-17:06:29
Belgavi | Instrumentation | RCL Analyser | LE200357-I-WS-WT-PR-5513 | LE200357-I-WS-WT-PR-5513-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | RCL Analyser | LE200357-I-WS-WT-PR-5513 | LE200357-I-WS-WT-PR-5513-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | RCL Analyser | LE200357-I-WS-WT-PR-5513 | LE200357-I-WS-WT-PR-5513-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 01.02.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-08.07.2024-17:54:44
Belgavi | Instrumentation | RCL Analyser | LE200357-I-WS-WT-PR-5513 | LE200357-I-WS-WT-PR-5513-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 20.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-17:06:29
Belgavi | Instrumentation | RCL Analyser | LE200357-I-WS-WT-PR-5513 | LE200357-I-WS-WT-PR-5513-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Battery Operated Datalogger | LE200357-I-WS-WT-PR-5519 | LE200357-I-WS-WT-PR-5519-A | Enviro | Sent to BU Operations | PR Closed |  | Sharad | Water.div@envirosafety.in | 25.08.22 | 29.08.22 | 03.09.22 | 16.09.22 | 19.09.22 | 19.09.22 | [6 empty] | 10.05.23 | 10.05.23 | 15.06.23 | T2 | [7 empty] | 10.05.23 | 27.05.23 | 26.07.23 | mehernani@lntecc.com-01.07.2024-16:45:51
Belgavi | Instrumentation | Battery Operated Datalogger | LE200357-I-WS-WT-PR-5519 | LE200357-I-WS-WT-PR-5519-B | GSV Microtech | Post-order technically cleared | 232 |  | Manikandan A | sales@gsv-microtech.com | 25.08.22 | 29.08.22 | 16.06.23 | 04.08.23 | [8 empty] | 04.08.23 | 04.08.23 | 10.08.23 | T1 | 20.10.23 | GSV Microtech | 02.12.23 | 15.12.23 | 16.12.23 | 16.12.23 |  | 04.08.23 | 21.08.23 | 20.10.23 | mehernani@lntecc.com-08.07.2024-17:54:44
Belgavi | Instrumentation | Instrumentation Cables | LE21M357-I-WS-PR-CA-5517 | LE21M357-I-WS-PR-CA-5517-A | Cords | Sent to BU Operations | 40 |  |  | hp@cordscable.com | 01.01.22 | 29.05.24 | 11.06.24 | 17.06.24 | 22.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T1 | [7 empty] | 22.06.24 | 09.07.24 | 07.09.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Instrumentation Cables | LE21M357-I-WS-PR-CA-5517 | LE21M357-I-WS-PR-CA-5517-B | PVESPL | Regret offer | PR Closed |  |  | pvespl@vashiisl.com |  | 29.05.24 | 09.06.24 | 10.06.24 | [22 empty] | mehernani@lntecc.com-08.07.2024-17:54:44
Belgavi | Instrumentation | Instrumentation Cables | LE21M357-I-WS-PR-CA-5517 | LE21M357-I-WS-PR-CA-5517-C | Gemscab | Sent to BU Operations | 40 |  |  | mrawoof@gemscab.com |  | 11.06.24 | 19.06.24 | 19.06.24 | [8 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T2 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Vibration Monitoring System | LE21M357-I-WS-WT-VMS-5521 | LE21M357-I-WS-WT-VMS-5521-A | Preipolar | Pre-order technically rejected | PR Closed |  | Sivanesh G | sivanesh@preipolar.com | 01.01.22 | 16.09.23 | 16.11.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:58:24
Belgavi | Instrumentation | Vibration Monitoring System | LE21M357-I-WS-WT-VMS-5521 | LE21M357-I-WS-WT-VMS-5521-B | Centum | Sent to BU Operations | 233 |  | Akhil suresh | akhil@centumcontrols.com | 01.01.22 | 16.09.23 | 29.11.23 | 15.12.23 | [8 empty] | 15.12.23 | 15.12.23 | 15.12.23 | T1 | [7 empty] | 15.12.23 | 01.01.24 | 01.03.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Vibration Monitoring System | LE21M357-I-WS-WT-VMS-5521 | LE21M357-I-WS-WT-VMS-5521-C | Forbes marshall | Sent to BU Operations | 233 |  | Pallavi Gajbhiye | pgajbhiye@forbesmarshall.com | 01.01.22 | 16.09.23 | 29.11.23 | 15.12.23 | [8 empty] | 15.12.23 | 15.12.23 | 15.12.23 | T2 | [7 empty] | 15.12.23 | 01.01.24 | 01.03.24 | mehernani@lntecc.com-11.07.2024-12:56:16
Belgavi | Instrumentation | Ultrasonic Level Transmitter | LEE200357-I-WS-PR-LT-5116 | LEE200357-I-WS-PR-LT-5116-A | Eximp | Sent to BU Operations | PR Closed |  | Jayakrishnan Pallath | Jayakrishnan.Pallath@eximpinc.com | 03.03.22 | 03.03.22 | 14.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 17.03.22 | 17.03.22 | 20.03.22 | T1 | [7 empty] | 17.03.22 | 03.04.22 | 02.06.22 | mehernani@lntecc.com-01.07.2024-17:01:06
Belgavi | Instrumentation | Ultrasonic Level Transmitter | LEE200357-I-WS-PR-LT-5116 | LEE200357-I-WS-PR-LT-5116-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 03.03.22 | 03.03.22 | 09.03.22 | 18.03.22 | [8 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T2 | [7 empty] | 28.03.22 | 14.04.22 | 13.06.22 | mehernani@lntecc.com-01.07.2024-17:01:07
Belgavi | Instrumentation | Ultrasonic Level Transmitter | LEE200357-I-WS-PR-LT-5116 | LEE200357-I-WS-PR-LT-5116-C | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 03.03.22 | 03.03.22 | 08.03.22 | 16.03.22 | [8 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-17:01:07
Belgavi | Instrumentation | Ultrasonic Level Transmitter | LEE200357-I-WS-PR-LT-5116 | LEE200357-I-WS-PR-LT-5116-D | Siemens | Approved by Client | PR Closed |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 03.03.22 | 03.03.22 | 16.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T4 | 14.09.22 | Siemens | 20.09.22 | 21.09.22 | 21.09.22 | 21.09.22 | 01.04.24 | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-08.07.2024-17:54:44
Belgavi | Electrical | Transformer | LE200357-E-WS-CW-PR-4002 | LE200357-E-WS-CW-PR-4002-A | Voltech | Pre-order comments issued | 272 |  |  |  |  | 21.10.23 | 30.10.23 | 01.11.23 | 06.11.23 | [10 empty] | T1 | [7 empty] | 25.07.24 | 11.08.24 | 10.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | Transformer | LE200357-E-WS-CW-PR-4002 | LE200357-E-WS-CW-PR-4002-B | Transcon | Pre-order comments issued | 45 |  |  |  |  | 29.04.24 | 03.05.24 | 08.05.24 | 15.06.24 | 20.06.24 | [17 empty] | 25.07.24 | 11.08.24 | 10.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | Transformer | LE200357-E-WS-CW-PR-4002 | LE200357-E-WS-CW-PR-4002-C | Telawne | Pre-order comments issued | 265 |  |  |  |  | 21.10.23 | 31.10.23 | 01.11.23 | 06.11.23 | 13.11.23 | [17 empty] | 25.07.24 | 11.08.24 | 10.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | Transformer | LE200357-E-WS-CW-PR-4002 | LE200357-E-WS-CW-PR-4002-D | Uttam Bharath | Pre-order comments issued | 274 |  |  |  |  | 21.10.23 | 26.10.23 | 04.11.23 | [11 empty] | T1 | [7 empty] | 25.07.24 | 11.08.24 | 10.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | DG Set | LE200357-E-WS-CW-PR-4003 | LE200357-E-WS-CW-PR-4003-A | Prime power | Sent to BU Operations | 45 |  |  |  |  | 17.05.24 | 18.05.24 | 21.05.24 | 29.05.24 | 10.06.24 | [6 empty] | 08.06.24 | 10.06.24 | 20.06.24 | t1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | DG Set | LE200357-E-WS-CW-PR-4003 | LE200357-E-WS-CW-PR-4003-B | Power Icad | Sent to BU Operations | 45 |  |  |  |  | 17.05.24 | 28.05.24 | 10.06.24 | [8 empty] | 08.06.24 | 10.06.24 | 20.06.24 | t1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | HT Switchgear | LE200357-E-WS-CW-PR-4005 | LE200357-E-WS-CW-PR-4005-A | Universal | Regret offer | PR Closed |  |  |  |  | 20.04.24 | 28.04.24 | 30.04.24 | [8 empty] | 04.05.24 | 06.05.24 | [12 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:47:16
Belgavi | Electrical | HT Switchgear | LE200357-E-WS-CW-PR-4005 | LE200357-E-WS-CW-PR-4005-B | Lotus | Sent to BU Operations | 45 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | 20.06.24 | t1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | HT Switchgear | LE200357-E-WS-CW-PR-4005 | LE200357-E-WS-CW-PR-4005-C | Sun Shine | Sent to BU Operations | 39 |  |  |  |  | 23.04.24 | 17.05.24 | 18.05.24 | [8 empty] | 23.05.24 | 23.05.24 | 26.06.24 | T1 | [7 empty] | 26.06.24 | 13.07.24 | 11.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | HT Soft Starters | LE200357-E-WS-CW-PR-4006 | LE200357-E-WS-CW-PR-4006-A | Lecon | Regret offer | PR Closed |  |  |  |  | 02.03.24 | 18.03.24 | 20.03.24 | [8 empty] | 23.03.24 | 24.04.24 | 24.05.24 | T1 | [7 empty] | 24.05.24 | 10.06.24 | 09.08.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | HT Soft Starters | LE200357-E-WS-CW-PR-4006 | LE200357-E-WS-CW-PR-4006-B | Jaya Shree | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 27.03.24 | 01.04.24 | 02.04.24 | 03.04.24 | [6 empty] | 07.05.24 | 10.05.24 | 24.05.24 | T1 | [7 empty] | 24.05.24 | 10.06.24 | 09.08.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | HT Capacitors | LE200357-E-WS-CW-PR-4007 | LE200357-E-WS-CW-PR-4007-A | Madhav Capacitors | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 31.03.24 | 10.04.24 | 23.04.24 | 24.04.24 | [6 empty] | 26.04.24 | 27.04.24 | 27.04.24 | T2 | [7 empty] | 27.04.24 | 14.05.24 | 13.07.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | HT Capacitors | LE200357-E-WS-CW-PR-4007 | LE200357-E-WS-CW-PR-4007-B | Lecon | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 27.02.24 | 28.02.24 | 08.03.24 | 20.03.24 | [6 empty] | 22.04.24 | 23.04.24 | 23.04.24 | T2 | 27.05.24 | Lecon | 27.05.24 | 04.06.24 |  |  |  | 23.04.24 | 10.05.24 | 09.07.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | HT Capacitors | LE200357-E-WS-CW-PR-4007 | LE200357-E-WS-CW-PR-4007-C | Shreem | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 26.02.24 | 19.03.24 | 26.04.24 | 29.04.24 | [6 empty] | 29.04.24 | 02.05.24 | 02.05.24 | T2 | [7 empty] | 02.05.24 | 19.05.24 | 18.07.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | HT CABLE TERMINATION KITS & LT CABLE LUGS AND GLANDS | LE200357-E-WS-CW-PR-4008 | LE200357-E-WS-CW-PR-4008-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [21 empty] | 24.07.24 | 10.08.24 | 09.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | HT CABLE TERMINATION KITS & LT CABLE LUGS AND GLANDS | LE200357-E-WS-CW-PR-4008 | LE200357-E-WS-CW-PR-4008-B | Govind Electricals | Pre-order technically cleared | 50 |  |  |  |  | 10.05.24 | 15.06.24 | 15.06.24 | [8 empty] | 15.06.24 | 15.06.24 | [9 empty] | 24.07.24 | 10.08.24 | 09.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:31
Belgavi | Electrical | LT Switchgear and Auxiliary Panels | LE200357-E-WS-CW-PR-4009 | LE200357-E-WS-CW-PR-4009-A | Lotus | Sent to BU Operations | 45 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | 20.06.24 | t1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | LT Switchgear and Auxiliary Panels | LE200357-E-WS-CW-PR-4009 | LE200357-E-WS-CW-PR-4009-B | Sunshine | Sent to BU Operations | 39 |  |  |  |  | 05.03.24 | 17.05.24 | 18.05.24 | 08.06.24 | [7 empty] | 08.06.24 | 08.06.24 | 26.06.24 | t1 | [7 empty] | 26.06.24 | 13.07.24 | 11.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | LT Switchgear and Auxiliary Panels | LE200357-E-WS-CW-PR-4009 | LE200357-E-WS-CW-PR-4009-C | SRCS | Sent to BU Operations | 39 |  |  |  |  | 05.03.24 | 20.06.24 | 26.06.24 | [8 empty] | 20.06.24 | 26.06.24 | 26.06.24 | t1 | [7 empty] | 26.06.24 | 13.07.24 | 11.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-A | Gemscab | Sent to BU Operations | 25 |  |  |  |  | 02.03.24 | 11.03.24 | 30.04.24 | 04.05.24 | 07.05.24 | [6 empty] | 10.05.24 | 13.05.24 | 10.07.24 | t1 | [7 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-B | Axelon | Sent to BU Operations | 25 |  |  |  |  | 02.03.24 | 02.05.24 | 07.05.24 | 08.05.24 | [7 empty] | 08.05.24 | 09.05.24 | 10.07.24 | t1 | [7 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-C | Vishal | Sent to BU Operations | 25 |  |  |  |  | 30.04.24 | 02.05.24 | 07.05.24 | 08.05.24 | [7 empty] | 08.05.24 | 09.05.24 | 10.07.24 | t1 | [7 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-D | Havells | Regret offer | PR Closed |  |  |  |  | 30.04.24 | [24 empty] | ananthakrishnan.krishnan@lntecc.com-22.05.2024-10:01:01
Belgavi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-E | KEI | Sent to BU Operations | 25 |  |  |  |  | 17.05.24 | 20.06.24 | 25.06.24 | 08.07.24 | [7 empty] | 08.07.24 | 08.07.24 | 10.07.24 | t1 | [7 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Cable Trays and Supports | LE200357-E-WS-CW-PR-4011 | LE200357-E-WS-CW-PR-4011-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-03.06.2024-15:03:28
Belgavi | Electrical | Cable Trays and Supports | LE200357-E-WS-CW-PR-4011 | LE200357-E-WS-CW-PR-4011-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 31.05.24 | [8 empty] | 06.06.24 | 06.06.24 | [9 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Earthing and Its Accessories | LE200357-E-WS-CW-PR-4013 | LE200357-E-WS-CW-PR-4013-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [21 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | Earthing and Its Accessories | LE200357-E-WS-CW-PR-4013 | LE200357-E-WS-CW-PR-4013-B | Govind Electricals | Pre-order technically cleared | 65 |  |  |  |  | 10.05.24 | 27.05.24 | 31.05.24 | [8 empty] | 31.05.24 | 31.05.24 | [9 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | NGR | LE200357-E-WS-CW-PR-4014 | LE200357-E-WS-CW-PR-4014-A | RSI switchgear | Sent to BU Operations | 47 |  |  |  |  | 17.05.24 | 14.06.24 | 17.06.24 | [8 empty] | 17.06.24 | 17.06.24 | 18.06.24 | t1 | [7 empty] | 18.06.24 | 05.07.24 | 03.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | NGR | LE200357-E-WS-CW-PR-4014 | LE200357-E-WS-CW-PR-4014-B | National Resistors | Sent to BU Operations | 47 |  |  |  |  | 17.05.24 | 04.06.24 | 08.06.24 | [8 empty] | 08.06.24 | 08.06.24 | 18.06.24 | t1 | [7 empty] | 18.06.24 | 05.07.24 | 03.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Electrical Safety Items | LE200357-E-WS-CW-PR-4015 | LE200357-E-WS-CW-PR-4015-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [21 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | Electrical Safety Items | LE200357-E-WS-CW-PR-4015 | LE200357-E-WS-CW-PR-4015-B | Govind Electricals | Pre-order technically cleared | 65 |  |  |  |  | 10.05.24 | 27.05.24 | 31.05.24 | [8 empty] | 31.05.24 | 31.05.24 | [9 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | LPBS | LE200357-E-WS-CW-PR-4016 | LE200357-E-WS-CW-PR-4016-A | Lotus | Sent to BU Operations | 45 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | 20.06.24 | t1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | LPBS | LE200357-E-WS-CW-PR-4016 | LE200357-E-WS-CW-PR-4016-B | Sunshine | Sent to BU Operations | 39 |  |  |  |  | 05.03.24 | 17.05.24 | 18.05.24 | [8 empty] | 08.06.24 | 08.06.24 | 26.06.24 | t1 | [7 empty] | 26.06.24 | 13.07.24 | 11.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | LPBS | LE200357-E-WS-CW-PR-4016 | LE200357-E-WS-CW-PR-4016-C | SRCS | Sent to BU Operations | 39 |  |  |  |  | 05.03.24 | 24.06.24 | 25.06.24 | [8 empty] | 24.06.24 | 24.06.24 | 26.06.24 | t1 | [7 empty] | 26.06.24 | 13.07.24 | 11.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Battery, Battery Charger and DCDB | LE200357-E-WS-CW-PR-4020 | LE200357-E-WS-CW-PR-4020-A | Liveline | Sent to BU Operations | 23 |  |  |  |  | 23.02.24 | 01.05.24 | 04.05.24 | 12.06.24 | 14.06.24 | [6 empty] | 14.06.24 | 14.06.24 | 12.07.24 | t2 | [7 empty] | 24.07.24 | 10.08.24 | 09.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Battery, Battery Charger and DCDB | LE200357-E-WS-CW-PR-4020 | LE200357-E-WS-CW-PR-4020-B | Voltech | Sent to BU Operations | 23 |  |  |  |  | 23.02.24 | 24.02.24 | 15.04.24 | 20.04.24 | 25.04.24 | [6 empty] | 07.05.24 | 15.05.24 | 12.07.24 | t2 | [7 empty] | 24.07.24 | 10.08.24 | 09.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Switchyard equipments | LE200357-E-WS-CW-PR-4021 | LE200357-E-WS-CW-PR-4021-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-03.06.2024-15:16:33
Belgavi | Electrical | Switchyard equipments | LE200357-E-WS-CW-PR-4021 | LE200357-E-WS-CW-PR-4021-B | Govind Electricals | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-03.06.2024-15:16:33
Belgavi | Electrical | Lighting Fixtures | LE200357-E-WS-CW-PR-4212 | LE200357-E-WS-CW-PR-4212-A | Monaj Trading | Awaiting pre-offer from vendor | 86 |  |  |  |  | 10.05.24 | [21 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Lighting Fixtures | LE200357-E-WS-CW-PR-4212 | LE200357-E-WS-CW-PR-4212-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | LDB | LE200357-E-WS-CW-PR-4218 | LE200357-E-WS-CW-PR-4218-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [21 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | LDB | LE200357-E-WS-CW-PR-4218 | LE200357-E-WS-CW-PR-4218-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Lighting Poles and Junction Boxes | LE200357-E-WS-CW-PR-4219 | LE200357-E-WS-CW-PR-4219-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [21 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | Lighting Poles and Junction Boxes | LE200357-E-WS-CW-PR-4219 | LE200357-E-WS-CW-PR-4219-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Belgavi | Electrical | Switchboards, Sockets and other accessories | LE200357-E-WS-CW-PR-4222 | LE200357-E-WS-CW-PR-4222-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [21 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:05:38
Belgavi | Electrical | Switchboards, Sockets and other accessories | LE200357-E-WS-CW-PR-4222 | LE200357-E-WS-CW-PR-4222-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:49:32
Boudh & Kandhamal | Process | Clariflocculator mechanism | LE21M985-P-WS-WT-PR-2202 | LE21M985-P-WS-WT-PR-2202-A | P&N Kulkarni | Post-order comments issued | 146 |  |  |  |  | 14.03.22 | 01.02.24 | 12.02.24 | [8 empty] | 11.03.24 | 11.03.24 | 11.03.24 | T1 | 01.02.24 | P&N Kulkarni | 01.02.24 | 11.03.24 | 25.06.24 |  |  |  |  | 01.04.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | Air Blower | LE21M985-P-WS-WT-PR-2203 | LE21M985-P-WS-WT-PR-2203-A | Everest | Post-order technically cleared | 104 |  |  |  |  | 14.03.22 | 19.01.24 | 12.02.24 | 22.02.24 | [7 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T1 | 19.01.24 | Everest | 19.01.24 | 12.02.24 | 26.04.24 | 22.04.24 |  |  |  | 19.03.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | Agitator | LE21M985-P-WS-WT-PR-2204 | LE21M985-P-WS-WT-PR-2204-A | Verito | Post-order technically cleared | 146 |  |  |  |  | 26.12.23 | 26.12.23 | 23.01.24 | [8 empty] | 11.03.24 | 11.03.24 | 11.03.24 | T1 | 26.12.23 | Verito | 26.12.23 | 23.01.24 | 11.03.24 | 11.03.24 |  |  |  | 24.02.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | WTP Sluice gates | LE21M985-P-WS-WT-PR-2205 | LE21M985-P-WS-WT-PR-2205-A | IVC | Post-order technically cleared | 17 |  |  |  |  | 19.01.24 | 19.01.24 | 12.02.24 | [8 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T1 | 19.01.24 | IVC | 19.01.24 | 12.02.24 | 18.06.24 | 18.07.24 |  |  |  | 19.03.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | Chlorination system | LE21M985-P-WS-WT-PR-2206 | LE21M985-P-WS-WT-PR-2206-A | Primo chloro | Post-order technically cleared | 53 |  |  |  |  | 19.01.24 | 19.01.24 | 12.02.24 | 12.06.24 | [7 empty] | 11.03.24 | 11.03.24 | 11.03.24 | T2 | 19.01.24 | Primo chloro | 19.01.24 | 12.02.24 | 12.04.24 | 12.06.24 |  |  |  | 19.03.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | Sludge thickener | LE21M985-P-WS-WT-PR-2207 | LE21M985-P-WS-WT-PR-2207-A | P&N Kulkarni | Post-order comments issued | 40 |  |  |  |  | 01.02.24 | 01.02.24 | 12.02.24 | 11.03.24 | 11.03.24 | [6 empty] | 17.04.24 | 17.04.24 | 17.04.24 | T1 | 01.02.24 | P&N Kulkarni | 01.02.24 | 11.03.24 | 26.04.24 | 25.06.24 |  |  |  | 01.04.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | Filter media | LE21M985-P-WS-WT-PR-2208 | LE21M985-P-WS-WT-PR-2208-A | vendor name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Centrifuge | LE21M985-P-WS-WT-PR-2209 | LE21M985-P-WS-WT-PR-2209-A | vendor name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Screw pumps | LE21M985-P-WS-WT-PR-2210 | LE21M985-P-WS-WT-PR-2210-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Backwash pump | LE21M985-P-WS-WT-PR-2211 | LE21M985-P-WS-WT-PR-2211-A | vendor name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Submersible pump | LE21M985-P-WS-WT-PR-2212 | LE21M985-P-WS-WT-PR-2212-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Electrical hoist | LE21M985-P-WS-WT-PR-2213 | LE21M985-P-WS-WT-PR-2213-A | Brady & Morris | Post-order technically cleared | 174 |  |  |  |  | 19.01.24 | 19.01.24 | 12.02.24 | [8 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T1 | 19.01.24 | Brady & Morris | 19.01.24 | 12.02.24 | 12.02.24 | 12.02.24 |  |  |  | 19.03.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | Manual chain pulley block | LE21M985-P-WS-WT-PR-2214 | LE21M985-P-WS-WT-PR-2214-A | Brady & Morris | Post-order technically cleared | 174 |  |  |  |  | 19.01.24 | 19.01.24 | 12.02.24 | [8 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T1 | 19.01.24 | Brady & Morris | 19.01.24 | 12.02.24 | 12.02.24 | 12.02.24 |  |  |  | 19.03.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | Dosing pump | LE21M985-P-WS-WT-PR-2215 | LE21M985-P-WS-WT-PR-2215-A | Verito | Post-order technically cleared | 158 |  |  |  |  | 19.01.24 | 19.01.24 | 12.02.24 | [8 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T1 | 19.01.24 | Verito | 19.01.24 | 12.02.24 | 28.02.24 | 28.02.24 |  |  |  | 19.03.24 | THENNARASU@lntecc.com-18.07.2024-16:54:01
Boudh & Kandhamal | Process | DWPE tank | LE21M985-P-WS-WT-PR-2216 | LE21M985-P-WS-WT-PR-2216-A | vendor name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | DWPE tank Agitators | LE21M985-P-WS-WT-PR-2217 | LE21M985-P-WS-WT-PR-2217-A | vendor name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Sampling pump | LE21M985-P-WS-WT-PR-2218 | LE21M985-P-WS-WT-PR-2218-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Submersible mixer | LE21M985-P-WS-WT-PR-2219 | LE21M985-P-WS-WT-PR-2219-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Dewatering pump | LE21M985-P-WS-WT-PR-2220 | LE21M985-P-WS-WT-PR-2220-A | vendor name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Dissolving tray | LE21M985-P-WS-WT-PR-2221 | LE21M985-P-WS-WT-PR-2221-A | vendor name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Trolley | LE21M985-P-WS-WT-PR-2222 | LE21M985-P-WS-WT-PR-2222-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Platform weighing machine | LE21M985-P-WS-WT-PR-2223 | LE21M985-P-WS-WT-PR-2223-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Service Water pump | LE21M985-P-WS-WT-PR-2224 | LE21M985-P-WS-WT-PR-2224-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | Lab Equipments | LE21M985-P-WS-WT-PR-2225 | LE21M985-P-WS-WT-PR-2225-A | vendor name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Process | PACL Unloading cum transfer pump | LE21M985-P-WS-WT-PR-2226 | LE21M985-P-WS-WT-PR-2226-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | THENNARASU@lntecc.com-29.06.2024-16:37:54
Boudh & Kandhamal | Mechanical | HSC Pump - CWPH & IBPS | LE21M985-M-WS-CW-PR-1503 | LE21M985-M-WS-CW-PR-1503-A | KBL | Regret offer | PR Closed | Not responded |  | karthikeyan.r@kbl.co.in |  | 18.03.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | HSC Pump - CWPH & IBPS | LE21M985-M-WS-CW-PR-1503 | LE21M985-M-WS-CW-PR-1503-B | WILO | Pre-order comments issued | 18 |  |  | manikkandan.pr@wilo.com |  | 18.03.24 | 27.04.24 | 27.05.24 | 20.06.24 | 17.07.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | HSC Pump - CWPH & IBPS | LE21M985-M-WS-CW-PR-1503 | LE21M985-M-WS-CW-PR-1503-C | WPIL | Pre-order comments issued | 18 |  |  | cmktg@wpil.co.in |  | 18.03.24 | 10.05.24 | 27.05.24 | 20.06.24 | 17.07.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1504 | LE21M985-M-WS-CW-PR-1504-A | avkindia | Sent to BU Operations | 25 |  | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1504 | LE21M985-M-WS-CW-PR-1504-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 09.07.24 | 26.07.24 | 24.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1504 | LE21M985-M-WS-CW-PR-1504-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1504 | LE21M985-M-WS-CW-PR-1504-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1504 | LE21M985-M-WS-CW-PR-1504-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | NRV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1505 | LE21M985-M-WS-CW-PR-1505-A | avkindia | Sent to BU Operations | 25 |  | +91 9176966455 | subhash@avkindia.com |  | 01.04.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | NRV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1505 | LE21M985-M-WS-CW-PR-1505-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 09.07.24 | 26.07.24 | 24.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | NRV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1505 | LE21M985-M-WS-CW-PR-1505-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | NRV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1505 | LE21M985-M-WS-CW-PR-1505-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | NRV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1505 | LE21M985-M-WS-CW-PR-1505-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | DJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1506 | LE21M985-M-WS-CW-PR-1506-A | avkindia | Regret offer | PR Closed | Regret | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | aknandy@lntecc.com-11.07.2024-18:38:17
Boudh & Kandhamal | Mechanical | DJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1506 | LE21M985-M-WS-CW-PR-1506-B | vag group | Regret offer | PR Closed | Regret |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [19 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | DJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1506 | LE21M985-M-WS-CW-PR-1506-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | DJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1506 | LE21M985-M-WS-CW-PR-1506-D | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | DJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1506 | LE21M985-M-WS-CW-PR-1506-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | AV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1507 | LE21M985-M-WS-CW-PR-1507-A | avkindia | Sent to BU Operations | 25 |  | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1507 | LE21M985-M-WS-CW-PR-1507-B | vag group | Pre-order technically rejected | PR Closed |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | [9 empty] | 09.07.24 | 26.07.24 | 24.09.24 | aknandy@lntecc.com-09.07.2024-18:53:00
Boudh & Kandhamal | Mechanical | AV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1507 | LE21M985-M-WS-CW-PR-1507-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1507 | LE21M985-M-WS-CW-PR-1507-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1507 | LE21M985-M-WS-CW-PR-1507-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | EOT Crane - CWPH & IBPS | LE21M985-M-WS-CW-PR-1509 | LE21M985-M-WS-CW-PR-1509-A | BRADYS | Awaiting pre-offer from vendor | 27 |  |  | srinivasan@bradys.in |  | 08.07.24 | [21 empty] | 14.08.24 | 31.08.24 | 30.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | EOT Crane - CWPH & IBPS | LE21M985-M-WS-CW-PR-1509 | LE21M985-M-WS-CW-PR-1509-B | JAPS | Regret offer | PR Closed | Not responded |  | sales.japs@gmail.com |  | 08.07.24 | [21 empty] | 14.08.24 | 31.08.24 | 30.10.24 | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | EOT Crane - CWPH & IBPS | LE21M985-M-WS-CW-PR-1509 | LE21M985-M-WS-CW-PR-1509-C | REVA | Awaiting pre-offer from vendor | 27 |  |  | mkt@revacranes.com |  | 08.07.24 | [21 empty] | 14.08.24 | 31.08.24 | 30.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | EOT Crane - CWPH & IBPS | LE21M985-M-WS-CW-PR-1509 | LE21M985-M-WS-CW-PR-1509-D | INDEF | Awaiting pre-offer from vendor | 27 |  |  | Mmkm@indef.com |  | 08.07.24 | [21 empty] | 14.08.24 | 31.08.24 | 30.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | BFV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1510 | LE21M985-M-WS-CW-PR-1510-A | avkindia | Sent to BU Operations | 25 |  | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | BFV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1510 | LE21M985-M-WS-CW-PR-1510-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 09.07.24 | 26.07.24 | 24.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | BFV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1510 | LE21M985-M-WS-CW-PR-1510-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | BFV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1510 | LE21M985-M-WS-CW-PR-1510-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | BFV - CWPH & IBPS | LE21M985-M-WS-CW-PR-1510 | LE21M985-M-WS-CW-PR-1510-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | Electric Hoist - CWPH & IBPS | LE21M985-M-WS-CW-PR-1511 | LE21M985-M-WS-CW-PR-1511-A | NA | Regret offer | PR Closed | NA |  |  |  | 08.07.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | Submersible Pump - CWPH & IBPS | LE21M985-M-WS-CW-PR-1512 | LE21M985-M-WS-CW-PR-1512-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | aknandy@lntecc.com-22.05.2024-20:14:20
Boudh & Kandhamal | Mechanical | Isolation Valve - Pipeline | LE21M985-M-WS-CW-PR-1513 | LE21M985-M-WS-CW-PR-1513-A | avkindia | Sent to BU Operations | 25 |  | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Isolation Valve - Pipeline | LE21M985-M-WS-CW-PR-1513 | LE21M985-M-WS-CW-PR-1513-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | 29.06.24 |  |  |  |  | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 09.07.24 | 26.07.24 | 24.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Isolation Valve - Pipeline | LE21M985-M-WS-CW-PR-1513 | LE21M985-M-WS-CW-PR-1513-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Isolation Valve - Pipeline | LE21M985-M-WS-CW-PR-1513 | LE21M985-M-WS-CW-PR-1513-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Isolation Valve - Pipeline | LE21M985-M-WS-CW-PR-1513 | LE21M985-M-WS-CW-PR-1513-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | AV - Pipeline | LE21M985-M-WS-CW-PR-1514 | LE21M985-M-WS-CW-PR-1514-A | avkindia | Sent to BU Operations | 25 |  | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - Pipeline | LE21M985-M-WS-CW-PR-1514 | LE21M985-M-WS-CW-PR-1514-B | vag group | Pre-order technically rejected | PR Closed |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | [9 empty] | 09.07.24 | 26.07.24 | 24.09.24 | aknandy@lntecc.com-09.07.2024-18:53:00
Boudh & Kandhamal | Mechanical | AV - Pipeline | LE21M985-M-WS-CW-PR-1514 | LE21M985-M-WS-CW-PR-1514-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - Pipeline | LE21M985-M-WS-CW-PR-1514 | LE21M985-M-WS-CW-PR-1514-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - Pipeline | LE21M985-M-WS-CW-PR-1514 | LE21M985-M-WS-CW-PR-1514-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | PRV - Pipeline | LE21M985-M-WS-CW-PR-1515 | LE21M985-M-WS-CW-PR-1515-A | avkindia | Regret offer | PR Closed | Regret | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | aknandy@lntecc.com-11.07.2024-18:38:17
Boudh & Kandhamal | Mechanical | PRV - Pipeline | LE21M985-M-WS-CW-PR-1515 | LE21M985-M-WS-CW-PR-1515-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 09.07.24 | 26.07.24 | 24.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | PRV - Pipeline | LE21M985-M-WS-CW-PR-1515 | LE21M985-M-WS-CW-PR-1515-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | PRV - Pipeline | LE21M985-M-WS-CW-PR-1515 | LE21M985-M-WS-CW-PR-1515-D | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | PRV - Pipeline | LE21M985-M-WS-CW-PR-1515 | LE21M985-M-WS-CW-PR-1515-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | FCV - Pipeline | LE21M985-M-WS-CW-PR-1516 | LE21M985-M-WS-CW-PR-1516-A | avkindia | Regret offer | PR Closed | Regret | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | aknandy@lntecc.com-11.07.2024-18:38:17
Boudh & Kandhamal | Mechanical | FCV - Pipeline | LE21M985-M-WS-CW-PR-1516 | LE21M985-M-WS-CW-PR-1516-B | vag group | Regret offer | PR Closed | Regret |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [19 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | FCV - Pipeline | LE21M985-M-WS-CW-PR-1516 | LE21M985-M-WS-CW-PR-1516-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | FCV - Pipeline | LE21M985-M-WS-CW-PR-1516 | LE21M985-M-WS-CW-PR-1516-D | ivc valves | Regret offer | PR Closed | Regret |  |  |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | FCV - Pipeline | LE21M985-M-WS-CW-PR-1516 | LE21M985-M-WS-CW-PR-1516-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | Sluice Gate - CWPH & IBPS | LE21M985-M-WS-CW-PR-1517 | LE21M985-M-WS-CW-PR-1517-A | Oriental Casting | Sent to BU Operations | 25 |  |  | orientalcastings@gmail.com |  | 22.04.24 | 02.05.24 | 27.05.24 | 12.06.24 | [7 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Sluice Gate - CWPH & IBPS | LE21M985-M-WS-CW-PR-1517 | LE21M985-M-WS-CW-PR-1517-B | JashIndia | Sent to BU Operations | 20 |  |  | abhijeet@jashindia.com |  | 22.04.24 | 15.07.24 | 15.07.24 | [8 empty] | 15.07.24 | 15.07.24 | 15.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Sluice Gate - CWPH & IBPS | LE21M985-M-WS-CW-PR-1517 | LE21M985-M-WS-CW-PR-1517-C | Fluid Control | Sent to BU Operations | 25 |  |  | sales@fluidcontrol.in |  | 22.04.24 | 26.04.24 | 27.05.24 | 12.06.24 | [7 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | ACV - Surge Protection Device | LE21M985-M-WS-CW-PR-1518 | LE21M985-M-WS-CW-PR-1518-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | aknandy@lntecc.com-22.05.2024-20:14:20
Boudh & Kandhamal | Mechanical | ZVV - Surge Protection Device | LE21M985-M-WS-CW-PR-1519 | LE21M985-M-WS-CW-PR-1519-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | aknandy@lntecc.com-22.05.2024-20:14:21
Boudh & Kandhamal | Mechanical | Surge Vessel - Surge Protection Device | LE21M985-M-WS-CW-PR-1520 | LE21M985-M-WS-CW-PR-1520-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | aknandy@lntecc.com-22.05.2024-20:14:21
Boudh & Kandhamal | Mechanical | Exhaust fan - Mech | LE21M985-M-WS-CW-PR-1521 | LE21M985-M-WS-CW-PR-1521-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | aknandy@lntecc.com-22.05.2024-20:14:21
Boudh & Kandhamal | Mechanical | EJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1522 | LE21M985-M-WS-CW-PR-1522-A | avkindia | Regret offer | PR Closed | Regret | +91 9176966455 | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | aknandy@lntecc.com-11.07.2024-18:38:17
Boudh & Kandhamal | Mechanical | EJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1522 | LE21M985-M-WS-CW-PR-1522-B | vag group | Regret offer | PR Closed | Regret |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [19 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | EJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1522 | LE21M985-M-WS-CW-PR-1522-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | EJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1522 | LE21M985-M-WS-CW-PR-1522-D | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | EJ - CWPH & IBPS | LE21M985-M-WS-CW-PR-1522 | LE21M985-M-WS-CW-PR-1522-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | VT Pump - Intake | LE21M985-M-WS-RW-PR-1501A | LE21M985-M-WS-RW-PR-1501A-A | KBL | Regret offer | PR Closed | Not responded |  | karthikeyan.r@kbl.co.in | 29.09.23 | 06.02.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:26:50
Boudh & Kandhamal | Mechanical | VT Pump - Intake | LE21M985-M-WS-RW-PR-1501A | LE21M985-M-WS-RW-PR-1501A-B | WILO | Sent to BU Operations | PR Closed |  |  | manikkandan.pr@wilo.com | 29.09.23 | 06.02.24 | 22.02.24 | 11.03.24 | 13.05.24 | 22.05.24 | [6 empty] | 22.05.24 | 20.05.24 | 12.06.24 | T1 | [7 empty] | 12.06.24 | 29.06.24 | 28.08.24 | aknandy@lntecc.com-11.07.2024-19:06:11
Boudh & Kandhamal | Mechanical | VT Pump - Intake | LE21M985-M-WS-RW-PR-1501A | LE21M985-M-WS-RW-PR-1501A-C | WPIL | Awaiting post-offer from vendor | 26 |  |  | cmktg@wpil.co.in | 29.09.23 | 06.02.24 | 19.03.24 | 04.04.24 | 22.04.24 | 12.05.24 | 27.05.24 | 10.06.24 |  |  |  |  | 27.05.24 | 27.05.24 | 12.06.24 | T2 | 09.07.24 | WPIL | [5 empty] | 12.06.24 | 29.06.24 | 28.08.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Sluice Gate - Intake | LE21M985-M-WS-RW-PR-1502A | LE21M985-M-WS-RW-PR-1502A-A | Fluid control | Sent to BU Operations | 102 |  | 6290671344 | sales@fluidcontrol.in | 29.09.23 | 17.02.24 | 19.02.24 | 13.03.24 | 15.03.24 | 29.03.24 | 06.04.24 | 24.04.24 |  |  |  |  | 24.04.24 | 06.04.24 | 24.04.24 | T1 | [7 empty] | 24.04.24 | 11.05.24 | 10.07.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Sluice Gate - Intake | LE21M985-M-WS-RW-PR-1502A | LE21M985-M-WS-RW-PR-1502A-B | JashIndia | Sent to BU Operations | 102 |  | 91-731-6732700 | abhijeet@jashindia.com | 29.09.23 | 17.02.24 | 27.03.24 | 29.03.24 | 18.04.24 | 18.04.24 | 18.04.24 | 24.04.24 |  |  |  |  | 24.04.24 | 18.04.24 | 24.04.24 | T1 | [7 empty] | 24.04.24 | 11.05.24 | 10.07.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | Sluice Gate - Intake | LE21M985-M-WS-RW-PR-1502A | LE21M985-M-WS-RW-PR-1502A-C | Orientalcastings | Sent to BU Operations | 102 |  |  | orientalcastings@gmail.com | 29.09.23 | 17.02.24 | 25.03.24 | 04.04.24 | 05.04.24 | 05.04.24 | 05.04.24 | 24.04.24 |  |  |  |  | 24.04.24 | 05.04.24 | 24.04.24 | T1 | [7 empty] | 24.04.24 | 11.05.24 | 10.07.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - Intake | LE21M985-M-WS-RW-PR-1504 | LE21M985-M-WS-RW-PR-1504-A | avkindia | Sent to BU Operations | 25 |  |  | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - Intake | LE21M985-M-WS-RW-PR-1504 | LE21M985-M-WS-RW-PR-1504-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 09.07.24 | 26.07.24 | 24.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - Intake | LE21M985-M-WS-RW-PR-1504 | LE21M985-M-WS-RW-PR-1504-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - Intake | LE21M985-M-WS-RW-PR-1504 | LE21M985-M-WS-RW-PR-1504-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | SLV - Intake | LE21M985-M-WS-RW-PR-1504 | LE21M985-M-WS-RW-PR-1504-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | NRV - Intake | LE21M985-M-WS-RW-PR-1505 | LE21M985-M-WS-RW-PR-1505-A | avkindia | Sent to BU Operations | 25 |  |  | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | NRV - Intake | LE21M985-M-WS-RW-PR-1505 | LE21M985-M-WS-RW-PR-1505-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 09.07.24 | 26.07.24 | 24.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | NRV - Intake | LE21M985-M-WS-RW-PR-1505 | LE21M985-M-WS-RW-PR-1505-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | NRV - Intake | LE21M985-M-WS-RW-PR-1505 | LE21M985-M-WS-RW-PR-1505-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | NRV - Intake | LE21M985-M-WS-RW-PR-1505 | LE21M985-M-WS-RW-PR-1505-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | DJ - Intake | LE21M985-M-WS-RW-PR-1506 | LE21M985-M-WS-RW-PR-1506-A | avkindia | Regret offer | PR Closed | Regret |  | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | aknandy@lntecc.com-11.07.2024-18:38:17
Boudh & Kandhamal | Mechanical | DJ - Intake | LE21M985-M-WS-RW-PR-1506 | LE21M985-M-WS-RW-PR-1506-B | vag group | Regret offer | PR Closed | Regret |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [19 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | DJ - Intake | LE21M985-M-WS-RW-PR-1506 | LE21M985-M-WS-RW-PR-1506-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | DJ - Intake | LE21M985-M-WS-RW-PR-1506 | LE21M985-M-WS-RW-PR-1506-D | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | DJ - Intake | LE21M985-M-WS-RW-PR-1506 | LE21M985-M-WS-RW-PR-1506-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | AV - Intake | LE21M985-M-WS-RW-PR-1507 | LE21M985-M-WS-RW-PR-1507-A | avkindia | Sent to BU Operations | 25 |  |  | subhash@avkindia.com |  | 22.03.24 | 04.06.24 | 09.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - Intake | LE21M985-M-WS-RW-PR-1507 | LE21M985-M-WS-RW-PR-1507-B | vag group | Pre-order technically rejected | PR Closed |  |  | s.deepkanti@vag-group.com |  | 22.03.24 | 08.04.24 | 09.05.24 | 31.05.24 | 13.06.24 | 20.06.24 | [5 empty] | 29.06.24 | 29.06.24 | [9 empty] | 09.07.24 | 26.07.24 | 24.09.24 | aknandy@lntecc.com-09.07.2024-18:53:00
Boudh & Kandhamal | Mechanical | AV - Intake | LE21M985-M-WS-RW-PR-1507 | LE21M985-M-WS-RW-PR-1507-C | R&D Multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 22.03.24 | 10.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - Intake | LE21M985-M-WS-RW-PR-1507 | LE21M985-M-WS-RW-PR-1507-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 22.03.24 | 11.05.24 | 23.05.24 | 27.05.24 | 13.06.24 | 24.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | AV - Intake | LE21M985-M-WS-RW-PR-1507 | LE21M985-M-WS-RW-PR-1507-E | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | EB - Intake | LE21M985-M-WS-RW-PR-1508 | LE21M985-M-WS-RW-PR-1508-A | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 22.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:44:58
Boudh & Kandhamal | Mechanical | EOT Crane - Intake | LE21M985-M-WS-RW-PR-1509 | LE21M985-M-WS-RW-PR-1509-A | INDEF | Awaiting pre-offer from vendor | 27 |  |  | Mmkm@indef.com |  | 08.07.24 | [21 empty] | 14.08.24 | 31.08.24 | 30.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | EOT Crane - Intake | LE21M985-M-WS-RW-PR-1509 | LE21M985-M-WS-RW-PR-1509-B | BRADYS | Awaiting pre-offer from vendor | 27 |  |  | srinivasan@bradys.in |  | 08.07.24 | [21 empty] | 14.08.24 | 31.08.24 | 30.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | EOT Crane - Intake | LE21M985-M-WS-RW-PR-1509 | LE21M985-M-WS-RW-PR-1509-C | REVA | Awaiting pre-offer from vendor | 27 |  |  | mkt@revacranes.com |  | 08.07.24 | [21 empty] | 14.08.24 | 31.08.24 | 30.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Mechanical | EOT Crane - Intake | LE21M985-M-WS-RW-PR-1509 | LE21M985-M-WS-RW-PR-1509-D | JAPS | Awaiting pre-offer from vendor | 27 |  |  | sales.japs@gmail.com |  | 08.07.24 | [21 empty] | 14.08.24 | 31.08.24 | 30.10.24 | deepak.sabnani@lntecc.com-18.07.2024-16:18:24
Boudh & Kandhamal | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE21M985-I-WS-WT-PR-5101 | LE21M985-I-WS-WT-PR-5101-A | H Guru | Sent to BU Operations | 73 |  |  | info@hgurusouth.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE21M985-I-WS-WT-PR-5101 | LE21M985-I-WS-WT-PR-5101-B | General gauges | Sent to BU Operations | 73 |  |  | gicchennai@general-gauges.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Pressure Switch | LE21M985-I-WS-WT-PR-5102 | LE21M985-I-WS-WT-PR-5102-A | H Guru | Sent to BU Operations | 73 |  |  | info@hgurusouth.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Pressure Switch | LE21M985-I-WS-WT-PR-5102 | LE21M985-I-WS-WT-PR-5102-B | General Gauges | Sent to BU Operations | 73 |  |  | gicchennai@general-gauges.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Pressure transmitter | LE21M985-I-WS-WT-PR-5103 | LE21M985-I-WS-WT-PR-5103-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Pressure transmitter | LE21M985-I-WS-WT-PR-5103 | LE21M985-I-WS-WT-PR-5103-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Pressure transmitter | LE21M985-I-WS-WT-PR-5103 | LE21M985-I-WS-WT-PR-5103-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Float & Board Level gauge | LE21M985-I-WS-WT-PR-5104 | LE21M985-I-WS-WT-PR-5104-A | SBEM | Sent to BU Operations | 30 |  |  | rajesh.p@sbem.co.in |  | 06.04.24 | 20.04.24 | 20.04.24 | 01.06.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:01
Boudh & Kandhamal | Instrumentation | Float & Board Level gauge | LE21M985-I-WS-WT-PR-5104 | LE21M985-I-WS-WT-PR-5104-B | Pune Techtrol | Sent to BU Operations | 30 |  |  | mktg2@punetechtrol.com |  | 06.04.24 | 20.04.24 | 14.05.24 | 01.06.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:01
Boudh & Kandhamal | Instrumentation | level switch - Conductivity type | LE21M985-I-WS-WT-PR-5105 | LE21M985-I-WS-WT-PR-5105-A | SBEM | Sent to BU Operations | 30 |  |  | rajesh.p@sbem.co.in |  | 06.04.24 | 20.04.24 | 20.04.24 | 01.06.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:01
Boudh & Kandhamal | Instrumentation | level switch - Conductivity type | LE21M985-I-WS-WT-PR-5105 | LE21M985-I-WS-WT-PR-5105-B | Pune Techtrol | Sent to BU Operations | 30 |  |  | mktg2@punetechtrol.com |  | 06.04.24 | 20.04.24 | 14.05.24 | 01.06.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:01
Boudh & Kandhamal | Instrumentation | Ultrasonic level Transmitter | LE21M985-I-WS-WT-PR-5106 | LE21M985-I-WS-WT-PR-5106-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Ultrasonic level Transmitter | LE21M985-I-WS-WT-PR-5106 | LE21M985-I-WS-WT-PR-5106-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Ultrasonic level Transmitter | LE21M985-I-WS-WT-PR-5106 | LE21M985-I-WS-WT-PR-5106-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Radar Level Transmitter | LE21M985-I-WS-WT-PR-5107 | LE21M985-I-WS-WT-PR-5107-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Radar Level Transmitter | LE21M985-I-WS-WT-PR-5107 | LE21M985-I-WS-WT-PR-5107-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Radar Level Transmitter | LE21M985-I-WS-WT-PR-5107 | LE21M985-I-WS-WT-PR-5107-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Loss of head transmitter | LE21M985-I-WS-WT-PR-5108 | LE21M985-I-WS-WT-PR-5108-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Loss of head transmitter | LE21M985-I-WS-WT-PR-5108 | LE21M985-I-WS-WT-PR-5108-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Loss of head transmitter | LE21M985-I-WS-WT-PR-5108 | LE21M985-I-WS-WT-PR-5108-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Rate for flow transmitter | LE21M985-I-WS-WT-PR-5109 | LE21M985-I-WS-WT-PR-5109-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Rate for flow transmitter | LE21M985-I-WS-WT-PR-5109 | LE21M985-I-WS-WT-PR-5109-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Rate for flow transmitter | LE21M985-I-WS-WT-PR-5109 | LE21M985-I-WS-WT-PR-5109-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Bypass Rotameter | LE21M985-I-WS-WT-PR-5110 | LE21M985-I-WS-WT-PR-5110-A | Scientific device | Pre-order comments issued | 13 |  |  | info@scientificdevices.org |  | 09.07.24 | 17.07.24 | 22.07.24 | [19 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:27:49
Boudh & Kandhamal | Instrumentation | Bypass Rotameter | LE21M985-I-WS-WT-PR-5110 | LE21M985-I-WS-WT-PR-5110-B | Eureka | Pre-order comments issued | 13 |  |  | chennaioffice@eurekaflow.com |  | 09.07.24 | 17.07.24 | 22.07.24 | [19 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:27:49
Boudh & Kandhamal | Instrumentation | Electromagnectic flow meter | LE21M985-I-WS-WT-PR-5111 | LE21M985-I-WS-WT-PR-5111-A | E&H | Sent to BU Operations | PR Closed |  |  | ramkumar.m@endress.com |  | 15.03.24 | 26.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T2 | [7 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:30:53
Boudh & Kandhamal | Instrumentation | Electromagnectic flow meter | LE21M985-I-WS-WT-PR-5111 | LE21M985-I-WS-WT-PR-5111-B | Krohne marshall | Sent to BU Operations | PR Closed |  |  | dilibanr@forbesmarshall.com |  | 15.03.24 | 25.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T3 | [7 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:30:53
Boudh & Kandhamal | Instrumentation | Electromagnectic flow meter | LE21M985-I-WS-WT-PR-5111 | LE21M985-I-WS-WT-PR-5111-C | Siemens | Awaiting post-offer from vendor | 13 |  |  | keerthi.guruswamy.ext@siemens.com |  | 15.03.24 | 24.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T1 | 22.07.24 | Siemens | [5 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:30:53
Boudh & Kandhamal | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M985-I-WS-WT-PR-5112 | LE21M985-I-WS-WT-PR-5112-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M985-I-WS-WT-PR-5112 | LE21M985-I-WS-WT-PR-5112-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M985-I-WS-WT-PR-5112 | LE21M985-I-WS-WT-PR-5112-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | Battery Operated Flow meter | LE21M985-I-WS-WT-PR-5113 | LE21M985-I-WS-WT-PR-5113-A | ABB | Pre-order comments issued | 13 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 01.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 15.07.24 | 22.07.24 | [15 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:27:49
Boudh & Kandhamal | Instrumentation | Battery Operated Flow meter | LE21M985-I-WS-WT-PR-5113 | LE21M985-I-WS-WT-PR-5113-B | Siemens | Pre-order comments issued | 13 |  |  | keerthi.guruswamy.ext@siemens.com |  | 06.04.24 | 26.04.24 | 30.05.24 | 07.06.24 | 15.06.24 | 15.07.24 | 22.07.24 | [15 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:27:49
Boudh & Kandhamal | Instrumentation | pH Meter | LE21M985-I-WS-WT-PR-5114 | LE21M985-I-WS-WT-PR-5114-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | pH Meter | LE21M985-I-WS-WT-PR-5114 | LE21M985-I-WS-WT-PR-5114-B | E&H | Sent to BU Operations | 17 |  |  | ramkumar.m@endress.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | pH Meter | LE21M985-I-WS-WT-PR-5114 | LE21M985-I-WS-WT-PR-5114-C | ABB | Sent to BU Operations | 17 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | Turbidity meter | LE21M985-I-WS-WT-PR-5115 | LE21M985-I-WS-WT-PR-5115-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | Turbidity meter | LE21M985-I-WS-WT-PR-5115 | LE21M985-I-WS-WT-PR-5115-B | E&H | Sent to BU Operations | 17 |  |  | ramkumar.m@endress.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | Turbidity meter | LE21M985-I-WS-WT-PR-5115 | LE21M985-I-WS-WT-PR-5115-C | ABB | Sent to BU Operations | 17 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | Residual Chlorine Analyzer | LE21M985-I-WS-WT-PR-5116 | LE21M985-I-WS-WT-PR-5116-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | Residual Chlorine Analyzer | LE21M985-I-WS-WT-PR-5116 | LE21M985-I-WS-WT-PR-5116-B | E&H | Sent to BU Operations | 17 |  |  | ramkumar.m@endress.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | Residual Chlorine Analyzer | LE21M985-I-WS-WT-PR-5116 | LE21M985-I-WS-WT-PR-5116-C | ABB | Sent to BU Operations | 17 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:28:40
Boudh & Kandhamal | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M985-I-WS-WT-PR-5117 | LE21M985-I-WS-WT-PR-5117-A | Schneider | Awaiting pre-offer from vendor | 30 |  |  | rushyendhar.repalli@se.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M985-I-WS-WT-PR-5117 | LE21M985-I-WS-WT-PR-5117-B | Honeywell | Awaiting pre-offer from vendor | 30 |  |  | Srinivasan.Venkateswaran@Honeywell.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:05
Boudh & Kandhamal | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M985-I-WS-WT-PR-5117 | LE21M985-I-WS-WT-PR-5117-C | siemens | Awaiting pre-offer from vendor | 30 |  |  | jeyanth.j@siemens.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:11:01
Boudh & Kandhamal | Instrumentation | instrumentation Control & signal Cables | LE21M985-I-WS-WT-PR-5118 | LE21M985-I-WS-WT-PR-5118-A | Delton | Sent to BU Operations | 24 |  |  | jus@deltoncables.com |  | 03.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-15.07.2024-10:04:34
Boudh & Kandhamal | Instrumentation | instrumentation Control & signal Cables | LE21M985-I-WS-WT-PR-5118 | LE21M985-I-WS-WT-PR-5118-B | Cords | Sent to BU Operations | 24 |  |  | tendering@cordscable.com |  | 03.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-15.07.2024-10:04:34
Boudh & Kandhamal | Instrumentation | instrumentation Control & signal Cables | LE21M985-I-WS-WT-PR-5118 | LE21M985-I-WS-WT-PR-5118-C | Thermocables | Sent to BU Operations | 24 |  |  | chennai@thermopads.com |  | 03.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-15.07.2024-10:04:34
Boudh & Kandhamal | Instrumentation | UPS | LE21M985-I-WS-WT-PR-5119 | LE21M985-I-WS-WT-PR-5119-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.09.24 | 17.10.24 | 16.12.24 | SURENDHAR@lntecc.com-02.07.2024-14:28:20
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-A | Voltech | Pre-order technically rejected | PR Closed | not as per approved make, offer has been rejected |  |  | 17.02.23 | 12.10.23 | 05.10.23 | 06.11.23 | [19 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:49:33
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-B | Voltamp | Regret offer | PR Closed | No Response |  | sasik_vtlchn@voltamptransformers.com | 17.02.23 | 27.03.24 | 05.10.23 | 06.11.23 | [19 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:49:33
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-C | CGL | Regret offer | PR Closed | No response |  | Ramesh.Ram@cgglobal.com |  | 26.03.24 | [21 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:49:33
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-D | Kirloskar | Regret offer | PR Closed | No response |  | aditya.ksr@kirloskarelectric.com |  | 27.03.24 | 9.5.24 | 18.5.24 | [19 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-10.07.2024-10:12:04
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-E | VOLTECH | Pre-order pending with EDRC | 17 |  |  | adalarasan.r@voltechgroup.com |  | 11.06.24 | 3.7.24 | 5.7.24 | 18.7.24 | [18 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:43
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-F | Power Star | Pre-order pending with EDRC | 23 |  |  | sailaja@powerstarelectric.net |  | 13.6.24 | 5.7.24 | 5.7.24 | 12.7.24 | [18 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:43
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-G | Toshiba | Regret offer | PR Closed | Not in their manufacturing range |  | marketing@toshiba-ttdi.com |  | 14.6.24 | [21 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:49:33
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-H | TBEA | Pre-order pending with EDRC | 23 |  |  |  |  | 2.7.24 | 12.7.24 | [20 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:43
Boudh & Kandhamal | Electrical | Transformer | LE21M985-E-WS-WT-PR-4103 | LE21M985-E-WS-WT-PR-4103-I | PETE | Regret offer | PR Closed | Regret offer mail received on 10.7.24 |  |  |  | 9.7.24 | [24 empty] | karthik.ajithkumar@lntecc.com-11.07.2024-17:23:47
Boudh & Kandhamal | Electrical | HT Panel | LE21M985-E-WS-WT-PR-4104 | LE21M985-E-WS-WT-PR-4104-A | UPE | Pre-order pending with EDRC | 26 |  |  |  |  | 2.7.24 | 9.7.24 | [20 empty] | 22.7.24 | 08.08.24 | 07.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:43
Boudh & Kandhamal | Electrical | HT Panel | LE21M985-E-WS-WT-PR-4104 | LE21M985-E-WS-WT-PR-4104-B | HTS | Pre-order pending with EDRC | 29 |  |  |  |  | 2.7.24 | 6.7.24 | [20 empty] | 22.7.24 | 08.08.24 | 07.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:43
Boudh & Kandhamal | Electrical | HT Panel | LE21M985-E-WS-WT-PR-4104 | LE21M985-E-WS-WT-PR-4104-C | Symatic South | Pre-order pending with EDRC | 18 |  |  | Vinay.a@siemens.com |  | 4.7.24 | 17.7.24 | [20 empty] | 22.7.24 | 08.08.24 | 07.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:43
Boudh & Kandhamal | Electrical | HT Panel | LE21M985-E-WS-WT-PR-4104 | LE21M985-E-WS-WT-PR-4104-D | Popular | Pre-order pending with EDRC | 12 |  |  | lkrishnamoorthi@popularswitchgears.co.in |  | 11.7.24 | 11.7.24 | 16.4.24 | 23.7.24 | [19 empty] | 08.08.24 | 07.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:43
Boudh & Kandhamal | Electrical | LT panels | LE21M985-E-WS-WT-PR-4107 | LE21M985-E-WS-WT-PR-4107-A | EAP | Pre-order technically rejected | PR Closed | not as per approved make, offer has been rejected |  |  | 03.03.23 | 10.11.23 | 09.10.23 | 30.12.23 | 27.2.24 | [18 empty] | 22.7.24 | 08.08.24 | 07.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:49:34
Boudh & Kandhamal | Electrical | LT Panels | LE21M985-E-WS-WT-PR-4107 | LE21M985-E-WS-WT-PR-4107-B | SRCS | Pre-order technically rejected | PR Closed | not as per approved make, offer has been rejected |  |  | 03.03.23 | 10.11.23 | 5.10.23 | 30.12.23 | 25.1.24 | [18 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:49:34
Boudh & Kandhamal | Electrical | LT Panels | LE21M985-E-WS-WT-PR-4107 | LE21M985-E-WS-WT-PR-4107-C | UPE | Pre-order technically rejected | PR Closed | not as per approved make, offer has been rejected |  |  | 03.03.23 | 10.11.23 | 18.8.23 | 30.12.23 | [19 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:49:34
Boudh & Kandhamal | Electrical | LT Panels | LE21M985-E-WS-WT-PR-4107 | LE21M985-E-WS-WT-PR-4107-D | SRCS | Pre-order pending with EDRC | 78 | pump not finalaized |  | ashok@ragavendracontrol.com | 03.03.23 | 08.04.24 | 18.5.24 | [20 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | LT Panels | LE21M985-E-WS-WT-PR-4107 | LE21M985-E-WS-WT-PR-4107-E | EAP | Pre-order pending with EDRC | 93 | pump not finalaized |  | sales@eapindia.com | 03.03.23 | 08.04.24 | 16.4.24 | 29.4.24 | 3.5.24 | [18 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | LT Panels | LE21M985-E-WS-WT-PR-4107 | LE21M985-E-WS-WT-PR-4107-F | UPE | Pre-order pending with EDRC | 27 | pump not finalaized |  | deepak@upe.co.in | 03.03.23 | 18.04.24 | 26.04.24 | 7.5.24 | 8.7.24 | [18 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | Power and Control Cable | LE21M985-E-WS-WT-PR-4110 | LE21M985-E-WS-WT-PR-4110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 6.8.24 | 23.08.24 | 22.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:49:34
Boudh & Kandhamal | Electrical | Cable Tray | LE21M985-E-WS-WT-PR-4111 | LE21M985-E-WS-WT-PR-4111-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | [7 empty] | 6.8.24 | 23.08.24 | 22.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | Lugs & Glands | LE21M985-E-WS-WT-PR-4112 | LE21M985-E-WS-WT-PR-4112-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | [7 empty] | 6.8.24 | 23.08.24 | 22.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | HT Termination Kit | LE21M985-E-WS-WT-PR-4112A | LE21M985-E-WS-WT-PR-4112A-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | [7 empty] | 6.8.24 | 23.08.24 | 22.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | LPBS | LE21M985-E-WS-WT-PR-4113 | LE21M985-E-WS-WT-PR-4113-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | [7 empty] | 6.8.24 | 23.08.24 | 22.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | Earthing & Lightning Material | LE21M985-E-WS-WT-PR-4114 | LE21M985-E-WS-WT-PR-4114-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | [7 empty] | 6.8.24 | 23.08.24 | 22.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | Lighting Fixtures | LE21M985-E-WS-WT-PR-4115 | LE21M985-E-WS-WT-PR-4115-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | [7 empty] | 8.8.24 | 25.08.24 | 24.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | Lighting Materials & accessories | LE21M985-E-WS-WT-PR-4115B | LE21M985-E-WS-WT-PR-4115B-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | [7 empty] | 8.8.24 | 25.08.24 | 24.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | LDB | LE21M985-E-WS-WT-PR-4115C | LE21M985-E-WS-WT-PR-4115C-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | [7 empty] | 8.8.24 | 25.08.24 | 24.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | DG Set | LE21M985-E-WS-WT-PR-4118 | LE21M985-E-WS-WT-PR-4118-A | Goel | Regret offer | PR Closed | No Response |  | marketing@goelpower.in | 03.03.23 | 28.11.23 | 05.10.23 | 03.01.24 | [19 empty] | 22.8.24 | 08.09.24 | 07.11.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:49:55
Boudh & Kandhamal | Electrical | DG Set | LE21M985-E-WS-WT-PR-4118 | LE21M985-E-WS-WT-PR-4118-B | Jackson | Pre-order technically cleared | 18 |  |  | Shashank.Gupta@Jakson.Com | 03.03.23 | 28.11.23 | 5.10.23 | 3.1.24 | 29.3.24 | 24.4.24 | 10.5.24 | 17.7.24 |  |  |  |  | 10.5.24 | 17.7.24 | [9 empty] | 22.8.24 | 08.09.24 | 07.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | DG Set | LE21M985-E-WS-WT-PR-4118 | LE21M985-E-WS-WT-PR-4118-C | Gainwell | Pre-order technically cleared | 17 |  |  | aftab.ali@gainwellindia.com | 03.03.23 | 28.11.23 | 5.10.23 | 30.12.23 | 29.3.24 | 24.4.24 | 30.4.24 | 17.5.24 | 18.7.24 |  |  |  | 17.5.24 | 18.7.24 | [9 empty] | 22.8.24 | 08.09.24 | 07.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
Boudh & Kandhamal | Electrical | DG Set | LE21M985-E-WS-WT-PR-4118 | LE21M985-E-WS-WT-PR-4118-D | IEC | Pre-order pending with EDRC | 27 |  |  | niraj.sharma@iecgensets.com | 03.03.23 | 28.11.23 | 7.10.23 | 30.12.23 | 8.7.24 | [18 empty] | 22.8.24 | 08.09.24 | 07.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:48:44
BWSSB 25MLD STP | Process | PR for After Cooler feed pump | BWSSPIII/26/BOM/STP/TAL/PR/PR/2296 | BWSSPIII/26/BOM/STP/TAL/PR/PR/2296-A |  | Enquiry yet to float | NA | Same will be released upon blower vendor finalization and receipt of after cooler inputs. | [28 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Dosing tank filling pumps | BWSSPIII/26/BOM/STP/TAL/PR/PR/2297 | BWSSPIII/26/BOM/STP/TAL/PR/PR/2297-A | Positive metering | Regret offer | PR Closed | Sent for site procurement based on vendor discussion as direct site procurement of the pump will be cheaper |  |  | 08.02.24 | 08.02.24 | 11.02.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Dosing tank filling pumps | BWSSPIII/26/BOM/STP/TAL/PR/PR/2297 | BWSSPIII/26/BOM/STP/TAL/PR/PR/2297-B | KSB | Regret offer | PR Closed | Sent for site procurement based on vendor discussion as direct site procurement of the pump will be cheaper |  |  | 08.02.24 | 08.02.24 | [24 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Dosing tank filling pumps | BWSSPIII/26/BOM/STP/TAL/PR/PR/2297 | BWSSPIII/26/BOM/STP/TAL/PR/PR/2297-C | Kishor pumps | Regret offer | PR Closed | Sent for site procurement based on vendor discussion as direct site procurement of the pump will be cheaper |  |  | 08.02.24 | 08.02.24 | [24 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Sludge conveyor & Hopper | BWSSPIII/26/BOM/STP/TAL/PR/PR/2298 | BWSSPIII/26/BOM/STP/TAL/PR/PR/2298-A | Aqseptance | Regret offer | PR Closed |  |  |  | 05.02.24 | 05.02.24 | 08.02.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Sludge conveyor & Hopper | BWSSPIII/26/BOM/STP/TAL/PR/PR/2298 | BWSSPIII/26/BOM/STP/TAL/PR/PR/2298-B | Huber | Regret offer | PR Closed |  |  |  | 05.02.24 | 05.02.24 | [24 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Sludge conveyor & Hopper | BWSSPIII/26/BOM/STP/TAL/PR/PR/2298 | BWSSPIII/26/BOM/STP/TAL/PR/PR/2298-C | JASH | Sent to BU Operations | 59 |  |  |  | 05.02.24 | 09.05.24 | 24.05.24 | 27.04.24 | 04.06.24 | 04.06.24 | [6 empty] | 05.06.24 | 06.06.24 | 06.06.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Dosing tank filling pumps | BWSSPIII/26/BOM/STP/VAR/PR/PR/2297 | BWSSPIII/26/BOM/STP/VAR/PR/PR/2297-D | Xylem | Regret offer | PR Closed | Sent for site procurement based on vendor discussion as direct site procurement of the pump will be cheaper |  |  | 18.03.24 | 18.03.24 | [24 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Mechanical Bar Screens | BWSSPIII/26/MAH/STP/VAR/PR/PR/2271 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2271-A | Aqseptance | Sent to BU Operations | 109 |  |  |  | 25.01.24 | 25.01.24 | 29.01.24 | 11.03.24 | 18.03.24 | [7 empty] | 13.03.24 | 27.03.24 | 17.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Mechanical Bar Screens | BWSSPIII/26/MAH/STP/VAR/PR/PR/2271 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2271-B | HUBER | Sent to BU Operations | 109 |  |  |  | 25.01.24 | 25.01.24 | 22.03.24 | 26.03.24 | [8 empty] | 10.04.24 | 17.04.24 | 17.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Mechanical Bar Screens | BWSSPIII/26/MAH/STP/VAR/PR/PR/2271 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2271-C | JASH | Sent to BU Operations | 109 |  |  |  | 25.01.24 | 25.01.24 | 05.02.24 | 11.03.24 | [8 empty] | 12.03.24 | 02.04.24 | 17.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Vortex Grit Mechanism | BWSSPIII/26/MAH/STP/VAR/PR/PR/2272 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2272-A | S&L | Regret offer | PR Closed |  |  |  | 24.01.24 | 24.01.24 | 25.01.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Vortex Grit Mechanism | BWSSPIII/26/MAH/STP/VAR/PR/PR/2272 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2272-B | Ovivo | Sent to BU Operations | 109 |  |  |  | 24.01.24 | 24.01.24 | 01.02.24 | 05.03.24 | 19.03.24 | [7 empty] | 12.03.24 | 27.03.24 | 17.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Vortex Grit Mechanism | BWSSPIII/26/MAH/STP/VAR/PR/PR/2272 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2272-C | Huber | Sent to BU Operations | 109 |  |  |  | 24.01.24 | 24.01.24 | 22.02.24 | 05.03.24 | 22.03.24 | 28.03.24 | 02.04.24 | [5 empty] | 12.03.24 | 02.04.24 | 17.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Vortex Grit Mechanism | BWSSPIII/26/MAH/STP/VAR/PR/PR/2272 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2272-D | Estragua | Sent to BU Operations | 109 |  |  |  | 13.03.24 | 13.03.24 | 21.03.24 | 01.04.24 | 04.04.24 | [7 empty] | 11.04.24 | 16.04.24 | 17.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Air Blowers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2273 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2273-A | Usha Neuros | Sent to BU Operations | 95 |  |  |  | 25.01.24 | 25.01.24 | 01.02.24 | 23.02.24 | 16.03.24 |  | 01.02.24 |  | 16.03.24 | 24.04.24 |  |  | 26.04.24 | 30.04.24 | 01.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Air Blowers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2273 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2273-B | Turbomax | Sent to BU Operations | 95 |  |  |  | 14.02.24 | 14.02.24 | 14.03.24 | 26.03.24 | 08.04.24 | 08.04.24 | 11.04.24 | 24.04.24 |  |  |  |  | 26.04.24 | 30.04.24 | 01.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Air Blowers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2273 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2273-C | Turbowin | Sent to BU Operations | 95 |  |  |  | 14.02.24 | 14.02.24 | 17.03.24 | 26.03.24 | 05.04.24 | 24.04.24 | [6 empty] | 26.04.24 | 30.04.24 | 01.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Air Blowers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2273 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2273-D | Aerzen | Regret offer | PR Closed |  |  |  | 14.02.24 | 14.02.24 | 21.02.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Fine Bubble Diffusers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2274 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2274-A | SSI | Sent to BU Operations | 66 | In Q2 Target |  |  | 02.02.24 | 02.02.24 | 22.02.24 | 21.03.24 | 22.03.24 | 08.05.24 | 21.05.24 | 21.05.24 | 23.05.24 |  |  |  | 30.05.24 | 30.05.24 | 30.05.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Fine Bubble Diffusers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2274 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2274-B | EDI | Sent to BU Operations | 66 | In Q2 Target |  | pallavi.gavandgave@wastewater.com | 02.02.24 | 02.02.24 | 21.02.24 | 21.03.24 | 23.05.24 | [7 empty] | 30.05.24 | 30.05.24 | 30.05.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Fine Bubble Diffusers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2274 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2274-C | OTT Titan | Sent to BU Operations | 66 | Vendor not meeting the technical requirements |  |  | 02.02.24 | 02.02.24 | 07.02.24 | 21.03.24 | [8 empty] | 30.05.24 | 30.05.24 | 30.05.24 | TR | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for submersible pumps (Treated water, Plant water, Dilution water) | BWSSPIII/26/MAH/STP/VAR/PR/PR/2275 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2275-A | KSB | Regret offer | PR Closed | No response from Vendor |  |  | 14.02.24 | 27.05.24 | [24 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for submersible pumps (Treated water, Plant water, Dilution water) | BWSSPIII/26/MAH/STP/VAR/PR/PR/2275 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2275-B | Kishor pumps | Sent to BU Operations | 48 | In Q2 Target |  |  | 14.02.24 | 27.05.24 | 30.05.24 | 31.05.24 | 11.06.24 | 11.06.24 | [6 empty] | 13.06.24 | 15.06.24 | 17.06.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for submersible pumps (Treated water, Plant water, Dilution water) | BWSSPIII/26/MAH/STP/VAR/PR/PR/2275 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2275-C | Ebara | Regret offer | PR Closed | No response from Vendor |  |  | 07.03.24 | 27.05.24 | 29.04.24 | 21.05.24 | [22 empty] | gokul.devaraj@lntecc.com-11.06.2024-16:12:45
BWSSB 25MLD STP | Process | PR for submersible pumps - Drain pump | BWSSPIII/26/MAH/STP/VAR/PR/PR/2276 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2276-A | KSB | Regret offer | PR Closed | No response from Vendor |  |  | 14.02.24 | 27.05.24 | [24 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for submersible pumps - Drain pump | BWSSPIII/26/MAH/STP/VAR/PR/PR/2276 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2276-B | Kishor pumps | Sent to BU Operations | 48 | In Q2 Target |  |  | 14.02.24 | 27.05.24 | 30.05.24 | 31.05.24 | 11.06.24 | 11.06.24 | [6 empty] | 13.06.24 | 15.06.24 | 17.06.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for submersible pumps - Drain pump | BWSSPIII/26/MAH/STP/VAR/PR/PR/2276 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2276-C | Ebara | Regret offer | PR Closed | No response from Vendor |  |  | 07.03.24 | 27.05.24 | 29.04.24 | 21.05.24 | [22 empty] | gokul.devaraj@lntecc.com-11.06.2024-16:12:45
BWSSB 25MLD STP | Process | PR for Horizontal centrifugal pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2277 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2277-A | KSB | Sent to BU Operations | 100 |  |  |  | 06.02.24 | 06.02.24 | 23.02.24 | 27.03.24 | 30.03.24 | 11.04.24 | 18.04.24 |  | 22.04.24 |  |  |  | 25.04.24 | 26.04.24 | 26.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Horizontal centrifugal pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2277 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2277-B | KBL | Regret offer | PR Closed |  |  |  | 06.02.24 | 06.02.24 | 11.03.24 | [11 empty] | 26.04.24 | [11 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Horizontal centrifugal pumps - RAS | BWSSPIII/26/MAH/STP/VAR/PR/PR/2277 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2277-C | XYLEM | Sent to BU Operations | 100 |  |  |  | 06.02.24 | 06.02.24 | 23.04.24 | 24.04.24 | [8 empty] | 25.04.24 | 26.04.24 | 26.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for Horizontal centrifugal pumps - RAS | BWSSPIII/26/MAH/STP/VAR/PR/PR/2277 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2277-D | Ebara | Regret offer | PR Closed |  |  |  | 18.03.24 | 18.03.24 | 26.03.24 | [11 empty] | 26.04.24 | [11 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for MLR pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278-A | WPIL | Sent to BU Operations | 88 |  |  |  | 30.01.24 | 30.01.24 | 02.03.24 | 02.04.24 | 18.04.24 | 23.04.24 | [6 empty] | 26.04.24 | 03.05.24 | 08.05.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for MLR pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278-B | Sulzer | Sent to BU Operations | 88 |  |  |  | 30.01.24 | 30.01.24 | 08.04.24 | 11.04.24 | 17.04.24 | 24.04.24 | [6 empty] | 26.04.24 | 30.04.24 | 08.05.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for MLR pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278-C | KSB | Sent to BU Operations | 88 |  |  |  | 30.01.24 | 30.01.24 | 09.02.24 | 26.03.24 | 20.04.24 | 23.04.24 | [6 empty] | 26.04.24 | 04.05.24 | 08.05.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for MLR pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278-D | Xylem | Sent to BU Operations | 88 | Long delay and No support in document submission and discussions. Hence rejected |  |  | 18.03.24 | 18.03.24 | 24.04.24 | 24.04.24 | [8 empty] | 08.05.24 | 08.05.24 | 08.05.24 | REJECT | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:20
BWSSB 25MLD STP | Process | PR for MLR pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2278-E | Ebara | Regret offer | PR Closed |  |  |  | 18.03.24 | 18.03.24 | 11.03.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Submersible mixers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2279 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2279-A | Geofluid | Regret offer | PR Closed |  |  |  | 08.02.24 | 08.02.24 | [24 empty] | gokul.devaraj@lntecc.com-11.06.2024-16:14:36
BWSSB 25MLD STP | Process | PR for Submersible mixers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2279 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2279-B | Grundfos | Regret offer | PR Closed | No response from vendor for a long time |  |  | 08.02.24 | 08.02.24 | [24 empty] | gokul.devaraj@lntecc.com-11.06.2024-16:14:36
BWSSB 25MLD STP | Process | PR for Submersible mixers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2279 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2279-C | Xylem | Sent to BU Operations | 35 | In Q2 Target |  |  | 08.02.24 | 08.02.24 | 02.04.24 | 09.05.24 | 22.05.24 | 06.06.24 | 29.06.24 | [5 empty] | 28.06.24 | 29.06.24 | 30.06.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-01.07.2024-09:56:47
BWSSB 25MLD STP | Process | PR for Submersible mixers | BWSSPIII/26/MAH/STP/VAR/PR/PR/2279 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2279-D | Sulzer | Sent to BU Operations | 35 | In Q2 Target |  |  | 18.02.24 | 18.02.24 | 04.04.24 | 09.05.24 | 23.05.24 | 23.05.24 | 31.05.24 | 01.06.24 | 07.06.24 | 10.06.24 |  |  | 28.06.24 | 29.06.24 | 30.06.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-01.07.2024-09:56:47
BWSSB 25MLD STP | Process | PR for Secondary clarifier | BWSSPIII/26/MAH/STP/VAR/PR/PR/2280 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2280-A | FFP | Sent to BU Operations | 117 |  |  |  | 17.01.24 | 17.01.24 | 12.03.24 | 12.03.24 | 13.03.24 | 13.03.24 | 20.03.24 | 29.03.24 | 29.03.24 |  |  |  | 13.03.24 | 08.04.24 | 09.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Secondary clarifier | BWSSPIII/26/MAH/STP/VAR/PR/PR/2280 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2280-B | SHIVPAD | Sent to BU Operations | 117 |  |  |  | 17.01.24 | 17.01.24 | 20.02.24 | 02.03.24 | 19.03.24 | [7 empty] | 13.03.24 | 08.04.24 | 09.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Secondary clarifier | BWSSPIII/26/MAH/STP/VAR/PR/PR/2280 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2280-C | TRIVENI | Sent to BU Operations | 117 |  |  |  | 17.01.24 | 17.01.24 | 20.02.24 | 26.02.24 | 04.04.24 | 04.04.24 | 05.04.24 | [5 empty] | 07.03.24 | 08.04.24 | 09.04.24 | T3 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Secondary clarifier | BWSSPIII/26/MAH/STP/VAR/PR/PR/2280 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2280-D | VOLTAS | Sent to BU Operations | 117 |  |  |  | 17.01.24 | 17.01.24 | 12.03.24 | 18.03.24 | 21.03.24 | 21.03.24 | 26.03.24 | 27.03.24 | 02.04.24 |  |  |  | 21.03.24 | 08.04.24 | 09.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Disc filter | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281-A | Huber | Sent to BU Operations | 102 |  |  |  | 25.01.24 | 25.01.24 | 12.03.24 | 03.04.24 | 10.04.24 | 22.04.24 | [6 empty] | 22.04.24 | 23.04.24 | 24.04.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Disc filter | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281-B | Nordic | Sent to BU Operations | 102 |  |  |  | 25.01.24 | 25.01.24 | 06.02.24 | 03.03.24 | 20.03.24 | 20.03.24 | 18.04.24 | 22.04.24 | 24.04.24 |  |  |  | 05.04.24 | 23.04.24 | 24.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Disc filter | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281-C | Estragua | Sent to BU Operations | 102 |  |  |  | 25.01.24 | 25.01.24 | 20.02.24 | 22.02.24 | 15.03.24 | 16.03.24 | 04.04.24 |  | 12.04.24 | 12.04.24 | 23.04.24 |  | 18.04.24 | 23.04.24 | 24.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Disc filter | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281-D | Hydrotech | Regret offer | PR Closed |  |  |  | 25.01.24 | 25.01.24 | 14.03.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Disc filter | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2281-E | Jash | Regret offer | PR Closed |  |  |  | 25.01.24 | 25.01.24 | 14.03.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Chlorination system | BWSSPIII/26/MAH/STP/VAR/PR/PR/2282 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2282-A | Evaquoa | Sent to BU Operations | 102 |  |  |  | 25.01.24 | 25.01.24 | 22.02.24 | 14.03.24 | 20.03.24 | [7 empty] | 18.04.24 | 23.04.24 | 24.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Chlorination system | BWSSPIII/26/MAH/STP/VAR/PR/PR/2282 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2282-B | Zion | Sent to BU Operations | 102 |  |  |  | 25.01.24 | 25.01.24 | 16.02.24 | 14.03.24 | 08.04.24 | 22.04.24 | 24.04.24 | [5 empty] | 18.04.24 | 24.04.24 | 24.04.24 | T | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Chlorination system | BWSSPIII/26/MAH/STP/VAR/PR/PR/2282 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2282-C | Chlorotech | Sent to BU Operations | 102 |  |  |  | 25.01.24 | 25.01.24 | 29.01.24 | 14.03.24 | 03.04.24 | [7 empty] | 18.04.24 | 23.04.24 | 24.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Sluice Gates | BWSSPIII/26/MAH/STP/VAR/PR/PR/2283 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2283-A | DVPL | Sent to BU Operations | 60 | In Q2 Target |  |  | 16.02.24 | 09.05.24 | 23.05.24 | 27.05.24 | 03.06.24 | [7 empty] | 29.05.24 | 03.06.24 | 05.06.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Sluice Gates | BWSSPIII/26/MAH/STP/VAR/PR/PR/2283 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2283-B | YASWANT | Sent to BU Operations | 60 | No response from vendor upon multiple remainders. Hence rejected |  |  | 16.02.24 | 09.05.24 | 24.05.24 | 27.05.24 | [8 empty] | 05.06.24 | 05.06.24 | 05.06.24 | Technically Rejected | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Sluice Gates | BWSSPIII/26/MAH/STP/VAR/PR/PR/2283 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2283-C | JASH | Sent to BU Operations | 60 | In Q2 Target |  |  | 16.02.24 | 16.02.24 | 26.02.24 | 20.05.24 | [8 empty] | 29.05.24 | 04.06.24 | 05.06.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dewatering Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284-A | Positive metering | Regret offer | PR Closed | In Q2 Target |  |  | 08.02.24 | 08.02.24 | [21 empty] | 31.12.24 | 17.01.25 | 18.03.25 | gokul.devaraj@lntecc.com-27.05.2024-17:12:44
BWSSB 25MLD STP | Process | PR for Dewatering Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284-B | KSB | Regret offer | PR Closed | No response from Vendor |  |  | 08.02.24 | 27.05.24 | [21 empty] | 31.12.24 | 17.01.25 | 18.03.25 | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dewatering Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284-C | Kishor pumps | Sent to BU Operations | 48 | In Q2 Target |  |  | 08.02.24 | 27.05.24 | 30.05.24 | 31.05.24 | 11.06.24 | 11.06.24 | [6 empty] | 13.06.24 | 15.06.24 | 17.06.24 | TC | [7 empty] | 31.12.24 | 17.01.25 | 18.03.25 | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dewatering Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284-D | WPIL | Regret offer | PR Closed | In Q2 Target |  |  | 18.03.24 | 18.03.24 | [21 empty] | 31.12.24 | 17.01.25 | 18.03.25 | gokul.devaraj@lntecc.com-27.05.2024-17:12:44
BWSSB 25MLD STP | Process | PR for Dewatering Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2284-E | Ebara | Regret offer | PR Closed | No response from Vendor |  |  | 18.03.24 | 27.05.24 | [21 empty] | 31.12.24 | 17.01.25 | 18.03.25 | gokul.devaraj@lntecc.com-11.06.2024-16:12:45
BWSSB 25MLD STP | Process | PR for centrifuge Feed Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285-A | Rotomac | Sent to BU Operations | 81 |  |  |  | 07.02.24 | 07.02.24 | 12.02.24 | 02.03.24 | 04.03.24 | [7 empty] | 09.05.24 | 15.05.24 | 15.05.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for centrifuge Feed Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285-B | Positive metering | Sent to BU Operations | 81 |  |  |  | 07.02.24 | 07.02.24 | 21.02.24 | 02.03.24 | 08.03.24 | [7 empty] | 09.05.24 | 15.05.24 | 15.05.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for centrifuge Feed Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285-C | CIRCOR | Sent to BU Operations | 81 |  |  |  | 06.03.24 | 06.03.24 | 08.03.24 | 13.03.24 | 27.03.24 | [7 empty] | 09.05.24 | 10.05.24 | 15.05.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for centrifuge Feed Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285-D | Neztch | Sent to BU Operations | 81 |  |  |  | 06.03.24 | 06.03.24 | 01.04.24 | 03.04.24 | 15.04.24 | [7 empty] | 09.05.24 | 15.05.24 | 15.05.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for centrifuge Feed Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2285-E | ROTO PUMPS | Sent to BU Operations | 80 | No response from vendor for a long time. Hence rejected |  |  |  | 29.03.24 | 10.04.24 | 07.05.24 | [8 empty] | 16.05.24 | 16.05.24 | 16.05.24 | REJECT | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dewatering centrifuge | BWSSPIII/26/MAH/STP/VAR/PR/PR/2286 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2286-A | Alfalaval | Sent to BU Operations | 115 |  |  |  | 24.01.24 | 24.01.24 | 12.03.24 | 18.03.24 | 02.04.24 | 02.04.24 | 03.04.24 | 03.04.24 | 04.04.24 |  |  |  | 18.03.24 | 04.04.24 | 11.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dewatering centrifuge | BWSSPIII/26/MAH/STP/VAR/PR/PR/2286 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2286-B | Hiller | Sent to BU Operations | 115 | Cannot meet the power requirements. Hence rejected technically |  |  | 24.01.24 | 24.01.24 | 05.03.24 | 11.03.24 | 26.03.24 | [7 empty] | 11.04.24 | 11.04.24 | 11.04.24 | REJECT | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dewatering centrifuge | BWSSPIII/26/MAH/STP/VAR/PR/PR/2286 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2286-C | Gea Westfalia | Sent to BU Operations | 115 |  |  |  | 24.01.24 | 24.01.24 | 01.02.24 | 23.02.24 | 05.03.24 | [7 empty] | 06.03.24 | 18.03.24 | 11.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Auto polymer dosing system | BWSSPIII/26/MAH/STP/VAR/PR/PR/2287 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2287-A | MILTON ROY | Sent to BU Operations | 106 |  |  |  | 05.02.24 | 05.02.24 | 03.04.24 | 05.04.24 | [8 empty] | 15.04.24 | 19.04.24 | 20.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Auto polymer dosing system | BWSSPIII/26/MAH/STP/VAR/PR/PR/2287 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2287-B | PSG DOVER | Sent to BU Operations | 106 |  |  |  | 05.02.24 | 05.02.24 | 04.04.24 | 05.04.24 | [8 empty] | 17.04.24 | 19.04.24 | 20.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Auto polymer dosing system | BWSSPIII/26/MAH/STP/VAR/PR/PR/2287 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2287-C | POSITIVE METERING | Sent to BU Operations | 106 |  |  |  | 05.02.24 | 05.02.24 | 12.02.24 | 05.04.24 | [8 empty] | 15.04.24 | 19.04.24 | 20.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dosing Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2288 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2288-A | MILTON ROY | Sent to BU Operations | 103 |  |  |  | 31.01.24 | 31.01.24 | 12.02.24 | 03.04.24 | [8 empty] | 20.04.24 | 23.04.24 | 23.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dosing Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2288 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2288-B | PSG DOVER | Sent to BU Operations | 103 |  |  |  | 31.01.24 | 31.01.24 | 05.03.24 | 03.04.24 | [8 empty] | 20.04.24 | 23.04.24 | 23.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dosing Pumps | BWSSPIII/26/MAH/STP/VAR/PR/PR/2288 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2288-C | POSITIVE METERING | Sent to BU Operations | 103 | Major deviation from contract specs. Hence rejected technically. |  |  | 31.01.24 | 31.01.24 | 25.02.24 | 03.04.24 | [8 empty] | 20.04.24 | 22.04.24 | 23.04.24 | REJECT | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dosing Tanks | BWSSPIII/26/MAH/STP/VAR/PR/PR/2289 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2289-A | POSITIVE METERING | Sent to BU Operations | 66 |  |  |  | 31.01.24 | 31.01.24 | 02.02.24 | 04.04.24 | 05.04.24 | [7 empty] | 18.04.24 | 18.04.24 | 30.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dosing Tanks | BWSSPIII/26/MAH/STP/VAR/PR/PR/2289 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2289-B | PSG DOVER | Regret offer | PR Closed |  |  |  | 31.01.24 | 31.01.24 | [24 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Dosing Tank | BWSSPIII/26/MAH/STP/VAR/PR/PR/2289 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2289-C | EPP COMPOSITE | Sent to BU Operations | 66 |  |  |  |  | 18.04.24 | 08.05.24 | 17.05.24 | 24.05.24 | [7 empty] | 30.05.24 | 30.05.24 | 30.05.24 | TR | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Dosing Tank | BWSSPIII/26/MAH/STP/VAR/PR/PR/2289 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2289-D | FFP | Sent to BU Operations | 66 |  |  |  |  | 18.04.24 | 27.05.24 | 28.05.24 | 30.05.24 | [7 empty] | 30.05.24 | 30.05.24 | 30.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Agitator | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290-A | MILTON ROY | Sent to BU Operations | 95 |  |  |  | 31.01.24 | 31.01.24 | 15.02.24 | 03.04.24 | 09.04.24 | 22.04.24 | [6 empty] | 26.04.24 | 29.04.24 | 01.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Agitator | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290-B | PSG DOVER | Regret offer | PR Closed |  |  |  | 31.01.24 | 31.01.24 | [24 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Agitator | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290-C | POSITIVE METERING | Sent to BU Operations | 95 |  |  |  | 31.01.24 | 31.01.24 | 14.02.24 | 03.04.24 | 11.04.24 | 22.04.24 | [6 empty] | 26.04.24 | 29.04.24 | 01.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Agitator | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290-D | FFP | Sent to BU Operations | 95 |  |  |  | 18.03.24 | 18.03.24 | 21.03.24 | 03.04.24 | 18.04.24 | 19.04.24 | 23.04.24 | [5 empty] | 26.04.24 | 29.04.24 | 01.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Agitator | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290-E | Remiprocess | Regret offer | PR Closed |  |  |  | 18.03.24 | 18.03.24 | 02.04.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Agitator | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2290-F | Ceecon Process | Sent to BU Operations | 95 |  |  |  | 18.03.24 | 18.03.24 | 13.04.24 | 15.04.24 | [8 empty] | 26.04.24 | 29.04.24 | 01.05.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Scum skimmer | BWSSPIII/26/MAH/STP/VAR/PR/PR/2291 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2291-A | FFP | Sent to BU Operations | 83 |  |  |  | 02.02.24 | 02.02.24 | 20.03.24 | 20.03.24 | [8 empty] | 10.05.24 | 13.05.24 | 13.05.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Scum skimmer | BWSSPIII/26/MAH/STP/VAR/PR/PR/2291 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2291-B | K pack | Sent to BU Operations | 83 |  |  |  | 02.02.24 | 02.02.24 | 13.03.24 | 13.03.24 | 02.04.24 | 05.04.24 | [6 empty] | 10.05.24 | 13.05.24 | 13.05.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Laboratory Equipments | BWSSPIII/26/MAH/STP/VAR/PR/PR/2292 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2292-A | Savant | Regret offer | PR Closed | Planned for order finalization and procurement along with 4&5 MLD STP supply |  |  | 30.01.24 | 30.01.24 | 23.02.24 | [23 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Laboratory Equipments | BWSSPIII/26/MAH/STP/VAR/PR/PR/2292 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2292-B | Spark | Regret offer | PR Closed | Planned for order finalization and procurement along with 4&5 MLD STP supply |  |  | 30.01.24 | 30.01.24 | [24 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Laboratory Equipments | BWSSPIII/26/MAH/STP/VAR/PR/PR/2292 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2292-C | Labard | Regret offer | PR Closed | Planned for order finalization and procurement along with 4&5 MLD STP supply |  |  | 30.01.24 | 30.01.24 | [24 empty] | gokul.devaraj@lntecc.com-21.05.2024-09:26:16
BWSSB 25MLD STP | Process | PR for Scum pump | BWSSPIII/26/MAH/STP/VAR/PR/PR/2294 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2294-A | Kishor pumps | Sent to BU Operations | 48 | In Q2 Target |  |  | 08.02.24 | 27.05.24 | 30.05.24 | 31.05.24 | 11.06.24 | 11.06.24 | [6 empty] | 13.06.24 | 15.06.24 | 17.06.24 | TC | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Scum pump | BWSSPIII/26/MAH/STP/VAR/PR/PR/2294 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2294-B | KSB | Regret offer | PR Closed | No response from Vendor |  |  | 08.02.24 | 27.05.24 | [24 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Scum pump | BWSSPIII/26/MAH/STP/VAR/PR/PR/2294 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2294-C | Xylem | Regret offer | PR Closed | In Q2 Target |  |  | 06.03.24 | 06.03.24 | [24 empty] | gokul.devaraj@lntecc.com-27.05.2024-17:12:44
BWSSB 25MLD STP | Process | PR for Scum pump | BWSSPIII/26/MAH/STP/VAR/PR/PR/2294 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2294-D | Ebara | Regret offer | PR Closed | No response from Vendor |  |  | 18.03.24 | 27.05.24 | 29.04.24 | 21.05.24 | [22 empty] | gokul.devaraj@lntecc.com-11.06.2024-16:12:45
BWSSB 25MLD STP | Process | PR for Sludge Thickener Mechanism | BWSSPIII/26/MAH/STP/VAR/PR/PR/2295 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2295-A | FFP | Sent to BU Operations | 116 |  |  |  | 17.01.24 | 17.01.24 | 21.02.24 | 28.02.24 | 13.03.24 | 19.03.24 | [6 empty] | 13.03.24 | 09.04.24 | 10.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Sludge Thickener Mechanism | BWSSPIII/26/MAH/STP/VAR/PR/PR/2295 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2295-B | SHIVPAD | Sent to BU Operations | 116 |  |  |  | 17.01.24 | 17.01.24 | 20.01.24 | 28.02.24 | 20.03.24 | [7 empty] | 13.03.24 | 09.04.24 | 10.04.24 | T1 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Sludge Thickener Mechanism | BWSSPIII/26/MAH/STP/VAR/PR/PR/2295 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2295-C | TRIVENI | Sent to BU Operations | 116 |  |  |  | 17.01.24 | 17.01.24 | 20.02.24 | 28.02.24 | 06.03.24 | 29.03.24 | 04.04.24 | [5 empty] | 07.03.24 | 09.04.24 | 10.04.24 | T3 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Process | PR for Sludge Thickener Mechanism | BWSSPIII/26/MAH/STP/VAR/PR/PR/2295 | BWSSPIII/26/MAH/STP/VAR/PR/PR/2295-D | VOLTAS | Sent to BU Operations | 116 |  |  |  | 17.01.24 | 17.01.24 | 12.03.24 | 18.03.24 | 21.03.24 | 21.03.24 | 26.03.24 | 27.03.24 | 28.03.24 | 02.04.24 | 02.04.24 |  | 21.03.24 | 09.04.24 | 10.04.24 | T2 | [10 empty] | gokul.devaraj@lntecc.com-17.06.2024-10:16:21
BWSSB 25MLD STP | Mechanical | PR of Sluice Gates for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1751 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1751-A | Yashwanth | Regret offer | PR Closed |  |  | info@superseal.in |  | 25.03.24 | 26.04.24 | 29.04.24 | 30.04.24 | 02.05.24 | [8 empty] | 17.05.24 | [11 empty] | d-saranya@lntecc.com-24.05.2024-10:15:07
BWSSB 25MLD STP | Mechanical | PR of Sluice Gates for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1751 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1751-B | DVPL | Pre-order technically cleared | 79 |  |  | chennai@dvpl.co.in |  | 25.03.24 | 27.03.24 | 28.03.24 | 05.04.24 | 06.04.24 | [6 empty] | 06.04.24 | 06.04.24 | 17.05.24 | [11 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Sluice Gates for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1751 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1751-C | Jash | Pre-order technically cleared | 79 |  |  | abhijeet@jashindia.com |  | 25.03.24 | 16.04.24 | 18.04.24 | 20.04.24 | 26.04.24 | 03.05.24 | 03.05.24 |  |  |  |  | 03.05.24 | 03.05.24 | 17.05.24 | [11 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Manual Coarse Screens(J-Type) for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1752 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1752-A | Jash | Pre-order technically cleared | 81 |  |  | abhijeet@jashindia.com |  | 25.03.24 | 04.04.24 | 05.04.24 | 29.04.24 | 30.04.24 | 03.05.24 | 03.05.24 |  |  |  |  | 03.05.24 | 03.05.24 | 15.05.24 | [11 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Manual Coarse Screens(J-Type) for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1752 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1752-B | Aqseptance | Pre-order technically cleared | 110 |  |  | meet.shah@johnsonscreens.com |  | 25.03.24 | 28.03.24 | 03.04.24 | 05.04.24 | 05.04.24 | 10.04.24 | 11.04.24 | 12.04.24 |  |  |  | 16.04.24 | 16.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Manual Coarse Screens(J-Type) for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1752 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1752-C | Huber | Regret offer | PR Closed |  |  | sandeep.somankop@atehuber.com |  | 25.03.24 | 22.04.24 | 25.04.24 | 06.05.24 | [21 empty] | nayana.r@lntecc.com-17.05.2024-09:33:34
BWSSB 25MLD STP | Mechanical | PR of Mechanical Coarse Screens for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1753 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1753-A | Jash | Pre-order technically cleared | 81 |  |  | abhijeet@jashindia.com |  | 25.03.24 | 04.04.24 | 05.04.24 | 29.04.24 | 30.04.24 | 03.05.24 | 03.05.24 |  |  |  |  | 03.05.24 | 03.05.24 | 15.05.24 | [11 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Mechanical Coarse Screens for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1753 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1753-B | Aqseptance | Pre-order technically cleared | 110 |  |  | meet.shah@johnsonscreens.com |  | 25.03.24 | 28.03.24 | 03.04.24 | 05.04.24 | 05.04.24 | 10.04.24 | 11.04.24 | 12.04.24 |  |  |  | 16.04.24 | 16.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Mechanical Coarse Screens for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1753 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1753-C | Huber | Regret offer | PR Closed |  |  | sandeep.somankop@atehuber.com |  | 25.03.24 | 22.04.24 | 25.04.24 | 06.05.24 | [21 empty] | nayana.r@lntecc.com-17.05.2024-09:33:34
BWSSB 25MLD STP | Mechanical | PR of Lifting Arrangements for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1754 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1754-A | Reva | Pre-order technically cleared | 88 |  |  | mkt@revacranes.com |  | 25.03.24 | 12.04.24 | 12.04.24 | 13.04.24 | 17.04.24 | 23.04.24 | 25.04.24 | 02.05.24 | 02.05.24 | 08.05.24 | 08.05.24 | 08.05.24 | 08.05.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Lifting Arrangements for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1754 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1754-B | Westwork | Pre-order technically cleared | 64 |  |  | skwestworksalescorporation@gmail.com |  | 07.05.24 | 14.05.24 | 17.05.24 | 26.05.24 | 01.06.24 | [6 empty] | 01.06.24 | 01.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Lifting Arrangements for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1754 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1754-C | Eddy | Pre-order technically cleared | 86 |  |  | insujan@eddycranes.com |  | 25.03.24 | 30.03.24 | 02.04.24 | 12.04.24 | 12.04.24 | 12.04.24 | 16.04.24 | 03.05.24 | 03.05.24 | 06.05.24 | 06.05.24 | 10.05.24 | 10.05.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Submersible Pumps for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1755 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1755-A | Kishor | Pre-order technically cleared | 73 |  |  | p.dixon@kishorpumps.com |  | 05.04.24 | 19.04.24 | 20.04.24 | 21.05.24 | [7 empty] | 23.05.24 | 23.05.24 | 23.05.24 | [11 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Submersible Pumps for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1755 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1755-B | Ebbara | Regret offer | PR Closed |  |  | sales42anala@gmail.com> |  | 05.04.24 | 15.04.24 | 18.04.24 | 02.05.24 | [21 empty] | nayana.r@lntecc.com-17.05.2024-09:33:34
BWSSB 25MLD STP | Mechanical | PR of Submersible Pumps for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1755 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1755-C | KSB | Regret offer | PR Closed |  |  | ashwin.sridhar@ksb.com |  | 16.04.24 | 26.04.24 | 30.04.24 | [22 empty] | d-saranya@lntecc.com-24.05.2024-10:24:20
BWSSB 25MLD STP | Mechanical | PR for KGV at 25 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1756 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1756-A | AVK | Pre-order technically cleared | 55 |  |  | subhash@avkindia.com |  | 25.03.24 | 25.04.24 | 29.04.24 | 04.05.24 | 07.05.24 | 20.05.24 | 28.05.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR for KGV at 25 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1756 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1756-B | KBL | Pre-order technically cleared | 68 |  |  | karthikeyan.r@kbl.co.in |  | 25.03.24 | 22.04.24 | 26.04.24 | 06.05.24 | 10.05.24 | 17.05.24 | 28.05.24 |  |  |  |  | 28.05.24 | 28.05.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR for KGV at 25 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1756 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1756-C | DVPL | Pre-order technically cleared | 120 |  |  | chennai@dvpl.co.in |  | 25.03.24 | 27.03.24 | 28.03.24 | 05.04.24 | [7 empty] | 06.04.24 | 06.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR for NRV at 25 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1757 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1757-A | AVK | Pre-order technically cleared | 55 |  |  | subhash@avkindia.com |  | 25.03.24 | 25.04.24 | 29.04.24 | 04.05.24 | 07.05.24 | 20.05.24 | 28.05.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR for NRV at 25 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1757 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1757-B | KBL | Pre-order technically cleared | 68 |  |  | karthikeyan.r@kbl.co.in |  | 25.03.24 | 22.04.24 | 26.04.24 | 06.05.24 | 10.05.24 | 17.05.24 | 28.05.24 |  |  |  |  | 28.05.24 | 28.05.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR for NRV at 25 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1757 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1757-C | DVPL | Pre-order technically cleared | 120 |  |  | chennai@dvpl.co.in |  | 25.03.24 | 27.03.24 | 28.03.24 | 05.04.24 | [7 empty] | 06.04.24 | 06.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Non-Metallic (NRV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1758 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1758-A | DVPL | Regret offer | PR Closed |  |  | chennai@dvpl.co.in |  | 09.04.24 | [24 empty] | nayana.r@lntecc.com-17.05.2024-09:33:34
BWSSB 25MLD STP | Mechanical | PR of Non-Metallic (NRV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1758 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1758-B | AVK | Pre-order technically cleared | 55 |  |  | subhash@avkindia.com |  | 09.04.24 | 25.04.24 | 29.04.24 | 04.05.24 | 07.05.24 | 20.05.24 | 28.05.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Non-Metallic (NRV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1758 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1758-C | KBL | Regret offer | PR Closed |  |  | karthikeyan.r@kbl.co.in |  | 09.04.24 | [24 empty] | nayana.r@lntecc.com-17.05.2024-09:33:34
BWSSB 25MLD STP | Mechanical | PR of Non-Metallic (Ball Valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1759 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1759-A | Brilliant Enterprise | Pre-order pending with EDRC | 16 |  |  | brilliant160@gmail.com |  | 09.07.24 | 19.07.24 | [23 empty] | d-saranya@lntecc.com-20.07.2024-11:12:16
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves (Sluice valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1760 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1760-A | DVPL | Pre-order technically cleared | 100 |  |  | chennai@dvpl.co.in |  | 09.04.24 | 12.04.24 | 17.04.24 | 18.04.24 | [7 empty] | 26.04.24 | 26.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves (Sluice valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1760 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1760-B | AVK | Pre-order technically cleared | 55 |  |  | subhash@avkindia.com |  | 09.04.24 | 25.04.24 | 29.04.24 | 04.05.24 | 07.05.24 | 20.05.24 | 28.05.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves (Sluice valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1760 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1760-C | KBL | Pre-order technically cleared | 68 |  |  | karthikeyan.r@kbl.co.in |  | 09.04.24 | 22.04.24 | 26.04.24 | 06.05.24 | 10.05.24 | 17.05.24 | 28.05.24 |  |  |  |  | 28.05.24 | 28.05.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves ( KGV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1761 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1761-A | DVPL | Pre-order technically cleared | 100 |  |  | chennai@dvpl.co.in |  | 09.04.24 | 12.04.24 | 17.04.24 | 18.04.24 | [7 empty] | 26.04.24 | 26.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves ( KGV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1761 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1761-B | AVK | Pre-order technically cleared | 55 |  |  | subhash@avkindia.com |  | 09.04.24 | 25.04.24 | 29.04.24 | 04.05.24 | 07.05.24 | 20.05.24 | 28.05.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves ( KGV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1761 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1761-C | KBL | Pre-order technically cleared | 68 |  |  | karthikeyan.r@kbl.co.in |  | 09.04.24 | 22.04.24 | 26.04.24 | 06.05.24 | 10.05.24 | 17.05.24 | 28.05.24 |  |  |  |  | 28.05.24 | 28.05.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves (BFV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1762 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1762-A | DVPL | Pre-order technically cleared | 100 |  |  | chennai@dvpl.co.in |  | 09.04.24 | 12.04.24 | 17.04.24 | 18.04.24 | [7 empty] | 26.04.24 | 26.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves (BFV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1762 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1762-B | AVK | Pre-order technically cleared | 55 |  |  | subhash@avkindia.com |  | 09.04.24 | 25.04.24 | 29.04.24 | 04.05.24 | 07.05.24 | 20.05.24 | 28.05.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves (BFV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1762 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1762-C | KBL | Pre-order technically rejected | PR Closed |  |  | karthikeyan.r@kbl.co.in |  | 09.04.24 | 22.04.24 | 26.04.24 | 06.05.24 | 10.05.24 | 17.05.24 | [19 empty] | d-saranya@lntecc.com-14.06.2024-16:08:27
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves( NRV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1763 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1763-A | DVPL | Pre-order technically cleared | 100 |  |  | chennai@dvpl.co.in |  | 09.04.24 | 12.04.24 | 17.04.24 | 18.04.24 | [7 empty] | 26.04.24 | 26.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves( NRV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1763 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1763-B | AVK | Pre-order technically cleared | 55 |  |  | subhash@avkindia.com |  | 09.04.24 | 25.04.24 | 29.04.24 | 04.05.24 | 07.05.24 | 20.05.24 | 28.05.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves( NRV) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1763 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1763-C | KBL | Pre-order technically cleared | 68 |  |  | karthikeyan.r@kbl.co.in |  | 09.04.24 | 22.04.24 | 26.04.24 | 06.05.24 | 10.05.24 | 17.05.24 | 27.05.24 |  |  |  |  | 28.05.24 | 28.05.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves ( Ball Valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1764 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1764-A | Brilliant Enterorises | Pre-order pending with EDRC | 11 |  |  | brilliant160@gmail.com |  | 09.07.24 | 24.07.24 | [23 empty] | d-saranya@lntecc.com-26.07.2024-16:09:56
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves ( Ball Valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1765 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1765 | ycubeholdings | Regret offer | PR Closed |  |  | naveen@ycubeholdings.com |  | 28.06.24 | [24 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves ( Solenoid valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1765 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1765-A | Ycube | Regret offer | PR Closed |  |  | balaraj@ycubeholdings.com |  | 09.07.24 | [24 empty] | d-saranya@lntecc.com-20.07.2024-11:09:58
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves ( Solenoid valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1765 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1765-B | AVK | Regret offer | PR Closed |  |  |  |  | 17.06.24 | [24 empty] | nayana.r@lntecc.com-28.06.2024-11:24:24
BWSSB 25MLD STP | Mechanical | PR of Metallic Valves ( Solenoid valves) for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1765 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1765-C | KBL | Regret offer | PR Closed |  |  | karthikeyan.r@kbl.co.in |  | 17.06.24 | [24 empty] | nayana.r@lntecc.com-28.06.2024-11:24:24
BWSSB 25MLD STP | Mechanical | PR of Lifting Arrangements for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1766 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1766-A | West Work | Pre-order technically cleared | 15 |  |  | skwestworksalescorporation@gmail.com |  | 17.05.24 | 27.06.24 | 05.07.24 | 15.07.24 | 20.07.24 | [6 empty] | 20.07.24 | 20.07.24 | [12 empty] | d-saranya@lntecc.com-20.07.2024-11:12:16
BWSSB 25MLD STP | Mechanical | PR of Lifting Arrangements for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1766 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1766-B | Reva | Pre-order technically cleared | 15 |  |  | mkt@revacranes.com |  | 17.05.24 | 29.06.24 | 05.07.24 | [8 empty] | 20.07.24 | 20.07.24 | [12 empty] | d-saranya@lntecc.com-20.07.2024-11:12:16
BWSSB 25MLD STP | Mechanical | PR of Lifting Arrangements for 25.0 MLD STP | BWSSPIII/26/MAH/STP/VAR/ME/DC/1766 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1766-C | Eddy | Regret offer | PR Closed |  |  | insujan@eddycranes.com |  | 17.05.24 | [24 empty] | d-saranya@lntecc.com-14.06.2024-16:08:27
BWSSB 25MLD STP | Mechanical | PR of Submersible Dewatering Pumps for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1767 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1767-A | Kishor | Pre-order technically cleared | 73 |  |  | p.dixon@kishorpumps.com |  | 05.04.24 | 19.04.24 | 20.04.24 | 21.05.24 | [7 empty] | 23.05.24 | 23.05.24 | 23.05.24 | [11 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Submersible Dewatering Pumps for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1767 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1767-B | Ebbara | Regret offer | PR Closed |  |  | sales42anala@gmail.com> |  | 05.04.24 | 15.04.24 | 18.04.24 | 02.05.24 | [21 empty] | nayana.r@lntecc.com-17.05.2024-09:33:34
BWSSB 25MLD STP | Mechanical | PR of Submersible Dewatering Pumps for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1767 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1767-C | KSB | Regret offer | PR Closed |  |  | ashwin.sridhar@ksb.com |  | 16.04.24 | 26.04.24 | 30.04.24 | [22 empty] | d-saranya@lntecc.com-24.05.2024-10:24:20
BWSSB 25MLD STP | Mechanical | PR of Air Valve for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1768 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1768-A | AVK | Pre-order technically cleared | 55 |  |  | subhash@avkindia.com |  | 25.03.24 | 25.04.24 | 29.04.24 | 04.05.24 | 07.05.24 | 20.05.24 | 28.05.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Mechanical | PR of Air Valve for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1768 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1768-B | KBL | Regret offer | PR Closed |  |  | karthikeyan.r@kbl.co.in |  | 25.03.24 | [24 empty] | nayana.r@lntecc.com-17.05.2024-09:33:34
BWSSB 25MLD STP | Mechanical | PR of Air Valve for 25.0 MLD TSPS | BWSSPIII/26/MAH/STP/VAR/ME/DC/1768 | BWSSPIII/26/MAH/STP/VAR/ME/DC/1768-C | DVPL | Pre-order technically cleared | 115 |  |  | chennai@dvpl.co.in |  | 25.03.24 | 10.04.24 | 11.04.24 | 11.04.24 | [7 empty] | 11.04.24 | 11.04.24 | [12 empty] | d-saranya@lntecc.com-09.07.2024-10:56:23
BWSSB 25MLD STP | Instrumentation | Electromagnetic Flowmeter | BWSSPIII26MAHSTPVARICPR5034 | BWSSPIII26MAHSTPVARICPR5034-A | E&H India Pvt Ltd | Pre-order technically cleared | 47 |  | Mr. Ramkumar, 9790952907 | ramkumar.m@endress.com |  | 19.03.24 | 31.05.24 | 07.06.24 | 17.06.24 | [7 empty] | 18.06.24 | 18.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Electromagnetic Flowmeter | BWSSPIII26MAHSTPVARICPR5034 | BWSSPIII26MAHSTPVARICPR5034-B | Siemens Ltd | Pre-order technically rejected | PR Closed |  | Mr. S K Jagthish, 9500172385 | jagatish.s_k@siemens.com |  | 19.03.24 | 27.03.24 | 26.04.24 | [22 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Electromagnetic Flowmeter | BWSSPIII26MAHSTPVARICPR5034 | BWSSPIII26MAHSTPVARICPR5034-C | Forbes Marshall | Pre-order technically rejected | PR Closed |  | Mr. Diliban, 9989725626 | dilibanr@forbesmarshall.com |  | 19.03.24 | 04.04.24 | 04.04.24 | 02.05.24 | 03.05.24 | [20 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Electromagnetic Flowmeter | BWSSPIII26MAHSTPVARICPR5034 | BWSSPIII26MAHSTPVARICPR5034-D | ABB India Ltd | Pre-order technically cleared | 17 |  | Mr. Sairam, 9533939906 | sai.ram@in.abb.com |  | 19.04.24 | 17.05.24 | 03.07.24 | 18.07.24 | [7 empty] | 18.07.24 | 18.07.24 | [12 empty] | hrithik.p@lntecc.com-20.07.2024-11:04:53
BWSSB 25MLD STP | Instrumentation | Thermal Mass Flowmeter | BWSSPIII26MAHSTPVARICPR5034A | BWSSPIII26MAHSTPVARICPR5034A-A | E&H India Pvt Ltd | Pre-order technically cleared | 47 |  | Mr. Ramkumar, 9790952907 | ramkumar.m@endress.com |  | 19.03.24 | 31.05.24 | 07.06.24 | 17.06.24 | [7 empty] | 18.06.24 | 18.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Thermal Mass Flowmeter | BWSSPIII26MAHSTPVARICPR5034A | BWSSPIII26MAHSTPVARICPR5034A-B | Siemens Ltd | Regret offer | PR Closed |  | Mr. S K Jagthish, 9500172385 | jagatish.s_k@siemens.com |  | 19.03.24 | [24 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Thermal Mass Flowmeter | BWSSPIII26MAHSTPVARICPR5034A | BWSSPIII26MAHSTPVARICPR5034A-C | ABB India Ltd | Pre-order technically cleared | 17 |  | Mr. Sairam, 9533939906 | sai.ram@in.abb.com |  | 19.04.24 | 17.05.24 | 03.07.24 | 18.07.24 | [7 empty] | 18.07.24 | 18.07.24 | [12 empty] | hrithik.p@lntecc.com-20.07.2024-11:04:53
BWSSB 25MLD STP | Instrumentation | Thermal Mass Flowmeter | BWSSPIII26MAHSTPVARICPR5034A | BWSSPIII26MAHSTPVARICPR5034A-D | Baumer Technologies India Pvt Ltd | Pre-order technically rejected | PR Closed |  | Mr. Raguman M, 9380283372 | RM@baumer.com |  | 19.03.24 | 14.05.24 | 15.05.24 | 31.05.24 | 18.06.24 | [20 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Open Channel Flowmeter | BWSSPIII26MAHSTPVARICPR5034B | BWSSPIII26MAHSTPVARICPR5034B-A | E&H India Pvt Ltd | Pre-order technically cleared | 47 |  | Mr. Ramkumar, 9790952907 | ramkumar.m@endress.com |  | 19.03.24 | 31.05.24 | 07.06.24 | 17.06.24 | [7 empty] | 18.06.24 | 18.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Open Channel Flowmeter | BWSSPIII26MAHSTPVARICPR5034B | BWSSPIII26MAHSTPVARICPR5034B-B | Siemens Ltd | Pre-order technically rejected | PR Closed |  | Mr. S K Jagthish, 9500172385 | jagatish.s_k@siemens.com |  | 19.03.24 | 27.03.24 | 26.04.24 | [22 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Open Channel Flowmeter | BWSSPIII26MAHSTPVARICPR5034B | BWSSPIII26MAHSTPVARICPR5034B-C | ABB India Ltd | Pre-order technically cleared | 17 |  | Mr. Sairam, 9533939906 | sai.ram@in.abb.com |  | 19.04.24 | 17.05.24 | 03.07.24 | 18.07.24 | [7 empty] | 18.07.24 | 18.07.24 | [12 empty] | hrithik.p@lntecc.com-20.07.2024-11:04:53
BWSSB 25MLD STP | Instrumentation | Area Velocity Flowmeter | BWSSPIII26MAHSTPVARICPR5034C | BWSSPIII26MAHSTPVARICPR5034C-A | Aaxis Nano Technologies Pvt Ltd | Pre-order technically cleared | 128 |  | Mr. Vysakh Mohan, 9176712369 | v.mohan@aaxisnano.com |  | 26.03.24 | 27.03.24 | 28.03.24 | 29.03.24 | [7 empty] | 29.03.24 | 29.03.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Area Velocity Flowmeter | BWSSPIII26MAHSTPVARICPR5034C | BWSSPIII26MAHSTPVARICPR5034C-B | JeSKON Systems Pvt Ltd | Pre-order technically cleared | 89 |  | Mr. Ankit Singh, 9826042443 | info@jeskon.com |  | 26.03.24 | 28.04.24 | 30.04.24 | 07.05.24 | [7 empty] | 07.05.24 | 07.05.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Pressure Transmitter | BWSSPIII26MAHSTPVARICPR5035 | BWSSPIII26MAHSTPVARICPR5035-A | E&H India Pvt Ltd | Pre-order technically cleared | 47 |  | Mr. Ramkumar, 9790952907 | ramkumar.m@endress.com |  | 19.03.24 | 31.05.24 | 07.06.24 | 17.06.24 | [7 empty] | 18.06.24 | 18.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Pressure Transmitter | BWSSPIII26MAHSTPVARICPR5035 | BWSSPIII26MAHSTPVARICPR5035-B | Siemens Ltd | Pre-order technically rejected | PR Closed |  | Mr. S K Jagthish, 9500172385 | jagatish.s_k@siemens.com |  | 19.03.24 | 27.03.24 | 26.04.24 | [22 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Pressure Transmitter | BWSSPIII26MAHSTPVARICPR5035 | BWSSPIII26MAHSTPVARICPR5035-C | Yokogawa India Ltd | Pre-order technically cleared | 65 |  | B Mohan, 9444025091 | b.mohan@yokogawa.com |  | 19.03.24 | 08.05.24 | 08.05.24 | 08.05.24 | 08.05.24 | 27.05.24 | 28.05.24 | 31.05.24 |  |  |  | 31.05.24 | 31.05.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Pressure Transmitter | BWSSPIII26MAHSTPVARICPR5035 | BWSSPIII26MAHSTPVARICPR5035-D | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Pressure Switch | BWSSPIII26MAHSTPVARICPR5035A | BWSSPIII26MAHSTPVARICPR5035A-A | Baumer Technologies India Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-16.05.2024-12:33:21
BWSSB 25MLD STP | Instrumentation | Pressure Switch | BWSSPIII26MAHSTPVARICPR5035A | BWSSPIII26MAHSTPVARICPR5035A-B | Precision Mass Products Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Pressure Switch | BWSSPIII26MAHSTPVARICPR5035A | BWSSPIII26MAHSTPVARICPR5035A-C | HGuru Instruments South India Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Pressure Switch | BWSSPIII26MAHSTPVARICPR5035A | BWSSPIII26MAHSTPVARICPR5035A-D | Wika Instruments India Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Pressure Gauge | BWSSPIII26MAHSTPVARICPR5035B | BWSSPIII26MAHSTPVARICPR5035B-A | Baumer Technologies India Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-16.05.2024-12:33:21
BWSSB 25MLD STP | Instrumentation | Pressure Gauge | BWSSPIII26MAHSTPVARICPR5035B | BWSSPIII26MAHSTPVARICPR5035B-B | Precision Mass Products Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Pressure Gauge | BWSSPIII26MAHSTPVARICPR5035B | BWSSPIII26MAHSTPVARICPR5035B-C | HGuru Instruments South India Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Pressure Gauge | BWSSPIII26MAHSTPVARICPR5035B | BWSSPIII26MAHSTPVARICPR5035B-D | Wika Instruments India Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-31.05.2024-10:39:08
BWSSB 25MLD STP | Instrumentation | Level Transmitter | BWSSPIII26MAHSTPVARICPR5036 | BWSSPIII26MAHSTPVARICPR5036-A | E&H India Pvt Ltd | Pre-order technically cleared | 47 |  | Mr. Ramkumar, 9790952907 | ramkumar.m@endress.com |  | 19.03.24 | 31.05.24 | 07.06.24 | 17.06.24 | [7 empty] | 18.06.24 | 18.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Level Transmitter | BWSSPIII26MAHSTPVARICPR5036 | BWSSPIII26MAHSTPVARICPR5036-B | Siemens Ltd | Pre-order technically rejected | PR Closed |  | Mr. S K Jagthish, 9500172385 | jagatish.s_k@siemens.com |  | 19.03.24 | 27.03.24 | 26.04.24 | [22 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Level Transmitter | BWSSPIII26MAHSTPVARICPR5036 | BWSSPIII26MAHSTPVARICPR5036-C | ABB India Ltd | Pre-order technically cleared | 17 |  | Mr. Sairam, 9533939906 | sai.ram@in.abb.com |  | 19.04.24 | 17.05.24 | 03.07.24 | 18.07.24 | [7 empty] | 18.07.24 | 18.07.24 | [12 empty] | hrithik.p@lntecc.com-20.07.2024-11:04:53
BWSSB 25MLD STP | Instrumentation | Level Switch - Conductivity Type | BWSSPIII26MAHSTPVARICPR5036A | BWSSPIII26MAHSTPVARICPR5036A-A | Pune Techtrol Pvt Ltd | Pre-order technically cleared | 40 |  | Ms. Anita Raskar, 020-66342913 | mktg2@punetechtrol.com |  | 19.03.24 | 29.03.24 | 30.03.24 | 25.06.24 | [7 empty] | 24.06.24 | 25.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Level Switch - Conductivity Type | BWSSPIII26MAHSTPVARICPR5036A | BWSSPIII26MAHSTPVARICPR5036A-B | Levcon Controls Pvt Ltd | Pre-order technically cleared | 81 |  | Mr. Badal Jana, 9831826885 | b_jana@levcongroup.com |  | 19.03.24 | 20.03.24 | 24.04.24 | 15.05.24 | [7 empty] | 15.05.24 | 15.05.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Level Switch - Conductivity Type | BWSSPIII26MAHSTPVARICPR5036A | BWSSPIII26MAHSTPVARICPR5036A-C | SBEM Pvt Ltd | Regret offer | PR Closed |  | Mr. P Rajesh, 8681898929 | rajesh.p@sbem.co.in |  | 19.03.24 | [24 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Level Switch - Magnetic Float Operated | BWSSPIII26MAHSTPVARICPR5036B | BWSSPIII26MAHSTPVARICPR5036B-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Temperature Measuring Instruments | BWSSPIII26MAHSTPVARICPR5037 | BWSSPIII26MAHSTPVARICPR5037-A | E&H India Pvt Ltd | Pre-order technically cleared | 47 |  | Mr. Ramkumar, 9790952907 | ramkumar.m@endress.com |  | 19.03.24 | 31.05.24 | 07.06.24 | 17.06.24 | [7 empty] | 18.06.24 | 18.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Temperature Measuring Instruments | BWSSPIII26MAHSTPVARICPR5037 | BWSSPIII26MAHSTPVARICPR5037-B | Siemens Ltd | Regret offer | PR Closed |  | Mr. S K Jagthish, 9500172385 | jagatish.s_k@siemens.com |  | 19.03.24 | [24 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Temperature Measuring Instruments | BWSSPIII26MAHSTPVARICPR5037 | BWSSPIII26MAHSTPVARICPR5037-C | Precision Mass Products Pvt Ltd | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Temperature Measuring Instruments | BWSSPIII26MAHSTPVARICPR5037 | BWSSPIII26MAHSTPVARICPR5037-D | ABB India Ltd | Pre-order technically rejected | PR Closed |  | Mr. Sairam, 9533939906 | sai.ram@in.abb.com |  | 19.04.24 | 17.05.24 | [23 empty] | hrithik.p@lntecc.com-18.06.2024-10:12:56
BWSSB 25MLD STP | Instrumentation | Online Analyzers | BWSSPIII26MAHSTPVARICPR5037A | BWSSPIII26MAHSTPVARICPR5037A-A | Aaxis Nano Technologies Pvt Ltd | Pre-order technically cleared | 41 |  | Mr. Vysakh Mohan, 9176712369 | v.mohan@aaxisnano.com |  | 19.04.24 | 06.05.24 | 06.05.24 | 31.05.24 | [7 empty] | 25.06.24 | 24.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Online Analyzers | BWSSPIII26MAHSTPVARICPR5037A | BWSSPIII26MAHSTPVARICPR5037A-B | Savant Instruments Pvt Ltd | Pre-order technically cleared | 40 |  | Mr. Gopala krishnam Raju, 9866777699 | gopi@savantindia.in |  | 19.04.24 | 30.03.24 | 28.05.24 | 25.06.24 | [7 empty] | 25.06.24 | 24.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Online Analyzers | BWSSPIII26MAHSTPVARICPR5037A | BWSSPIII26MAHSTPVARICPR5037A-C | Next Engineering | Pre-order technically cleared | 41 |  | Mr. Jaydeep, 9033731196 | jaydeep@nextengineering.in |  | 19.03.24 | 20.04.24 | 24.04.24 | 31.05.24 | [7 empty] | 25.06.24 | 24.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Online Analyzers | BWSSPIII26MAHSTPVARICPR5037A | BWSSPIII26MAHSTPVARICPR5037A-D | E&H India Pvt Ltd | Pre-order technically cleared | 47 |  | Mr. Ramkumar, 9790952907 | ramkumar.m@endress.com |  | 19.03.24 | 31.05.24 | 07.06.24 | 17.06.24 | [7 empty] | 18.06.24 | 18.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | RTOMS | BWSSPIII26MAHSTPVARICPR5038 | BWSSPIII26MAHSTPVARICPR5038-A | Aaxis Nano Technologies Pvt Ltd | Pre-order technically cleared | 101 |  | Mr. Vysakh Mohan, 9176712369 | v.mohan@aaxisnano.com |  | 19.04.24 | 25.03.24 | 22.04.24 | 25.04.24 | [7 empty] | 22.04.24 | 25.04.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | RTOMS | BWSSPIII26MAHSTPVARICPR5038 | BWSSPIII26MAHSTPVARICPR5038-B | Savant Instruments Pvt Ltd | Pre-order technically cleared | 40 |  | Mr. Gopala krishnam Raju, 9866777699 | gopi@savantindia.in |  | 19.04.24 | 30.03.24 | 28.05.24 | 25.06.24 | [7 empty] | 25.06.24 | 24.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | RTOMS | BWSSPIII26MAHSTPVARICPR5038 | BWSSPIII26MAHSTPVARICPR5038-C | Next Engineering | Pre-order technically cleared | 41 |  | Mr. Jaydeep, 9033731196 | jaydeep@nextengineering.in |  | 19.03.24 | 20.04.24 | 24.04.24 | 31.05.24 | [7 empty] | 25.06.24 | 24.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Weight Indicating Transmitter | BWSSPIII26MAHSTPVARICPR5039 | BWSSPIII26MAHSTPVARICPR5039-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | Auto Sampler | BWSSPIII26MAHSTPVARICPR5040 | BWSSPIII26MAHSTPVARICPR5040-A | Aaxis Nano Technologies Pvt Ltd | Pre-order technically cleared | 101 |  | Mr. Vysakh Mohan, 9176712369 | v.mohan@aaxisnano.com |  | 19.03.24 | 25.03.24 | 22.04.24 | 25.04.24 | [7 empty] | 22.04.24 | 25.04.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Auto Sampler | BWSSPIII26MAHSTPVARICPR5040 | BWSSPIII26MAHSTPVARICPR5040-B | Savant Instruments Pvt Ltd | Pre-order technically cleared | 40 |  | Mr. Gopala krishnam Raju, 9866777699 | gopi@savantindia.in |  | 19.04.24 | 30.03.24 | 28.05.24 | 25.06.24 | [7 empty] | 25.06.24 | 24.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Auto Sampler | BWSSPIII26MAHSTPVARICPR5040 | BWSSPIII26MAHSTPVARICPR5040-C | Next Engineering | Pre-order technically cleared | 41 |  | Mr. Jaydeep, 9033731196 | jaydeep@nextengineering.in |  | 19.03.24 | 20.04.24 | 24.04.24 | 31.05.24 | [7 empty] | 25.06.24 | 24.06.24 | [12 empty] | hrithik.p@lntecc.com-27.06.2024-16:58:48
BWSSB 25MLD STP | Instrumentation | Intrumentation Signal and Control Cable | BWSSPIII26MAHSTPVARICPR5041 | BWSSPIII26MAHSTPVARICPR5041-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | UPS Panel | BWSSPIII26MAHSTPVARICPR5042 | BWSSPIII26MAHSTPVARICPR5042-A | Hitachi Hirel power Electronics Pvt Ltd | Pre-order pending with EDRC | 16 |  | Mr. Balakumaran S, 6359800016 | balakumaran_s@hitachi-hirel.com |  | 11.06.24 | 19.07.24 | [23 empty] | hrithik.p@lntecc.com-20.07.2024-11:07:00
BWSSB 25MLD STP | Instrumentation | PLC / RIO Panel | BWSSPIII26MAHSTPVARICPR5043 | BWSSPIII26MAHSTPVARICPR5043-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | SCADA Software & Hardware Equipments | BWSSPIII26MAHSTPVARICPR5044 | BWSSPIII26MAHSTPVARICPR5044-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | hrithik.p@lntecc.com-17.05.2024-12:18:29
BWSSB 25MLD STP | Instrumentation | CCTV System | BWSSPIII26MAHSTPVARICPR5045 | BWSSPIII26MAHSTPVARICPR5045-A | Indian Network Technology | Pre-order technically cleared | 19 |  | Mr. K Loganathan, 9842218835 | kl@inttech.in |  | 11.06.24 | 27.06.24 | 01.07.24 | 16.07.24 | [7 empty] | 16.07.24 | 16.07.24 | [12 empty] | hrithik.p@lntecc.com-20.07.2024-11:06:02
BWSSB 25MLD STP | Instrumentation | Fire Alarm and Detection System | BWSSPIII26MAHSTPVARICPR5046 | BWSSPIII26MAHSTPVARICPR5046-A | Indian Network Technology | Pre-order pending with EDRC | 16 |  | Mr. K Loganathan, 9842218835 | kl@inttech.in |  | 11.06.24 | 19.07.24 | [23 empty] | hrithik.p@lntecc.com-20.07.2024-11:07:00
BWSSB 25MLD STP | Electrical | PR for HT Switchboard for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4227 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4227-A | Sun Shine Control | Pre-order technically cleared | 180 | POST ORDER DOCUMENT TO BE SUBMITTED TO CLIENT AFTER SLD APPROVAL |  |  | 22.01.24 | 22.01.24 | 03.02.24 | 22.01.24 | [8 empty] | 05.02.24 | 06.02.24 |  |  |  | Sun Shine Control | [8 empty] | s-kannan@lntecc.com-11.06.2024-10:23:29
BWSSB 25MLD STP | Electrical | PR for LT Switchboard for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4228 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4228-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for LT Switchboard for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4228 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4228-B | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for LT Switchboard for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4228 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4228-C | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for Transformers for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4229 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4229-A | SAI ELECTRICAL | Pre-order technically cleared | 180 | POST ORDER DOCUMENT TO BE SUBMITTED TO CLIENT AFTER DESIGN CALCULATION APPROVAL |  |  | 22.01.24 | 22.01.24 | 31.01.24 | 22.01.24 | [8 empty] | 05.02.24 | 06.02.24 | [12 empty] | s-kannan@lntecc.com-11.06.2024-10:23:29
BWSSB 25MLD STP | Electrical | PR for415 V LT Non Segregated Busduct for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4230 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4230-A | SUN AUTOMAT | Pre-order technically cleared | 68 |  |  | design@sunautomat.com |  | 18.03.24 | 09.05.24 | 13.05.24 | 21.05.24 | [7 empty] | 27.05.24 | 28.05.24 | [12 empty] | s-kannan@lntecc.com-11.06.2024-10:23:38
BWSSB 25MLD STP | Electrical | PR for415 V LT Non Segregated Busduct for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4230 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4230-B | Lotus Powergear | Pre-order technically cleared | 115 |  |  | vinaykumar_s@lotuspowergear.co.in |  | 18.03.24 | 03.04.24 | 09.04.24 | 11.04.24 | [7 empty] | 11.04.24 | 11.04.24 | [12 empty] | s-kannan@lntecc.com-11.06.2024-10:23:29
BWSSB 25MLD STP | Electrical | PR for415 V LT Non Segregated Busduct for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4230 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4230-C | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for Diesel Generator for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4231 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4231-A | GREAVE COTTON | Pre-order technically cleared | 181 | POST ORDER DOCUMENT TO BE SUBMITTED TO CLIENT AFTER DESIGN CALCULATION APPROVAL |  |  | 22.01.24 | 22.01.24 | 03.02.24 | 05.02.24 | [8 empty] | 05.02.24 | 05.02.24 | [12 empty] | s-kannan@lntecc.com-11.06.2024-10:23:29
BWSSB 25MLD STP | Electrical | PR for LT Distribution Boards for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4232 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4232-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for LT Distribution Boards for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4232 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4232-B | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for Lighting System for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4233 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4233-A | Manoj Trading | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for Lighting System for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4233 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4233-B | Wipro | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for Earthing and Lightning Materials for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4234 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4234-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for Local Push Button station for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4235 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4235-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for Cable Tray & Accessories for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4236 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4236-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for HT & LT Cables for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4237 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4237-A | Havelles | Pre-order technically cleared | 180 |  |  |  | 22.01.24 | 22.01.24 | 03.02.24 | 03.02.24 | [8 empty] | 05.02.24 | 06.02.24 | [12 empty] | s-kannan@lntecc.com-11.06.2024-10:23:29
BWSSB 25MLD STP | Electrical | PR for Battery & Battery charger for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4238 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4238-A | Exide | Pre-order technically cleared | 181 |  |  |  | 03.02.24 | 22.01.24 | 03.02.24 | 05.02.24 | [8 empty] | 05.02.24 | 05.02.24 | [12 empty] | s-kannan@lntecc.com-11.06.2024-10:23:29
BWSSB 25MLD STP | Electrical | PR for Battery & Battery charger for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4238 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4238-B | Amararaja | Pre-order technically cleared | 181 |  |  |  | 03.02.24 | 22.01.24 | 03.02.24 | 05.02.24 | [8 empty] | 05.02.24 | 05.02.24 | [12 empty] | s-kannan@lntecc.com-11.06.2024-10:23:29
BWSSB 25MLD STP | Electrical | PR for Safety accessories for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4239 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4239-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
BWSSB 25MLD STP | Electrical | PR for Safety accessories for 25MLD STP | BWSSPIII/26/MAH/STP/VAR/EL/PR/4239 | BWSSPIII/26/MAH/STP/VAR/EL/PR/4239-B | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | s-kannan@lntecc.com-24.05.2024-10:09:59
Chittorgarh | Process | Clariflocculator mechanism | LE23M849-P-WS-WT-PR-2302 | LE23M849-P-WS-WT-PR-2302-A | Filsep | Sent to BU Operations | 27 | E&I cleared on - 1.7.24 | S.Sivamurugan - 9444022982 | filsepengineers@gmail.com |  | 22.05.24 | 09.06.24 | 18.06.24 | 28.06.24 | 05.07.24 | [6 empty] | 08.07.24 | 08.07.24 | 08.07.24 | T1 | [7 empty] | 04.07.24 | 21.07.24 | 19.09.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Clariflocculator mechanism | LE23M849-P-WS-WT-PR-2302 | LE23M849-P-WS-WT-PR-2302-B | Triveni | Sent to BU Operations | 27 | Instru. cleared on 25.6.24 Electr. cleared on -2.7.24 | Neeraj Aggarwal -9311695899 | neeraj.aggarwal@projects.trivenigroup.com; h.sathyanarayanan@projects.trivenigroup.com |  | 22.05.24 | 04.06.24 | 12.06.24 | 25.06.24 | 05.07.24 | [6 empty] | 08.07.24 | 08.07.24 | 08.07.24 | T3 | [7 empty] | 04.07.24 | 21.07.24 | 19.09.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Clariflocculator mechanism | LE23M849-P-WS-WT-PR-2302 | LE23M849-P-WS-WT-PR-2302-C | Shivpad | Sent to BU Operations | 27 | Electrical cleared on 3.7.24 Instru - Cleared | Ragavendar- 9003243278 | ragavendar@shivpad.com |  | 22.05.24 | 07.06.24 | 18.06.24 | 27.06.24 | 06.07.24 | [6 empty] | 08.07.24 | 08.07.24 | 08.07.24 | T4 | [7 empty] | 04.07.24 | 21.07.24 | 19.09.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Clariflocculator mechanism | LE23M849-P-WS-WT-PR-2302 | LE23M849-P-WS-WT-PR-2302-D | Sritech | Sent to BU Operations | 27 | Instru. - Cleared Electrical - cleared on 8.7.24 | Mohan - 9422111017 / 9511744307 | mohan@sritechindia.com |  | 22.05.24 | 03.06.24 | 12.06.24 | 15.06.24 | 08.07.24 | [6 empty] | 08.07.24 | 08.07.24 | 08.07.24 | T2 | [7 empty] | 04.07.24 | 21.07.24 | 19.09.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Air Blower | LE23M849-P-WS-WT-PR-2303 | LE23M849-P-WS-WT-PR-2303-A | Everest | Regret offer | PR Closed | Vendor not responding more than a month time | 95826 49157 - Saif Ali | saif.ali@irco.com |  | 21.06.24 | [21 empty] | 08.08.24 | 25.08.24 | 24.10.24 | karthiga@lntecc.com-22.07.2024-11:57:52
Chittorgarh | Process | Air Blower | LE23M849-P-WS-WT-PR-2303 | LE23M849-P-WS-WT-PR-2303-B | Kay | Pre-order comments issued | 13 |  | 8077285046 | project@kayblowers.com |  | 21.06.24 | 24.06.24 | 28.06.24 | 29.06.24 | 06.07.24 | 16.07.24 | 22.07.24 | [15 empty] | 08.08.24 | 25.08.24 | 24.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Air Blower | LE23M849-P-WS-WT-PR-2303 | LE23M849-P-WS-WT-PR-2303-C | Swam | Pre-order pending with EDRC | 15 | Electrical compliance yet to receive from vendor | 8130744229 - Shailesh Srivastava | shailesh@swamatics.com; sales@swamatics.com |  | 21.06.24 | 29.06.24 | 05.07.24 | 20.07.24 | [18 empty] | 08.08.24 | 25.08.24 | 24.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Air Blower | LE23M849-P-WS-WT-PR-2303 | LE23M849-P-WS-WT-PR-2303-D | ACME | Pre-order comments issued | 13 |  | 9099053221 - Vishwesh Pardeshi | vishwesh.p@airequipments.com |  | 21.06.24 | 26.06.24 | 05.07.24 | 15.07.24 | 22.07.24 | [17 empty] | 08.08.24 | 25.08.24 | 24.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Agitator | LE23M849-P-WS-WT-PR-2304 | LE23M849-P-WS-WT-PR-2304-A | Shivpad | Pre-order pending with EDRC | 15 | Forwarded to E&I on 20.7.24 Electrical received on 29.7.24 | Ragavendar- 9003243278 | ragavendar@shivpad.com |  | 21.06.24 | 01.07.24 | 17.07.24 | 20.07.24 | [18 empty] | 10.08.24 | 27.08.24 | 26.10.24 | karthiga@lntecc.com-29.07.2024-11:26:01
Chittorgarh | Process | Agitator | LE23M849-P-WS-WT-PR-2304 | LE23M849-P-WS-WT-PR-2304-B | Sritech | Pre-order comments issued | 18 |  | Mohan - 9422111017 / 9511744307 | mohan@sritechindia.com |  | 21.06.24 | 01.07.24 | 17.07.24 | [19 empty] | 10.08.24 | 27.08.24 | 26.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Agitator | LE23M849-P-WS-WT-PR-2304 | LE23M849-P-WS-WT-PR-2304-C | Milton Roy | Pre-order pending with EDRC | 12 | Forwarded to E&I on 23.7.24 |  | sales@fluidoze.com; proposal@fluidoze.com |  | 04.07.24 | 28.06.24 | 17.07.24 | 23.07.24 | [18 empty] | 10.08.24 | 27.08.24 | 26.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Agitator | LE23M849-P-WS-WT-PR-2304 | LE23M849-P-WS-WT-PR-2304-D | FFP | Pre-order pending with EDRC | 16 | Forwarded to E&I on 20.7.24 | 81049 82550 | fibrein@gmail.com |  | 21.06.24 | 11.07.24 | 17.07.24 | 19.07.24 | [18 empty] | 10.08.24 | 27.08.24 | 26.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | WTP Sluice gates | LE23M849-P-WS-WT-PR-2305 | LE23M849-P-WS-WT-PR-2305-A | Jash | Sent to BU Operations | 27 | E&I - cleared on 1.7.24 | 72900 40772 -Prateek Verma | lpgsouth2@jashindia.com |  | 04.05.24 | 15.05.24 | 20.05.24 | 05.06.24 | 07.06.24 | 17.06.24 | 18.06.24 | 29.06.24 | 06.07.24 |  |  | 08.07.24 | 08.07.24 | 08.07.24 | T1 | [7 empty] | 05.07.24 | 22.07.24 | 20.09.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | WTP Sluice gates | LE23M849-P-WS-WT-PR-2305 | LE23M849-P-WS-WT-PR-2305-B | Oriental | Sent to BU Operations | 27 | Electrical - Cleared on 3.7.24 Instr-cleared on 6.6.24 | 9810206011 - Sanjay Mahensaria | orientalcastings@gmail.com |  | 04.05.24 | 22.05.24 | 01.06.24 | 06.06.24 | 10.06.24 | 15.06.24 | 18.06.24 | 27.06.24 | 01.07.24 | 03.07.24 | 06.07.24 | 08.07.24 | 08.07.24 | 08.07.24 | T2 | [7 empty] | 05.07.24 | 22.07.24 | 20.09.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | WTP Sluice gates | LE23M849-P-WS-WT-PR-2305 | LE23M849-P-WS-WT-PR-2305-C | DVPL | Sent to BU Operations | 27 | Electrical -cleared on 3.6.24 Instr-cleared on 1.6.24 | 9840049843 - K L Narayana | chennai@dvpl.co.in |  | 04.05.24 | 09.05.24 | 20.05.24 | 21.05.24 | 31.05.24 | 03.06.24 | 03.06.24 | 04.06.24 | 07.06.24 | 15.06.24 | 06.07.24 | 08.07.24 | 08.07.24 | 08.07.24 | T3 | [7 empty] | 05.07.24 | 22.07.24 | 20.09.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Chlorination system with tonners | LE23M849-P-WS-WT-PR-2306 | LE23M849-P-WS-WT-PR-2306-A | Toshcon | Pre-order comments issued | 10 | Forwarded to E&I -16.7.24 Electrical received on 17.7.24 | 9314397727 | metering2@toshcon.com; metering@toshcon.com |  | 28.06.24 | 15.07.24 | 25.07.24 | [19 empty] | 13.08.24 | 30.08.24 | 29.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Chlorination system with tonners | LE23M849-P-WS-WT-PR-2306 | LE23M849-P-WS-WT-PR-2306-B | IEC FAB CHEM | Pre-order comments issued | 11 | Forwarded to E&I -16.7.24 Electrical received on 17.7.24 | 7550013258 | marketing@iecfabchem.in |  | 28.06.24 | 16.07.24 | 24.07.24 | [19 empty] | 13.08.24 | 30.08.24 | 29.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Chlorination system with tonners | LE23M849-P-WS-WT-PR-2306 | LE23M849-P-WS-WT-PR-2306-C | Capco water | Pre-order comments issued | 12 | Forwarded to E&I -11.7.24 Electrical received on 18.7.24 | Dhruv Kocha - 9920024888 | dmkocha@capcowater.com |  | 29.06.24 | 08.07.24 | 23.07.24 | [19 empty] | 13.08.24 | 30.08.24 | 29.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Chlorination system with tonners | LE23M849-P-WS-WT-PR-2306 | LE23M849-P-WS-WT-PR-2306-D | Industrial Device | Awaiting pre-offer from vendor | 23 |  | 9884378053 | sales@industrialdevices.in |  | 12.07.24 | [21 empty] | 13.08.24 | 30.08.24 | 29.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Chlorination system with tonners | LE23M849-P-WS-WT-PR-2306 | LE23M849-P-WS-WT-PR-2306-E | Zion Controlmatik ABW | Pre-order pending with EDRC | 15 | Forwarded to E&I on 20.7.24 | Deepak - 9828977765 | deepak@ziontech.in; sales.ziontech@gmail.com |  | 15.07.24 | 20.07.24 | [20 empty] | 13.08.24 | 30.08.24 | 29.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Filter media | LE23M849-P-WS-WT-PR-2308 | LE23M849-P-WS-WT-PR-2308-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 13.11.24 | 30.11.24 | 29.01.25 | karthiga@lntecc.com-16.07.2024-09:50:30
Chittorgarh | Process | Backwash & Service water pump | LE23M849-P-WS-WT-PR-2309 | LE23M849-P-WS-WT-PR-2309-A | Wilo | Awaiting pre-offer from vendor | 24 |  | 8680068301 | manikkandan.pr@wilo.com |  | 11.07.24 | [21 empty] | 10.08.24 | 27.08.24 | 26.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Backwash & Service water pump | LE23M849-P-WS-WT-PR-2309 | LE23M849-P-WS-WT-PR-2309-B | KBL | Awaiting pre-offer from vendor | 24 |  | 9962071698 | Mohan.kumar@kbl.co.in |  | 11.07.24 | [21 empty] | 10.08.24 | 27.08.24 | 26.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Backwash & Service water pump | LE23M849-P-WS-WT-PR-2309 | LE23M849-P-WS-WT-PR-2309-C | WPIL | Awaiting pre-offer from vendor | 24 |  | 9331259876 | contracts.kolkata@wpil.co.in; r.chandramohan@wpil.co.in |  | 11.07.24 | [21 empty] | 10.08.24 | 27.08.24 | 26.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Backwash & Service water pump | LE23M849-P-WS-WT-PR-2309 | LE23M849-P-WS-WT-PR-2309-D | Jyoti | Regret offer | PR Closed |  | 6352771915 | pereira@jyoti.com; pearsonpereira@yahoo.com |  | 11.07.24 | [21 empty] | 10.08.24 | 27.08.24 | 26.10.24 | karthiga@lntecc.com-20.07.2024-16:09:18
Chittorgarh | Process | Submersible pump | LE23M849-P-WS-WT-PR-2310 | LE23M849-P-WS-WT-PR-2310-A | Aqua | Awaiting pre-offer from vendor | 23 |  | S.T.Sambandam -8144003131 | chennai@aquapumps.com |  | 12.07.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Submersible pump | LE23M849-P-WS-WT-PR-2310 | LE23M849-P-WS-WT-PR-2310-B | MBH | Pre-order pending with EDRC | 15 | Forwarded to E&I on 23.7.24 | Naresh B Koul - 99200 13772 | northindustrial@mbhpumps.com |  | 12.07.24 | 20.07.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Submersible pump | LE23M849-P-WS-WT-PR-2310 | LE23M849-P-WS-WT-PR-2310-C | WPIL | Awaiting pre-offer from vendor | 23 |  | 9331259876 | contracts.kolkata@wpil.co.in; r.chandramohan@wpil.co.in |  | 12.07.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Submersible pump | LE23M849-P-WS-WT-PR-2310 | LE23M849-P-WS-WT-PR-2310-D | Jasco | Pre-order comments issued | 10 |  | 7069099037 - Arvish Modi | hyd@jascopump.com |  | 12.07.24 | 15.07.24 | 25.07.24 | [19 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Electrical hoist | LE23M849-P-WS-WT-PR-2311 | LE23M849-P-WS-WT-PR-2311-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 26.09.24 | 13.10.24 | 12.12.24 | karthiga@lntecc.com-16.07.2024-09:50:30
Chittorgarh | Process | Manual chain pulley block | LE23M849-P-WS-WT-PR-2312 | LE23M849-P-WS-WT-PR-2312-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 26.09.24 | 13.10.24 | 12.12.24 | karthiga@lntecc.com-16.07.2024-09:50:30
Chittorgarh | Process | Dosing pump | LE23M849-P-WS-WT-PR-2313 | LE23M849-P-WS-WT-PR-2313-A | SR Metering | Pre-order pending with EDRC | 11 | Forwarded to E&I on 24.7.24 | 8888865119 | sr1@srmetering.com |  | 12.07.24 | 24.07.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Dosing pump | LE23M849-P-WS-WT-PR-2313 | LE23M849-P-WS-WT-PR-2313-B | Asia LMI | Pre-order pending with EDRC | 6 | Forwarded to E&I on 29.7.24 Electrical received on 29.7.24 | 8939883044 | sales1@fluidoze.com; proposal@fluidoze.com; biz.dev@fluidoze.com |  | 12.07.24 | 29.07.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthiga@lntecc.com-29.07.2024-14:19:19
Chittorgarh | Process | Dosing pump | LE23M849-P-WS-WT-PR-2313 | LE23M849-P-WS-WT-PR-2313-C | Swelore | Awaiting pre-offer from vendor | 23 |  | Smita 022 24938394 / 95 | gp@easwargroup.com; sales@hwelore.com |  | 12.07.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Dosing pump | LE23M849-P-WS-WT-PR-2313 | LE23M849-P-WS-WT-PR-2313-D | VK Pumps | Awaiting pre-offer from vendor | 23 |  | 7058810266 -Swati T+ 91 (020) 6654 1909 | swati.jadhav@vkpumps.com; kiran.kadam@vkpumps.com; chetan.kalwankar@vkpumps.com |  | 12.07.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Submersible mixer | LE23M849-P-WS-WT-PR-2315 | LE23M849-P-WS-WT-PR-2315-A | WWT Sulzer | Pre-order pending with EDRC | 12 | E&I forwarded on 23.7.24 | 9319094421 | wwtechennai@gmail.com |  | 03.07.24 | 10.07.24 | 20.07.24 | 23.07.24 | [18 empty] | 01.08.24 | 18.08.24 | 17.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Submersible mixer | LE23M849-P-WS-WT-PR-2315 | LE23M849-P-WS-WT-PR-2315-B | FFP | Pre-order pending with EDRC | 10 | Forwarded to E&I on 25.7.24 | Lovendra agarwal - 8104982550 | fibrein@gmail.com |  | 03.07.24 | 17.07.24 | 20.07.24 | 25.07.24 | [18 empty] | 01.08.24 | 18.08.24 | 17.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Submersible mixer | LE23M849-P-WS-WT-PR-2315 | LE23M849-P-WS-WT-PR-2315-C | Xylem | Regret offer | PR Closed | Xylem mixers not available for smaller size tanks in 3.55MLD & 1.5MLD WTPs. |  | siva.natarajan@xylem.com |  | 04.07.24 | [21 empty] | 01.08.24 | 18.08.24 | 17.10.24 | karthiga@lntecc.com-16.07.2024-10:37:20
Chittorgarh | Process | Submersible mixer | LE23M849-P-WS-WT-PR-2315 | LE23M849-P-WS-WT-PR-2315-D | Grundfos | Pre-order comments issued | 15 | Electr. received on 16.7.24 Instru. received on 16.7.24 | 9840320809 | ramesh.sivasubramanian@grundfos.com |  | 04.07.24 | 12.07.24 | 20.07.24 | [19 empty] | 01.08.24 | 18.08.24 | 17.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Sludge Thickener | LE23M849-P-WS-WT-PR-2321 | LE23M849-P-WS-WT-PR-2321-A | Filsep | Pre-order pending with EDRC | 6 | Forwarded to E&I on 29.7.24 | S.Sivamurugan - 9444022982 | filsepengineers@gmail.com |  | 16.07.24 | 23.07.24 | 25.07.24 | 29.07.24 | [18 empty] | 12.08.24 | 29.08.24 | 28.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Sludge Thickener | LE23M849-P-WS-WT-PR-2321 | LE23M849-P-WS-WT-PR-2321-B | Triveni | Pre-order comments issued | 10 |  | Neeraj Aggarwal -9311695899 | neeraj.aggarwal@projects.trivenigroup.com; h.sathyanarayanan@projects.trivenigroup.com |  | 16.07.24 | 23.07.24 | 25.07.24 | [22 empty] | karthiga@lntecc.com-29.07.2024-10:01:57
Chittorgarh | Process | Sludge Thickener | LE23M849-P-WS-WT-PR-2321 | LE23M849-P-WS-WT-PR-2321-C | Shivpad | Pre-order pending with EDRC | 10 | Forwarded to E&I on 25.7.24 | Ragavendar- 9003243278 | ragavendar@shivpad.com |  | 16.07.24 | 20.07.24 | 25.07.24 | 25.07.24 | [21 empty] | karthiga@lntecc.com-29.07.2024-10:01:57
Chittorgarh | Process | Sludge Thickener | LE23M849-P-WS-WT-PR-2321 | LE23M849-P-WS-WT-PR-2321-D | Sritech | Pre-order pending with EDRC | 6 | Forwarded to E&I on 29.7.24 | Mohan - 9422111017 / 9511744307 | mohan@sritechindia.com |  | 16.07.24 | 24.07.24 | 25.07.24 | 29.07.24 | [21 empty] | karthiga@lntecc.com-29.07.2024-14:19:19
Chittorgarh | Process | Centrifuge | LE23M849-P-WS-WT-PR-2323 | LE23M849-P-WS-WT-PR-2323-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 17.09.24 | 04.10.24 | 03.12.24 | karthiga@lntecc.com-16.07.2024-09:50:31
Chittorgarh | Process | Screw pumps | LE23M849-P-WS-WT-PR-2324 | LE23M849-P-WS-WT-PR-2324-A | Flosys | Pre-order pending with EDRC | 13 | Forwarded to electrical on 22.7.24 | Jagadeesan.P -9361303055 | sales@flosys.in |  | 02.07.24 | 12.07.24 | 18.07.24 | 22.07.24 | [18 empty] | 05.08.24 | 22.08.24 | 21.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Screw pumps | LE23M849-P-WS-WT-PR-2324 | LE23M849-P-WS-WT-PR-2324-B | Tap Engineering | Pre-order comments issued | 17 | Electrical received on 17.7.24 | Kavin kumar | Kavinkumar.Jaganathan@circor.com; pumps1@tapengineering.com |  | 02.07.24 | 08.07.24 | 18.07.24 | [19 empty] | 05.08.24 | 22.08.24 | 21.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Screw pumps | LE23M849-P-WS-WT-PR-2324 | LE23M849-P-WS-WT-PR-2324-C | Roto Pumps | Pre-order comments issued | 17 | Electrical received on 17.7.24 | Anandan Ethiraj | brd1@rotopumps.com; chn3@rotopumps.com; chn1@rotopumps.com |  | 02.07.24 | 05.07.24 | 18.07.24 | [19 empty] | 05.08.24 | 22.08.24 | 21.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Process | Filter Nozzles | LE23M849-P-WS-WT-PR-2326 | LE23M849-P-WS-WT-PR-2326-A | Guddi | Sent to BU Operations | PR Closed |  | 98197 53544 - Riyaz Shaikh | sales@guddiindia.com |  | 04.05.24 | 15.05.24 | 16.05.24 | [8 empty] | 23.05.24 | 23.05.24 | 24.05.24 | T2 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | karthiga@lntecc.com-12.07.2024-16:03:37
Chittorgarh | Process | Filter Nozzles | LE23M849-P-WS-WT-PR-2326 | LE23M849-P-WS-WT-PR-2326-B | VP Engineers | Post-order technically cleared | 12 |  | 9445003987 - Karthik | karthik@vpengineers.com |  | 04.05.24 | 09.05.24 | 16.05.24 | 21.05.24 | 23.05.24 | [6 empty] | 23.05.24 | 24.05.24 | 24.05.24 | T1 | 11.07.24 | VP Engineers | 12.07.24 | 16.07.24 | 22.07.24 | 23.07.24 |  | 24.07.24 | 10.08.24 | 09.10.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Mechanical | MS Pipe linevalves & DJ | LE23M849-M-WS-CW-PR-1 | LE23M849-M-WS-CW-PR-1-A | Sigma Flow | Post-order technically cleared | 118 | we are taking only sluice valve from this vendor |  | jagadesh@sigmaflow.in | 19.12.23 | 19.12.23 | 21.12.23 | 21.12.23 | [8 empty] | 02.01.24 | 26.12.23 | 15.03.24 | T1 | 05.04.24 | Sigma Flow | 08.04.24 | 08.04.24 | 08.04.24 | 08.04.24 |  | 31.08.24 | 17.09.24 | 04.06.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Mechanical | MS Pipe linevalves & DJ | LE23M849-M-WS-CW-PR-1 | LE23M849-M-WS-CW-PR-1-B | DURGA | Post-order technically cleared | 118 | we are taking Butterfly valve from this vendor |  | chennai@dvpl.co.in | 19.12.23 | 19.12.23 | 21.12.23 | 26.12.23 | [8 empty] | 05.02.24 | 05.02.24 | 15.03.24 | T1 | 02.04.24 | DURGA | 08.04.24 | 08.04.24 | 08.04.24 | 08.04.24 |  | 31.08.24 | 17.09.24 | 01.06.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Mechanical | MS Pipe linevalves & DJ | LE23M849-M-WS-CW-PR-1 | LE23M849-M-WS-CW-PR-1-C | AVK | Post-order technically cleared | 114 | SV,AV,BFV |  |  | 19.12.23 | 19.12.23 | 21.12.23 | 26.12.23 | [8 empty] | 04.02.24 | 01.02.24 | 15.03.24 | T1 | 01.04.24 | AVK | 04.04.24 | 08.04.24 | 16.04.24 | 12.04.24 |  | 31.08.24 | 17.09.24 | 31.05.24 | karthiga@lntecc.com-29.07.2024-10:47:49
Chittorgarh | Mechanical | MS Pipe linevalves & DJ | LE23M849-M-WS-CW-PR-1 | LE23M849-M-WS-CW-PR-1-D | VAG | Sent to BU Operations | PR Closed | Deviations are strictly Subjected to client approval |  |  | 19.12.23 | 19.12.23 | 06.01.24 | 22.01.24 | [8 empty] | 04.02.24 | 02.02.24 | 15.04.24 | T1 |  | VAG | [5 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-10.07.2024-15:43:33
Chittorgarh | Mechanical | Surge valves | LE23M849-M-WS-CW-PR-2 | LE23M849-M-WS-CW-PR-2-A | DURGA | Sent to BU Operations | 19 |  |  |  | 19.12.23 | 19.12.23 | 06.02.24 | 20.02.24 | [8 empty] | 20.02.24 | 18.02.24 | 16.07.24 | T1 | [7 empty] | 11.08.24 | 28.08.24 | 27.10.24 | karthiga@lntecc.com-29.07.2024-10:47:50
Chittorgarh | Mechanical | Surge valves | LE23M849-M-WS-CW-PR-2 | LE23M849-M-WS-CW-PR-2-B | Jash | Sent to BU Operations | 19 |  |  |  |  | 18.03.24 | 25.04.24 | 30.04.24 | 06.05.24 | 08.05.24 | [6 empty] | 08.05.24 | 06.05.24 | 16.07.24 | T1 | [7 empty] | 11.08.24 | 28.08.24 | 27.10.24 | karthiga@lntecc.com-29.07.2024-10:47:50
Chittorgarh | Mechanical | Surge valves | LE23M849-M-WS-CW-PR-2 | LE23M849-M-WS-CW-PR-2-C | Sigma Flow | Sent to BU Operations | 19 |  |  | jagadesh@sigmaflow.in |  | 18.03.24 | 18.03.24 | 19.03.24 | 24.03.24 | 28.03.24 | 22.04.24 | 25.04.24 |  |  |  |  | 25.04.24 | 22.04.24 | 16.07.24 | T1 | [7 empty] | 11.08.24 | 28.08.24 | 27.10.24 | karthiga@lntecc.com-29.07.2024-10:47:50
Chittorgarh | Mechanical | Surge valves | LE23M849-M-WS-CW-PR-2 | LE23M849-M-WS-CW-PR-2-D | Flownix | Regret offer | PR Closed |  |  |  |  | 18.03.24 | 22.04.24 | 29.04.24 | 30.04.24 | 30.04.24 | [17 empty] | 11.08.24 | 28.08.24 | 27.10.24 | karthiga@lntecc.com-16.07.2024-18:24:39
Chittorgarh | Mechanical | Dismantling Joint | LE23M849-M-WS-CW-PR-3 | LE23M849-M-WS-CW-PR-3-A | Vedanta | Post-order technically cleared | 36 |  |  |  |  | 21.03.24 | 23.03.24 | 25.03.24 | 26.03.24 | 28.03.24 | 03.04.24 | 04.04.24 | 04.04.24 | 08.04.24 |  |  | 08.04.24 | 08.04.24 | 08.04.24 | T1 | 09.05.24 | Vedanta | 10.05.24 | 16.05.24 | 29.06.24 | 29.06.24 |  | 31.08.24 | 17.09.24 | 08.07.24 | karthiga@lntecc.com-29.07.2024-10:47:50
Chittorgarh | Mechanical | Dismantling Joint | LE23M849-M-WS-CW-PR-3 | LE23M849-M-WS-CW-PR-3-B | Bikaner | Sent to BU Operations | PR Closed |  |  |  |  | 18.03.24 | 28.03.24 | 03.04.24 | 11.04.24 | 12.04.24 | [6 empty] | 11.04.24 | 11.04.24 | 11.04.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-10.07.2024-15:43:33
Chittorgarh | Mechanical | Dismantling Joint | LE23M849-M-WS-CW-PR-3 | LE23M849-M-WS-CW-PR-3-C | SUR | Regret offer | PR Closed |  |  |  |  | 18.03.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-10.07.2024-15:43:33
Chittorgarh | Mechanical | Dismantling Joint | LE23M849-M-WS-CW-PR-3 | LE23M849-M-WS-CW-PR-3-D | Qualitech | Sent to BU Operations | PR Closed |  |  |  |  | 06.05.24 | 07.05.24 | 08.05.24 | [8 empty] | 08.05.24 | 07.05.24 | 07.05.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-10.07.2024-15:43:33
Chittorgarh | Mechanical | WTP Valves | LE23M849-P-WS-WT-PR-2327 | LE23M849-P-WS-WT-PR-2327-A | AVK | Pre-order pending with EDRC | 29 | Final BOQ is not received yet from Process Team | Subhash -9176966455 | subhash@avkindia.com |  | 10.06.24 | 19.06.24 | 06.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | karthiga@lntecc.com-29.07.2024-10:47:50
Chittorgarh | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE23M849-I-WS-WT-PR-5501 | LE23M849-I-WS-WT-PR-5501-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 01.01.25 | 18.01.25 | 19.03.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:53
Chittorgarh | Instrumentation | Pressure Switch | LE23M849-I-WS-WT-PR-5502 | LE23M849-I-WS-WT-PR-5502-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 03.01.25 | 20.01.25 | 21.03.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Pressure transmitter | LE23M849-I-WS-WT-PR-5503 | LE23M849-I-WS-WT-PR-5503-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 08.01.25 | 25.01.25 | 26.03.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Float & Board Level gauge | LE23M849-I-WS-WT-PR-5504 | LE23M849-I-WS-WT-PR-5504-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 01.02.25 | 18.02.25 | 19.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | level switch - Conductivity type | LE23M849-I-WS-WT-PR-5505 | LE23M849-I-WS-WT-PR-5505-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 24.01.25 | 10.02.25 | 11.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Ultrasonic level Transmitter | LE23M849-I-WS-WT-PR-5506 | LE23M849-I-WS-WT-PR-5506-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 22.01.25 | 08.02.25 | 09.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Radar Level Transmitter | LE23M849-I-WS-WT-PR-5507 | LE23M849-I-WS-WT-PR-5507-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 03.02.25 | 20.02.25 | 21.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Loss of head transmitter | LE23M849-I-WS-WT-PR-5508 | LE23M849-I-WS-WT-PR-5508-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.01.25 | 16.02.25 | 17.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Rate for flow transmitter | LE23M849-I-WS-WT-PR-5509 | LE23M849-I-WS-WT-PR-5509-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 28.01.25 | 14.02.25 | 15.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Bypass Rotameter | LE23M849-I-WS-WT-PR-5510 | LE23M849-I-WS-WT-PR-5510-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 29.01.25 | 15.02.25 | 16.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Electromagnectic flow meter | LE23M849-I-WS-WT-PR-5511 | LE23M849-I-WS-WT-PR-5511-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 05.02.25 | 22.02.25 | 23.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Ultrasonic type Open channel flow transmitter | LE23M849-I-WS-WT-PR-5512 | LE23M849-I-WS-WT-PR-5512-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 04.02.25 | 21.02.25 | 22.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Battery Operated Flow meter | LE23M849-I-WS-WT-PR-5513 | LE23M849-I-WS-WT-PR-5513-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 27.01.25 | 13.02.25 | 14.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | pH Meter | LE23M849-I-WS-WT-PR-5514 | LE23M849-I-WS-WT-PR-5514-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 04.02.25 | 21.02.25 | 22.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Turbidity meter | LE23M849-I-WS-WT-PR-5515 | LE23M849-I-WS-WT-PR-5515-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 22.01.25 | 08.02.25 | 09.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Residual Chlorine Analyzer | LE23M849-I-WS-WT-PR-5516 | LE23M849-I-WS-WT-PR-5516-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 22.01.25 | 08.02.25 | 09.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M849-I-WS-WT-PR-5517 | LE23M849-I-WS-WT-PR-5517-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 01.02.25 | 18.02.25 | 19.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | Instrumentation Control & signal Cables | LE23M849-I-WS-WT-PR-5518 | LE23M849-I-WS-WT-PR-5518-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 05.02.25 | 22.02.25 | 23.04.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Instrumentation | UPS | LE23M849-I-WS-WT-PR-5519 | LE23M849-I-WS-WT-PR-5519-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 20.02.25 | 09.03.25 | 08.05.25 | vignesh.c1@lntecc.com-04.07.2024-12:09:54
Chittorgarh | Electrical | CTPT Unit, Poles & conductors | LE23M849-E-WS-WT-PR-4001 | LE23M849-E-WS-WT-PR-4001-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Transformer | LE23M849-E-WS-WT-PR-4002 | LE23M849-E-WS-WT-PR-4002-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | DG Set | LE23M849-E-WS-WT-PR-4003 | LE23M849-E-WS-WT-PR-4003-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | HT Panel | LE23M849-E-WS-WT-PR-4004 | LE23M849-E-WS-WT-PR-4004-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | HT Fixed Capacitor | LE23M849-E-WS-WT-PR-4005 | LE23M849-E-WS-WT-PR-4005-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | HT Soft Starter | LE23M849-E-WS-WT-PR-4006 | LE23M849-E-WS-WT-PR-4006-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | HT VFD | LE23M849-E-WS-WT-PR-4007 | LE23M849-E-WS-WT-PR-4007-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | LT panels | LE23M849-E-WS-WT-PR-4008 | LE23M849-E-WS-WT-PR-4008-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | DCDB | LE23M849-E-WS-WT-PR-4009 | LE23M849-E-WS-WT-PR-4009-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Bus Duct | LE23M849-E-WS-WT-PR-4010 | LE23M849-E-WS-WT-PR-4010-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Cable | LE23M849-E-WS-WT-PR-4011 | LE23M849-E-WS-WT-PR-4011-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Lugs & Glands | LE23M849-E-WS-WT-PR-4012 | LE23M849-E-WS-WT-PR-4012-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | HT Termination Kit | LE23M849-E-WS-WT-PR-4013 | LE23M849-E-WS-WT-PR-4013-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Cable Tray | LE23M849-E-WS-WT-PR-4014 | LE23M849-E-WS-WT-PR-4014-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Lighting Fixtures | LE23M849-E-WS-WT-PR-4015 | LE23M849-E-WS-WT-PR-4015-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Lighting Materials & accessories | LE23M849-E-WS-WT-PR-4016 | LE23M849-E-WS-WT-PR-4016-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Earthing & Lightning Material | LE23M849-E-WS-WT-PR-4017 | LE23M849-E-WS-WT-PR-4017-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | LDB | LE23M849-E-WS-WT-PR-4018 | LE23M849-E-WS-WT-PR-4018-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | LPBS | LE23M849-E-WS-WT-PR-4019 | LE23M849-E-WS-WT-PR-4019-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Chittorgarh | Electrical | Safety Accessories | LE23M849-E-WS-WT-PR-4020 | LE23M849-E-WS-WT-PR-4020-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | balajirajadurai@lntecc.com-15.04.2024-15:42:25
Dhanbad | Instrumentation | Electromagnetic flow meter | LE190967-I-WS-PR-EF-5505 | LE190967-I-WS-PR-EF-5505-A | ABB | Regret offer | PR Closed |  | Sairam - 9533939906 | sai.ram@in.abb.com |  | 30.09.23 | 30.10.23 | 30.11.23 | [8 empty] | 16.02.24 |  |  | - | [10 empty] | nagendras@lntecc.com-10.07.2024-15:28:43
Dhanbad | Instrumentation | Electromagnetic flow meter | LE190967-I-WS-PR-EF-5505 | LE190967-I-WS-PR-EF-5505-B | Siemens | Regret offer | PR Closed |  | Keerthi guruswamy | keerthi.guruswamy.ext@siemens.com |  | 30.09.23 | 17.01.24 | 30.11.23 | [8 empty] | 16.02.24 |  |  | - | [10 empty] | nagendras@lntecc.com-10.07.2024-15:28:43
Dhanbad | Instrumentation | Electromagnetic flow meter | LE190967-I-WS-PR-EF-5505 | LE190967-I-WS-PR-EF-5505-C | E&H | Sent to BU Operations | 195 |  | Ram Kumar - 9790952907 | ramkumar.m@endress.com |  | 30.09.23 | 10.10.23 | 30.11.23 | [8 empty] | 17.01.24 | 22.01.24 | 22.01.24 | T2 | [8 empty] | Invalid date |  | nagendras@lntecc.com-10.07.2024-15:28:43
Dhanbad | Instrumentation | Electromagnetic flow meter | LE190967-I-WS-PR-EF-5505 | LE190967-I-WS-PR-EF-5505-D | SBEM | Sent to BU Operations | 122 |  | Rajesh - 8681898929 | rajesh.p@sbem.co.in |  | 30.09.23 | 11.10.23 | 22.01.24 | [8 empty] | 31.01.24 | 05.02.24 | 05.02.24 | T1 | 13.03.24 |  | 13.03.24 | 26.03.24 | 04.04.24 | 04.04.24 | 04.04.24 |  | 12.05.24 |  | nagendras@lntecc.com-10.07.2024-16:40:04
Dhanbad | Instrumentation | Pressure gauge | LE190967-I-WS-PR-PG-5500 | LE190967-I-WS-PR-PG-5500A | General instruments | Sent to BU Operations | 200 |  | Dinabandhu Bhatta - 7506042373 | gicchennai@general-gauges.com |  | 30.09.23 | 05.10.23 | 01.12.23 | 12.01.24 | [7 empty] | 17.01.24 | 17.01.24 | 17.01.24 | T2 | [10 empty] | nagendras@lntecc.com-10.07.2024-17:06:15
Dhanbad | Instrumentation | Pressure gauge | LE190967-I-WS-PR-PG-5500 | LE190967-I-WS-PR-PG-5500B | Wika | Regret offer | PR Closed |  | VIJAYALAKSHMI KRISHNAMURTHY | Vijayalakshmi.Krishnamurthy@wika.com |  | 30.09.23 | 20.10.23 | [23 empty] | nagendras@lntecc.com-10.07.2024-17:06:15
Dhanbad | Instrumentation | Pressure gauge | LE190967-I-WS-PR-PG-5500 | LE190967-I-WS-PR-PG-5500C | H Guru | Sent to BU Operations | 201 |  | Anand - 8296294809 | info@hgurusouth.com |  | 30.09.23 | 30.09.23 | 01.12.23 | 11.01.24 | [7 empty] | 16.01.24 | 16.01.24 | 16.01.24 | T1 | [10 empty] | nagendras@lntecc.com-10.07.2024-17:06:15
Dhanbad | Instrumentation | Pressure gauge | LE190967-I-WS-PR-PG-5500 | LE190967-I-WS-PR-PG-5500D | Omega | Regret offer | PR Closed |  | Omega | Omega |  | 30.09.23 | [24 empty] | nagendras@lntecc.com-10.07.2024-17:06:15
Dhanbad | Instrumentation | Pressure switch | LE190967-I-WS-PR-PS-5502 | LE190967-I-WS-PR-PS-5502A | General instruments | Sent to BU Operations | 200 |  | Dinabandhu Bhatta - 7506042373 | gicchennai@general-gauges.com |  | 30.09.23 | 05.10.23 | 01.12.23 | 12.01.24 | [7 empty] | 17.01.24 | 17.01.24 | 17.01.24 | T2 | [10 empty] | nagendras@lntecc.com-10.07.2024-17:06:15
Dhanbad | Instrumentation | Pressure switch | LE190967-I-WS-PR-PS-5502 | LE190967-I-WS-PR-PS-5502B | Wika | Regret offer | PR Closed |  | VIJAYALAKSHMI KRISHNAMURTHY | Vijayalakshmi.Krishnamurthy@wika.com |  | 30.09.23 | 20.10.23 | [23 empty] | nagendras@lntecc.com-10.07.2024-17:06:15
Dhanbad | Instrumentation | Pressure switch | LE190967-I-WS-PR-PS-5502 | LE190967-I-WS-PR-PS-5502C | Omega | Regret offer | PR Closed |  | Omega | Omega |  | 30.09.23 | [24 empty] | nagendras@lntecc.com-10.07.2024-17:06:15
Dhanbad | Instrumentation | Pressure switch | LE190967-I-WS-PR-PS-5502 | LE190967-I-WS-PR-PS-5502D | H Guru | Sent to BU Operations | 201 |  | Anand - 8296294809 | info@hgurusouth.com |  | 30.09.23 | 30.09.23 | 01.12.23 | 11.01.24 | [7 empty] | 16.01.24 | 16.01.24 | 16.01.24 | T1 | [10 empty] | nagendras@lntecc.com-10.07.2024-17:06:15
Dhanbad | Instrumentation | Pressure transmitter | LE190967-I-WS-PR-PT-5503 | LE190967-I-WS-PR-PT-5503A | Siemens | Enquiry yet to float | NA | [29 empty] | nagendras@lntecc.com-10.07.2024-17:35:55
Dhanbad | Instrumentation | Pressure transmitter | LE190967-I-WS-PR-PT-5503 | LE190967-I-WS-PR-PT-5503B | E&H | Enquiry yet to float | NA | [29 empty] | nagendras@lntecc.com-10.07.2024-17:35:55
Dhanbad | Instrumentation | Ultrasonic flow meter | LE190967-I-WS-PR-UF-5501 | LE190967-I-WS-PR-UF-5501-A | E&H | Sent to BU Operations | 247 |  | Ram Kumar - 9790952907 | ramkumar.m@endress.com |  | 30.09.23 | 10.10.23 | 01.12.23 | [8 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T1 | [10 empty] | nagendras@lntecc.com-10.07.2024-15:30:34
Dhanbad | Instrumentation | Ultrasonic flow meter | LE190967-I-WS-PR-UF-5501 | LE190967-I-WS-PR-UF-5501-B | Siemens | Sent to BU Operations | 200 |  | Keerthi guruswamy | keerthi.guruswamy.ext@siemens.com |  | 30.09.23 | 17.01.24 | 01.12.23 | [8 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T3 | [10 empty] | nagendras@lntecc.com-10.07.2024-15:30:34
Dhanbad | Instrumentation | Ultrasonic flow meter | LE190967-I-WS-PR-UF-5501 | LE190967-I-WS-PR-UF-5501-C | ABB | Sent to BU Operations | 247 |  | Sairam - 9533939906 | sai.ram@in.abb.com |  | 30.09.23 | 30.10.23 | 01.12.23 | [8 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T2 | [10 empty] | nagendras@lntecc.com-10.07.2024-15:30:34
Dhanbad | Instrumentation | Ultrasonic flow meter | LE190967-I-WS-PR-UF-5501 | LE190967-I-WS-PR-UF-5501-D | SBEM | Regret offer | PR Closed |  | Rajesh - 8681898929 | rajesh.p@sbem.co.in |  | 30.09.23 | 11.10.23 | [23 empty] | nagendras@lntecc.com-10.07.2024-15:30:34
Dharwad | Process | Clariflocculator | LE22M318-P-001 | LE22M318-P-001-A | Sritech | Sent to BU Operations | PR Closed |  |  |  | 05.12.22 | 05.12.22 | 07.04.23 | 29.04.23 | [8 empty] | 29.04.23 | 29.04.23 | 10.05.23 | T2 | [7 empty] | 10.05.23 | 27.05.23 | 26.07.23 | KUMUTHA@lntecc.com-02.07.2024-11:12:20
Dharwad | Process | Clariflocculator | LE22M318-P-001 | LE22M318-P-001-B | Shivpad | Post-order technically cleared | 226 |  |  |  | 05.12.22 | 05.12.22 | 18.04.23 | 08.05.23 | [8 empty] | 08.05.23 | 08.05.23 | 19.05.23 | T1 | 22.05.23 | Shivpad | 15.12.23 | 22.12.23 | 22.12.23 | 22.12.23 |  | 19.05.23 | 05.06.23 | 21.07.23 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Clariflocculator | LE22M318-P-001 | LE22M318-P-001-C | Triveni | Sent to BU Operations | PR Closed |  |  |  | 05.12.22 | 05.12.22 | 22.08.23 | 30.08.23 | [8 empty] | 30.08.23 | 30.08.23 | 27.09.23 | T3 | [7 empty] | 27.09.23 | 14.10.23 | 13.12.23 | KUMUTHA@lntecc.com-02.07.2024-11:12:20
Dharwad | Process | Air Blower | LE22M318-P-002 | LE22M318-P-002-A | Kay | Post-order technically cleared | 130 |  |  |  | 07.12.22 | 07.12.22 | 29.08.23 | 31.08.23 | [8 empty] | 31.08.23 | 31.08.23 | 15.11.23 | T1 | 23.01.24 | Kay | 05.02.24 | 16.03.24 | 27.03.24 | 27.03.24 |  | 15.11.23 | 02.12.23 | 31.01.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Air Blower | LE22M318-P-002 | LE22M318-P-002-B | Everest | Sent to BU Operations | PR Closed |  |  |  | 07.12.22 | 07.12.22 | 28.10.23 | 04.11.23 | [8 empty] | 04.11.23 | 04.11.23 | 01.12.23 | T2 | [6 empty] | 04.12.23 | 01.12.23 | 18.12.23 | 16.02.24 | KUMUTHA@lntecc.com-02.07.2024-11:11:23
Dharwad | Process | Air Blower | LE22M318-P-002 | LE22M318-P-002-C | Swam | Sent to BU Operations | PR Closed |  |  |  | 07.12.22 | 07.12.22 | 27.11.23 | 06.12.23 | [8 empty] | 25.12.23 | 27.12.23 | 31.12.23 | T3 | [6 empty] | 05.01.24 | 31.12.23 | 17.01.24 | 17.03.24 | KUMUTHA@lntecc.com-02.07.2024-11:11:23
Dharwad | Process | Agitator | LE22M318-P-003 | LE22M318-P-003-A | Sritech | Sent to BU Operations | PR Closed |  |  |  | 21.12.22 | 21.12.22 | 03.04.23 | 09.05.23 | [8 empty] | 09.05.23 | 09.05.23 | 11.05.23 | T2 | [6 empty] | 08.06.23 | 11.05.23 | 28.05.23 | 27.07.23 | KUMUTHA@lntecc.com-02.07.2024-11:13:54
Dharwad | Process | Agitator | LE22M318-P-003 | LE22M318-P-003-B | Shivpad | Post-order technically cleared | 222 |  |  |  | 21.12.22 | 21.12.22 | 29.05.23 | 03.06.23 | [8 empty] | 03.06.23 | 03.06.23 | 15.06.23 | T1 | 27.06.23 | Shivpad | 12.12.23 | 26.12.23 | 26.12.23 | 26.12.23 | 03.07.23 | 15.06.23 | 02.07.23 | 26.08.23 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Agitator | LE22M318-P-003 | LE22M318-P-003-C | Triveni | Sent to BU Operations | PR Closed |  |  |  | 21.12.22 | 21.12.22 | 18.08.23 | 23.08.23 | [8 empty] | 23.08.23 | 23.08.23 | 01.09.23 | T3 | [6 empty] | 22.09.23 | 01.09.23 | 18.09.23 | 17.11.23 | KUMUTHA@lntecc.com-02.07.2024-11:13:54
Dharwad | Process | Sluice gates | LE22M318-P-004 | LE22M318-P-004-A | IVC | Pre-order technically rejected | PR Closed |  |  |  | 16.05.23 | 16.05.23 | 13.12.23 | 22.12.23 | [10 empty] | 22.12.23 | T3 | [7 empty] | 22.05.24 | 08.06.24 | 07.08.24 | KUMUTHA@lntecc.com-02.07.2024-11:40:34
Dharwad | Process | Sluice gates | LE22M318-P-004 | LE22M318-P-004-B | JASH | Pre-order technically cleared | 309 |  |  |  | 16.05.23 | 16.05.23 | 05.09.23 | 16.09.23 | [8 empty] | 16.09.23 | 16.09.23 | 30.09.23 | T1 | [7 empty] | 22.05.24 | 08.06.24 | 07.08.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Sluice gates | LE22M318-P-004 | LE22M318-P-004-C | Oriental | Pre-order technically cleared | 74 |  | 9810205011 | orientalcastings@gmail.com | 16.05.23 | 03.01.24 | 03.04.24 | 16.04.24 | 10.05.24 | 16.05.24 | 18.05.24 | 22.05.24 |  |  |  |  | 22.05.24 | 22.05.24 | 22.05.24 | T2 | [7 empty] | 22.05.24 | 08.06.24 | 07.08.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Chlorination system | LE22M318-P-005 | LE22M318-P-005-A | IEC | Sent to BU Operations | PR Closed |  |  |  | 13.01.23 | 13.01.23 | 19.10.23 | 30.10.23 | [8 empty] | 30.10.23 | 30.10.23 | 11.11.23 | T2 | [6 empty] | 29.11.23 | 11.11.23 | 28.11.23 | 27.01.24 | KUMUTHA@lntecc.com-02.07.2024-11:14:41
Dharwad | Process | Chlorination system | LE22M318-P-005 | LE22M318-P-005-B | ZION | Post-order technically cleared | 53 | Electrical clearance given | 9828977765 Deepak Santram | deepak@ziontech.in | 13.01.23 | 13.01.23 | 19.10.23 | 30.10.23 | [8 empty] | 30.10.23 | 30.10.23 | 07.11.23 | T1 | 08.01.24 | ZION | 04.05.24 | 12.06.24 | 12.06.24 | 12.06.24 |  | 07.11.23 | 24.11.23 | 23.01.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Chlorination system | LE22M318-P-005 | LE22M318-P-005-C | Chloro tech | Sent to BU Operations | PR Closed |  |  |  | 13.01.23 | 13.01.23 | 27.12.23 | 28.12.23 | [8 empty] | 28.12.23 | 28.12.23 | 17.01.24 | T3 | [6 empty] | 27.01.24 | 17.01.24 | 03.02.24 | 03.04.24 | KUMUTHA@lntecc.com-02.07.2024-11:14:41
Dharwad | Process | Chlorine Tonner | LE22M318-P-006 | LE22M318-P-006-A | ZION | Post-order technically cleared | 53 |  |  |  | 13.01.23 | 13.01.23 | 15.11.23 | 28.11.23 | [8 empty] | 21.01.24 | 03.02.24 | 14.02.24 | T1 | 14.02.24 | ZION | 04.05.24 | 12.06.24 | 12.06.24 | 12.06.24 |  | 14.02.24 | 02.03.24 | 14.04.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Filter media | LE22M318-P-007 | LE22M318-P-007-A |  | Enquiry yet to float | NA | Site Procurement |  |  | 07.12.22 | 07.12.22 | [24 empty] | KUMUTHA@lntecc.com-17.07.2024-15:27:23
Dharwad | Process | Backwash pump | LE22M318-P-008 | LE22M318-P-008-A | KBL | Sent to BU Operations | PR Closed |  |  |  | 30.12.22 | 30.12.22 | 03.07.23 | 11.07.23 | [8 empty] | 11.07.23 | 11.07.23 | 06.08.23 | T3 | [6 empty] | 10.08.23 | 06.08.23 | 23.08.23 | 22.10.23 | KUMUTHA@lntecc.com-02.07.2024-11:16:36
Dharwad | Process | Backwash pump | LE22M318-P-008 | LE22M318-P-008-B | Wilo | Post-order technically cleared | 97 |  |  |  | 30.12.22 | 30.12.22 | 15.11.23 | 22.11.23 | [8 empty] | 22.11.23 | 22.11.23 | 26.12.23 | T1 | 20.01.24 | Wilo | 29.01.24 | 29.04.24 | 29.04.24 | 29.04.24 |  | 26.12.23 | 12.01.24 | 12.03.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Backwash pump | LE22M318-P-008 | LE22M318-P-008-C | WPIL | Sent to BU Operations | PR Closed |  |  |  | 30.12.22 | 30.12.22 | 31.08.23 | 04.09.23 | [8 empty] | 04.09.23 | 04.09.23 | 17.09.23 | T2 | [6 empty] | 04.10.23 | 17.09.23 | 04.10.23 | 03.12.23 | KUMUTHA@lntecc.com-02.07.2024-11:16:36
Dharwad | Process | Submersible pump | LE22M318-P-009 | LE22M318-P-009-A | MBH | Post-order technically cleared | 123 | Electrical Clearance given |  |  | 16.05.23 | 16.05.23 | 05.09.23 | 11.09.23 | [8 empty] | 11.09.23 | 11.09.23 | 21.01.24 | TI | 30.01.24 | MBH | 31.01.24 | 03.04.24 | 03.04.24 | 03.04.24 |  | 21.01.24 | 07.02.24 | 30.03.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Submersible pump | LE22M318-P-009 | LE22M318-P-009-B | Aqua Machinary | Sent to BU Operations | PR Closed |  |  |  | 16.05.23 | 16.05.23 | 21.06.23 | 29.06.23 | [8 empty] | 29.06.23 | 07.07.23 | 04.08.23 | T3 | [6 empty] | 06.08.23 | 04.08.23 | 21.08.23 | 20.10.23 | KUMUTHA@lntecc.com-02.07.2024-11:17:26
Dharwad | Process | Submersible pump | LE22M318-P-009 | LE22M318-P-009-C | KSB | Sent to BU Operations | PR Closed |  |  |  | 16.05.23 | 16.05.23 | 10.12.23 | 18.12.23 | [8 empty] | 18.12.23 | 18.12.23 | 31.12.23 | T2 | [6 empty] | 17.01.24 | 31.12.23 | 17.01.24 | 17.03.24 | KUMUTHA@lntecc.com-02.07.2024-11:17:26
Dharwad | Process | Electrical hoist | LE22M318-P-010 | LE22M318-P-010-A | Reva | Sent to BU Operations | PR Closed |  |  |  | 05.01.23 | 05.01.23 | 06.01.24 | 12.01.24 | [8 empty] | 23.01.24 | 23.01.24 | 20.02.24 | T3 | [7 empty] | 20.02.24 | 08.03.24 | 07.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:29:57
Dharwad | Process | Electrical hoist | LE22M318-P-010 | LE22M318-P-010-B | Brady | Regret offer | PR Closed |  |  |  | 05.01.23 | 05.01.23 | 26.06.23 | 13.07.23 | [8 empty] | 25.11.23 | 19.01.24 | 20.02.24 | T4 | [7 empty] | 20.02.24 | 08.03.24 | 07.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:29:57
Dharwad | Process | Electrical hoist | LE22M318-P-010 | LE22M318-P-010-C | Indef | Post-order technically cleared | 53 |  |  |  | 05.01.23 | 05.01.23 | 14.09.23 | 19.09.23 | [8 empty] | 19.09.23 | 19.09.23 | 20.02.24 | T1 | 18.03.24 | Indef | 10.05.24 | 12.06.24 | 12.06.24 | 12.06.24 |  | 20.02.24 | 08.03.24 | 07.05.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Electrical hoist | LE22M318-P-010 | LE22M318-P-010-D | Japs | Sent to BU Operations | PR Closed |  |  |  | 05.01.23 | 05.01.23 | 26.12.23 | 29.12.23 | [8 empty] | 03.01.24 | 17.01.24 | 25.01.24 | T2 | [7 empty] | 25.01.24 | 11.02.24 | 11.04.24 | KUMUTHA@lntecc.com-02.07.2024-11:29:57
Dharwad | Process | Manual chain pulley block | LE22M318-P-011 | LE22M318-P-011-A | Reva | Sent to BU Operations | PR Closed |  |  |  | 05.01.23 | 05.01.23 | 06.01.24 | 07.01.24 | [8 empty] | 16.02.24 | 19.02.24 | 20.02.24 | T3 | [7 empty] | 20.02.24 | 08.03.24 | 07.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:30:34
Dharwad | Process | Manual chain pulley block | LE22M318-P-011 | LE22M318-P-011-B | Brady | Sent to BU Operations | PR Closed |  |  |  | 05.01.23 | 05.01.23 | 26.06.23 | 13.07.23 | [8 empty] | 27.11.23 | 01.12.23 | 20.02.24 | T4 | [7 empty] | 20.02.24 | 08.03.24 | 07.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:30:34
Dharwad | Process | Manual chain pulley block | LE22M318-P-011 | LE22M318-P-011-C | Indef | Post-order technically cleared | 53 |  |  |  | 05.01.23 | 05.01.23 | 14.09.23 | 19.09.23 | [8 empty] | 19.09.23 | 19.09.23 | 20.02.24 | T1 | 18.03.24 | Indef | 10.05.24 | 12.06.24 | 12.06.24 | 12.06.24 |  | 20.02.24 | 08.03.24 | 07.05.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Manual chain pulley block | LE22M318-P-011 | LE22M318-P-011-D | Japs | Sent to BU Operations | PR Closed |  |  |  | 05.01.23 | 05.01.23 | 26.12.23 | 06.01.24 | [8 empty] | 22.01.24 | 23.01.24 | 25.01.24 | T2 | [10 empty] | KUMUTHA@lntecc.com-20.05.2024-09:35:25
Dharwad | Process | Dosing pump | LE22M318-P-012 | LE22M318-P-012-A | Positive Metering | Sent to BU Operations | PR Closed |  |  |  | 03.01.23 | 03.01.23 | 14.12.23 | 22.12.23 | [8 empty] | 22.12.23 | 22.12.23 | 21.02.24 | T1 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Dosing pump | LE22M318-P-012 | LE22M318-P-012-B | SR Metering | Post-order technically cleared | 116 |  |  |  | 03.01.23 | 03.01.23 | 07.10.23 | 15.11.23 | [8 empty] | 02.02.24 | 07.02.24 | 21.02.24 | T2 | 09.03.23 | SR Metering | 13.03.24 | 10.04.24 | 10.04.24 | 10.04.24 |  | 21.02.24 | 09.03.24 | 08.05.23 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Dosing pump | LE22M318-P-012 | LE22M318-P-012-C | Swellore | Sent to BU Operations | PR Closed |  |  |  | 03.01.23 | 03.01.23 | 10.11.23 | 23.11.23 | [8 empty] | 16.01.24 | 17.01.24 | 21.02.24 | T3 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Sampling pump | LE22M318-P-013 | LE22M318-P-013-A | KSB | Pre-order comments issued | 230 | Vendor not responding |  |  | 30.12.22 | 30.12.22 | 09.12.23 | 18.12.23 | [22 empty] | KUMUTHA@lntecc.com-17.07.2024-15:06:23
Dharwad | Process | Submersible mixer | LE22M318-P-014 | LE22M318-P-014-A | ABS | Post-order technically cleared | 150 |  |  |  | 06.01.23 | 06.01.23 | 10.05.23 | 15.05.23 | [8 empty] | 15.05.23 | 15.05.23 | 21.02.24 | T1 | 07.03.24 | ABS | 16.02.24 | 23.02.24 | 23.02.24 | 23.02.24 |  | 21.02.24 | 09.03.24 | 06.05.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Submersible mixer | LE22M318-P-014 | LE22M318-P-014-B | Xylem | Sent to BU Operations | PR Closed |  |  |  | 06.01.23 | 06.01.23 | 22.06.23 | 06.07.23 | [8 empty] | 06.07.23 | 06.07.23 | 21.02.24 | T3 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:34:03
Dharwad | Process | Submersible mixer | LE22M318-P-014 | LE22M318-P-014-C | Grundfos | Sent to BU Operations | PR Closed |  |  |  | 06.01.23 | 06.01.23 | 16.05.23 | 22.05.23 | [8 empty] | 01.08.23 | 14.09.23 | 21.02.24 | T4 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:34:03
Dharwad | Process | Submersible mixer | LE22M318-P-014 | LE22M318-P-014-D | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 06.01.23 | 06.01.23 | 14.06.23 | 21.06.23 | [8 empty] | 21.06.23 | 21.06.23 | 21.02.24 | T2 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:34:03
Dharwad | Process | Dewatering pump | LE22M318-P-015 | LE22M318-P-015-A | MBH | Post-order technically cleared | 58 | Order confirmed to MBH | 99200 13772 | mailto:northindustrial@mbhpumps.com | 03.01.23 | 03.01.23 | 11.09.23 | 20.02.24 | [8 empty] | 20.02.24 | 20.02.24 | 20.02.24 | T1 | 06.03.24 | MBH | 05.04.24 | 07.06.24 | 07.06.24 | 07.06.24 |  | 20.02.24 | 08.03.24 | 05.05.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Dewatering pump | LE22M318-P-015 | LE22M318-P-015-B | SJI | Sent to BU Operations | PR Closed |  |  |  | 03.01.23 | 03.01.23 | 23.01.24 | 14.02.24 | 22.02.24 | 04.03.24 | 06.03.24 | 16.03.24 |  |  |  |  | 16.03.24 | 16.03.24 | 16.03.24 | T2 | [7 empty] | 16.03.24 | 02.04.24 | 01.06.24 | KUMUTHA@lntecc.com-02.07.2024-11:34:41
Dharwad | Process | Sludge thickener | LE22M318-P-016 | LE22M318-P-016-A | Sritech | Sent to BU Operations | PR Closed |  |  |  | 21.12.22 | 21.12.22 | 10.04.23 | 02.05.23 | [8 empty] | 02.05.23 | 02.05.23 | 08.05.23 | T2 | [6 empty] | 01.06.23 | 08.05.23 | 25.05.23 | 24.07.23 | KUMUTHA@lntecc.com-02.07.2024-11:53:18
Dharwad | Process | Sludge thickener | LE22M318-P-016 | LE22M318-P-016-B | Shivpad | Post-order technically cleared | 226 |  |  |  | 21.12.22 | 21.12.22 | 25.04.23 | 08.05.23 | [8 empty] | 08.05.23 | 08.05.23 | 20.05.23 | T1 | 22.05.23 | Shivpad | 15.12.23 | 22.12.23 | 22.12.23 | 22.12.23 | 07.06.23 | 20.05.23 | 06.06.23 | 21.07.23 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Sludge thickener | LE22M318-P-016 | LE22M318-P-016-C | Triveni | Sent to BU Operations | PR Closed |  |  |  | 21.12.22 | 21.12.22 | 07.08.23 | 19.08.23 | [8 empty] | 19.08.23 | 19.08.23 | 28.08.23 | T3 | [6 empty] | 18.09.23 | 28.08.23 | 14.09.23 | 13.11.23 | KUMUTHA@lntecc.com-02.07.2024-11:53:18
Dharwad | Process | Centrifuge | LE22M318-P-017 | LE22M318-P-017-A | SKS Decanter | Sent to BU Operations | PR Closed |  |  |  | 27.12.22 | 27.12.22 | 02.08.23 | 09.08.23 | [8 empty] | 09.08.23 | 09.08.23 | 21.02.24 | T1 |  | SKS Decanter | 12.03.24 | 22.03.24 |  |  |  | 21.02.24 | 09.03.24 | 08.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:56:08
Dharwad | Process | Centrifuge | LE22M318-P-017 | LE22M318-P-017-B | Hiller | Sent to BU Operations | PR Closed |  |  |  | 27.12.22 | 27.12.22 | 28.08.23 | 31.08.23 | [8 empty] | 05.12.23 | 06.01.24 | 21.02.24 | T4 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:56:08
Dharwad | Process | Centrifuge | LE22M318-P-017 | LE22M318-P-017-C | Tega | Post-order technically cleared | 25 |  | Pratik kumar - 87892 86713 (Tega) Tapan datta - 9830380032 (Tega) |  | 27.12.22 | 27.12.22 | 14.12.23 | 27.12.23 | [8 empty] | 16.02.24 | 16.02.24 | 21.02.24 | T2 | 03.06.24 | Tega | 05.06.24 | 10.07.24 | 10.07.24 | 10.07.24 |  | 21.02.24 | 09.03.24 | 08.05.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Centrifuge | LE22M318-P-017 | LE22M318-P-017-D | Alpha | Sent to BU Operations | PR Closed |  |  |  | 27.12.22 | 27.12.22 | 06.01.24 | 07.01.24 | [8 empty] | 15.01.24 | 16.02.24 | 21.02.24 | T3 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:56:08
Dharwad | Process | Trolley | LE22M318-P-018 | LE22M318-P-018-A |  | Enquiry yet to float | NA | Site procurement |  |  | 05.12.22 | 05.12.22 | [24 empty] | KUMUTHA@lntecc.com-17.07.2024-15:27:23
Dharwad | Process | DWPE tank | LE22M318-P-019 | LE22M318-P-019-A | FFP | Awaiting post-offer from vendor | 13 |  |  |  | 28.12.22 | 28.12.22 | 04.11.23 | 22.03.24 | [8 empty] | 22.03.24 | 22.03.24 | 22.03.24 | T1 | 22.07.24 | FFP | [5 empty] | 22.03.24 | 08.04.24 | 07.06.24 | KUMUTHA@lntecc.com-22.07.2024-17:06:12
Dharwad | Process | DWPE tank | LE22M318-P-019 | LE22M318-P-019-B | Spiral Specialist | Sent to BU Operations | PR Closed |  |  |  | 28.12.22 | 28.12.22 | 03.11.23 | 19.03.24 | [8 empty] | 19.03.24 | 19.03.24 | 19.03.24 | T2 | [7 empty] | 22.03.24 | 08.04.24 | 07.06.24 | KUMUTHA@lntecc.com-22.07.2024-17:06:12
Dharwad | Process | DWPE tank | LE22M318-P-019 | LE22M318-P-019-C | BS Projects | Regret offer | PR Closed | offer not evaluated |  |  | 28.12.22 | 28.12.22 | [21 empty] | 22.03.24 | 08.04.24 | 07.06.24 | KUMUTHA@lntecc.com-01.07.2024-14:23:26
Dharwad | Process | DWPE tank agitator | LE22M318-P-020 | LE22M318-P-020-A | Positive metering | Sent to BU Operations | PR Closed |  |  |  | 28.12.22 | 28.12.22 | 28.12.22 | 04.01.23 | [8 empty] | 15.03.23 | 25.01.24 | 21.02.24 | T3 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:54:05
Dharwad | Process | DWPE tank agitator | LE22M318-P-020 | LE22M318-P-020-B | FFP | Sent to BU Operations | PR Closed |  |  |  | 28.12.22 | 28.12.22 | 29.12.22 | 04.01.23 | [8 empty] | 14.10.23 | 03.02.24 | 21.02.24 | T2 | [7 empty] | 21.02.24 | 09.03.24 | 08.05.24 | KUMUTHA@lntecc.com-02.07.2024-11:54:05
Dharwad | Process | DWPE tank agitator | LE22M318-P-020 | LE22M318-P-020-C | Verito Engineering Private Limited | Post-order technically cleared | 109 |  | 91-8511744393 | parth@veritoengineering.com | 28.12.22 | 28.12.22 | 19.12.23 | 29.01.24 | [8 empty] | 04.02.24 | 14.02.24 | 21.02.24 | T1 | 13.02.24 | Verito Engineering Private Limited | 27.03.24 | 17.04.24 | 17.04.24 | 17.04.24 |  | 21.02.24 | 09.03.24 | 13.04.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Platform weighing machine | LE22M318-P-021 | LE22M318-P-021-A |  | Enquiry yet to float | NA | Site procurement |  |  | 27.12.22 | 27.12.22 | [24 empty] | KUMUTHA@lntecc.com-17.07.2024-15:27:23
Dharwad | Process | Screw pumps | LE22M318-P-022 | LE22M318-P-022-A | Positive | Post-order technically cleared | 352 |  |  |  | 11.01.23 | 11.01.23 | 13.07.23 | 19.07.23 | [8 empty] | 19.07.23 | 19.07.23 | 31.07.23 | T1 | 02.08.23 | Positive | 16.08.23 | 17.08.23 | 17.08.23 | 17.08.23 | 18.08.23 | 31.07.23 | 17.08.23 | 01.10.23 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Screw pumps | LE22M318-P-022 | LE22M318-P-022-B | Tushaco | Sent to BU Operations | PR Closed |  |  |  | 11.01.23 | 11.01.23 | 02.09.23 | 04.09.23 | [8 empty] | 04.09.23 | 04.09.23 | 12.09.23 | T3 | [6 empty] | 04.10.23 | 12.09.23 | 29.09.23 | 28.11.23 | KUMUTHA@lntecc.com-02.07.2024-11:55:12
Dharwad | Process | Screw pumps | LE22M318-P-022 | LE22M318-P-022-C | Netzsch | Sent to BU Operations | PR Closed |  |  |  | 11.01.23 | 11.01.23 | 01.08.23 | 04.09.23 | [8 empty] | 04.09.23 | 04.09.23 | 25.09.23 | T2 | [6 empty] | 04.10.23 | 25.09.23 | 12.10.23 | 11.12.23 | KUMUTHA@lntecc.com-02.07.2024-11:55:12
Dharwad | Process | Dissolving tray | LE22M318-P-023 | LE22M318-P-023-A |  | Enquiry yet to float | NA | Site Procurement |  |  | 11.01.23 | 11.01.23 | [24 empty] | KUMUTHA@lntecc.com-17.07.2024-15:27:23
Dharwad | Process | Exhaust fan | LE22M318-P-024 | LE22M318-P-024-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site procurement |  |  | 10.04.23 | 10.04.23 | [24 empty] | KUMUTHA@lntecc.com-02.07.2024-11:56:15
Dharwad | Process | Lab Equipments | LE22M318-P-025 | LE22M318-P-025-A | Labard | Pre-order comments issued | 210 | Pending with vendor |  |  | 18.12.23 | 18.12.23 | 28.12.23 | 07.01.24 | [22 empty] | KUMUTHA@lntecc.com-17.07.2024-15:27:23
Dharwad | Process | Air compressor | LE22M318-P-026 | LE22M318-P-026-A | ELGI | Regret offer | PR Closed | Vendor is not responding |  |  | 6.07.23 | 06.07.23 | 28.07.23 | 01.08.23 | [19 empty] | 30.03.24 | 16.04.24 | 15.06.24 | KUMUTHA@lntecc.com-02.07.2024-11:56:15
Dharwad | Process | Air compressor | LE22M318-P-026 | LE22M318-P-026-B | Atlas copcos | Pre-order technically cleared | 345 |  |  |  | 6.07.23 | 06.07.23 | 17.08.23 | 25.08.23 | [8 empty] | 25.08.23 | 25.08.23 | [9 empty] | 30.03.24 | 16.04.24 | 15.06.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Air compressor | LE22M318-P-026 | LE22M318-P-026-C | Indo Air | Pre-order technically cleared | 127 |  |  |  | 6.07.23 | 06.07.23 | 18.03.24 | 28.03.24 | 29.03.24 | 30.03.24 | [6 empty] | 30.03.24 | 30.03.24 | [9 empty] | 30.03.24 | 16.04.24 | 15.06.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Process | Re chlorination system | LE22M318-P-027 | LE22M318-P-027-A | Verito | Pre-order technically cleared | 125 | Electrical comments issued | 91- 7859801358 - Jay Shukla 079-90045766 | mailto:dosingsystems@veritoengineering.com | 4.09.23 | 04.09.23 | 22.02.24 | 07.03.24 | 09.03.24 | 19.03.24 | 20.03.24 | 01.04.24 | 01.04.24 | 01.04.24 |  |  | 01.04.24 | 01.04.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-25.07.2024-19:03:39
Dharwad | Process | Re chlorination system | LE22M318-P-027 | LE22M318-P-027-B | Shivnetra Enterprises | Pre-order comments issued | 55 |  |  |  |  | 04.09.23 | 24.05.24 | 03.06.24 | 06.06.24 | 10.06.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-25.07.2024-19:03:39
Dharwad | Process | Re chlorination system | LE22M318-P-027 | LE22M318-P-027-C | Positive Metering | Pre-order technically cleared | 10 |  | Dhiraj More - 7385559871 |  |  | 04.09.23 | 10.06.24 | 19.06.24 | 27.06.24 | 02.07.24 | 05.07.24 | 06.07.24 | 22.07.24 | 25.07.24 |  |  | 25.07.24 | 25.07.24 | 25.07.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-25.07.2024-19:03:39
Dharwad | Process | Re chlorination system | LE22M318-P-027 | LE22M318-P-027-D | Milton Roy | Pre-order comments issued | 18 |  |  |  |  | 04.09.23 | 12.06.24 | 19.06.24 | 15.07.24 | 17.07.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-25.07.2024-19:03:39
Dharwad | Mechanical | Sluice Gates | LE22M318-M-001 | LE22M318-M-001-A | JASH | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 03.05.23 | 03.05.23 | [8 empty] | 18.05.23 | 19.01.23 | 12.02.23 | T1 | 17.06.23 | [8 empty] | 16.08.23 | rallabandi.bharadwaj@lntecc.com-01.07.2024-18:00:16
Dharwad | Mechanical | Sluice Gates | LE22M318-M-001 | LE22M318-M-001-B | AVK | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 13.04.23 | 13.04.23 | [8 empty] | 14.05.23 | 29.12.22 | 12.02.23 | T1 | [10 empty] | mallipudi.raju@lntecc.com-17.05.2024-12:11:57
Dharwad | Mechanical | Sluice Gates | LE22M318-M-001 | LE22M318-M-001-C | IVC | Post-order technically cleared | 78 |  |  |  | 22.02.23 | 22.02.23 | 14.04.23 | 14.04.23 | 18.05.24 | 18.05.24 | [6 empty] | 09.01.24 | 08.02.23 | 12.02.23 | T1 | 09.06.23 | IVC | 10.05.24 | 13.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  |  | 08.08.23 | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | HSC Pumps | LE22M318-M-002 | LE22M318-M-002-A | Wilo | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 12.04.23 | 26.02.24 | [8 empty] | 26.02.24 | 27.02.24 | 28.02.24 | T2 | [6 empty] | 19.03.24 |  |  |  | deepak.sabnani@lntecc.com-17.07.2024-15:28:36
Dharwad | Mechanical | HSC Pumps | LE22M318-M-002 | LE22M318-M-002-B | WPIL | Post-order technically cleared | 47 |  |  |  | 22.02.23 | 22.02.23 | 01.06.23 | 01.06.23 | [8 empty] | 21.02.24 | 07.03.24 | 18.03.24 | T3 | 15.04.24 | WPIL | 13.05.24 | 14.05.24 | 18.06.24 | 18.06.24 | 19.03.24 |  |  | 14.06.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | HSC Pumps | LE22M318-M-002 | LE22M318-M-002-C | KBL | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 13.03.23 | 13.03.23 | [8 empty] | 21.02.24 | 10.03.24 | 18.03.24 | T4 | [6 empty] | 19.03.24 |  |  |  | deepak.sabnani@lntecc.com-17.07.2024-15:28:36
Dharwad | Mechanical | HSC Pumps | LE22M318-M-002 | LE22M318-M-002-E | XYLEM | Sent to BU Operations | PR Closed | Motor weight is not provided |  |  | 22.02.23 | 22.02.23 | 30.01.24 | 21.02.24 | [8 empty] | 20.03.24 | 19.03.24 | 19.03.24 | T1 | [6 empty] | 19.03.24 |  |  |  | deepak.sabnani@lntecc.com-17.07.2024-15:28:36
Dharwad | Mechanical | VT Pumps | LE22M318-M-003 | LE22M318-M-003-A | Wilo | Approved by Client | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 25.05.23 | 25.05.23 | [8 empty] | 26.10.23 | 30.10.23 | 16.01.24 | T2 | 08.02.24 | Wilo | 24.11.23 | 26.12.23 | 02.01.24 | 02.01.24 | 08.02.24 |  |  | 08.04.24 | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | VT Pumps | LE22M318-M-003 | LE22M318-M-003-B | WPIL | Post-order technically cleared | 24 |  |  |  | 22.02.23 | 22.02.23 | 29.06.23 | 29.06.23 | [8 empty] | 07.12.23 | 09.12.23 | 16.01.24 | T2 | 15.04.24 | WPIL | 16.05.24 | 17.05.24 | 11.07.24 | 11.07.24 |  |  |  | 14.06.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | VT Pumps | LE22M318-M-003 | LE22M318-M-003-C | KBL | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 14.03.23 | 14.03.23 | [8 empty] | 10.08.23 | 10.08.23 | 16.01.24 | T2 | [10 empty] | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | VT Pumps | LE22M318-M-003 | LE22M318-M-003-D | XYLEM | Sent to BU Operations | PR Closed | Motor weight is not provided |  |  | 22.02.23 | 22.02.23 | 30.01.24 | 01.03.24 | [8 empty] | 10.03.24 | 19.03.24 | 19.03.24 | T1 | [6 empty] | 19.03.24 |  |  |  | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | Pipe Line Valves (AV,SLV,BFV) | LE22M318-M-004 | LE22M318-M-004-A | Jupiter | Sent to BU Operations | PR Closed |  |  |  | 4.05.23 | 04.05.23 | 18.07.23 | 18.07.23 | [8 empty] | 18.10.23 | 16.10.23 | 17.10.23 | T3 | [10 empty] | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | Pipe Line Valves (AV,SLV,BFV) | LE22M318-M-004 | LE22M318-M-004-B | KBL | Sent to BU Operations | PR Closed |  |  |  | 4.05.23 | 04.05.23 | 17.07.23 | 17.07.23 | [8 empty] | 30.08.23 | 30.08.23 | 17.10.23 | T2 | [10 empty] | mallipudi.raju@lntecc.com-17.05.2024-12:11:57
Dharwad | Mechanical | Pipe Line Valves (AV,SLV,BFV) | LE22M318-M-004-BFYV | LE22M318-M-004-BFYV-A | Durga | Post-order technically cleared | 203 | Butterfly valve - offer cancelled |  |  | 4.05.23 | 04.05.23 | 03.11.23 | 03.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.12.23 | T1 | 07.01.24 | Durga | 12.01.24 | 13.01.24 | 13.01.24 | 13.01.24 | 14.01.24 |  |  | 07.03.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | Pipe Line Valves (AV,SLV,BFV) | LE22M318-M-004 | LE22M318-M-004-C | VAG cleared | Sent to BU Operations | PR Closed |  |  |  | 4.05.23 | 04.05.23 | 17.07.23 | 17.07.23 | [8 empty] | 05.10.23 | 05.10.23 | 17.10.23 | T3 | [10 empty] | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | Pipe Line Valves (AV,SLV,BFV) | LE22M318-M-004 | LE22M318-M-004-D | AVK cleared | Post-order technically cleared | 108 | only Butterfly valve we are taking |  |  | 4.05.23 | 04.05.23 | 17.07.23 | 17.07.23 | [8 empty] | 16.09.23 | 16.09.23 | 17.10.23 | T2 | 12.04.24 | AVK cleared | 18.04.24 | 18.04.24 | 18.04.24 | 18.04.24 |  |  |  | 11.06.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | Pipe Line Valves (AV,SLV,BFV) | LE22M318-M-004 | LE22M318-M-004-F | Hawle | Post-order technically cleared | 223 | Air valve & Sluice valve - post order doc. approval with client |  |  | 4.05.23 | 04.05.23 | 26.10.23 | 26.10.23 | [8 empty] | 26.10.23 | 03.11.23 | 25.11.23 | T1 | 08.12.23 | Hawle | 17.12.23 | 17.12.23 | 24.12.23 | 24.12.23 | 25.12.23 |  |  | 06.02.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | Pump House Valves (AV,BFV,NRV,SLV) | LE22M318-M-004 | LE22M318-M-004-G | VAG | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 19.08.23 | 19.08.23 | [8 empty] | 14.11.23 | 14.11.23 | 05.02.24 | T2 | [10 empty] | mallipudi.raju@lntecc.com-17.05.2024-12:11:57
Dharwad | Mechanical | Pump House Valves (AV,BFV,NRV,SLV) | LE22M318-M-004 | LE22M318-M-004-H | AVK | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 21.08.23 | 21.08.23 | [8 empty] | 02.09.23 | 16.09.23 | 05.02.24 | T3 | [10 empty] | mallipudi.raju@lntecc.com-17.05.2024-12:11:57
Dharwad | Mechanical | Pump House Valves (AV,BFV,NRV,SLV) | LE22M318-M-004 | LE22M318-M-004-I | KBL | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 12.09.23 | 12.09.23 | [8 empty] | 03.11.23 | 03.11.23 | 05.02.24 | T3 | [10 empty] | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | Pump House Valves (AV,BFV,NRV,SLV) | LE22M318-M-004 | LE22M318-M-004-J | Hawle | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 26.10.23 | 26.10.23 | [8 empty] | 06.11.23 | 06.11.23 | 05.02.24 | T3 | [10 empty] | mallipudi.raju@lntecc.com-17.05.2024-12:11:57
Dharwad | Mechanical | Pump House Valves (AV,BFV,NRV,SLV) | LE22M318-M-004 | LE22M318-M-004-K | Durga | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 04.12.23 | 04.12.23 | [8 empty] | 08.12.23 | 08.12.23 | 05.02.24 | T3 | [10 empty] | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | Pump House Valves (AV,BFV,NRV,SLV) | LE22M318-M-004 | LE22M318-M-004-L | MAGWEN | Sent to BU Operations | PR Closed | PR Released By SCM |  |  | 11.03.24 | 11.03.24 | 11.03.24 | 12.03.24 | [8 empty] | 08.12.23 | 08.12.23 | 05.02.24 | T1 | 21.03.24 | MAGWEN | 06.04.24 | 12.04.24 | 16.04.24 | 16.04.24 |  |  |  | 20.05.24 | deepak.sabnani@lntecc.com-01.07.2024-11:16:35
Dharwad | Mechanical | DJ &EB | LE22M318-M-004 | LE22M318-M-004-M | Qualitech | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 16.01.24 | 16.01.24 | [8 empty] | 16.01.24 | 16.01.24 | 20.01.24 | T2 | [6 empty] | 15.02.24 |  |  |  | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | DJ &EB | LE22M318-M-004 | LE22M318-M-004-N | PRECISE ENGINEER | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 16.01.24 | 16.01.24 | [8 empty] | 18.01.24 | 18.01.24 | 24.01.24 | T1 | [6 empty] | 17.02.24 |  |  |  | mallipudi.raju@lntecc.com-15.05.2024-14:37:02
Dharwad | Mechanical | EOT CRANE | LE22M318-M-005 | LE22M318-M-005-A | INDEF | Regret offer | PR Closed | Order confirmed to Indef |  |  | 22.02.23 | 22.02.23 | 19.01.24 | 05.02.24 | [8 empty] | 29.02.24 | 11.03.24 | 12.03.24 | T1 | 30.03.24 | INDEF | 16.05.24 | 16.05.24 | [5 empty] | 29.05.24 | rohit.shaw@lntecc.com-26.06.2024-13:45:05
Dharwad | Mechanical | EOT CRANE | LE22M318-M-005 | LE22M318-M-005-B | REVA | Sent to BU Operations | PR Closed |  |  |  | 22.02.23 | 22.02.23 | 16.01.24 | 18.01.24 | [8 empty] | 27.01.24 | 10.02.24 | 12.03.24 | T2 | [10 empty] | deepak.sabnani@lntecc.com-01.07.2024-11:16:35
Dharwad | Mechanical | EOT CRANE | LE22M318-M-005 | LE22M318-M-005-C | JAPS | Post-order technically cleared | 29 | Technical clears given ,subjected to client approval |  |  | 22.02.23 | 22.02.23 | 17.01.24 | 18.01.24 | [8 empty] | 09.02.24 | 14.02.24 | 12.03.24 | T3 | 26.06.24 | JAPS | 26.06.24 | 05.07.24 | 05.07.24 | 06.07.24 |  |  |  | 25.08.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | Surge Valves | LE22M318-M-006 | LE22M318-M-006-A | Durga Valves | Sent to BU Operations | 17 |  |  |  |  | 12.10.23 | 18.07.24 | 18.07.24 | [8 empty] | 18.07.24 | 18.07.24 | 18.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | Surge Valves | LE22M318-M-006 | LE22M318-M-006-B | Magwane | Sent to BU Operations | 26 |  |  |  |  | 12.10.23 | 27.06.24 | 01.07.24 | 09.07.24 | 09.07.24 | [6 empty] | 09.07.24 | 09.07.24 | 09.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | Surge Valves | LE22M318-M-006 | LE22M318-M-006-C | Jash | Sent to BU Operations | 9 |  |  |  |  | 12.10.23 | 20.07.24 | 24.07.24 | 24.07.24 | 25.07.24 | [6 empty] | 25.07.24 | 25.07.24 | 26.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-26.07.2024-18:47:49
Dharwad | Mechanical | WTP MBR and ZBT Valves(SV,AV,BFV,NRV) | LE22M318-M-007 | LE22M318-M-007-A | KBL | Regret offer | PR Closed |  |  |  |  | 07.06.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthiga@lntecc.com-17.07.2024-15:46:20
Dharwad | Mechanical | WTP MBR and ZBT Valves(SV,AV,BFV,NRV) | LE22M318-M-007 | LE22M318-M-007-B | AVK | Awaiting pre-offer from vendor | 57 |  |  |  |  | 08.06.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:50
Dharwad | Mechanical | WTP MBR and ZBT Valves(SV,AV,BFV,NRV) | LE22M318-M-007 | LE22M318-M-007-C | Magwane | Pre-order comments issued | 24 |  |  |  |  | 07.06.24 | 10.07.24 | 11.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:50
Dharwad | Mechanical | WTP MBR and ZBT Valves(SV,AV,BFV,NRV) | LE22M318-M-007 | LE22M318-M-007-D | Durga | Pre-order comments issued | 18 |  |  | chennai@dvpl.co.in |  | 10.06.24 | 11.07.24 | 17.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:50
Dharwad | Mechanical | WTP Valves (Knife Gate,Diaphragm,Ball valve) | LE22M318-M-007 | LE22M318-M-007-E | Hawa | Enquiry yet to float | NA |  |  | azhar@hawaengltd.com |  | 26.06.24 | 01.07.24 | 06.07.24 | 09.07.24 | 18.07.24 | [20 empty] | rallabandi.bharadwaj@lntecc.com-18.07.2024-15:50:05
Dharwad | Mechanical | WTP Valves (Knife Gate,Diaphragm,Ball valve,Solenoid) | LE22M318-M-007 | LE22M318-M-007-F | CAIR | Enquiry yet to float | NA |  |  | tamilnadu@cairindia.com |  | 26.06.24 | 06.07.24 | 18.07.24 | [22 empty] | rallabandi.bharadwaj@lntecc.com-18.07.2024-15:50:05
Dharwad | Mechanical | WTP Valves (Knife Gate) | LE22M318-M-007 | LE22M318-M-007-G | Sigma Flow | Enquiry yet to float | NA |  |  | jagadesh@sigmaflow.in |  | 26.06.24 | 11.07.24 | 11.07.24 | [22 empty] | rallabandi.bharadwaj@lntecc.com-18.07.2024-15:50:05
Dharwad | Mechanical | Exhaust Fan | LE22M318-M-008 | LE22M318-M-008-A | Howden | Sent to BU Operations | 20 |  |  |  |  | 15.12.23 | 10.06.24 | 18.06.24 | 15.07.24 | 15.07.24 | [6 empty] | 15.07.24 | 15.07.24 | 15.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:50
Dharwad | Mechanical | Exhaust Fan | LE22M318-M-008 | LE22M318-M-008-B | Nadi | Sent to BU Operations | 29 |  |  |  |  | 15.12.23 | 05.07.24 | 05.07.24 | [8 empty] | 06.07.24 | 06.07.24 | 05.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-26.07.2024-18:47:50
Dharwad | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M318-I-001 | LE22M318-I-001-A | General Instruments | Sent to BU Operations | 29 |  |  |  | 20.11.23 | 31.05.24 | 08.06.24 | 13.06.24 | 15.06.24 | 06.07.24 | 06.07.24 | [5 empty] | 06.07.24 | 06.07.24 | 06.07.24 | T1 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:23
Dharwad | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M318-I-001 | LE22M318-I-001-B | HGuru | Pre-order pending with EDRC | 17 |  |  |  | 20.11.23 | 31.05.24 | 18.07.24 | [20 empty] | 13.09.24 |  |  | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M318-I-001 | LE22M318-I-001-C | WIKA | Awaiting pre-offer from vendor | 65 |  |  |  | 20.11.23 | 31.05.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:23
Dharwad | Instrumentation | Pressure transmitter | LE22M318-I-002 | LE22M318-I-002-A | SIEMENS | Approved by Client | PR Closed |  |  |  | 20.11.23 | 03.10.23 | 18.10.23 | 20.10.23 | [8 empty] | 24.10.23 | 31.10.23 | 31.10.23 | T2 | 14.12.23 | SIEMENS | 25.01.24 | 26.01.24 | 27.01.24 | 30.01.24 | 30.01.24 | 13.09.24 | 30.09.24 | 12.02.24 | sooryaprakash.t@lntecc.com-04.07.2024-10:08:19
Dharwad | Instrumentation | Pressure transmitter | LE22M318-I-002 | LE22M318-I-002-B | E&H | Sent to BU Operations | PR Closed |  |  |  | 20.11.23 | 03.10.23 | 18.10.23 | 18.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T2 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:13
Dharwad | Instrumentation | Pressure transmitter | LE22M318-I-002 | LE22M318-I-002-C | ABB | Sent to BU Operations | PR Closed |  |  |  | 20.11.23 | 20.11.23 | 24.11.23 | 24.11.23 | [8 empty] | 30.11.23 | 30.11.23 | 30.11.23 | T3 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:13
Dharwad | Instrumentation | level switch - Conductivity type | LE22M318-I-003 | LE22M318-I-003-D | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 20.11.23 | [22 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | level switch - Conductivity type | LE22M318-I-003 | LE22M318-I-003-E | Pune Techtrol | Pre-order comments issued | 29 |  |  |  | 20.11.23 | 31.05.24 | 26.06.24 | 06.07.24 | [19 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:24
Dharwad | Instrumentation | level switch - Conductivity type | LE22M318-I-003 | LE22M318-I-003-F | SBEM | Pre-order comments issued | 72 |  |  |  | 20.11.23 | 22.05.24 | 24.05.24 | 24.05.24 | [19 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Ultrasonic level Transmitter | LE22M318-I-004 | LE22M318-I-004-A | Siemens | Approved by Client | PR Closed |  |  |  | 20.11.23 | 10.10.23 | 18.10.23 | 31.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T1 | 28.11.23 | Siemens | 25.01.24 | 25.01.24 | 25.01.24 | 30.01.24 | 30.01.24 | 13.09.24 | 30.09.24 | 27.01.24 | sooryaprakash.t@lntecc.com-04.07.2024-10:08:19
Dharwad | Instrumentation | Ultrasonic level Transmitter | LE22M318-I-004 | LE22M318-I-004-B | ABB | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 20.10.23 | 30.10.23 | 20.11.23 | [8 empty] | 20.11.23 | 30.11.23 | 30.11.23 | T2 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:13
Dharwad | Instrumentation | Ultrasonic level Transmitter | LE22M318-I-004 | LE22M318-I-004-C | E&H | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 16.10.23 | 18.10.23 | 31.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T3 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:13
Dharwad | Instrumentation | Radar Level Transmitter | LE22M318-I-005 | LE22M318-I-005-A | Siemens | Approved by Client | PR Closed |  |  |  | 20.11.23 | 14.10.23 | 18.10.23 | 31.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T1 | 24.11.23 | Siemens | 25.01.24 | 26.01.24 | 29.01.24 | 30.01.24 | 30.01.24 | 13.09.24 | 30.09.24 | 23.01.24 | sooryaprakash.t@lntecc.com-04.07.2024-10:08:19
Dharwad | Instrumentation | Radar Level Transmitter | LE22M318-I-005 | LE22M318-I-005-B | ABB | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 25.10.23 | 30.10.23 | 20.11.23 | [8 empty] | 20.11.23 | 30.11.23 | 30.11.23 | T2 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:13
Dharwad | Instrumentation | Radar Level Transmitter | LE22M318-I-005 | LE22M318-I-005-C | E&H | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 15.10.23 | 18.10.23 | 31.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T3 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:13
Dharwad | Instrumentation | Rate for flow transmitter | LE22M318-I-006 | LE22M318-I-006-A | Siemens | Approved by Client | PR Closed |  |  |  | 20.11.23 | 13.10.23 | 18.10.23 | 31.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T1 | 29.11.23 | Siemens | 25.01.24 | 27.01.24 | 29.01.24 | 30.01.24 | 30.01.24 | 13.09.24 | 30.09.24 | 28.01.24 | sooryaprakash.t@lntecc.com-04.07.2024-10:08:19
Dharwad | Instrumentation | Rate for flow transmitter | LE22M318-I-006 | LE22M318-I-006-B | ABB | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 21.10.23 | 30.10.23 | 20.11.23 | [8 empty] | 20.11.23 | 30.11.23 | 30.11.23 | T2 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:14
Dharwad | Instrumentation | Rate for flow transmitter | LE22M318-I-006 | LE22M318-I-006-C | E&H | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 14.10.23 | 18.10.23 | 31.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T3 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:14
Dharwad | Instrumentation | Bypass Rotameter | LE22M318-I-007 | LE22M318-I-007-A | Eureka | Sent to BU Operations | 47 |  |  |  | 20.11.23 | 31.05.24 | 01.06.24 | 01.06.24 | 01.06.24 | [7 empty] | 18.06.24 | 18.06.24 | 18.06.24 | T1 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:24
Dharwad | Instrumentation | Bypass Rotameter | LE22M318-I-007 | LE22M318-I-007-B | Scientific Devices | Sent to BU Operations | 47 |  |  |  | 20.11.23 | 31.05.24 | 04.06.24 | 04.06.24 | 04.06.24 | [7 empty] | 18.06.24 | 18.06.24 | 18.06.24 | T2 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:24
Dharwad | Instrumentation | Bypass Rotameter | LE22M318-I-007 | LE22M318-I-007-C | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 20.11.23 | [22 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:50:21
Dharwad | Instrumentation | Electromagnectic flow meter | LE22M318-I-008 | LE22M318-I-008-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 20.11.23 | 17.08.23 | 26.09.23 | 25.10.23 | [8 empty] | 26.10.23 | 26.10.23 | 26.10.23 | T2 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:14
Dharwad | Instrumentation | Electromagnectic flow meter | LE22M318-I-008 | LE22M318-I-008-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 20.11.23 | 25.09.23 | 28.09.23 | 25.10.23 | [8 empty] | 26.10.23 | 26.10.23 | 26.10.23 | T3 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:14
Dharwad | Instrumentation | Electromagnectic flow meter | LE22M318-I-008 | LE22M318-I-008-C | Khrone Marshall | Approved by Client | PR Closed | conditional clearance issued |  |  | 20.11.23 | 11.08.23 | 26.09.23 | 25.10.23 | [8 empty] | 20.11.23 | 20.11.23 | 20.11.23 | T1 | 08.12.23 | Khrone Marshall | 22.04.23 | 14.07.23 | 10.11.23 | 27.11.23 | 08.02.24 | 13.09.24 | 30.09.24 | 06.02.24 | sooryaprakash.t@lntecc.com-04.07.2024-10:08:19
Dharwad | Instrumentation | Electromagnectic flow meter | LE22M318-I-008 | LE22M318-I-008-D | Siemens | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 22.08.23 | 26.09.23 | 25.10.23 | [8 empty] | 20.11.23 | 20.11.23 | 20.11.23 | T2 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:14
Dharwad | Instrumentation | Electromagnectic flow meter | LE22M318-I-008 | LE22M318-I-008-E | Honeywell | Sent to BU Operations | PR Closed |  |  |  | 20.11.23 | 10.11.23 | 15.11.23 | 20.11.23 | [8 empty] | 20.11.23 | 20.11.23 | 20.11.23 | T4 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:14
Dharwad | Instrumentation | Ultrasonic type Open channel flow transmitter | LE22M318-I-009 | LE22M318-I-009-A | Siemens | Approved by Client | PR Closed | conditional clearance issued |  |  | 20.11.23 | 09.10.23 | 18.10.23 | 31.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T1 | 15.12.23 | Siemens | 25.01.24 | 25.01.24 | 29.01.24 | 30.01.24 | 30.01.24 | 13.09.24 | 30.09.24 | 13.02.24 | sooryaprakash.t@lntecc.com-04.07.2024-10:08:19
Dharwad | Instrumentation | Ultrasonic type Open channel flow transmitter | LE22M318-I-009 | LE22M318-I-009-B | ABB | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 22.10.23 | 30.10.23 | 20.11.23 | [8 empty] | 20.11.23 | 30.11.23 | 30.11.23 | T2 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:14
Dharwad | Instrumentation | Ultrasonic type Open channel flow transmitter | LE22M318-I-009 | LE22M318-I-009-C | E&H | Sent to BU Operations | PR Closed | conditional clearance issued |  |  | 20.11.23 | 03.10.23 | 18.10.23 | 31.10.23 | [8 empty] | 31.10.23 | 31.10.23 | 31.10.23 | T3 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-11:53:14
Dharwad | Instrumentation | battery operated Flow meter | LE22M318-I-010 | LE22M318-I-010-A | ABB | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | battery operated Flow meter | LE22M318-I-010 | LE22M318-I-010-B | Siemens | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | battery operated Flow meter | LE22M318-I-010 | LE22M318-I-010-C | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 20.11.23 | [22 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:50:21
Dharwad | Instrumentation | pH Meter | LE22M318-I-011 | LE22M318-I-011-A | ABB | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | pH Meter | LE22M318-I-011 | LE22M318-I-011-B | HACH | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | pH Meter | LE22M318-I-011 | LE22M318-I-011-C | E&H | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Turbidity meter | LE22M318-I-012 | LE22M318-I-012-A | ABB | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Turbidity meter | LE22M318-I-012 | LE22M318-I-012-B | HACH | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Turbidity meter | LE22M318-I-012 | LE22M318-I-012-C | E&H | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Residual Chlorine Analyzer | LE22M318-I-013 | LE22M318-I-013-A | ABB | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Residual Chlorine Analyzer | LE22M318-I-013 | LE22M318-I-013-B | HACH | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Residual Chlorine Analyzer | LE22M318-I-013 | LE22M318-I-013-C | E&H | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Conductivity Analyzer | LE22M318-I-014 | LE22M318-I-014-A | ABB | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Conductivity Analyzer | LE22M318-I-014 | LE22M318-I-014-B | HACH | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Conductivity Analyzer | LE22M318-I-014 | LE22M318-I-014-C | E&H | Awaiting pre-offer from vendor | 17 |  |  |  | 20.11.23 | 18.07.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M318-I-015 | LE22M318-I-015-A | Siemens | Awaiting pre-offer from vendor | 48 |  |  |  | 20.11.23 | 17.06.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:24
Dharwad | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M318-I-015 | LE22M318-I-015-B | Schneider | Awaiting pre-offer from vendor | 48 |  |  |  | 20.11.23 | 17.06.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:24
Dharwad | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M318-I-015 | LE22M318-I-015-C | ABB | Awaiting pre-offer from vendor | 48 |  |  |  | 20.11.23 | 17.06.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:24
Dharwad | Instrumentation | instrumentation Control & signal Cables | LE22M318-I-016 | LE22M318-I-016-A | Thermocable | Sent to BU Operations | PR Closed |  |  |  | 20.11.23 | 08.10.22 | 11.04.23 | 07.10.23 | [8 empty] | 30.12.23 | 30.12.23 | 30.12.23 | T1 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:50:22
Dharwad | Instrumentation | instrumentation Control & signal Cables | LE22M318-I-016 | LE22M318-I-016-B | Delton | Post-order technically cleared | 24 |  |  |  | 20.11.23 | 09.02.23 | 11.04.23 | 22.11.23 | [8 empty] | 30.12.23 | 30.12.23 | 30.12.23 | T2 | 08.07.24 | Delton | 08.07.24 | 11.07.24 | 11.07.24 | 11.07.24 |  | 13.09.24 | 30.09.24 | 06.09.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | instrumentation Control & signal Cables | LE22M318-I-016 | LE22M318-I-016-C | Polycab | Sent to BU Operations | PR Closed |  |  |  | 20.11.23 | 02.04.23 | 11.04.23 | 09.08.23 | [8 empty] | 30.12.23 | 30.12.23 | 30.12.23 | T3 | [7 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:50:22
Dharwad | Instrumentation | UPS | LE22M318-I-017 | LE22M318-I-017-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 20.11.23 | [22 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:50:22
Dharwad | Instrumentation | UPS | LE22M318-I-017 | LE22M318-I-017-B | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 20.11.23 | [22 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:50:22
Dharwad | Instrumentation | UPS | LE22M318-I-017 | LE22M318-I-017-C | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 20.11.23 | [22 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:50:22
Dharwad | Instrumentation | Float & Board Level gauge | LE22M318-I-018 | LE22M318-I-018-A | Pune Techtrol | Pre-order comments issued | 29 |  |  |  | 20.11.23 | 31.05.24 | 26.06.24 | 06.07.24 | [19 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:24
Dharwad | Instrumentation | Float & Board Level gauge | LE22M318-I-018 | LE22M318-I-018-B | SBEM | Pre-order comments issued | 72 |  |  |  | 20.11.23 | 22.05.24 | 24.05.24 | 24.05.24 | [19 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:19:03
Dharwad | Instrumentation | Float & Board Level gauge | LE22M318-I-018 | LE22M318-I-018-C | Vendor Name yet to provide | Awaiting pre-offer from vendor | 65 |  |  |  | 20.11.23 | 31.05.24 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | sooryaprakash.t@lntecc.com-18.07.2024-14:15:24
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-A | Kirlosker | Regret offer | PR Closed | Revised offer yet to recieve |  | aditya.ksr@kirloskarelectric.com | 18.7.22 | 18.07.22 | 03.11.23 | 26.02.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-16.07.2024-09:58:45
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-B | voltech | Pre-order technically rejected | PR Closed | Not as per approved make |  |  | 18.7.22 | 18.07.22 | 26.10.23 | 19.02.24 | [22 empty] | karthik.ajithkumar@lntecc.com-24.05.2024-18:10:56
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-C | Uttam bharat | Pre-order technically rejected | PR Closed | Not as per approved make |  |  | 18.7.22 | 18.07.22 | 26.10.23 | 09.02.24 | 2.3.24 | 12.3.24 | [20 empty] | karthik.ajithkumar@lntecc.com-24.05.2024-18:10:56
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-D | Universal | Regret offer | PR Closed |  |  | abhishek@upt.in | 18.7.22 | 16.5.24 | 26.10.23 | 09.02.24 | 2.3.24 | 12.3.24 | [20 empty] | karthik.ajithkumar@lntecc.com-16.07.2024-09:58:45
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-E | Voltamp | Regret offer | PR Closed |  |  | sasik_vtlchn@voltamptransformers.com | 18.7.22 | 16.5.24 | 26.10.23 | 09.02.24 | 2.3.24 | 12.3.24 | [20 empty] | duppalapudi.raviteja@lntecc.com-01.07.2024-11:59:24
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-F | Voltech | Sent to BU Operations | 18 |  |  | adalarasan.r@voltechgroup.com | 18.7.22 | 1.6.24 | 15.06.24 | 21.02.24 | 25.06.24 | 02.07.24 | 09.07.24 | 11.07.24 |  |  |  |  | 11.06.24 | 11.06.24 | 17.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-G | Power Star | Sent to BU Operations | 18 |  |  | sailaja@powerstarelectric.net | 18.7.22 | 13.6.24 | 28.06.24 | 04.07.24 | 16.7.24 | 17.7.24 | [6 empty] | 16.7.24 | 17.7.24 | 17.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-H | Toshiba | Regret offer | PR Closed |  |  | marketing@toshiba-ttdi.com |  | 14.6.24 | [24 empty] | athira.s1@lntecc.com-26.06.2024-18:13:30
Dharwad | Electrical | Transformer | LE22M318-E-001 | LE22M318-E-001-I | Uttam Bharat | Sent to BU Operations | 18 | Not as per approved make |  |  |  | 21.06.24 | 25.06.24 | 26.06.24 | 06.07.24 | 06.07.24 | 11.07.24 | 11.07.24 |  |  |  |  | 11.06.24 | 11.06.24 | 17.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Cable Lugs and Glands | LE22M318-E-WS-PR-4003 | LE22M318-E-WS-PR-4003-A | Monaj | Awaiting pre-offer from vendor | 51 |  |  | monajtrading@gmail.com | 4.4.23 | 14.6.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Cable Lugs and Glands | LE22M318-E-WS-PR-4003 | LE22M318-E-WS-PR-4003-B | Govind | Pre-order pending with EDRC | 36 |  |  | sgovindele@gmail.com | 4.4.23 | 14.6.24 | 29.06.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Cable Lugs and Glands | LE22M318-E-WS-PR-4003 | LE22M318-E-WS-PR-4003-C | Das | Awaiting pre-offer from vendor | 51 |  |  | enterprisesdas8@gmail.com |  | 14.6.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Panel | LE22M318-E-WS-PR-4005 | LE22M318-E-WS-PR-4005-A | Lotus Powergear | Sent to BU Operations | 10 |  |  | vinaykumar_s@lotuspowergear.co.in | 3.3.23 | 21.5.24 | 27.05.24 | 1.6.24 | 15.06.24 | 27.06.24 | 05.07.24 | 17.7.24 |  |  |  |  | 05.07.24 | 17.7.24 | 25.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Panel | LE22M318-E-WS-PR-4005 | LE22M318-E-WS-PR-4005-B | Load controls | Regret offer | PR Closed |  |  | sales@loadcontrols.net | 3.3.23 | 21.5.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:27:06
Dharwad | Electrical | HT Panel | LE22M318-E-WS-PR-4005 | LE22M318-E-WS-PR-4005-C | Symatic South | Sent to BU Operations | 10 | Siemens |  | Vinay.a@siemens.com | 3.3.23 | 23.5.24 | 16.7.24 | 20.7.24 | [8 empty] | 16.7.24 | 20.7.24 | 25.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Panel | LE22M318-E-WS-PR-4005 | LE22M318-E-WS-PR-4005-D | Schnieder | Regret offer | PR Closed | No response |  | j.sasikumar@se.com |  | 09.07.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-20.07.2024-11:00:51
Dharwad | Electrical | HT Panel | LE22M318-E-WS-PR-4005 | LE22M318-E-WS-PR-4005-E | Universal | Sent to BU Operations | 10 |  |  | deepak@upe.co.in |  | 12.07.24 | 17.7.24 | 20.7.24 | [8 empty] | 17.7.24 | 20.7.24 | 25.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Panel | LE22M318-E-WS-PR-4005 | LE22M318-E-WS-PR-4005-F | HTS | Sent to BU Operations | 10 |  |  | hitesh.vadnagare@htswitchgears.com |  | 12.07.24 | 16.7.24 | 20.7.24 | [8 empty] | 16.7.24 | 20.7.24 | 25.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Cables | LE22M318-E-WS-PR-4006 | LE22M318-E-WS-PR-4006-A | FOMRA | Pre-order pending with EDRC | 46 |  |  | sales2@fomra.co.in | 3.4.23 | 10.6.24 | 19.06.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Cables | LE22M318-E-WS-PR-4006 | LE22M318-E-WS-PR-4006-B | Finolex | Pre-order pending with EDRC | 48 |  |  | naveen.cj@finolex.com | 3.4.23 | 10.6.24 | 17.06.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | LT Panel | LE22M318-E-WS-PR-4007 | LE22M318-E-WS-PR-4007-A | Lotus Power gear | Pre-order comments issued | 13 |  |  | vinaykumar_s@lotuspowergear.co.in | 2.3.23 | 02.03.23 | 14.06.24 | 02.07.24 | 12.07.24 | 22.7.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | LT Panel | LE22M318-E-WS-PR-4007 | LE22M318-E-WS-PR-4007-B | Load Controls | Awaiting pre-offer from vendor | 67 |  |  | sales@loadcontrols.net | 2.3.23 | 29.5.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | LT Panel | LE22M318-E-WS-PR-4007 | LE22M318-E-WS-PR-4007-C | SRCS | Pre-order technically cleared | 15 |  |  | ashok@ragavendracontrol.com |  | 29.05.24 | 19.06.24 | 29.06.24 | 02.07.24 | 03.07.24 | 06.07.24 | 08.07.24 | 18.7.24 | 20.7.24 |  |  | 18.7.24 | 20.7.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | LT Panel | LE22M318-E-WS-PR-4007 | LE22M318-E-WS-PR-4007-D | Pragathi Controls | Awaiting pre-offer from vendor | 26 |  |  | sales@pragathicontrols.in |  | 09.07.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Termination kit | LE22M318-E-WS-PR-4008 | LE22M318-E-WS-PR-4008-A | Monaj | Awaiting pre-offer from vendor | 51 |  |  | monajtrading@gmail.com | 13.4.23 | 14.6.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Termination kit | LE22M318-E-WS-PR-4008 | LE22M318-E-WS-PR-4008-B | Govind | Pre-order pending with EDRC | 36 |  |  | sgovindele@gmail.com | 13.4.23 | 14.6.24 | 29.06.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | HT Termination kit | LE22M318-E-WS-PR-4008 | LE22M318-E-WS-PR-4008-C | Das Enterprise | Awaiting pre-offer from vendor | 51 |  |  | enterprisesdas8@gmail.com |  | 14.6.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Capacitor | LE22M318-E-WS-PR-4009 | LE22M318-E-WS-PR-4009-A | ABB | Pre-order pending with EDRC | 10 |  |  | karthik.kaki@hitachienergy.com | 7.5.19 | 3.6.24 | 27.06.24 | 11.07.24 | 25.07.24 | [18 empty] | 15.08.24 | 01.09.24 | 31.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Capacitor | LE22M318-E-WS-PR-4009 | LE22M318-E-WS-PR-4009-B | Madhav Capacitor | Pre-order comments issued | 12 |  |  | vaibhav@madhavcapacitors.co.in | 7.5.19 | 3.6.24 | 5.6.24 | 11.07.24 | 16.7.24 | 23.07.24 | [17 empty] | 15.08.24 | 01.09.24 | 31.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Capacitor | LE22M318-E-WS-PR-4009 | LE22M318-E-WS-PR-4009-C | Unistar | Pre-order comments issued | 12 |  |  | varadharajan.n@unistar.co.in |  | 05.07.24 | 07.07.24 | 23.07.24 | [19 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:12
Dharwad | Electrical | Capacitor | LE22M318-E-WS-PR-4009 | LE22M318-E-WS-PR-4009-D | UPE | Regret offer | PR Closed | Not Manufacturing |  | deepak@upe.co.in |  | 3.6.24 | [21 empty] | 15.08.24 | 01.09.24 | 31.10.24 | karthik.ajithkumar@lntecc.com-16.07.2024-09:58:45
Dharwad | Electrical | Capacitor | LE22M318-E-WS-PR-4009 | LE22M318-E-WS-PR-4009-E | TDK | Regret offer | PR Closed |  |  | info@conquerent.in |  | 03.06.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-20.07.2024-10:59:44
Dharwad | Electrical | Power and Control Cables | LE22M318-E-WS-PR-4010 | LE22M318-E-WS-PR-4010-A | FOMRA | Pre-order pending with EDRC | 46 |  |  | sales2@fomra.co.in | 1.4.23 | 10.6.24 | 19.06.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Power and Control Cables | LE22M318-E-WS-PR-4010 | LE22M318-E-WS-PR-4010-B | Finolex | Pre-order pending with EDRC | 48 |  |  | naveen.cj@finolex.com | 1.4.23 | 10.6.24 | 17.06.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Earthing and Lightning | LE22M318-E-WS-PR-4011 | LE22M318-E-WS-PR-4011-A | Monaj | Awaiting pre-offer from vendor | 51 |  |  | monajtrading@gmail.com | 1.4.23 | 14.6.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Earthing and Lightning | LE22M318-E-WS-PR-4011 | LE22M318-E-WS-PR-4011-B | Govind Electricals | Pre-order pending with EDRC | 36 |  |  | sgovindele@gmail.com | 1.4.23 | 14.6.24 | 29.06.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Earthing and Lightning | LE22M318-E-WS-PR-4011 | LE22M318-E-WS-PR-4011-C | Das Enterprise | Awaiting pre-offer from vendor | 51 |  |  | enterprisesdas8@gmail.com | 1.4.23 | 14.6.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Safety Accessories | LE22M318-E-WS-PR-4012 | LE22M318-E-WS-PR-4012-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 13.4.23 | 13.04.23 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:27:07
Dharwad | Electrical | Cable trays and accessories | LE22M318-E-WS-PR-4013 | LE22M318-E-WS-PR-4013-A | Monaj | Awaiting pre-offer from vendor | 51 |  |  | monajtrading@gmail.com | 3.4.23 | 14.6.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Cable trays and accessories | LE22M318-E-WS-PR-4013 | LE22M318-E-WS-PR-4013-B | Govind | Pre-order pending with EDRC | 36 |  |  | sgovindele@gmail.com | 3.4.23 | 14.6.24 | 29.06.24 | [20 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Cable trays and accessories | LE22M318-E-WS-PR-4013 | LE22M318-E-WS-PR-4013-C | Das Enterprice | Awaiting pre-offer from vendor | 51 |  |  | enterprisesdas8@gmail.com | 3.4.23 | 14.6.24 | [21 empty] | 16.08.24 | 02.09.24 | 01.11.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Soft Starter | LE22M318-E-WS-PR-4014 | LE22M318-E-WS-PR-4014-A | JAYASHREE | Sent to BU Operations | 23 |  | 9975598078 | ssb@jayashree.in | 13.4.23 | 29.05.24 | 03.06.24 | 26.06.24 | 29.06.24 | 01.07.24 | 09.07.24 | 12.07.24 |  |  |  |  | 12.07.24 | 09.07.24 | 12.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Soft Starter | LE22M318-E-WS-PR-4014 | LE22M318-E-WS-PR-4014-B | LECON | Sent to BU Operations | 23 |  | 9449041220 | lecongm@gmail.com | 13.4.23 | 29.05.24 | 11.06.24 | 20.06.24 | 27.06.24 | 01.07.24 | 06.07.24 | 12.07.24 |  |  |  |  | 12.07.24 | 12.07.24 | 12.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dharwad | Electrical | Soft Starter | LE22M318-E-WS-PR-4014 | LE22M318-E-WS-PR-4014-C | INNOVATIVE TECHNOMICS | Sent to BU Operations | 23 |  | 9423578196 | nandkishor.lembhe@itechnomics.com | 13.4.23 | 29.05.24 | 13.06.24 | 25.06.24 | 04.07.24 | 12.07.24 | [6 empty] | 12.07.24 | 04.07.24 | 12.7.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | karthik.ajithkumar@lntecc.com-29.07.2024-08:46:13
Dwaraka | Process | Raw Water Analysis | LE21M708-P-WS-WT-PR-2101 | LE21M708-P-WS-WT-PR-2101-A | NA | Regret offer | PR Closed | Report Received |  |  |  | 01.08.21 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:34:25
Dwaraka | Process | UPVC Plates | LE21M708-P-WS-WT-PR-2102 | LE21M708-P-WS-WT-PR-2102-A | Sangir | Sent to BU Operations | PR Closed |  |  |  |  | 13.09.21 | 13.12.22 | 19.12.22 | 22.12.22 | 31.12.22 | [6 empty] | 31.12.22 | 31.12.22 | 31.12.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:50:10
Dwaraka | Process | UPVC Plates | LE21M708-P-WS-WT-PR-2102 | LE21M708-P-WS-WT-PR-2102-B | Tega | Regret offer | PR Closed | Vendor offer rejected |  |  |  | 13.09.21 | 25.01.23 | 03.02.23 | [22 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:38:41
Dwaraka | Process | UPVC Plates | LE21M708-P-WS-WT-PR-2102 | LE21M708-P-WS-WT-PR-2102-C | Prashant Plastics | Sent to BU Operations | PR Closed |  |  |  |  | 13.09.21 | 27.04.23 | 29.04.23 | 29.04.23 | 06.05.23 | [6 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:50:10
Dwaraka | Process | UPVC Plates | LE21M708-P-WS-WT-PR-2102 | LE21M708-P-WS-WT-PR-2102-D | Cooldeck | Post-order technically cleared | 121 |  |  |  |  | 13.09.21 | 21.02.24 | 27.02.24 | 01.03.24 | 02.03.24 | [6 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T1 | 28.03.24 | Cooldeck | 03.03.24 | 05.04.24 | 05.04.24 | 05.04.24 |  |  |  | 27.05.24 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | UPVC Plates | LE21M708-P-WS-WT-PR-2102 | LE21M708-P-WS-WT-PR-2102-E | Tainwala | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 13.09.21 | [24 empty] | deepak.choudhary@lntecc.com-20.05.2024-12:37:39
Dwaraka | Process | Filter Nozzles | LE21M708-P-WS-WT-PR-2103 | LE21M708-P-WS-WT-PR-2103-A | Guddi Plastcon | Sent to BU Operations | PR Closed |  |  |  |  | 13.09.21 | 18.01.22 | 20.01.22 | [8 empty] | 20.01.22 | 20.01.22 | 20.01.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | Filter Nozzles | LE21M708-P-WS-WT-PR-2103 | LE21M708-P-WS-WT-PR-2103-B | VP Engineers | Post-order technically cleared | 750 |  |  |  |  | 13.09.21 | 18.01.22 | 20.01.22 | 21.01.22 | 29.01.22 | [6 empty] | 29.01.22 | 29.01.22 | 29.01.22 | T1 | 16.06.22 | VP Engineers | 16.06.22 | 16.06.22 | 15.07.22 | 16.07.22 |  |  |  | 15.08.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | IPS & Flocculator Mechanism | LE21M708-P-WS-WT-PR-2104 | LE21M708-P-WS-WT-PR-2104-A | Shivpad | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 29.01.24 | 05.02.22 | 15.04.22 | 03.05.22 | 19.05.22 | 01.06.22 | 10.06.22 | 10.06.22 |  |  | 10.06.22 | 10.06.22 | 10.06.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | IPS & Flocculator Mechanism | LE21M708-P-WS-WT-PR-2104 | LE21M708-P-WS-WT-PR-2104-B | Sritech | Post-order technically cleared | 654 |  |  |  |  | 01.10.21 | 15.04.22 | 12.05.22 | 17.05.22 | 03.06.22 | 06.06.22 | 10.06.22 |  |  |  |  | 10.06.22 | 10.06.22 | 10.06.22 | T1 | 15.09.22 | Sritech | 21.09.22 | 28.09.22 | 18.10.22 | 20.10.22 |  |  |  | 14.11.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | IPS & Flocculator Mechanism | LE21M708-P-WS-WT-PR-2104 | LE21M708-P-WS-WT-PR-2104-C | Triveni | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 11.05.22 | 17.05.22 | 26.05.22 | 30.05.22 | 10.06.22 | 13.06.22 |  |  |  |  | 13.06.22 | 13.06.22 | 13.06.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | Air Blower | LE21M708-P-WS-WT-PR-2106 | LE21M708-P-WS-WT-PR-2106-A | ACME | Regret offer | PR Closed | Vendor offer rejected |  |  |  | 17.09.21 | 11.04.22 | 16.04.22 | 22.04.22 | 03.05.22 | 13.05.22 | 20.05.22 | [18 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:38:41
Dwaraka | Process | Air Blower | LE21M708-P-WS-WT-PR-2106 | LE21M708-P-WS-WT-PR-2106-B | Kay | Post-order technically cleared | 305 |  |  |  |  | 17.09.21 | 11.04.22 | 16.04.22 | 10.05.22 | 03.06.22 | 06.06.22 | 14.06.22 |  |  |  |  | 14.06.22 | 14.06.22 | 14.06.22 | T1 | 07.09.22 | Kay | 16.09.22 | 11.11.22 | 20.09.23 | 04.10.23 |  |  |  | 06.11.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Air Blower | LE21M708-P-WS-WT-PR-2106 | LE21M708-P-WS-WT-PR-2106-C | Everest | Sent to BU Operations | PR Closed |  |  |  |  | 17.09.21 | 18.05.22 | 21.05.22 | 26.05.22 | 27.05.22 | [6 empty] | 27.05.22 | 27.05.22 | 27.05.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | Air Blower | LE21M708-P-WS-WT-PR-2106 | LE21M708-P-WS-WT-PR-2106-D | Swam | Sent to BU Operations | PR Closed |  |  |  |  | 17.09.21 | 15.06.22 | 08.07.22 | 19.07.22 | 21.07.22 | 01.08.22 | 02.08.22 |  |  |  |  | 02.08.22 | 02.08.22 | 02.08.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | Backwash Pump & Recycle Supernatant Pumps | LE21M708-P-WS-WT-PR-2107 | LE21M708-P-WS-WT-PR-2107-A | Andritz | Sent to BU Operations | PR Closed |  |  |  |  | 17.09.21 | 07.04.22 | 21.04.22 | 13.05.22 | 21.05.22 | [6 empty] | 21.05.22 | 21.05.22 | 21.05.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | Backwash Pump & Recycle Supernatant Pumps | LE21M708-P-WS-WT-PR-2107 | LE21M708-P-WS-WT-PR-2107-B | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 17.09.21 | 19.04.22 | 03.05.22 | 01.07.22 | 20.07.22 | [6 empty] | 20.07.22 | 20.07.22 | 20.07.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | Backwash Pump & Recycle Supernatant Pumps | LE21M708-P-WS-WT-PR-2107 | LE21M708-P-WS-WT-PR-2107-C | Wilo | Post-order technically cleared | 503 | Supernatant Pumps |  |  |  | 17.09.21 | 28.07.22 | 01.08.22 | 24.08.22 | 30.08.22 | [6 empty] | 30.08.22 | 30.08.22 | 30.08.22 | T1 | 15.02.23 | Wilo | 22.02.23 | 13.03.23 | 13.03.23 | 20.03.23 |  |  |  | 16.04.23 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Backwash Pump & Recycle Supernatant Pumps | LE21M708-P-WS-WT-PR-2107 | LE21M708-P-WS-WT-PR-2107-D | Wilo | Sent to BU Operations | PR Closed | Backwash Pumps |  |  |  | 17.09.21 | 28.07.22 | 01.08.22 | 02.08.22 | 16.08.22 | [6 empty] | 16.08.22 | 16.08.22 | 16.08.22 | T1 |  | Wilo | 16.05.24 | [7 empty] | THENNARASU@lntecc.com-21.05.2024-10:33:45
Dwaraka | Process | Backwash Pump & Recycle Supernatant Pumps | LE21M708-P-WS-WT-PR-2107 | LE21M708-P-WS-WT-PR-2107-E | KSB | Sent to BU Operations | PR Closed |  |  |  |  | 17.09.21 | 28.08.23 | 11.09.23 | 05.10.23 | 07.11.23 | [6 empty] | 07.11.23 | 07.11.23 | 07.11.23 | T4 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | Backwash Pump & Supernatant Recycle Pumps | LE21M708-P-WS-WT-PR-2107 | LE21M708-P-WS-WT-PR-2107-F | Lubi | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 17.09.21 | [24 empty] | deepak.choudhary@lntecc.com-20.05.2024-12:37:39
Dwaraka | Process | Service Water Pump | LE21M708-P-WS-WT-PR-2108 | LE21M708-P-WS-WT-PR-2108-A | MBH | Sent to BU Operations | 524 |  |  |  |  | 17.09.21 | 16.01.23 | 25.01.23 | 02.02.23 | 06.02.23 | 14.02.23 | 27.02.23 |  |  |  |  | 14.02.23 | 14.02.23 | 27.02.23 | T1 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Service Water Pump | LE21M708-P-WS-WT-PR-2108 | LE21M708-P-WS-WT-PR-2108-B | SR Metering | Enquiry yet to float | NA |  |  |  |  | 17.09.21 | 19.04.22 | 11.05.22 | 13.05.22 | 16.05.22 | [6 empty] | 13.05.22 | 13.05.22 | 16.05.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:01:16
Dwaraka | Process | Service Water Pump | LE21M708-P-WS-WT-PR-2108 | LE21M708-P-WS-WT-PR-2108-C | KSB | Sent to BU Operations | 374 |  |  |  |  | 17.09.21 | 10.04.23 | 13.04.23 | 09.05.23 | 19.05.23 | 26.07.23 | 27.07.23 |  |  |  |  | 26.07.23 | 26.07.23 | 27.07.23 | T3 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Service Water Pump | LE21M708-P-WS-WT-PR-2108 | LE21M708-P-WS-WT-PR-2108-D | WWTE SULZER | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 17.09.21 | [24 empty] | THENNARASU@lntecc.com-21.05.2024-10:31:17
Dwaraka | Process | Agitator | LE21M708-P-WS-WT-PR-2109 | LE21M708-P-WS-WT-PR-2109-A | Shivpad | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 29.01.22 | 05.02.22 | 15.04.22 | 03.05.22 | 26.05.22 | 01.06.22 |  |  |  |  | 01.06.22 | 01.06.22 | 01.06.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:08:25
Dwaraka | Process | Agitator | LE21M708-P-WS-WT-PR-2109 | LE21M708-P-WS-WT-PR-2109-B | Triveni | Regret offer | PR Closed | Offer rejected |  |  |  | 01.10.21 | 05.05.22 | 26.05.22 | [22 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:38:41
Dwaraka | Process | Agitator | LE21M708-P-WS-WT-PR-2109 | LE21M708-P-WS-WT-PR-2109-C | Verito | Post-order technically cleared | 653 |  |  |  |  | 01.10.21 | 16.05.22 | 26.05.22 | 15.06.22 | 01.07.22 | 09.07.22 | 15.07.22 |  |  |  |  | 15.07.22 | 15.07.22 | 15.07.22 | T1 | 03.09.22 | Verito | 17.09.22 | 29.09.22 | 20.10.22 | 21.10.22 |  |  |  | 02.11.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Agitator | LE21M708-P-WS-WT-PR-2109 | LE21M708-P-WS-WT-PR-2109-D | FFP | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 31.05.22 | 04.06.22 | 07.06.22 | 08.07.22 | 02.08.22 | 03.08.22 |  |  |  |  | 03.08.22 | 03.08.22 | 03.08.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:08:25
Dwaraka | Process | Agitator | LE21M708-P-WS-WT-PR-2109 | LE21M708-P-WS-WT-PR-2109-E | Sritech | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 20.06.22 | 22.07.22 | 25.07.22 | 02.08.22 | [6 empty] | 02.08.22 | 02.08.22 | 02.08.22 | T4 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:08:25
Dwaraka | Process | Chlorination System | LE21M708-P-WS-WT-PR-2110 | LE21M708-P-WS-WT-PR-2110-A | Supreme | Sent to BU Operations | PR Closed |  |  |  |  | 12.10.21 | 16.04.22 | 27.05.22 | 04.06.22 | 28.07.22 | [6 empty] | 28.07.22 | 28.07.22 | 28.07.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:08:25
Dwaraka | Process | Chlorination System | LE21M708-P-WS-WT-PR-2110 | LE21M708-P-WS-WT-PR-2110-B | Zion | Post-order technically cleared | 558 |  |  |  |  | 12.10.21 | 10.05.22 | 27.05.22 | 31.05.22 | 25.07.22 | [6 empty] | 25.07.22 | 25.07.22 | 25.07.22 | T1 | 29.11.22 | Zion | 14.12.22 | 21.12.22 | 13.01.23 | 24.01.23 |  |  |  | 28.01.23 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Chlorination System | LE21M708-P-WS-WT-PR-2110 | LE21M708-P-WS-WT-PR-2110-C | Chlorotech | Sent to BU Operations | PR Closed |  |  |  |  | 12.10.21 | 13.05.22 | 30.05.22 | 24.06.22 | 26.07.22 | 02.09.22 | 03.09.22 |  |  |  |  | 03.09.22 | 03.09.22 | 03.09.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:08:25
Dwaraka | Process | Chlorine Tonners | LE21M708-P-WS-WT-PR-2111 | LE21M708-P-WS-WT-PR-2111-A | NA | Regret offer | PR Closed |  |  |  |  | 01.10.21 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:25:38
Dwaraka | Process | Electrical Hoist | LE21M708-P-WS-WT-PR-2112 | LE21M708-P-WS-WT-PR-2112-A | Japs | Post-order technically cleared | 458 | NOT IN APPROVED MAKE |  |  |  | 01.10.21 | 26.05.22 | 29.08.22 | 03.09.22 | 12.09.22 | [6 empty] | 12.09.22 | 12.09.22 | 12.09.22 | T1 | 28.03.23 | Japs | 19.04.22 | 04.05.23 | 04.05.23 | 04.05.23 |  |  |  | 27.05.23 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Electrical Hoist | LE21M708-P-WS-WT-PR-2112 | LE21M708-P-WS-WT-PR-2112-B | Reva | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 22.06.22 | 29.06.22 | 16.09.22 | 17.09.22 | [6 empty] | 17.09.22 | 17.09.22 | 17.09.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:22:48
Dwaraka | Process | Electrical Hoist | LE21M708-P-WS-WT-PR-2112 | LE21M708-P-WS-WT-PR-2112-C | Indef | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 31.08.22 | 31.08.22 | 01.09.22 | 02.09.22 | [6 empty] | 02.09.22 | 02.09.22 | 02.09.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:22:48
Dwaraka | Process | Electrical Hoist | LE21M708-P-WS-WT-PR-2112 | LE21M708-P-WS-WT-PR-2112-D | Brady | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 01.10.21 | [24 empty] | deepak.choudhary@lntecc.com-20.05.2024-12:37:39
Dwaraka | Process | Manual Chain Pulley Block | LE21M708-P-WS-WT-PR-2113 | LE21M708-P-WS-WT-PR-2113-A | Japs | Regret offer | PR Closed | Rejected by client NOT IN APPROVED MAKE |  |  |  | 01.10.21 | 22.06.22 | 29.06.22 | 16.09.22 | 17.09.22 | [6 empty] | 17.09.22 | 17.09.22 | 17.09.22 | [11 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:08:25
Dwaraka | Process | Manual Chain Pulley Block | LE21M708-P-WS-WT-PR-2113 | LE21M708-P-WS-WT-PR-2113-B | Reva | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 31.08.22 | 31.08.22 | 01.09.22 | 02.09.22 | [6 empty] | 02.09.22 | 02.09.22 | 02.09.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:22:48
Dwaraka | Process | Manual Chain Pulley Block | LE21M708-P-WS-WT-PR-2113 | LE21M708-P-WS-WT-PR-2113-C | Indef | Post-order technically cleared | 150 |  |  |  |  | 01.10.21 | 31.08.22 | 31.08.22 | 01.09.22 | 02.09.22 | [6 empty] | 02.09.22 | 02.09.22 | 02.09.22 | T1 | 30.11.23 | Indef | 02.12.23 | 03.01.24 | 22.02.24 | 07.03.24 |  |  |  | 29.01.24 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Manual Chain Pulley Block | LE21M708-P-WS-WT-PR-2113 | LE21M708-P-WS-WT-PR-2113-D | Brady | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 01.10.21 | [24 empty] | deepak.choudhary@lntecc.com-20.05.2024-12:37:39
Dwaraka | Process | EOT Crane | LE21M708-P-WS-WT-PR-2114 | LE21M708-P-WS-WT-PR-2114-A | Japs | Sent to BU Operations | PR Closed | NOT IN APPROVED MAKE |  |  |  | 01.10.21 | 22.06.22 | 29.06.22 | 16.09.22 | 17.09.22 | [6 empty] | 17.09.22 | 17.09.22 | 17.09.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:22:48
Dwaraka | Process | EOT Crane | LE21M708-P-WS-WT-PR-2114 | LE21M708-P-WS-WT-PR-2114-B | Reva | Sent to BU Operations | PR Closed |  |  |  |  | 01.10.21 | 22.06.22 | 29.06.22 | 16.09.22 | 17.09.22 | [6 empty] | 17.09.22 | 17.09.22 | 17.09.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:22:48
Dwaraka | Process | EOT Crane | LE21M708-P-WS-WT-PR-2114 | LE21M708-P-WS-WT-PR-2114-C | Indef | Post-order technically cleared | 96 |  |  |  |  | 01.10.21 | 31.08.22 | 31.08.22 | 01.09.22 | 02.09.22 | [6 empty] | 02.09.22 | 02.09.22 | 02.09.22 | T1 | 30.11.23 | Indef | 02.12.23 | 03.01.24 | 24.04.24 | 30.04.24 |  |  |  | 29.01.24 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | EOT Crane | LE21M708-P-WS-WT-PR-2114 | LE21M708-P-WS-WT-PR-2114-D | Brady | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 01.10.21 | [24 empty] | deepak.choudhary@lntecc.com-20.05.2024-12:37:39
Dwaraka | Process | Submersible Pump | LE21M708-P-WS-WT-PR-2115 | LE21M708-P-WS-WT-PR-2115-A | Jasco | Regret offer | PR Closed | offer rejected (not in approved make) |  |  |  | 12.10.21 | 04.07.22 | 03.08.22 | [22 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:38:41
Dwaraka | Process | Submersible Pump | LE21M708-P-WS-WT-PR-2115 | LE21M708-P-WS-WT-PR-2115-B | MBH | Sent to BU Operations | 303 |  |  |  |  | 12.10.21 | 21.07.23 | 23.08.23 | 06.10.23 | 06.10.23 | [6 empty] | 06.10.23 | 06.10.23 | 06.10.23 | T1 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Submersible Pump | LE21M708-P-WS-WT-PR-2115 | LE21M708-P-WS-WT-PR-2115-C | Aqua | Sent to BU Operations | 272 |  |  |  |  | 12.10.21 | 19.10.22 | 05.11.22 | 08.12.22 | 12.12.22 | [6 empty] | 27.10.23 | 06.11.23 | 06.11.23 | T2 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Submersible Pump | LE21M708-P-WS-WT-PR-2115 | LE21M708-P-WS-WT-PR-2115-D | WWTE SULZER | Regret offer | PR Closed | offer rejected (not in approved make) |  |  |  | 12.10.21 | 27.01.22 | 03.02.22 | [22 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:23:36
Dwaraka | Process | Submersible Pump | LE21M708-P-WS-WT-PR-2115 | LE21M708-P-WS-WT-PR-2115-E | KSB | Sent to BU Operations | 374 |  |  |  |  | 12.10.21 | 10.04.23 | 13.04.23 | 09.05.23 | 19.05.23 | 26.07.23 | 27.07.23 |  |  |  |  | 26.07.23 | 26.07.23 | 27.07.23 | T3 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Submersible Pump | LE21M708-P-WS-WT-PR-2115 | LE21M708-P-WS-WT-PR-2115-F | Lubi | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 12.10.21 | [24 empty] | THENNARASU@lntecc.com-21.05.2024-10:31:17
Dwaraka | Process | Dosing pump | LE21M708-P-WS-WT-PR-2116 | LE21M708-P-WS-WT-PR-2116-A | SR Metering | Sent to BU Operations | PR Closed |  |  |  |  | 17.09.21 | 19.04.22 | 11.05.22 | 13.05.22 | 16.05.22 | [6 empty] | 16.05.22 | 16.05.22 | 16.05.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:33:43
Dwaraka | Process | Dosing pump | LE21M708-P-WS-WT-PR-2116 | LE21M708-P-WS-WT-PR-2116-B | Positive Metering | Sent to BU Operations | PR Closed |  |  |  |  | 17.09.21 | 16.04.22 | 11.05.22 | 16.05.22 | 16.05.22 | [6 empty] | 16.05.22 | 16.05.22 | 16.05.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:33:43
Dwaraka | Process | Dosing pump | LE21M708-P-WS-WT-PR-2116 | LE21M708-P-WS-WT-PR-2116-C | Verito | Post-order technically cleared | 692 |  |  |  |  | 17.09.21 | 10.05.22 | 13.05.22 | 17.05.22 | 18.05.22 | [6 empty] | 18.05.22 | 18.05.22 | 18.05.22 | T1 | 06.08.22 | Verito | 22.08.22 | 01.09.22 | 01.09.22 | 12.09.22 |  |  |  | 05.10.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Sampling Pump | LE21M708-P-WS-WT-PR-2117 | LE21M708-P-WS-WT-PR-2117-A | Lubi | Regret offer | PR Closed | Site Procurement |  |  |  | 27.09.21 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:34:25
Dwaraka | Process | Sampling Pump | LE21M708-P-WS-WT-PR-2117 | LE21M708-P-WS-WT-PR-2117-B | KSB | Regret offer | PR Closed | Site Procurement |  |  |  | 27.09.21 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:34:40
Dwaraka | Process | Dewatering Pump | LE21M708-P-WS-WT-PR-2118 | LE21M708-P-WS-WT-PR-2118-A | Lubi | Sent to BU Operations | 601 |  |  |  |  | 27.09.21 | 19.10.22 | 05.11.22 | 08.12.22 | 12.12.22 | [6 empty] | 08.12.22 | 08.12.22 | 12.12.22 | T1 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Dewatering Pump | LE21M708-P-WS-WT-PR-2118 | LE21M708-P-WS-WT-PR-2118-B | MBH | Sent to BU Operations | 443 |  |  |  |  | 27.09.21 | 18.03.23 | 04.04.23 | 10.04.23 | 13.04.23 | 09.05.23 | 19.05.23 |  |  |  |  | 09.05.23 | 09.05.23 | 19.05.23 | T2 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Dewatering Pump | LE21M708-P-WS-WT-PR-2118 | LE21M708-P-WS-WT-PR-2118-C | Aqua | Regret offer | PR Closed |  |  |  |  | 27.09.21 | 27.02.23 | 01.03.23 | 02.03.23 | 15.03.23 | [6 empty] | 02.03.23 | 02.03.23 | [12 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:34:54
Dwaraka | Process | Dewatering Pump | LE21M708-P-WS-WT-PR-2118 | LE21M708-P-WS-WT-PR-2118-D | KSB | Sent to BU Operations | 374 |  |  |  |  | 27.09.21 | 10.04.23 | 13.04.23 | 09.05.23 | 19.05.23 | 26.07.23 | 27.07.23 |  |  |  |  | 26.07.23 | 26.07.23 | 27.07.23 | T3 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Dewatering Pump | LE21M708-P-WS-WT-PR-2118 | LE21M708-P-WS-WT-PR-2118-E | WWTE SULZER | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 27.09.21 | [24 empty] | THENNARASU@lntecc.com-21.05.2024-10:31:17
Dwaraka | Process | Submersible Mixer | LE21M708-P-WS-WT-PR-2119 | LE21M708-P-WS-WT-PR-2119-A | FFP | Sent to BU Operations | PR Closed |  |  |  |  | 27.09.21 | 30.05.22 | 03.08.22 | [8 empty] | 03.08.22 | 03.08.22 | 03.08.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:38:40
Dwaraka | Process | Submersible Mixer | LE21M708-P-WS-WT-PR-2119 | LE21M708-P-WS-WT-PR-2119-B | Sulzer | Post-order technically cleared | 577 |  |  |  |  | 27.09.21 | 08.07.22 | 03.08.22 | [8 empty] | 03.08.22 | 03.08.22 | 03.08.22 | T1 | 19.09.22 | Sulzer | 22.09.22 | 23.09.22 | 31.12.22 | 05.01.23 |  |  |  | 18.11.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | WTP Sluice Gates | LE21M708-P-WS-WT-PR-2120 | LE21M708-P-WS-WT-PR-2120-A | Jash | Post-order technically cleared | 150 | BASED ON REVISED PR |  |  |  | 01.02.23 | 08.02.23 | 18.02.23 | [8 empty] | 01.02.23 | 18.02.23 | 18.02.23 | T1 | 13.12.23 | Jash | 16.12.23 | 12.02.24 | 24.02.24 | 07.03.24 |  |  |  | 11.02.24 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | WTP Sluice Gates | LE21M708-P-WS-WT-PR-2120 | LE21M708-P-WS-WT-PR-2120-B | IVC | Regret offer | PR Closed | AWAITING RESPONSE FROM VENDOR |  |  |  | 08.02.23 | [24 empty] | deepak.choudhary@lntecc.com-20.05.2024-12:37:39
Dwaraka | Process | Air Compressor | LE21M708-P-WS-WT-PR-2121 | LE21M708-P-WS-WT-PR-2121-A | Atlas Corpo | Regret offer | PR Closed | Offer is not valid |  |  |  | 12.10.21 | 16.04.22 | [23 empty] | THENNARASU@lntecc.com-21.05.2024-10:29:36
Dwaraka | Process | Air Compressor | LE21M708-P-WS-WT-PR-2121 | LE21M708-P-WS-WT-PR-2121-B | Ingersoll | Pre-order pending with EDRC | 92 |  |  |  |  | 12.10.21 | 04.05.24 | [20 empty] | 26.07.24 | 12.08.24 | 11.10.24 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Air Compressor | LE21M708-P-WS-WT-PR-2121 | LE21M708-P-WS-WT-PR-2121-C | ELGI | Pre-order pending with EDRC | 88 |  |  |  |  | 12.10.21 | 08.05.24 | [20 empty] | 26.07.24 | 12.08.24 | 11.10.24 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Trolley | LE21M708-P-WS-WT-PR-2122 | LE21M708-P-WS-WT-PR-2122-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 17.09.21 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:27:15
Dwaraka | Process | Sludge Thickener | LE21M708-P-WS-WT-PR-2123 | LE21M708-P-WS-WT-PR-2123-A | Shivpad | Sent to BU Operations | PR Closed |  |  |  |  | 27.09.21 | 22.04.22 | 13.05.22 | 19.05.22 | 20.05.22 | 13.06.22 | 13.06.22 |  |  |  |  | 13.06.22 | 13.06.22 | 13.06.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:47:34
Dwaraka | Process | Sludge Thickener | LE21M708-P-WS-WT-PR-2123 | LE21M708-P-WS-WT-PR-2123-B | Triveni | Sent to BU Operations | PR Closed |  |  |  |  | 27.09.21 | 05.05.22 | 13.05.22 | 17.05.22 | 19.05.22 | 27.05.22 | 30.05.22 |  |  |  |  | 30.05.22 | 30.05.22 | 30.05.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:47:34
Dwaraka | Process | Sludge Thickener | LE21M708-P-WS-WT-PR-2123 | LE21M708-P-WS-WT-PR-2123-C | Sritech | Post-order technically cleared | 655 |  |  |  |  | 27.09.21 | 20.06.22 | 20.06.22 | 28.06.22 | 01.07.22 | [6 empty] | 01.07.22 | 01.07.22 | 01.07.22 | T1 | 15.09.22 | Sritech | 21.09.22 | 28.09.22 | 18.10.22 | 19.10.22 |  |  |  | 14.11.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Screw Pumps | LE21M708-P-WS-WT-PR-2124 | LE21M708-P-WS-WT-PR-2124-A | Verito | Sent to BU Operations | PR Closed |  |  |  |  | 17.09.21 | 08.07.22 | 25.07.22 | 10.08.22 | 22.08.22 | [6 empty] | 22.08.22 | 22.08.22 | 22.08.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:49:52
Dwaraka | Process | Screw Pumps | LE21M708-P-WS-WT-PR-2124 | LE21M708-P-WS-WT-PR-2124-B | Minimax | Post-order technically cleared | 473 |  |  |  |  | 17.09.21 | 26.06.22 | 25.07.22 | 26.09.22 | 28.09.22 | [6 empty] | 28.09.22 | 28.09.22 | 28.09.22 | T1 | 02.02.23 | Minimax | 06.02.23 | 18.03.23 | 15.04.23 | 19.04.23 |  |  |  | 03.04.23 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | Centrifuge | LE21M708-P-WS-WT-PR-2125 | LE21M708-P-WS-WT-PR-2124-C | Alfa Level | Regret offer | PR Closed | vendor did not reply after pre order |  |  |  | 12.10.21 | 16.04.22 | 12.05.22 | 30.05.22 | 01.06.22 | 22.07.22 | 02.08.22 | 12.08.22 | 18.08.22 | [16 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:38:41
Dwaraka | Process | Centrifuge | LE21M708-P-WS-WT-PR-2125 | LE21M708-P-WS-WT-PR-2125-A | GEA | Regret offer | PR Closed |  |  |  |  | 12.10.21 | 11.04.22 | 12.05.22 | 06.06.22 | 14.06.22 | [20 empty] | deepak.choudhary@lntecc.com-20.05.2024-11:49:52
Dwaraka | Process | Centrifuge | LE21M708-P-WS-WT-PR-2125 | LE21M708-P-WS-WT-PR-2125-B | Hiller | Post-order technically cleared | 653 |  |  |  |  | 12.10.21 | 25.05.22 | 04.06.22 | 16.06.22 | 15.07.22 | 25.07.22 | 29.07.22 |  |  |  |  | 29.07.22 | 29.07.22 | 29.07.22 | T1 | 18.10.22 | Hiller | 20.10.22 | 21.10.22 | 21.10.22 | 21.10.22 |  |  |  | 17.12.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | DWPE Tanks | LE21M708-P-WS-WT-PR-2126 | LE21M708-P-WS-WT-PR-2126-A | EPP | Post-order technically cleared | 619 |  |  |  |  | 27.09.21 | 20.07.22 | 25.07.22 | 27.07.22 | 17.08.22 | [6 empty] | 17.08.22 | 17.08.22 | 17.08.22 | T1 | 19.10.22 | EPP | 21.10.22 | 08.11.22 | 21.11.22 | 24.11.22 |  |  |  | 18.12.22 | THENNARASU@lntecc.com-11.07.2024-14:16:08
Dwaraka | Process | DWPE Tanks | LE21M708-P-WS-WT-PR-2126 | LE21M708-P-WS-WT-PR-2126-B | Dolf | Sent to BU Operations | PR Closed |  |  |  |  | 27.09.21 | 19.07.22 | 25.07.22 | 16.08.22 | 18.08.22 | [6 empty] | 18.08.22 | 18.08.22 | 18.08.22 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-12:36:58
Dwaraka | Process | DWPE Tanks | LE21M708-P-WS-WT-PR-2126 | LE21M708-P-WS-WT-PR-2126-C | Sunrise | Sent to BU Operations | PR Closed |  |  |  |  | 27.09.21 | 30.07.22 | 01.08.22 | 06.08.22 | 11.08.22 | [6 empty] | 11.08.22 | 11.08.22 | 11.08.22 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-12:36:58
Dwaraka | Process | Platform Weighing Machine | LE21M708-P-WS-WT-PR-2127 | LE21M708-P-WS-WT-PR-2127 | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 17.09.21 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:26:42
Dwaraka | Mechanical | EOT crane | LE21M708-M-WS-WT-PR-1001 | LE21M708-M-WS-WT-PR-1001-A | Indef | Pre-order technically cleared | 61 |  |  |  |  | 08.05.24 | 30.05.24 | 30.05.24 | 31.05.24 | 01.06.24 | [6 empty] | 01.06.24 | 01.06.24 | 04.06.24 | T1 | [7 empty] | 01.06.24 | 18.06.24 | 17.08.24 | gopal.samarth@lntecc.com-23.07.2024-10:05:15
Dwaraka | Mechanical | EOT crane | LE21M708-M-WS-WT-PR-1001 | LE21M708-M-WS-WT-PR-1001-B | JAPS | Regret offer | PR Closed |  |  |  |  | 30.05.24 | 30.05.24 | 30.05.24 | 30.05.24 | [19 empty] | 17.09.24 | 16.11.24 | gopal.samarth@lntecc.com-12.07.2024-17:11:28
Dwaraka | Mechanical | Dismantling joints | LE21M708-M-WS-WT-PR-1002 | LE21M708-M-WS-WT-PR-1002-A | SUR Industries | Sent to BU Operations | PR Closed |  |  |  |  | 11.12.23 | 12.12.23 | 12.12.23 | 20.03.24 | 26.03.24 | [6 empty] | 26.03.24 | 26.03.24 | 26.03.24 | T1 | [7 empty] | 26.03.24 | 12.04.24 | 11.06.24 | gopal.samarth@lntecc.com-12.07.2024-16:47:18
Dwaraka | Mechanical | Dismantling joints | LE21M708-M-WS-WT-PR-1002 | LE21M708-M-WS-WT-PR-1002-B | Precise Engineers | Post-order technically cleared | 100 |  |  |  |  | 11.12.23 | 12.12.23 | 12.12.23 | 04.01.24 | 05.01.24 | 06.01.24 | 08.01.24 | 15.01.24 |  |  |  | 08.01.24 | 08.01.24 | 08.01.24 | T1 | 15.04.24 | Precise Engineers | 17.04.24 | 18.04.24 | 20.04.24 | 26.04.24 |  | 08.01.24 | 25.01.24 | 25.03.24 | gopal.samarth@lntecc.com-23.07.2024-10:05:15
Dwaraka | Mechanical | HSC pumps | LE21M708-M-WS-WT-PR-1003 | LE21M708-M-WS-WT-PR-1003-A | WILO | Post-order technically cleared | 62 |  |  |  |  | 08.01.24 | 15.01.24 | 19.01.24 | 29.01.24 | 05.02.24 | 12.02.24 | 15.02.24 | 26.02.24 | 01.03.24 |  |  | 11.03.24 | 15.03.24 | 25.03.24 | T1 | 03.06.24 | WILO | 03.06.24 | 03.06.24 | 03.06.24 | 03.06.24 |  | 11.03.24 | 28.03.24 | 27.05.24 | gopal.samarth@lntecc.com-23.07.2024-10:05:15
Dwaraka | Mechanical | Butterfly valves | LE21M708-M-WS-WT-PR-1004 | LE21M708-M-WS-WT-PR-1004-A | AVK | Approved by Client | PR Closed |  |  |  |  | 18.12.23 | 02.01.24 | 05.01.24 | 08.01.24 | 11.01.24 | 15.01.24 | 18.01.24 | 29.01.24 | 30.01.24 |  |  | 01.02.24 | 02.02.24 | 05.02.24 | T1 | 19.02.24 | AVK | 20.02.24 | 21.02.24 | 22.02.24 | 22.02.24 | 27.02.24 | 01.02.24 | 18.02.24 | 18.04.24 | svcn@lntecc.com-03.07.2024-15:21:09
Dwaraka | Mechanical | Sluice valves | LE21M708-M-WS-WT-PR-1005 | LE21M708-M-WS-WT-PR-1005-A | AVK | Approved by Client | PR Closed |  |  |  |  | 18.12.23 | 02.01.24 | 05.01.24 | 08.01.24 | 11.01.24 | 15.01.24 | 18.01.24 | 29.01.24 | 30.01.24 |  |  | 01.02.24 | 02.02.24 | 05.02.24 | T1 | 19.02.24 | AVK | 20.02.24 | 21.02.24 | 22.02.24 | 22.02.24 | 27.02.24 | 01.02.24 | 18.02.24 | 18.04.24 | svcn@lntecc.com-03.07.2024-15:21:09
Dwaraka | Mechanical | nonreturn valves | LE21M708-M-WS-WT-PR-1006 | LE21M708-M-WS-WT-PR-1006-A | AVK | Approved by Client | PR Closed |  |  |  |  | 18.12.23 | 02.01.24 | 05.01.24 | 08.01.24 | 11.01.24 | 15.01.24 | 18.01.24 | 29.01.24 | 30.01.24 |  |  | 01.02.24 | 02.02.24 | 05.02.24 | T1 | 19.02.24 | AVK | 20.02.24 | 21.02.24 | 22.02.24 | 22.02.24 | 27.02.24 | 01.02.24 | 18.02.24 | 18.04.24 | svcn@lntecc.com-03.07.2024-15:21:09
Dwaraka | Mechanical | Sluice gate | LE21M708-M-WS-WT-PR-1007 | LE21M708-M-WS-WT-PR-1007-A | JASH | Post-order technically cleared | 75 |  |  |  |  | 01.03.24 | 19.03.24 | 19.03.24 | 26.03.24 | 29.03.24 | 03.04.24 | 17.04.24 | 01.05.24 | 03.05.24 | 15.05.24 | 16.05.24 | 17.05.24 | 18.05.24 | 18.05.24 | T1 | 21.05.24 | JASH | 21.05.24 | 21.05.24 | 21.05.24 | 21.05.24 |  | 17.05.24 | 03.06.24 | 20.07.24 | gopal.samarth@lntecc.com-23.07.2024-10:05:15
Dwaraka | Mechanical | Sluice gate | LE21M708-M-WS-WT-PR-1007 | LE21M708-M-WS-WT-PR-1007-B | IVC | Sent to BU Operations | PR Closed |  |  |  |  | 01.03.24 | 12.03.24 | 14.03.24 | 15.03.24 | 18.03.24 | [6 empty] | 19.03.24 | 19.03.24 | 19.03.24 | T1 | [7 empty] | 19.03.24 | 05.04.24 | 04.06.24 | svcn@lntecc.com-03.07.2024-15:21:09
Dwaraka | Mechanical | Ventilation fans | LE21M708-M-WS-WT-PR-1008 | LE21M708-M-WS-WT-PR-1008-A |  | Enquiry yet to float | NA | [29 empty] | gopal.samarth@lntecc.com-12.07.2024-17:17:08
Dwaraka | Mechanical | WTP valves | LE21M708-M-WS-WT-PR-1009 | LE21M708-M-WS-WT-PR-1009-A | CAIR | Pre-order comments issued | 23 |  |  |  |  | 04.06.24 | 18.06.24 | 25.06.24 | 11.07.24 | 12.07.24 | [20 empty] | gopal.samarth@lntecc.com-23.07.2024-10:05:15
Dwaraka | Instrumentation | Pressure Gauge | LE21M708-I-WS-PR-5500 | LE21M708-I-WS-PR-5500-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | AN Instruments | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:03:19
Dwaraka | Instrumentation | Pressure Switch | LE21M708-I-WS-PR-5501 | LE21M708-I-WS-PR-5501-A | AN Instruments | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | AN Instruments | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:03:19
Dwaraka | Instrumentation | Pressure Transmitter | LE21M708-I-WS-PR-5502 | LE21M708-I-WS-PR-5502-A | E&H | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | E&H | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Instrumentation | Ultrasonic level transmitter | LE21M708-I-WS-PR-5503 | LE21M708-I-WS-PR-5503-A | E&H | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | E&H | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Instrumentation | Electromagnetic flow meter | LE21M708-I-WS-PR-5505 | LE21M708-I-WS-PR-5505-A | Krohne marshall | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | Krohne marshall | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Instrumentation | Level Indicator | LE21M708-I-WS-PR-5506 | LE21M708-I-WS-PR-5506-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | SBEM | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Instrumentation | level switch | LE21M708-I-WS-PR-5507 | LE21M708-I-WS-PR-5507-A | SBEM | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | SBEM | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Instrumentation | PH Meter | LE21M708-I-WS-PR-5508 | LE21M708-I-WS-PR-5508-A | Xylem | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | Xylem | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Instrumentation | Residual chlorine analsyer | LE21M708-I-WS-PR-5509 | LE21M708-I-WS-PR-5509-A | Xylem | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | Xylem | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Instrumentation | Turbidity meter | LE21M708-I-WS-PR-5510 | LE21M708-I-WS-PR-5510-A | Xylem | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | Xylem | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Instrumentation | Instrumentation signal and control cables | LE21M708-I-WS-PR-5511 | LE21M708-I-WS-PR-55111-A | Delton | Approved by Client | PR Closed |  |  |  |  | 09.11.22 | 23.05.22 | 23.05.22 | [8 empty] | 22.07.22 | 22.07.22 | 22.07.22 | T1 | 14.11.23 | Delton | 14.11.23 | 14.11.23 | 14.11.23 | 14.11.23 | 24.11.23 |  |  | 13.01.24 | SURENDHAR@lntecc.com-04.05.2024-12:04:30
Dwaraka | Electrical | Transformer | LE21M708-E-WS-WT-PR-4002 | LE21M708-E-WS-WT-PR-4002-A | KEC | Pre-order technically cleared | 213 |  |  | jakson.sharadj@jakpower.com |  | 29.05.23 | 05.06.23 | 14.06.23 | 20.06.23 | 05.07.23 | 11.07.23 | 21.07.23 |  |  |  |  | 15.09.23 | 04.01.24 |  | T3 | [7 empty] | 04.01.24 | 21.01.24 | 21.03.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | Transformer | LE21M708-E-WS-WT-PR-4002 | LE21M708-E-WS-WT-PR-4002-B | TMC | Sent to BU Operations | 153 |  |  | sanjib@tmc-india.com |  | 23.11.23 | 27.11.23 | 11.01.24 | [8 empty] | 04.12.23 | 08.01.24 | 04.03.24 | T3 | [7 empty] | 08.01.24 | 25.01.24 | 25.03.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | Transformer | LE21M708-E-WS-WT-PR-4002 | LE21M708-E-WS-WT-PR-4002-C | Voltamp | Pre-order technically rejected | PR Closed |  |  | sasik_vtlchn@voltamptransformers.com |  | 20.04.22 | 18.05.22 | [23 empty] | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:45:11
Dwaraka | Electrical | DG Set | LE21M708-E-WS-WT-PR-4003 | LE21M708-E-WS-WT-PR-4003-A | Sudhir | Enquiry yet to float | NA |  |  | mithlesh@sudhirpower.com |  | 21.02.23 | 22.09.23 | 28.09.23 | [19 empty] | 05.09.24 | 22.09.24 | 21.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | HT Panel | LE21M708-E-WS-WT-PR-4004 | LE21M708-E-WS-WT-PR-4004-A | Coronet | Post-order technically cleared | 201 |  |  | laxman@coronet.in |  | 21.06.23 | 26.06.23 | 03.07.23 | [8 empty] | 17.07.23 | 24.07.23 | 26.07.23 | T3 | 07.09.23 | Coronet | 11.09.23 | 14.09.23 | 21.09.23 | 16.01.24 |  | 24.07.23 | 10.08.23 | 09.10.23 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | HT Panel | LE21M708-E-WS-WT-PR-4004 | LE21M708-E-WS-WT-PR-4004-B | HTS | Regret offer | PR Closed |  |  | suhel.sayyad@htswitchgears.com |  | 16.05.22 | 27.07.23 | 23.08.23 | [22 empty] | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:45:11
Dwaraka | Electrical | HT Cables & Termination Kits | LE21M708-E-WS-WT-PR-4005 | LE21M708-E-WS-WT-PR-4005-A | Grandlay | Pre-order technically cleared | 129 |  |  | gaurav.arora@grandlaycable.com |  | 19.08.23 | 21.08.23 | 22.08.23 | [8 empty] | 26.03.24 | 28.03.24 | [9 empty] | 28.03.24 | 14.04.24 | 13.06.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | HT Cables & Termination Kits | LE21M708-E-WS-WT-PR-4005 | LE21M708-E-WS-WT-PR-4005-B | Universal | Pre-order technically cleared | 129 |  |  | ranjith@unsitar.co.in |  | 08.08.23 | 14.08.23 | 18.08.23 | [8 empty] | 27.03.24 | 28.03.24 | [9 empty] | 28.03.24 | 14.04.24 | 13.06.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | LT Panel | LE21M708-E-WS-WT-PR-4006 | LE21M708-E-WS-WT-PR-4006-A | Coronet | Post-order comments issued | 20 |  |  | pawan@coronet.in |  | 02.09.22 | 01.04.23 | 04.05.23 | 24.05.23 | 27.06.23 | 30.06.23 | 25.07.23 |  |  |  |  | 11.08.23 | 19.08.23 | 14.03.24 | t1 | 10.04.24 | Coronet | 10.07.24 | 15.07.24 |  |  |  | 19.08.23 | 05.09.23 | 04.11.23 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | LT Panel | LE21M708-E-WS-WT-PR-4006 | LE21M708-E-WS-WT-PR-4006-B | HTS | Sent to BU Operations | PR Closed |  |  | madhuri.raut@htswitchgears.com |  | 11.05.22 | 17.05.22 | 06.06.22 | 18.06.22 | 29.06.22 | 01.12.22 | 20.02.23 | 06.07.23 | 08.07.23 |  |  | 30.03.24 | 30.03.24 | 14.03.24 | t1 | [7 empty] | 30.03.24 | 16.04.24 | 15.06.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | LT Panel | LE21M708-E-WS-WT-PR-4006 | LE21M708-E-WS-WT-PR-4006-C | Ragavendra | Sent to BU Operations | PR Closed |  |  | operation@ragavendracontrol.com |  | 15.12.23 | 02.02.24 | 07.02.24 | 27.03.24 | 28.03.24 | [6 empty] | 01.04.24 | 02.04.24 | 21.07.23 | t3 | [7 empty] | 02.04.24 | 19.04.24 | 18.06.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | LT Power and Control Cables | LE21M708-E-WS-WT-PR-4007 | LE21M708-E-WS-WT-PR-4007-A | Grandlay | Pre-order technically cleared | 129 |  |  | gaurav.arora@grandlaycable.com |  | 19.08.23 | 21.08.23 | 22.08.23 | [8 empty] | 26.03.24 | 28.03.24 | [9 empty] | 28.03.24 | 14.04.24 | 13.06.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | LT Power and Control Cables | LE21M708-E-WS-WT-PR-4007 | LE21M708-E-WS-WT-PR-4007-B | Universal | Pre-order technically cleared | 129 |  |  | ranjith@unsitar.co.in |  | 08.08.23 | 14.08.23 | 18.08.23 | [8 empty] | 27.03.24 | 28.03.24 | [9 empty] | 28.03.24 | 14.04.24 | 13.06.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | Cable Trays & its supports | LE21M708-E-WS-WT-PR-4008 | LE21M708-E-WS-WT-PR-4008-A | Not decided yet | Enquiry yet to float | NA | [26 empty] | 04.09.24 | 21.09.24 | 20.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | LPBS | LE21M708-E-WS-WT-PR-4009 | LE21M708-E-WS-WT-PR-4009-A | Coronet | Pre-order technically cleared | 351 |  |  | pawan@coronet.in |  | 02.09.22 | 01.04.23 | 04.05.23 | 24.05.23 | 27.06.23 | 30.06.23 | 25.07.23 |  |  |  |  | 11.08.23 | 19.08.23 | [9 empty] | 19.08.23 | 05.09.23 | 04.11.23 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | LPBS | LE21M708-E-WS-WT-PR-4009 | LE21M708-E-WS-WT-PR-4009-B | HTS | Pre-order technically cleared | 127 |  |  | madhuri.raut@htswitchgears.com |  | 11.05.22 | 17.05.22 | 06.06.22 | 18.06.22 | 29.06.22 | 01.12.22 | 20.02.23 | 06.07.23 | 08.07.23 |  |  | 30.03.24 | 30.03.24 | [9 empty] | 30.03.24 | 16.04.24 | 15.06.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | LPBS | LE21M708-E-WS-WT-PR-4009 | LE21M708-E-WS-WT-PR-4009-C | Ragavendra | Pre-order technically cleared | 124 |  |  | operation@ragavendracontrol.com |  | 15.12.23 | 02.02.24 | 07.02.24 | 27.03.24 | 28.03.24 | [6 empty] | 01.04.24 | 02.04.24 | [9 empty] | 02.04.24 | 19.04.24 | 18.06.24 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | Earthing & Lightning protection materials with accessories | LE21M708-E-WS-WT-PR-4010 | LE21M708-E-WS-WT-PR-4010-A | Not decided yet | Enquiry yet to float | NA | [26 empty] | 07.09.24 | 24.09.24 | 23.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | Lighting Fixture | LE21M708-E-WS-WT-PR-4011 | LE21M708-E-WS-WT-PR-4011-A | Santech Engineers | Post-order technically cleared | 87 |  |  | sales@santechengineers.in |  | 21.03.23 | 03.04.23 | 12.04.23 | 01.05.23 | 22.05.23 | [6 empty] | 10.07.23 | 12.07.23 | 24.07.23 | T3 | 18.03.24 | Santech Engineers | 18.04.24 | 02.05.24 | 03.05.24 | 09.05.24 |  | 12.07.23 | 29.07.23 | 27.09.23 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | Electrical Safety Items | LE21M708-E-WS-WT-PR-4012 | LE21M708-E-WS-WT-PR-4012-A | Not decided yet | Enquiry yet to float | NA | [26 empty] | 06.09.24 | 23.09.24 | 22.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | Cable Glands and Lugs | LE21M708-E-WS-WT-PR-4013 | LE21M708-E-WS-WT-PR-4013-A | Not decided yet | Enquiry yet to float | NA | [26 empty] | 04.09.24 | 21.09.24 | 20.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | Switchboards, Sockets & Other Accessories | LE21M708-E-WS-WT-PR-4014 | LE21M708-E-WS-WT-PR-4014-A | Not decided yet | Enquiry yet to float | NA | [26 empty] | 07.09.24 | 24.09.24 | 23.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | Lighting pole and Junction Box | LE21M708-E-WS-WT-PR-4015 | LE21M708-E-WS-WT-PR-4015-A | Not decided yet | Enquiry yet to float | NA | [26 empty] | 09.09.24 | 26.09.24 | 25.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | Battery and Battery Charger | LE21M708-E-WS-WT-PR-4016 | LE21M708-E-WS-WT-PR-4016-A | Not decided yet | Enquiry yet to float | NA | [26 empty] | 03.09.24 | 20.09.24 | 19.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | Distribution Board | LE21M708-E-WS-WT-PR-4017 | LE21M708-E-WS-WT-PR-4017-A | Not decided yet | Enquiry yet to float | NA | [26 empty] | 02.09.24 | 19.09.24 | 18.11.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:43:26
Dwaraka | Electrical | HT Capacitor | LE21M708-E-WS-WT-PR-4017B | LE21M708-E-WS-WT-PR-4017B-A | CGL | Post-order technically cleared | 314 |  |  |  |  | 30.06.22 | 25.07.22 | 01.08.22 | 31.08.22 | 07.09.22 | [6 empty] | 01.10.22 | 22.10.22 | 31.10.22 | T3 | 07.07.23 | CGL | 17.07.23 | 24.07.23 | 21.08.23 | 25.09.23 |  | 22.10.22 | 08.11.22 | 07.01.23 | usman.mohideen@lntecc.com-15.07.2024-15:17:28
Dwaraka | Electrical | HT Capacitor | LE21M708-E-WS-WT-PR-4017B | LE21M708-E-WS-WT-PR-4017B-B | Madhav | Regret offer | PR Closed |  |  |  |  | 07.07.22 | 04.08.22 | 23.08.22 | [22 empty] | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:45:11
Dwaraka | Electrical | HT Capacitor | LE21M708-E-WS-WT-PR-4017B | LE21M708-E-WS-WT-PR-4017B-C | Shreem | Regret offer | PR Closed |  |  |  |  | 25.07.22 | 29.07.22 | 24.08.22 | [22 empty] | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:45:11
East Medinipur EM 01 | Process | IPS and flocculator paddles | LE200021-P-WS-WT-PR-2262 | LE200021-P-WS-WT-PR-2262A | Sritech | Post-order technically cleared | 38 |  |  |  | 08.01.24 | 08.01.24 | 08.01.24 | 12.01.24 | [8 empty] | 31.01.24 | 31.01.24 | 31.01.24 | T1 | 25.03.24 | Sritech | 10.04.24 | 27.04.24 | 27.06.24 | 27.06.24 |  |  |  | 24.05.24 | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | IPS and flocculator paddles | LE200021-P-WS-WT-PR-2262 | LE200021-P-WS-WT-PR-2262B | Filsep | Sent to BU Operations | PR Closed |  |  |  | 24.12.20 | 24.12.20 | 24.12.20 | 31.12.20 | [8 empty] | 12.03.21 | 16.03.21 | 16.03.21 | T2 | [10 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | IPS and flocculator paddles | LE200021-P-WS-WT-PR-2262 | LE200021-P-WS-WT-PR-2262C | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 01.12.20 | 01.12.20 | 01.12.20 | 05.12.20 | [8 empty] | 01.06.21 | 01.07.21 | 01.07.21 | T3 | [10 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Air blowers | LE200021-P-WS-WT-PR-2263 | LE200021-P-WS-WT-PR-2263-A | SWAM | Post-order technically cleared | 24 |  |  |  | 05.12.23 | 05.12.23 | 05.12.23 | 27.12.23 | 08.01.24 | 12.01.24 | 08.02.24 | 09.02.24 | 19.02.24 | 06.03.24 |  |  | 25.04.24 | 27.03.24 | 29.03.24 | T2 | 20.05.24 | SWAM | 30.05.24 | 10.06.24 | 12.07.24 | 11.07.24 |  |  |  | 19.07.24 | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | Air blowers | LE200021-P-WS-WT-PR-2263 | LE200021-P-WS-WT-PR-2263-B | KAY | Sent to BU Operations | PR Closed |  |  |  | 05.12.23 | 05.12.23 | 05.12.23 | 05.12.23 | 12.01.24 | 18.01.24 | 08.02.24 | 13.02.24 | 23.02.24 | 06.03.24 |  |  | 25.04.24 | 29.03.24 | 29.03.24 | T1 | [10 empty] | PVVKSG@lntecc.com-31.05.2024-09:55:55
East Medinipur EM 01 | Process | Agitators | LE200021-P-WS-WT-PR-2264 | LE200021-P-WS-WT-PR-2264-A | Shivpad | Sent to BU Operations | 129 |  |  |  | 01.12.20 | 01.12.20 | 28.03.24 | 28.03.24 | [8 empty] | 28.03.24 | 28.03.24 | 28.03.24 | T2 | [10 empty] | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | Agitators | LE200021-P-WS-WT-PR-2264 | LE200021-P-WS-WT-PR-2264-B | Positive Metering | Pre-order comments issued | 20 |  |  |  |  | 14.03.24 | 28.03.24 | 26.04.24 | 04.07.24 | 15.07.24 | [17 empty] | 18.07.24 | 04.08.24 | 03.10.24 | PVVKSG@lntecc.com-26.07.2024-10:08:40
East Medinipur EM 01 | Process | Chlorination system | LE200021-P-WS-WT-PR-2265 | LE200021-P-WS-WT-PR-2265-A | ME Infra | Sent to BU Operations | 25 |  |  |  | 07.12.23 | 07.12.23 | 07.12.23 | 27.12.23 | 09.01.24 | 14.02.24 | 14.03.24 | 29.03.24 | 23.04.24 | 30.04.24 | 21.05.24 | 28.05.24 | 10.07.24 | 29.06.24 | 10.07.24 | T2 | [6 empty] | 08.02.24 | 04.07.24 | 21.07.24 | 19.09.24 | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | Chlorination system | LE200021-P-WS-WT-PR-2265 | LE200021-P-WS-WT-PR-2265-B | Supreme | Regret offer | PR Closed |  |  |  | 07.12.23 | 07.12.23 | 07.12.23 | 27.12.23 | 08.01.24 | 12.01.24 | 14.03.24 | 04.04.24 | [18 empty] | PVVKSG@lntecc.com-02.07.2024-16:45:46
East Medinipur EM 01 | Process | Chlorination system | LE200021-P-WS-WT-PR-2265 | LE200021-P-WS-WT-PR-2265-C | Zion | Sent to BU Operations | 54 |  |  |  | 19.02.24 | 19.02.24 | 19.02.24 | 21.02.24 | 14.03.24 | 29.03.24 | 23.04.24 | 30.04.24 | 03.05.24 | 15.05.24 |  |  | 11.06.24 | 31.05.24 | 11.06.24 | T1 | [10 empty] | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | Hoist | LE200021-P-WS-WT-PR-2266 | LE200021-P-WS-WT-PR-2266-A | Reva | Enquiry yet to float | NA |  |  |  | 07.08.20 | 07.08.20 | [10 empty] | 05.09.20 | 05.09.20 |  | T2 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | PVVKSG@lntecc.com-02.07.2024-16:45:46
East Medinipur EM 01 | Process | Hoist | LE200021-P-WS-WT-PR-2266 | LE200021-P-WS-WT-PR-2266-B | Indef | Pre-order comments issued | 144 |  |  |  | 30.11.23 | 30.11.23 | 26.02.24 | 13.03.24 | [19 empty] | 30.07.24 | 16.08.24 | 15.10.24 | PVVKSG@lntecc.com-26.07.2024-10:08:40
East Medinipur EM 01 | Process | Chain pully block | LE200021-P-WS-WT-PR-2267 | LE200021-P-WS-WT-PR-2267-A | Reva | Enquiry yet to float | NA |  |  |  | 07.08.20 | 07.08.20 | [10 empty] | 28.08.20 | 05.09.20 |  | T2 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | PVVKSG@lntecc.com-02.07.2024-16:45:46
East Medinipur EM 01 | Process | Chain pully block | LE200021-P-WS-WT-PR-2267 | LE200021-P-WS-WT-PR-2267-B | Indef | Pre-order comments issued | 144 |  |  |  |  | 30.11.23 | 26.02.24 | 13.03.24 | [22 empty] | PVVKSG@lntecc.com-26.07.2024-10:08:40
East Medinipur EM 01 | Process | Trolley | LE200021-P-WS-WT-PR-2268 | LE200021-P-WS-WT-PR-2268-A | NA | Regret offer | PR Closed | Site Procurement. |  |  | 31.07.20 | 31.07.20 | [24 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Filter media | LE200021-P-WS-WT-PR-2269 | LE200021-P-WS-WT-PR-2269-A | NA | Regret offer | PR Closed | Site Procurement. Vendor Under approval with SCM |  |  | 18.08.20 | 18.08.20 | [24 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Sluice gates | LE200021-P-WS-WT-PR-2270 | LE200021-P-WS-WT-PR-2270-A | Oriental | Sent to BU Operations | PR Closed |  |  |  | 12.01.24 | 12.01.24 | 12.01.24 | 16.02.24 | 19.02.24 | 21.02.24 | 23.02.24 | 26.02.24 | 27.02.24 |  |  |  | 04.03.24 | 27.02.24 | 02.03.24 | T1 | [10 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Sluice gates | LE200021-P-WS-WT-PR-2270 | LE200021-P-WS-WT-PR-2270-B | IVC | Post-order technically cleared | 53 |  |  |  | 12.01.24 | 12.01.24 | 13.02.24 | 17.02.24 | 19.02.24 | 21.02.24 | 23.02.24 | 26.02.24 | 02.03.24 |  |  |  | 04.03.24 | 02.03.24 | 02.03.24 | T2 | 11.03.24 | IVC | 14.03.24 | 28.03.24 | 12.06.24 | 12.06.24 |  |  |  | 10.05.24 | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | Dosing pumps | LE200021-P-WS-WT-PR-2271 | LE200021-P-WS-WT-PR-2271-A | Swelore | Regret offer | PR Closed |  |  |  | 08.01.24 | 30.11.23 | 30.11.23 | 02.12.23 | 08.01.24 | 09.01.24 | [20 empty] | PVVKSG@lntecc.com-02.07.2024-16:57:52
East Medinipur EM 01 | Process | Dosing pumps | LE200021-P-WS-WT-PR-2271 | LE200021-P-WS-WT-PR-2271-B | Verito | Sent to BU Operations | 68 |  |  |  | 08.01.24 | 30.11.23 | 30.11.23 | 02.12.23 | 08.01.24 | 18.01.24 | 19.02.24 | 06.03.24 | 28.03.24 | 11.04.24 | 03.05.24 | 09.05.24 | 28.05.24 | 21.05.24 | 28.05.24 | T2 | [10 empty] | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | Dosing pumps | LE200021-P-WS-WT-PR-2271 | LE200021-P-WS-WT-PR-2271-C | Positive metering | Sent to BU Operations | 54 |  |  |  | 08.01.24 | 30.11.23 | 30.11.23 | 07.02.24 | 10.01.24 | 18.01.24 | 19.02.24 | 04.03.24 | 28.03.24 | 11.04.24 |  |  | 11.06.24 | 31.05.24 | 11.06.24 | T1 | [10 empty] | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | Backwash pump | LE200021-P-WS-WT-PR-2272 | LE200021-P-WS-WT-PR-2272-A | Vendor Name yet to provide | Enquiry yet to float | NA | KBL, WPIL, WILO regretted |  |  | 31.07.20 | 31.07.20 | [21 empty] | 12.08.24 | 29.08.24 | 28.10.24 | PVVKSG@lntecc.com-02.07.2024-16:57:52
East Medinipur EM 01 | Process | Submersible pumps | LE200021-P-WS-WT-PR-2273 | LE200021-P-WS-WT-PR-2273-A | Aqua | Sent to BU Operations | 155 |  |  |  | 18.01.24 | 29.12.23 | 29.12.23 | 02.01.24 | 09.01.24 | 12.01.24 | 18.01.24 | 24.01.24 | 21.02.24 |  |  |  | 02.03.24 | 02.03.24 | 02.03.24 | T1 | [10 empty] | PVVKSG@lntecc.com-26.07.2024-16:24:05
East Medinipur EM 01 | Process | Sampling pumps | LE200021-P-WS-WT-PR-2274 | LE200021-P-WS-WT-PR-2274-A | NA | Regret offer | PR Closed | Site Procurement. Aqua, KBL, MBH |  |  | 27.07.20 | 27.07.20 | [24 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Submersible mixer | LE200021-P-WS-WT-PR-2275 | LE200021-P-WS-WT-PR-2275-A | FFP | Pre-order comments issued | 20 |  | Namrata S, FFP Eco Technologies Pvt. Ltd., Tel: +91 22 4967 3980 ¦ + 91 81049 82550 | fibrein@gmail.com | 22.07.20 | 28.06.24 | 02.07.24 | 15.07.24 | [19 empty] | 28.08.24 | 14.09.24 | 13.11.24 | PVVKSG@lntecc.com-26.07.2024-10:08:40
East Medinipur EM 01 | Process | Submersible mixer | LE200021-P-WS-WT-PR-2275 | LE200021-P-WS-WT-PR-2275-B | World Water Tech | Pre-order pending with EDRC | 11 |  |  |  |  | 02.07.24 | 10.07.24 | 16.07.24 | 24.07.24 | [21 empty] | PVVKSG@lntecc.com-26.07.2024-16:24:06
East Medinipur EM 01 | Process | Dewatering pumps | LE200021-P-WS-WT-PR-2276 | LE200021-P-WS-WT-PR-2276-A | Aqua | Sent to BU Operations | 155 |  |  |  | 18.01.24 | 29.12.23 | 29.12.23 | 02.01.24 | 09.01.24 | 12.01.24 | 18.01.24 | 24.01.24 | 21.02.24 |  |  |  | 02.03.24 | 02.03.24 | 02.03.24 | T1 | [10 empty] | PVVKSG@lntecc.com-26.07.2024-16:24:06
East Medinipur EM 01 | Process | Chemical Unloading cum Transfer Pump | LE200021-P-WS-WT-PR-2277 | LE200021-P-WS-WT-PR-2277-A | Vendor Name yet to provide | Enquiry yet to float | NA | Aqua, KBL, MBH |  |  | 27.07.20 | 27.07.20 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | PVVKSG@lntecc.com-02.07.2024-17:21:05
East Medinipur EM 01 | Process | Sludge Transfer pump | LE200021-P-WS-WT-PR-2278 | LE200021-P-WS-WT-PR-2278-A | KBL | Pre-order comments issued | 68 |  | Azharuddin Tamboli Senior Manager Mob: +918669664820 | Azharuddin.Tamboli@kbl.co.in | 27.07.20 | 07.12.23 | 08.05.24 | 17.05.24 | 21.05.24 | 28.05.24 | [17 empty] | 20.07.24 | 06.08.24 | 05.10.24 | PVVKSG@lntecc.com-26.07.2024-10:08:41
East Medinipur EM 01 | Process | Dissolving tray | LE200021-P-WS-WT-PR-2279 | LE200021-P-WS-WT-PR-2279-A | NA | Regret offer | PR Closed | Site Procurement |  |  | 13.08.20 | 13.08.20 | [24 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Poly Electrolyte Dosing Tanks and Agitators | LE200021-P-WS-WT-PR-2280 | LE200021-P-WS-WT-PR-2280-A | Vendor Name yet to provide | Enquiry yet to float | NA | Small items will be finalized after major orders. |  |  | 13.08.20 | 13.08.20 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | PVVKSG@lntecc.com-02.07.2024-17:21:05
East Medinipur EM 01 | Process | Nozzles | LE200021-P-WS-WT-PR-2281 | LE200021-P-WS-WT-PR-2281-A | Guddi Plastcon | Approved by Client | PR Closed | Nozzles received at site |  |  | 06.01.23 | 06.01.23 | 06.01.23 | 12.01.23 | [8 empty] | 02.02.23 | 02.02.23 | 02.02.23 | T1 | 07.02.23 | Guddi Plastcon | 09.02.23 | 23.02.23 | 13.03.23 | 21.03.23 | 24.03.23 |  |  | 08.04.23 | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Nozzles | LE200021-P-WS-WT-PR-2281 | LE200021-P-WS-WT-PR-2281-B | VP Engineers | Regret offer | PR Closed | MFC issued for Nozzles for Guddi Plastcon |  |  | 06.01.23 | 06.01.23 | 06.01.23 | 12.01.23 | [8 empty] | 22.01.23 | 30.01.23 | [12 empty] | PVVKSG@lntecc.com-21.05.2024-10:37:24
East Medinipur EM 01 | Process | Exhaust Fans | LE200021-P-WS-WT-PR-2282 | LE200021-P-WS-WT-PR-2282-A | NA | Regret offer | PR Closed | Site Procurement |  |  | 27.07.20 | 27.07.20 | [24 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Lab Equipment | LE200021-P-WS-WT-PR-2283 | LE200021-P-WS-WT-PR-2283-A | NA | Regret offer | PR Closed | Site Procurement |  |  | 31.07.20 | 31.07.20 | [24 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Platform weighing machine | LE200021-P-WS-WT-PR-2284 | LE200021-P-WS-WT-PR-2284-A | NA | Regret offer | PR Closed | Site Procurement |  |  | 22.07.20 | 22.07.20 | [24 empty] | PVVKSG@lntecc.com-31.05.2024-09:44:43
East Medinipur EM 01 | Process | Rate of Flow Controller | LE200021-P-WS-WT-PR-2285 | LE200021-P-WS-WT-PR-2285-A | NA | Enquiry yet to float | NA | Small items will be finalized after major orders. |  |  | 27.08.20 | 27.08.20 | [21 empty] | 13.09.24 | 30.09.24 | 29.11.24 | PVVKSG@lntecc.com-02.07.2024-17:21:05
East Medinipur EM 01 | Mechanical | Sluice gate | LE200021-M-001 | LE200021-M-001-A | IVC | Post-order comments issued | 139 |  |  |  | 4.01.24 | 04.01.24 | 10.01.24 | 22.01.24 | [8 empty] | 29.01.24 | 02.02.24 | 02.02.24 | T1 | 19.02.24 | IVC | 14.03.24 | 18.03.24 |  |  |  | 02.02.24 | 19.02.24 | 19.04.24 | gopal.samarth@lntecc.com-03.07.2024-17:12:42
East Medinipur EM 01 | Mechanical | Sluice gate | LE200021-M-001 | LE200021-M-001-B | Jash | Sent to BU Operations | PR Closed |  |  |  | 4.01.24 | 04.01.24 | 28.01.24 | 28.01.24 | [8 empty] | 01.02.24 | 02.02.24 | 02.02.24 | T1 | [7 empty] | 02.02.24 | 19.02.24 | 19.04.24 | gopal.samarth@lntecc.com-03.07.2024-17:12:42
East Medinipur EM 01 | Mechanical | Sluice gate | LE200021-M-001 | LE200021-M-001-C | Oriental | Sent to BU Operations | PR Closed |  |  |  | 4.01.24 | 04.01.24 | 28.01.24 | 29.01.24 | [8 empty] | 31.01.24 | 02.02.24 | 02.02.24 | T1 | [7 empty] | 02.02.24 | 19.02.24 | 19.04.24 | gopal.samarth@lntecc.com-03.07.2024-17:12:42
East Medinipur EM 01 | Mechanical | Pump house valves | LE200021-M-002 | LE200021-M-002-A | AVK | Approved by Client | PR Closed | Lot 2 |  |  | 5.01.24 | 05.01.24 | 24.01.24 | 30.01.24 | [8 empty] | 31.01.24 | 01.02.24 | 03.02.24 | T1 | 03.02.24 | AVK | 03.02.24 | 04.03.24 | 04.03.24 | 05.03.24 | 26.02.24 | 03.02.24 | 20.02.24 | 03.04.24 | gopal.samarth@lntecc.com-03.07.2024-14:16:24
East Medinipur EM 01 | Mechanical | Pump house valves | LE200021-M-002 | LE200021-M-002-B | Durga | Sent to BU Operations | PR Closed |  |  |  | 5.01.24 | 05.01.24 | 07.01.24 | 07.01.24 | [8 empty] | 03.02.24 | 03.02.24 | 01.03.24 | T1 | [7 empty] | 01.03.24 | 18.03.24 | 17.05.24 | gopal.samarth@lntecc.com-03.07.2024-17:12:42
East Medinipur EM 01 | Mechanical | Pump house valves | LE200021-M-002 | LE200021-M-002-C | KBL | Sent to BU Operations | PR Closed |  |  |  | 5.01.24 | 05.01.24 | 10.01.24 | 25.01.24 | [8 empty] | 03.02.24 | 05.02.24 | 05.02.24 | T1 | [7 empty] | 05.02.24 | 22.02.24 | 22.04.24 | gopal.samarth@lntecc.com-03.07.2024-17:12:42
East Medinipur EM 01 | Mechanical | EOT-crane | LE200021-M-003 | LE200021-M-003 | indef | Pre-order technically cleared | 87 | PR released on 12/4/24 |  |  | 4.01.24 | 22.04.24 | 30.04.24 | 03.05.24 | [8 empty] | 09.05.24 | 09.05.24 | 09.05.24 | T1 | [7 empty] | 09.05.24 | 26.05.24 | 25.07.24 | gopal.samarth@lntecc.com-03.07.2024-14:14:51
East Medinipur EM 01 | Mechanical | EOT-crane | LE200021-M-003 | LE200021-M-003-B | REVA | Pre-order technically cleared | 54 | PR released on 12/4/24 |  |  |  | 22.04.24 | 07.05.24 | 09.05.24 | [8 empty] | 11.06.24 | 11.06.24 | 11.06.24 | T1 | [7 empty] | 11.06.24 | 28.06.24 | 27.08.24 | gopal.samarth@lntecc.com-03.07.2024-14:14:51
East Medinipur EM 01 | Mechanical | VT-pumps | LE200021-M-004 | LE200021-M-004-A | WILO | Sent to BU Operations | PR Closed |  |  |  |  | 23.10.23 | 06.11.23 | 10.11.23 | 20.11.23 | 22.11.23 | 11.12.23 | 22.12.23 | 26.12.23 | 02.01.24 | 08.01.24 | 11.01.24 | 11.01.24 | 11.01.24 | 11.01.24 | T1 | [7 empty] | 11.01.24 | 28.01.24 | 28.03.24 | gopal.samarth@lntecc.com-03.07.2024-14:14:51
East Medinipur EM 01 | Mechanical | VT-pumps | LE200021-M-004 | LE200021-M-004-B | WPIL | Approved by Client | PR Closed |  |  |  |  | 23.10.23 | 06.11.23 | 10.11.23 | 20.11.23 | 22.11.23 | 11.12.23 | 22.12.23 | 26.12.23 | 02.02.24 | 08.01.24 |  | 08.01.24 | 11.01.24 | 11.01.24 | T1 | 12.02.24 | WPIL | 28.03.24 | 30.03.24 | 30.03.24 | 30.03.24 | 10.06.24 | 11.01.24 | 28.01.24 | 28.03.24 | gopal.samarth@lntecc.com-03.07.2024-14:02:30
East Medinipur EM 01 | Mechanical | VT-pumps | LE200021-M-004 | LE200021-M-004-C | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 23.10.23 | 06.11.23 | 10.11.23 | 20.11.23 | 22.11.23 | 11.12.23 | 22.12.23 | 26.12.23 | 05.01.24 |  |  | 05.01.24 | 05.01.24 | 05.01.24 | T1 | [7 empty] | 05.01.24 | 22.01.24 | 22.03.24 | gopal.samarth@lntecc.com-03.07.2024-14:14:51
East Medinipur EM 01 | Instrumentation | Pressure Gauge | LE200021-I-001 | LE200021-I-001-A | Hguru | Sent to BU Operations | 189 |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 22.01.24 | 25.01.24 | 28.01.24 | T1 | [7 empty] | 26.09.24 | 13.10.24 | 12.12.24 | SURENDHAR@lntecc.com-09.07.2024-16:13:15
East Medinipur EM 01 | Instrumentation | Pressure Gauge | LE200021-I-001 | LE200021-I-001-B | Forbes marshall | Sent to BU Operations | 189 |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 14.01.24 | 24.01.24 | 28.01.24 | T2 | [7 empty] | 27.09.24 | 14.10.24 | 13.12.24 | SURENDHAR@lntecc.com-09.07.2024-16:13:15
East Medinipur EM 01 | Instrumentation | Pressure Switch | LE200021-I-002 | LE200021-I-002-A | Hguru | Sent to BU Operations | 189 |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 17.01.24 | 24.01.24 | 28.01.24 | T1 | [7 empty] | 29.09.24 | 16.10.24 | 15.12.24 | SURENDHAR@lntecc.com-09.07.2024-16:13:15
East Medinipur EM 01 | Instrumentation | Pressure Switch | LE200021-I-002 | LE200021-I-002-B | Forbes marshall | Sent to BU Operations | 189 |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 06.01.24 | 13.01.24 | 28.01.24 | T2 | [7 empty] | 27.09.24 | 14.10.24 | 13.12.24 | SURENDHAR@lntecc.com-09.07.2024-16:13:15
East Medinipur EM 01 | Instrumentation | Pressure indicating transmitter | LE200021-I-003 | LE200021-I-003-A | ABB | Pre-order technically cleared | 189 |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 10.01.24 | 12.01.24 | 28.01.24 | T1 | [7 empty] | 30.09.24 | 17.10.24 | 16.12.24 | SURENDHAR@lntecc.com-09.07.2024-15:17:20
East Medinipur EM 01 | Instrumentation | Pressure indicating transmitter | LE200021-I-003 | LE200021-I-003-B | E&H | Pre-order technically cleared | 189 |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 29.12.23 | 14.01.24 | 28.01.24 | T2 | [7 empty] | 29.09.24 | 16.10.24 | 15.12.24 | SURENDHAR@lntecc.com-09.07.2024-15:17:20
East Medinipur EM 01 | Instrumentation | float & board level indicator | LE200021-I-004 | LE200021-I-004-A | SBEM | Awaiting pre-offer from vendor | 30 |  |  |  | 29.09.22 | 05.07.24 | [21 empty] | 29.09.24 | 16.10.24 | 15.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | float & board level indicator | LE200021-I-004 | LE200021-I-004-B | Pune Techtrol | Awaiting pre-offer from vendor | 30 |  |  |  |  | 05.07.24 | [21 empty] | 29.09.24 | 16.10.24 | 15.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Ultrasonic Flow Meter | LE200021-I-005 | LE200021-I-005-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 29.12.23 | 05.01.24 | 28.01.24 | T3 | [7 empty] | 15.10.24 | 01.11.24 | 31.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Ultrasonic Flow Meter | LE200021-I-005 | LE200021-I-005-B | E&H | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 29.12.23 | 05.01.24 | 28.01.24 | T2 | [7 empty] | 09.09.24 | 26.09.24 | 25.11.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Ultrasonic Flow Meter | LE200021-I-005 | LE200021-I-005-C | siemens | Approved by Client | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 29.12.23 | 05.01.24 | 28.01.24 | T1 | 21.06.24 | siemens | 21.06.24 | 21.06.24 | 21.06.24 | 21.06.24 | 05.07.24 | 09.09.24 | 26.09.24 | 20.08.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | level switch - Conductivity type | LE200021-I-006 | LE200021-I-006-A | SBEM | Awaiting pre-offer from vendor | 30 |  |  |  | 29.09.22 | 05.07.24 | [21 empty] | 23.09.24 | 10.10.24 | 09.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | level switch - Conductivity type | LE200021-I-006 | LE200021-I-006-B | Pune Techtrol | Awaiting pre-offer from vendor | 30 |  |  |  |  | 05.07.24 | [21 empty] | 23.09.24 | 10.10.24 | 09.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | radar/Ultrasonic level transmitter | LE200021-I-007 | LE200021-I-007-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 19.01.24 | 22.01.24 | 28.01.24 | T3 | [7 empty] | 02.10.24 | 19.10.24 | 18.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | radar/Ultrasonic level transmitter | LE200021-I-007 | LE200021-I-007-B | E&H | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 17.01.24 | 25.01.24 | 28.01.24 | T2 | [7 empty] | 29.09.24 | 16.10.24 | 15.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | radar/Ultrasonic level transmitter | LE200021-I-007 | LE200021-I-007-C | siemens | Approved by Client | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 12.01.24 | 12.01.24 | 28.01.24 | T1 | 21.06.24 | siemens | 21.06.24 | 21.06.24 | 21.06.24 | 21.06.24 | 05.07.24 | 01.10.24 | 18.10.24 | 20.08.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | AC Powered Electromagnectic flow meter | LE200021-I-008 | LE200021-I-008-A | Adept | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 11.01.24 | 01.02.24 | 10.02.24 | T2 | [7 empty] | 02.10.24 | 19.10.24 | 18.12.24 | vignesh.c1@lntecc.com-09.07.2024-15:38:22
East Medinipur EM 01 | Instrumentation | AC Powered Electromagnectic flow meter | LE200021-I-008 | LE200021-I-008-B | SBEM | Approved by Client | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 11.01.24 | 19.01.24 | 10.02.24 | T1 | 13.02.24 | SBEM | 15.02.24 | 15.02.24 | 20.02.24 | 20.02.24 | 20.02.24 | 29.09.24 | 16.10.24 | 13.04.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | AC Powered Electromagnectic flow meter | LE200021-I-008 | LE200021-I-008-C | krohne marshall | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 11.01.24 | 29.01.24 | 10.02.24 | T3 | [7 empty] | 01.10.24 | 18.10.24 | 17.12.24 | vignesh.c1@lntecc.com-09.07.2024-15:38:22
East Medinipur EM 01 | Instrumentation | Bypass Type Rotameter (Transmitter) | LE200021-I-009 | LE200021-I-009-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 29.09.22 | [22 empty] | 03.10.24 | 20.10.24 | 19.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Loss of Head transmitter | LE200021-I-010 | LE200021-I-010-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 19.01.24 | 26.01.24 | 28.01.24 | T3 | [7 empty] | 26.09.24 | 13.10.24 | 12.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Loss of Head transmitter | LE200021-I-010 | LE200021-I-010-B | E&H | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 24.01.24 | 26.01.24 | 28.01.24 | T2 | [7 empty] | 02.10.24 | 19.10.24 | 18.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Loss of Head transmitter | LE200021-I-010 | LE200021-I-010-C | siemens | Approved by Client | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 27.01.24 | 27.01.24 | 28.01.24 | T1 | 21.06.24 | siemens | 21.06.24 | 21.06.24 | 21.06.24 | 05.07.24 | 05.07.24 | 02.10.24 | 19.10.24 | 20.08.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Rate of flow transmitter | LE200021-I-011 | LE200021-I-011-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 01.01.24 | 14.01.24 | 28.01.24 | T3 | [7 empty] | 23.09.24 | 10.10.24 | 09.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Rate of flow transmitter | LE200021-I-011 | LE200021-I-011-B | E&H | Sent to BU Operations | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 30.12.23 | 11.01.24 | 28.01.24 | T2 | [7 empty] | 08.10.24 | 25.10.24 | 24.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Rate of flow transmitter | LE200021-I-011 | LE200021-I-011-C | siemens | Approved by Client | PR Closed |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 29.12.23 | 04.01.24 | 28.01.24 | T1 | 21.06.24 | siemens | 21.06.24 | 21.06.24 | 21.06.24 | 21.06.24 | 05.07.24 | 23.09.24 | 10.10.24 | 20.08.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | pH meter | LE200021-I-012 | LE200021-I-012-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 29.09.22 | [22 empty] | 02.10.24 | 19.10.24 | 18.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Turbidity meter | LE200021-I-013 | LE200021-I-013-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 29.09.22 | [22 empty] | 10.10.24 | 27.10.24 | 26.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Residual Chlorine analyzer | LE200021-I-014 | LE200021-I-014-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 29.09.22 | [22 empty] | 02.10.24 | 19.10.24 | 18.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | instrumentation Control & signal Cables | LE200021-I-015 | LE200021-I-015-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 29.09.22 | [22 empty] | 24.09.24 | 11.10.24 | 10.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Purchase requisition for ICP, PLC panel & SCADA Accessories | LE200021-I-WS-PR-PC-5521 | LE200021-I-WS-PR-PC-5521-A | Siemens | Awaiting pre-offer from vendor | 27 |  | Prem kumar jagadeesan |  |  | 08.07.24 | [21 empty] | 02.10.24 | 19.10.24 | 18.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Purchase requisition for ICP, PLC panel & SCADA Accessories | LE200021-I-WS-PR-PC-5521 | LE200021-I-WS-PR-PC-5521-B | Pheonix contact | Awaiting pre-offer from vendor | 27 |  | K Vigneshwaran |  |  | 08.07.24 | [21 empty] | 02.10.24 | 19.10.24 | 18.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Purchase requisition for ICP, PLC panel & SCADA Accessories | LE200021-I-WS-PR-PC-5521 | LE200021-I-WS-PR-PC-5521-C | Schinder Electric | Awaiting pre-offer from vendor | 27 |  | Rushyendher |  |  | 08.07.24 | [21 empty] | 02.10.24 | 19.10.24 | 18.12.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Instrumentation | Pressure Gauge | LE200021-P-001 | LE200021-P-001-C | AN Instruments | Pre-order technically cleared | 189 |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 11.01.24 | 20.01.24 | 28.01.24 | T3 | [7 empty] | 01.10.24 | 18.10.24 | 17.12.24 | SURENDHAR@lntecc.com-09.07.2024-15:17:20
East Medinipur EM 01 | Instrumentation | Pressure Switch | LE200021-P-002 | LE200021-P-002-C | AN Instruments | Pre-order technically cleared | 189 |  |  |  | 29.09.22 | 29.09.22 | 21.12.23 | 29.12.23 | [8 empty] | 04.01.24 | 23.01.24 | 28.01.24 | T3 | [7 empty] | 09.10.24 | 26.10.24 | 25.12.24 | SURENDHAR@lntecc.com-09.07.2024-15:17:20
East Medinipur EM 01 | Instrumentation | Pressure indicating transmitter | LE200021-P-003 | LE200021-P-003-C | siemens | Pre-order technically cleared | 30 |  |  |  | 29.09.22 | 29.09.22 | 14.12.23 | 29.12.23 | [8 empty] | 29.12.23 | 05.01.24 | 28.01.24 | T1 | 21.06.24 | siemens | 21.06.24 | 21.06.24 | 21.06.24 | 21.06.24 | 05.07.24 | 23.09.24 | 10.10.24 | 20.08.24 | SURENDHAR@lntecc.com-09.07.2024-17:02:04
East Medinipur EM 01 | Electrical | Cable glands and lugs | LE-200021-E-WS-WT-PR-4111 | LE-200021-E-WS-WT-PR-4111-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | Cable trays | LE-200021-E-WS-WT-PR-4112 | LE-200021-E-WS-WT-PR-4112-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | LT Panel | LE200021-E-001 | LE200021-E-001-A | EAP | Post-order technically cleared | 125 |  |  |  | 29.6.20 | 29.06.20 | 06.12.23 | 06.12.23 | [8 empty] | 06.12.23 | 05.01.24 | 05.01.24 | T1 | 05.02.24 | EAP | 22.02.24 | 12.03.24 | 03.04.24 | 01.04.24 |  |  |  | 05.04.24 | rawabi.c@lntecc.com-10.06.2024-17:21:21
East Medinipur EM 01 | Electrical | LT Panel | LE200021-E-001 | LE200021-E-001-B | PCE | Sent to BU Operations | PR Closed |  |  |  | 29.6.20 | 29.06.20 | 08.12.23 | 09.12.23 | [8 empty] | 08.12.23 | 09.12.23 | 9.12.23 | T2 | [10 empty] | rawabi.c@lntecc.com-10.06.2024-17:21:21
East Medinipur EM 01 | Electrical | DG | LE200021-E-002 | LE200021-E-002-A | IEC | Sent to BU Operations | PR Closed |  |  |  | 11.8.20 | 11.08.20 | 07.12.23 | 20.01.24 | [8 empty] | 24.01.24 | 24.01.24 | 24.01.24 | T2 | [10 empty] | karthik.ajithkumar@lntecc.com-07.06.2024-18:20:52
East Medinipur EM 01 | Electrical | DG | LE200021-E-002 | LE200021-E-002-B | Jakson | Post-order technically cleared | 73 |  |  |  | 11.8.20 | 11.08.20 | 12.12.23 | 14.12.23 | [8 empty] | 29.12.23 | 17.01.24 | 04.02.24 | T1 | 6.2.24 | Jakson | 10.4.24 | 2.5.24 | 5.3.24 | 23.5.24 |  |  |  | 06.04.24 | rawabi.c@lntecc.com-10.06.2024-17:23:23
East Medinipur EM 01 | Electrical | HT Panel | LE200021-E-003 | LE200021-E-003-A | EAP | Post-order technically cleared | 121 |  |  |  | 26.6.20 | 26.06.20 | 08.12.23 | 20.01.24 | [8 empty] | 15.01.24 | 17.01.24 | 20.01.24 | T1 | 06.02.24 | EAP | 20.02.24 | 13.03.24 | 3.4.24 | 5.4.24 |  |  |  | 06.04.24 | rawabi.c@lntecc.com-10.06.2024-17:21:47
East Medinipur EM 01 | Electrical | HT Panel | LE200021-E-003 | LE200021-E-003-B | CGL | Sent to BU Operations | PR Closed |  |  |  | 26.6.20 | 26.06.20 | 14.12.23 | 20.01.24 | [8 empty] | 22.01.24 | 23.01.24 | 07.02.24 | T2 | [6 empty] | 22.02.24 |  |  |  | karthik.ajithkumar@lntecc.com-14.05.2024-10:05:54
East Medinipur EM 01 | Electrical | LT Panel | LE200021-E-001 | LE200021-E-003-C | BCH | Sent to BU Operations | PR Closed |  |  |  | 29.6.20 | 29.06.20 | 11.12.23 | 05.01.24 | [8 empty] | 11.12.23 | 05.01.24 | 5.1.24 | T2 | [10 empty] | rawabi.c@lntecc.com-10.06.2024-17:21:21
East Medinipur EM 01 | Electrical | Transformer | LE200021-E-WS-WT-PR-4102 | LE200021-E-WS-WT-PR-4102-A | Kirloskar | Sent to BU Operations | PR Closed |  |  |  | 7.5.20 | 07.05.20 | 08.01.24 | 23.01.24 | [8 empty] | 25.01.24 | 03.02.24 | 14.02.24 | T2 | [6 empty] | 04.03.24 |  |  |  | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | Transformer | LE200021-E-WS-WT-PR-4102 | LE200021-E-WS-WT-PR-4102-B | Voltamp | Sent to BU Operations | PR Closed |  |  |  | 7.5.20 | 07.05.20 | 11.01.24 | 23.01.24 | [8 empty] | 23.01.24 | 03.02.24 | 11.02.24 | T2 | [6 empty] | 04.03.24 |  |  |  | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | Transformer | LE200021-E-WS-WT-PR-4102 | LE200021-E-WS-WT-PR-4102-C | Sai Electrical | Post-order technically cleared | 56 | First Post order observation sent on 2.5.24 Reminder mail sent on 9.5.24 |  |  | 7.5.20 | 07.05.20 | 12.02.24 | 14.02.24 | [8 empty] | 14.02.24 | 15.02.24 | 20.02.24 | T1 | 30.4.24 | Sai Electrical | 30.4.24 | 2.5.24 | 09.06.24 | 09.06.24 | 16.03.24 |  |  | 29.06.24 | rawabi.c@lntecc.com-10.06.2024-17:23:23
East Medinipur EM 01 | Electrical | HT Panel | LE200021-E-WS-WT-PR-4103 | LE200021-E-WS-WT-PR-4103-C | ABB | Sent to BU Operations | 170 |  |  |  | 26.6.20 | 26.06.20 | 11.01.24 | 11.01.24 | [8 empty] | 13.01.24 | 17.01.24 | 27.01.24 | T2 | [6 empty] | 16.02.24 |  |  |  | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | LT & HT Cables | LE200021-E-WS-WT-PR-4105 | LE200021-E-WS-WT-PR-4105-A | KEI | Pre-order comments issued | 181 |  |  |  | 30.7.20 | 30.07.20 | 11.01.24 | 05.02.24 | [22 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | Lighting fixture | LE200021-E-WS-WT-PR-4107 | LE200021-E-WS-WT-PR-4107-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | Earthing and Lightning | LE200021-E-WS-WT-PR-4108 | LE200021-E-WS-WT-PR-4108-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | Electrical safety items | LE200021-E-WS-WT-PR-4109 | LE200021-E-WS-WT-PR-4109-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | Switchboards | LE200021-E-WS-WT-PR-4113 | LE200021-E-WS-WT-PR-4113-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | Lighting poles and junction box | LE200021-E-WS-WT-PR-4114 | LE200021-E-WS-WT-PR-4114-A | Not decided yet | Enquiry yet to float | NA | [29 empty] | rawabi.c@lntecc.com-28.05.2024-14:18:52
East Medinipur EM 01 | Electrical | LDB | LE200021-E-WS-WT-PR-4115 | LE200021-E-WS-WT-PR-4115-A | SRCS | Pre-order pending with EDRC | 103 |  |  |  |  | 10.4.24 | 23.4.24 | [23 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | LDB | LE200021-E-WS-WT-PR-4115 | LE200021-E-WS-WT-PR-4115-B | EAP | Pre-order comments issued | 106 |  |  |  |  | 10.4.24 | 15.4.24 | 20.4.24 | [22 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | Bus Duct | LE200021-E-WS-WT-PR-4117 | LE200021-E-WS-WT-PR-4117-A | C&S | Sent to BU Operations | 169 |  |  |  | 11.8.20 | 11.08.20 | 10.01.24 | 16.01.24 | [8 empty] | 19.01.24 | 22.01.24 | 17.02.24 | T2 | [10 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | Bus Duct | LE200021-E-WS-WT-PR-4117 | LE200021-E-WS-WT-PR-4117-B | Star Drive | Pre-order comments issued | 153 |  |  |  | 11.8.20 | 11.08.20 | 28.02.24 | 04.03.24 | [22 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | Soft Starter | LE200021-E-WS-WT-PR-4118 | LE200021-E-WS-WT-PR-4118-A | Jayashree | Sent to BU Operations | PR Closed |  |  |  | 4.1.24 | 04.01.24 | 08.01.24 | 31.01.24 | [8 empty] | 02.02.24 | 03.02.24 | 14.02.24 | T2 | [6 empty] | 04.03.24 |  |  |  | karthik.ajithkumar@lntecc.com-07.06.2024-18:18:12
East Medinipur EM 01 | Electrical | Soft Starter | LE200021-E-WS-WT-PR-4118 | LE200021-E-WS-WT-PR-4118-B | Lecon | Post-order technically cleared | 61 |  |  |  | 4.1.24 | 04.01.24 | 06.01.24 | 15.02.24 | [8 empty] | 04.01.24 | 06.01.24 | 06.01.24 | T1 | 10.1.24 | Lecon | 21.5.24 | 28.5.24 | 3.6.24 | 4.6.24 |  |  |  | 10.03.24 | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | Fixed Capacitor | LE200021-E-WS-WT-PR-4119 | LE200021-E-WS-WT-PR-4119-A | Madhav | Post-order comments issued | 29 |  |  |  | 4.1.24 | 04.01.24 | 06.01.24 | 12.01.24 | [8 empty] | 13.01.24 | 17.01.24 | 30.01.24 | T1 | 10.06.24 | Madhav | 10.06.24 | 06.07.24 | [5 empty] | 09.08.24 | rawabi.c@lntecc.com-11.07.2024-10:04:31
East Medinipur EM 01 | Electrical | Fixed Capacitor | LE200021-E-WS-WT-PR-4119 | LE200021-E-WS-WT-PR-4119-B | CGL | Sent to BU Operations | PR Closed |  |  |  | 4.1.24 | 02.01.24 | 03.01.24 | 20.02.24 | [8 empty] | 13.01.24 | 13.01.24 | 30.01.24 | T2 | [10 empty] | rawabi.c@lntecc.com-10.06.2024-17:21:07
East Medinipur EM 01 | Electrical | Fixed Capacitor | LE200021-E-WS-WT-PR-4119 | LE200021-E-WS-WT-PR-4119-C | Conquerent | Sent to BU Operations | PR Closed |  |  |  | 4.1.24 | 04.01.24 | 06.02.24 | 07.02.24 | [8 empty] | 13.01.24 | 13.01.24 | 30.01.24 | T3 | [10 empty] | rawabi.c@lntecc.com-10.06.2024-17:21:07
East Medinipur EM 01 | Electrical | Battery & Battery Charger | LE200021-E-WS-WT-PR-4120 | LE200021-E-WS-WT-PR-4120-A | Amar | Pre-order comments issued | 152 |  |  |  | 2.2.24 | 02.02.24 | 06.02.24 | 05.03.24 | [22 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | Battery & Battery charger | LE200021-E-WS-WT-PR-4120 | LE200021-E-WS-WT-PR-4120-B | Liveline | Sent to BU Operations | 90 |  |  |  | 2.2.24 | 02.02.24 | 08.02.24 | 16.02.24 | 2.5.24 | 21.3.24 | [6 empty] | 2.5.24 | 6.5.24 | 6.5.24 | T1 | [10 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | LT & HT Cables | LE200021-E-WS-WT-PR4105 | LE200021-E-WS-WT-PR4105 | Purva | Pre-order comments issued | 181 |  |  |  | 30.7.20 | 30.07.20 | 03.01.24 | 05.02.24 | [22 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
East Medinipur EM 01 | Electrical | LT & HT Cable | LE2000220-E-WS-WT-PR-4105 | LE2000220-E-WS-WT-PR-4105-B | Havells | Pre-order comments issued | 181 | PR Number to be corrected |  |  | 30.7.20 | 30.07.20 | 24.01.24 | 05.02.24 | [22 empty] | rawabi.c@lntecc.com-10.06.2024-17:09:00
EM - 02 | Process | Chlorination system | LE190889-P-WS-WT-PR-2286 | LE190889-P-WS-WT-PR-2286-A | Zion Technologies | Regret offer | PR Closed | Awaiting for the site input |  |  | 22.02.24 | 22.02.24 | 23.02.24 | [23 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Process | Chlorination system | LE190889-P-WS-WT-PR-2286 | LE190889-P-WS-WT-PR-2286-B | ME Infra | Regret offer | PR Closed | Awaiting for the site input |  |  | 22.02.24 | 22.02.24 | 24.02.24 | [23 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Process | Chlorination system | LE190889-P-WS-WT-PR-2286 | LE190889-P-WS-WT-PR-2286-C | Supreme technology | Regret offer | PR Closed |  |  |  | 22.02.24 | 22.02.24 | [24 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Mechanical | Sluice gate | LE190889-M-WS-CW-PR-1 | LE190889-M-WS-CW-PR-1-A | ORIENTAL | Sent to BU Operations | 37 |  |  |  | 04.01.24 | 15.05.24 | 07.06.24 | 07.06.24 | 13.06.24 | 15.06.24 | [6 empty] | 15.06.24 | 15.06.24 | 28.06.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Sluice gate | LE190889-M-WS-CW-PR-1 | LE190889-M-WS-CW-PR-1-B | JASH | Sent to BU Operations | 37 |  |  | lpgsouth2@jashindia.com |  | 15.05.24 | 27.03.24 | 07.06.24 | 17.06.24 | 17.06.24 | 20.06.24 | 20.06.24 |  |  |  |  | 20.06.24 | 20.06.24 | 28.06.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Sluice gate | LE190889-M-WS-CW-PR-1 | LE190889-M-WS-CW-PR-1-C | Cair | Sent to BU Operations | 37 |  |  |  |  | 17.05.24 | 21.06.24 | 25.06.24 | 10.06.24 | 10.06.24 | [6 empty] | 10.06.24 | 10.06.24 | 28.06.24 | T1 | [7 empty] | 31.08.24 |  |  | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Air valve | LE190889-M-WS-CW-PR-2 | LE190889-M-WS-CW-PR-2-A | Durga | Pre-order technically cleared | 37 |  |  |  |  | 17.05.24 | 12.06.24 | 12.06.24 | 13.06.24 | 18.06.24 | [6 empty] | 28.06.24 | 28.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Air valve | LE190889-M-WS-CW-PR-2 | LE190889-M-WS-CW-PR-2-B | Sigma Flow | Pre-order technically cleared | 20 |  |  |  |  | 17.05.24 | 28.06.24 | 02.07.24 | 08.07.24 | 08.07.24 | 15.07.24 | 15.07.24 |  |  |  |  | 15.07.24 | 15.07.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Air valve | LE190889-M-WS-CW-PR-2 | LE190889-M-WS-CW-PR-2-C | Cair | Pre-order comments issued | 26 |  |  |  |  | 17.05.24 | 21.06.24 | 25.06.24 | 08.07.24 | 09.07.24 | [17 empty] | 31.08.24 |  |  | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Butterfly valve | LE190889-M-WS-CW-PR-3 | LE190889-M-WS-CW-PR-3-A | Durga | Pre-order technically cleared | 37 |  |  |  |  | 17.05.24 | 12.06.24 | 12.06.24 | 13.06.24 | 18.06.24 | [6 empty] | 28.06.24 | 28.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Butterfly valve | LE190889-M-WS-CW-PR-3 | LE190889-M-WS-CW-PR-3-B | Sigma Flow | Pre-order technically cleared | 20 |  |  |  |  | 17.05.24 | 28.06.24 | 02.07.24 | 15.07.24 | 15.07.24 | [6 empty] | 15.07.24 | 15.07.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Butterfly valve | LE190889-M-WS-CW-PR-3 | LE190889-M-WS-CW-PR-3-C | Cair | Pre-order comments issued | 26 |  |  |  |  | 17.05.24 | 21.06.24 | 25.06.24 | 08.07.24 | 09.07.24 | [17 empty] | 31.08.24 |  |  | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Dismantling joint | LE190889-M-WS-CW-PR-4 | LE190889-M-WS-CW-PR-4-A | Durga | Pre-order technically cleared | 37 |  |  |  |  | 17.05.24 | 12.06.24 | 12.06.24 | 13.06.24 | 18.06.24 | [6 empty] | 28.06.24 | 28.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | NRV | LE190889-M-WS-CW-PR-5 | LE190889-M-WS-CW-PR-5-A | Durga | Pre-order technically cleared | 37 |  |  |  |  | 17.05.24 | 12.06.24 | 12.06.24 | 13.06.24 | 18.06.24 | [6 empty] | 28.06.24 | 28.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | NRV | LE190889-M-WS-CW-PR-5 | LE190889-M-WS-CW-PR-5-B | Sigma Flow | Pre-order technically cleared | 20 |  |  |  |  | 17.05.24 | 28.06.24 | 02.07.24 | 15.07.24 | 15.07.24 | [6 empty] | 15.07.24 | 15.07.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Sluice valve | LE190889-M-WS-CW-PR-6 | LE190889-M-WS-CW-PR-6-A | Durga | Pre-order technically cleared | 37 |  |  |  |  | 17.05.24 | 12.06.24 | 12.06.24 | 13.06.24 | 18.06.24 | [6 empty] | 28.06.24 | 28.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | Sluice valve | LE190889-M-WS-CW-PR-6 | LE190889-M-WS-CW-PR-6-B | Sigma Flow | Pre-order technically cleared | 20 |  |  |  |  | 17.05.24 | 28.06.24 | 02.07.24 | 15.07.24 | 15.07.24 | [6 empty] | 15.07.24 | 15.07.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:12:59
EM - 02 | Mechanical | EOT Crane | LE190889-M-WS-CW-PR-7 | LE190889-M-WS-CW-PR-7-A | REVA | Sent to BU Operations | 16 |  |  | mkt@revacranes.com |  | 18.05.24 | 21.05.24 | 21.05.24 | 29.05.24 | 07.06.24 | 27.06.24 | 07.07.24 |  |  |  |  | 07.06.24 | 07.06.24 | 19.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:15:37
EM - 02 | Mechanical | EOT Crane | LE190889-M-WS-CW-PR-7 | LE190889-M-WS-CW-PR-7-B | INDEF | Sent to BU Operations | 16 |  |  | mrs@indef.com |  | 18.05.24 | 27.05.24 | 28.05.24 | 04.06.24 | 06.06.24 | 27.06.24 | 27.06.24 | 04.07.24 | 09.07.24 |  |  | 06.06.24 | 18.06.24 | 19.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:15:37
EM - 02 | Mechanical | HSC Pump | LE190889-M-WS-CW-PR-8 | LE190889-M-WS-CW-PR-8-A | KBL | Regret offer | PR Closed |  |  | Azharuddin.Tamboli@kbl.co.in |  | 15.05.24 | 15.05.24 | 17.05.24 | 20.05.24 | 21.05.24 | [6 empty] | 21.05.24 | 20.05.24 | 19.07.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:15:37
EM - 02 | Mechanical | HSC Pump | LE190889-M-WS-CW-PR-8 | LE190889-M-WS-CW-PR-8-B | WPIL | Sent to BU Operations | 16 |  |  | cmktg@wpil.co.in |  | 15.05.24 | 24.05.24 | 27.05.24 | 29.05.24 | 07.06.24 | 25.06.24 | 04.07.24 | 05.07.24 | 19.07.24 |  |  | 07.06.24 | 07.06.24 | 19.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:15:37
EM - 02 | Mechanical | HSC Pump | LE190889-M-WS-CW-PR-8 | LE190889-M-WS-CW-PR-8-C | WILO | Sent to BU Operations | 16 |  |  | manikkandan.pr@wilo.com |  | 15.05.24 | 18.06.24 | 26.06.24 | 10.07.24 | 19.07.24 | [6 empty] | 19.07.24 | 19.07.24 | 19.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-20.07.2024-11:15:37
EM - 02 | Instrumentation | Battery Operated Flow meter | LE190889-I-WS-PR-BF-5517 | LE190889-I-WS-PR-BF-5517-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Instrumentation Cables | LE190889-I-WS-PR-CA-5512 | LE190889-I-WS-PR-CA-5512-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | IP Based PA System | LE190889-I-WS-PR-CA-5515 | LE190889-I-WS-PR-CA-5515-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Electro Magnetic Flow meter | LE190889-I-WS-PR-EF-5506 | LE190889-I-WS-PR-EF-5506-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Float & Dial Type Level indicator | LE190889-I-WS-PR-LI-5505 | LE190889-I-WS-PR-LI-5505-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Ultrasonic Type Level Transmitter | LE190889-I-WS-PR-LT-5504 | LE190889-I-WS-PR-LT-5504-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Multijet water meter | LE190889-I-WS-PR-MU-5516 | LE190889-I-WS-PR-MU-5516-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Compound Pressure Gauge/Pressure Gauge | LE190889-I-WS-PR-PG-5501 | LE190889-I-WS-PR-PG-5501-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Ph Analyzer | LE190889-I-WS-PR-PH-5507 | LE190889-I-WS-PR-PH-5507-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | PLC\SCADA | LE190889-I-WS-PR-PL-5510 | LE190889-I-WS-PR-PL-5510-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | CCTV SYSTEM | LE190889-I-WS-PR-PL-5513 | LE190889-I-WS-PR-PL-5513-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Pressure Switch | LE190889-I-WS-PR-PS-5502 | LE190889-I-WS-PR-PS-5502-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Pressure Transmitter | LE190889-I-WS-PR-PT-5503 | LE190889-I-WS-PR-PT-5503-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | Residual Chlroine Analyzer | LE190889-I-WS-PR-RC-5508 | LE190889-I-WS-PR-RC-5508-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | UPS | LE190889-I-WS-PR-UP-5511 | LE190889-I-WS-PR-UP-5511-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Instrumentation | EPABX SYSTEM | LE190889-I-WS-PR-UP-5514 | LE190889-I-WS-PR-UP-5514-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | Transformer | LE190889-E-WS-CW-PR-4102 | LE190889-E-WS-CW-PR-4102-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | HT Panel | LE190889-E-WS-CW-PR-4103 | LE190889-E-WS-CW-PR-4103-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | LT panels | LE190889-E-WS-CW-PR-4104 | LE190889-E-WS-CW-PR-4104-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | HT Termination Kit | LE190889-E-WS-CW-PR-4105 | LE190889-E-WS-CW-PR-4105-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | Power and Control Cable | LE190889-E-WS-CW-PR-4106 | LE190889-E-WS-CW-PR-4106-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | Lighting Fixtures | LE190889-E-WS-CW-PR-4107 | LE190889-E-WS-CW-PR-4107-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | Lighting Materials & accessories | LE190889-E-WS-CW-PR-4107A | LE190889-E-WS-CW-PR-4107A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | LDB | LE190889-E-WS-CW-PR-4107B | LE190889-E-WS-CW-PR-4107B-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | Earthing & Lightning Material | LE190889-E-WS-CW-PR-4108 | LE190889-E-WS-CW-PR-4108-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | Safety Accessories | LE190889-E-WS-CW-PR-4109 | LE190889-E-WS-CW-PR-4109-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | LPBS | LE190889-E-WS-CW-PR-4110 | LE190889-E-WS-CW-PR-4110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | Lugs & Glands | LE190889-E-WS-CW-PR-4111 | LE190889-E-WS-CW-PR-4111-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
EM - 02 | Electrical | Cable Tray | LE190889-E-WS-CW-PR-4112 | LE190889-E-WS-CW-PR-4112-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-09.07.2024-11:44:16
Fazilka 1 | Process | Scraper mechanism for Reactor clarifier | LE22M164-P-WS-WT-PR-2202 | LE22M164-P-WS-WT-PR-2202-A | Triveni | Post-order technically cleared | 73 |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 13.10.22 | 13.10.22 | 16.09.23 | 25.09.23 | 09.10.23 | 09.10.23 | 27.10.23 | 27.10.23 | 20.11.23 | 20.11.23 |  |  | 20.11.23 | 20.11.23 | 11.12.23 | T1 | 02.03.24 | Triveni | 15.05.24 | 15.05.24 | 23.05.24 | 23.05.24 |  | 11.12.23 | 28.12.23 | 26.02.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:16
Fazilka 1 | Process | Scraper mechanism for Reactor clarifier | LE22M164-P-WS-WT-PR-2202 | LE22M164-P-WS-WT-PR-2202-B | Filsep | Sent to BU Operations | PR Closed |  | Sivamurgan | filsepengineers@gmail.com | 13.10.22 | 13.10.22 | 06.11.23 | 13.11.23 | 22.11.23 | 28.11.23 | 27.10.23 | 27.10.23 | 07.12.23 | 11.12.23 |  |  | 11.12.23 | 11.12.23 | 11.12.23 | T2 | [7 empty] | 11.12.23 | 28.12.23 | 26.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Air Blower | LE22M164-P-WS-WT-PR-2203 | LE22M164-P-WS-WT-PR-2203-A | ACME | Regret offer | PR Closed |  |  | vishwesh.p@airequipments.com | 17.09.22 | 17.09.22 | 12.07.23 | 12.07.23 | 14.07.23 | 15.07.23 | [20 empty] | SNEHA-S@lntecc.com-16.05.2024-15:56:58
Fazilka 1 | Process | Purchase requisition for Air Blower | LE22M164-P-WS-WT-PR-2203 | LE22M164-P-WS-WT-PR-2203-B | KAY | Sent to BU Operations | PR Closed |  | Manish Arya | manish@kayblowers.com | 17.09.22 | 17.09.22 | 05.09.23 | 11.09.23 | 13.09.23 | 15.09.23 | 20.09.23 | 21.09.23 | 21.10.23 | 21.10.23 |  |  | 21.10.23 | 21.10.23 | 18.11.23 | T2 | [7 empty] | 18.11.23 | 05.12.23 | 03.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Air Blower | LE22M164-P-WS-WT-PR-2203 | LE22M164-P-WS-WT-PR-2203-C | EVEREST | Post-order technically cleared | 25 |  | Anurag Arora | armoghan.anwar@irco.com | 17.09.22 | 17.09.22 | 13.09.23 | 15.09.23 | 03.11.23 | 04.11.23 | 18.11.23 | 18.11.23 | 18.11.23 | 18.11.23 |  |  | 18.11.23 | 18.11.23 | 18.11.23 | T1 | 25.01.24 | EVEREST | 27.05.24 | 28.05.24 | 06.07.24 | 10.07.24 |  | 18.11.23 | 05.12.23 | 03.02.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:16
Fazilka 1 | Process | Purchase requisition for Agitator | LE22M164-P-WS-WT-PR-2204 | LE22M164-P-WS-WT-PR-2204-A | FFP | Approved by Client | PR Closed |  | Ganesh | fibrein@gmail.com | 31.10.22 | 31.10.22 | 04.10.23 | 04.10.23 | 24.10.23 | 24.10.23 | 25.10.23 | 25.10.23 | 27.10.23 | 27.10.23 |  |  | 30.10.23 | 30.10.23 | 30.10.23 | T1 | 25.01.24 | FFP | 27.03.24 | 01.04.24 | 11.04.24 | 12.04.24 | 30.05.24 | 30.10.23 | 16.11.23 | 15.01.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Agitator | LE22M164-P-WS-WT-PR-2204 | LE22M164-P-WS-WT-PR-2204-B | Triveni | Regret offer | PR Closed |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 31.10.22 | 31.10.22 | 18.12.23 | 18.12.23 | [22 empty] | SNEHA-S@lntecc.com-16.05.2024-15:56:58
Fazilka 1 | Process | Purchase requisition for WTP Sluice gates | LE22M164-P-WS-WT-PR-2205 | LE22M164-P-WS-WT-PR-2205-A | JASH | Sent to BU Operations | PR Closed |  | Prateek | lpgsouth2@jashindia.com | 01.12.22 | 01.12.22 | 07.09.23 | 15.09.23 | 07.10.23 | 07.10.23 | 16.10.23 | 16.10.23 | 01.11.23 | 01.11.23 |  |  | 01.11.23 | 01.11.23 | 01.11.23 | T2 | [7 empty] | 01.11.23 | 18.11.23 | 17.01.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for WTP Sluice gates | LE22M164-P-WS-WT-PR-2205 | LE22M164-P-WS-WT-PR-2205-B | ORIENTAL | Approved by Client | PR Closed |  | Sanjay Mahensaria | orientalcastings@gmail.com | 01.12.22 | 01.12.22 | 12.09.23 | 15.09.23 | 22.09.23 | 29.09.23 | 06.10.23 | 07.10.23 | 13.10.23 | 13.10.23 |  |  | 13.10.23 | 13.10.23 | 01.11.23 | T1 | 28.11.23 | ORIENTAL | 28.11.23 | 02.12.23 | 22.12.23 | 22.12.23 | 29.01.24 | 01.11.23 | 18.11.23 | 17.01.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Chlorination system | LE22M164-P-WS-WT-PR-2206 | LE22M164-P-WS-WT-PR-2206-A | METITO | Sent to BU Operations | PR Closed |  |  |  | 31.10.22 | 31.10.22 | 25.10.23 | 27.10.23 | 08.11.23 | 17.11.23 | 29.11.23 | 30.11.23 |  |  |  |  | 30.11.23 | 30.11.23 | 01.12.23 | T1 | [7 empty] | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Chlorination system | LE22M164-P-WS-WT-PR-2206 | LE22M164-P-WS-WT-PR-2206-B | CHLOROTECH | Sent to BU Operations | PR Closed |  |  |  | 31.10.22 | 31.10.22 | 15.09.23 | 03.10.23 | 13.10.23 | 18.10.23 | 25.10.23 | 27.10.23 |  |  |  |  | 27.10.23 | 27.10.23 | 01.12.23 | T3 | [7 empty] | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Chlorination system | LE22M164-P-WS-WT-PR-2206 | LE22M164-P-WS-WT-PR-2206-C | ZION | Post-order technically cleared | 125 |  | Deepak Santaram | deepak@ziontech.in | 31.10.22 | 31.10.22 | 08.11.23 | 17.11.23 | 29.11.23 | 30.11.23 | 01.12.23 | [5 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T2 | 11.01.24 | ZION | 13.02.24 | 17.02.24 | 16.03.24 | 01.04.24 |  | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:16
Fazilka 1 | Process | Purchase requisition for Sludge thickener | LE22M164-P-WS-WT-PR-2207 | LE22M164-P-WS-WT-PR-2207-A | TRIVENI | Approved by Client | PR Closed |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 31.10.22 | 31.10.22 | 16.09.23 | 21.09.23 | 27.09.23 | 28.09.23 | [6 empty] | 07.12.23 | 08.12.23 | 08.12.23 | T3 | 02.03.24 | TRIVENI | 02.03.24 | 06.03.24 | 06.04.24 | 03.05.24 | 30.05.24 | 08.12.23 | 25.12.23 | 23.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Sludge thickener | LE22M164-P-WS-WT-PR-2207 | LE22M164-P-WS-WT-PR-2207-B | VOLTAS | Sent to BU Operations | PR Closed |  |  | rohankakde@voltas.co | 31.10.22 | 31.10.22 | 30.10.23 | 31.10.23 | 16.11.23 | 18.11.23 | [6 empty] | 18.11.23 | 18.11.23 | 08.12.23 | T2 | [7 empty] | 08.12.23 | 25.12.23 | 23.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Sludge thickener | LE22M164-P-WS-WT-PR-2207 | LE22M164-P-WS-WT-PR-2207-C | SRITECH | Sent to BU Operations | PR Closed |  | Mohan P | mohan@sritechindia.com | 31.10.22 | 31.10.22 | 03.11.23 | 03.11.23 | 06.11.23 | 13.11.23 | 14.11.23 | 14.11.23 |  |  |  |  | 14.11.23 | 14.11.23 | 08.12.23 | T4 | [7 empty] | 08.12.23 | 25.12.23 | 23.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Sludge thickener | LE22M164-P-WS-WT-PR-2207 | LE22M164-P-WS-WT-PR-2207-D | FILSEP | Sent to BU Operations | PR Closed |  | Sivamurgan | filsepengineers@gmail.com | 31.10.22 | 31.10.22 | 06.11.23 | 13.11.23 | 22.11.23 | 24.11.23 | 07.12.23 | 07.12.23 |  |  |  |  | 07.12.23 | 07.12.23 | 08.12.23 | T1 | [7 empty] | 08.12.23 | 25.12.23 | 23.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Filter media | LE22M164-P-WS-WT-PR-2208 | LE22M164-P-WS-WT-PR-2208-A | GLOBAL ADSORBENTS | Sent to BU Operations | PR Closed |  |  |  | 13.10.22 | 13.10.22 | 16.09.23 | 20.09.23 | 21.09.23 | 21.09.23 | [6 empty] | 21.09.23 | 21.09.23 | 15.03.24 | T1 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Filter media | LE22M164-P-WS-WT-PR-2208 | LE22M164-P-WS-WT-PR-2208-B | DALTON | Post-order technically cleared | 18 |  |  |  | 13.10.22 | 13.10.22 | 02.03.24 | 02.03.24 | 15.03.24 | 15.03.24 | [6 empty] | 15.03.24 | 15.03.24 | 15.03.24 | T2 | 22.04.24 | DALTON | 22.04.24 | 06.05.24 | 21.06.24 | 17.07.24 |  | 15.03.24 | 01.04.24 | 31.05.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:17
Fazilka 1 | Process | Purchase requisition for Centrifuge | LE22M164-P-WS-WT-PR-2209 | LE22M164-P-WS-WT-PR-2209-A | HILLER | Approved by Client | PR Closed |  | Mitali Ojha | enquiry@hillerindia.com | 14.09.22 | 14.09.22 | 18.07.23 | 18.07.23 | 21.07.23 | 29.07.23 | 16.10.23 | 25.10.23 |  |  |  |  | 03.11.23 | 03.11.23 | 02.12.23 | T1 | 02.01.24 | HILLER | 02.01.24 | 08.01.24 | 16.01.24 | 03.02.24 | 03.02.24 | 03.02.24 | 20.02.24 | 02.03.24 | SNEHA-S@lntecc.com-04.06.2024-12:03:01
Fazilka 1 | Process | Purchase requisition for Centrifuge | LE22M164-P-WS-WT-PR-2209 | LE22M164-P-WS-WT-PR-2209-B | ALFA LAVAL | Regret offer | PR Closed |  |  |  | 14.09.22 | 14.09.22 | 11.10.23 | 12.10.23 | 30.10.23 | 30.10.23 | [20 empty] | SNEHA-S@lntecc.com-16.05.2024-15:56:58
Fazilka 1 | Process | Purchase requisition for Centrifuge | LE22M164-P-WS-WT-PR-2209 | LE22M164-P-WS-WT-PR-2209-C | MSEL | Sent to BU Operations | PR Closed |  | Tapan Datta | tapan.datta@msel.co.in | 14.09.22 | 14.09.22 | 20.11.23 | 22.11.23 | 27.11.23 | 28.11.23 | 02.12.23 | 02.12.23 |  |  |  |  | 02.12.23 | 02.12.23 | 02.12.23 | T2 | [7 empty] | 02.12.23 | 19.12.23 | 17.02.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for screw pump | LE22M164-P-WS-WT-PR-2210 | LE22M164-P-WS-WT-PR-2210-A | Tap Engineering | Regret offer | PR Closed | offer technically rejected by electrical discipline |  |  | 14.09.22 | 14.09.22 | 14.02.24 | 20.02.24 | 28.02.24 | 06.03.24 | 04.04.24 | 05.04.24 | [15 empty] | 31.05.24 | 17.06.24 | 16.08.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for screw pump | LE22M164-P-WS-WT-PR-2210 | LE22M164-P-WS-WT-PR-2210-B | ROTO PUMPS | Regret offer | PR Closed |  | Anandan Ethiraj | chn1@rotopumps.com | 14.09.22 | 14.09.22 | 14.03.24 | 21.03.24 | 30.03.24 | 05.04.24 | 08.04.24 | 10.04.24 | [15 empty] | 31.05.24 | 17.06.24 | 16.08.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for screw pump | LE22M164-P-WS-WT-PR-2210 | LE22M164-P-WS-WT-PR-2210-C | FLOSYS | Post-order comments issued | 17 |  | Manoj | info@flosys.in | 14.09.22 | 14.09.22 | 26.04.24 | 06.04.24 | 22.05.24 | [7 empty] | 29.05.24 | 29.05.24 | 31.05.24 | T1 | 05.07.24 | FLOSYS | 16.07.24 | 18.07.24 |  |  |  | 31.05.24 | 17.06.24 | 16.08.24 | SNEHA-S@lntecc.com-18.07.2024-17:33:08
Fazilka 1 | Process | Purchase requisition for Backwash Reservoir pump | LE22M164-P-WS-WT-PR-2211 | LE22M164-P-WS-WT-PR-2211-A | KBL | Regret offer | PR Closed |  | Mohan Kumar | mohan.kumar@kbl.co.in | 21.10.22 | 21.10.22 | 17.11.23 | 23.11.23 | 24.11.23 | 24.11.23 | [17 empty] | 06.05.24 | 23.05.24 | 22.07.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Backwash Reservoir pump | LE22M164-P-WS-WT-PR-2211 | LE22M164-P-WS-WT-PR-2211-B | KSB | Sent to BU Operations | PR Closed |  |  | dhananjay.bidnur@ksb.com | 21.10.22 | 21.10.22 | 28.02.24 | 04.03.24 | 19.03.24 | 22.03.24 | 08.04.24 | 08.04.24 |  |  |  |  | 22.04.24 | 24.04.24 | 06.05.24 | T1 | [7 empty] | 06.05.24 | 23.05.24 | 22.07.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Backwash Reservoir pump | LE22M164-P-WS-WT-PR-2211 | LE22M164-P-WS-WT-PR-2211-C | WILO | Post-order comments issued | 32 |  |  | manikkandan.pr@wilo.com | 21.10.22 | 21.10.22 | 22.02.24 | 04.03.24 | 22.03.24 | 29.03.24 | [6 empty] | 04.04.24 | 05.04.24 | 06.05.24 | T2 | 29.05.24 | WILO | 01.07.24 | 03.07.24 |  |  |  | 06.05.24 | 23.05.24 | 22.07.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:17
Fazilka 1 | Process | Purchase requisition for Submersible pump | LE22M164-P-WS-WT-PR-2212 | LE22M164-P-WS-WT-PR-2212-A | KBL | Sent to BU Operations | PR Closed |  |  | mohan.kumar@kbl.co.in | 07.10.22 | 07.10.22 | 16.01.24 | 23.01.24 | 07.02.23 | 12.02.24 | [6 empty] | 22.02.24 | 22.02.24 | 05.03.24 | T3 | [7 empty] | 05.03.24 | 22.03.24 | 21.05.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Submersible pump | LE22M164-P-WS-WT-PR-2212 | LE22M164-P-WS-WT-PR-2212-B | Aqua | Approved by Client | PR Closed |  |  | chennai@aquapumps.com | 07.10.22 | 07.10.22 | 23.01.24 | 24.01.24 | 326.02.24 | 05.03.24 | [6 empty] | 05.03.24 | 05.03.24 | 05.03.24 | T2 | 30.03.24 | Aqua | 03.04.24 | 20.04.24 | 09.05.24 | 09.05.24 | 15.05.24 | 05.03.24 | 22.03.24 | 21.05.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Submersible pump | LE22M164-P-WS-WT-PR-2212 | LE22M164-P-WS-WT-PR-2212-C | MBH | Sent to BU Operations | PR Closed |  |  | northindustrial@mbhpumps.com | 07.10.22 | 07.10.22 | 21.02.24 | 26.02.24 | 29.02.24 | 04.03.24 | 05.03.24 | 05.03.24 | 30.04.24 |  |  |  | 05.03.24 | 05.03.24 | 05.03.24 | T1 | [7 empty] | 05.03.24 | 22.03.24 | 21.05.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Electrical hoist | LE22M164-P-WS-WT-PR-2213 | LE22M164-P-WS-WT-PR-2213-A | Eddy cranes | Regret offer | PR Closed |  |  | info@eddycranes.in | 12.12.22 | 12.12.22 | 19.12.23 | 02.01.24 | 04.01.24 | 06.01.24 | 08.01.24 | 08.01.24 | [18 empty] | SNEHA-S@lntecc.com-16.05.2024-15:56:58
Fazilka 1 | Process | Purchase requisition for Electrical hoist | LE22M164-P-WS-WT-PR-2213 | LE22M164-P-WS-WT-PR-2213-B | Indef | Post-order technically cleared | 39 |  |  | mkm@indef.com | 12.12.22 | 12.12.22 | 23.01.24 | 29.01.24 | 15.02.24 | 17.02.24 | 26.02.24 | 26.02.24 |  |  |  |  | 26.02.24 | 26.02.24 | 04.04.24 | T2 | 03.06.24 | Indef | 21.06.24 | 21.06.24 | 25.06.24 | 26.06.24 | 26.06.24 | 04.04.24 | 21.04.24 | 20.06.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:17
Fazilka 1 | Process | Purchase requisition for Electrical hoist | LE22M164-P-WS-WT-PR-2213 | LE22M164-P-WS-WT-PR-2213-C | Reva | Sent to BU Operations | PR Closed |  |  | mkt@revacranes.com | 12.12.22 | 12.12.22 | 24.01.24 | 29.01.24 | 05.02.24 | 05.02.24 | 13.02.24 | 13.02.24 | 26.02.24 | 26.02.24 |  |  | 26.02.24 | 26.02.24 | 04.04.24 | T3 | [7 empty] | 04.04.24 | 21.04.24 | 20.06.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Electrical hoist | LE22M164-P-WS-WT-PR-2213 | LE22M164-P-WS-WT-PR-2213-D | JAPS | Sent to BU Operations | PR Closed |  |  | sales.japs@gmail.com | 12.12.22 | 12.12.22 | 01.04.24 | 02.04.24 | 03.04.24 | 03.04.24 | [6 empty] | 04.04.24 | 04.04.24 | 04.04.24 | T1 | [7 empty] | 04.04.24 | 21.04.24 | 20.06.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Manual chain pulley block | LE22M164-P-WS-WT-PR-2214 | LE22M164-P-WS-WT-PR-2214-A | Brady | Regret offer | PR Closed |  |  | srinivasan@bradys.in | 12.12.22 | 12.12.22 | 14.2.24 | [23 empty] | SNEHA-S@lntecc.com-16.05.2024-15:56:58
Fazilka 1 | Process | Purchase requisition for Manual chain pulley block | LE22M164-P-WS-WT-PR-2214 | LE22M164-P-WS-WT-PR-2214-B | JAPS | Sent to BU Operations | 74 |  |  | sales.japs@gmail.com | 12.12.22 | 12.12.22 | 03.04.24 | 03.04.24 | 04.04.24 | 05.04.24 | [6 empty] | 05.04.24 | 05.04.24 | 22.05.24 | T1 | [7 empty] | 22.05.24 | 08.06.24 | 07.08.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:17
Fazilka 1 | Process | Purchase requisition for Manual chain pulley block | LE22M164-P-WS-WT-PR-2214 | LE22M164-P-WS-WT-PR-2214-C | Indef | Sent to BU Operations | 74 |  |  | mkm@indef.com | 12.12.22 | 12.12.22 | 16.04.24 | 24.04.24 | 15.05.24 | [7 empty] | 20.05.24 | 22.05.24 | 22.05.24 | T2 | [7 empty] | 22.05.24 | 08.06.24 | 07.08.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:17
Fazilka 1 | Process | Purchase requisition for Dosing pump | LE22M164-P-WS-WT-PR-2215 | LE22M164-P-WS-WT-PR-2215-A | Milton Roy | Sent to BU Operations | PR Closed |  | Swati | proposal@fluidoze.com | 31.10.22 | 31.10.22 | 02.11.23 | 09.11.23 | [8 empty] | 22.11.23 | 24.11.23 | 15.02.24 | T2 | [7 empty] | 15.02.24 | 03.03.24 | 02.05.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Dosing pump | LE22M164-P-WS-WT-PR-2215 | LE22M164-P-WS-WT-PR-2215-B | Positive Metering | Approved by Client | PR Closed |  |  | offers1@positivemetering.com | 31.10.22 | 31.10.22 | 01.12.23 | 06.12.23 | 13.02.24 | 13.02.24 | [6 empty] | 15.02.24 | 15.02.24 | 15.02.24 | T1 | 22.03.24 | Positive Metering | 22.03.24 | 29.03.24 | 16.04.24 | 20.04.24 | 30.05.24 | 15.02.24 | 03.03.24 | 02.05.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for DWPE dosing tanks | LE22M164-P-WS-WT-PR-2216 | LE22M164-P-WS-WT-PR-2216-A | FFP | Post-order technically cleared | 18 |  |  | fibrein@gmail.com | 21.10.22 | 21.10.22 | 06.03.24 | 15.03.24 | 06.04.24 | 06.04.24 | [6 empty] | 06.04.24 | 06.04.24 | 06.04.24 | T1 | 06.05.24 | FFP | 19.06.24 | 21.06.24 | 11.07.24 | 17.07.24 |  | 06.04.24 | 23.04.24 | 22.06.24 | SNEHA-S@lntecc.com-18.07.2024-17:25:26
Fazilka 1 | Process | Purchase requisition for HDPE tank Agitators | LE22M164-P-WS-WT-PR-2217 | LE22M164-P-WS-WT-PR-2217-A | FFP | Post-order technically cleared | 18 |  |  | fibrein@gmail.com | 21.10.22 | 21.10.22 | 16.03.24 | 16.03.24 | 03.04.24 | 03.04.24 | [6 empty] | 06.04.24 | 06.04.24 | 06.04.24 | T1 | 06.05.24 | FFP | 19.06.24 | 21.06.24 | 11.07.24 | 17.07.24 |  | 06.04.24 | 23.04.24 | 22.06.24 | SNEHA-S@lntecc.com-18.07.2024-17:25:26
Fazilka 1 | Process | Purchase requisition for Sampling pump | LE22M164-P-WS-WT-PR-2218 | LE22M164-P-WS-WT-PR-2218-A | SITE PROCUREMENT | Regret offer | PR Closed | SITE PROCUREMENT |  |  | 21.10.22 | 21.10.22 | [24 empty] | SNEHA-S@lntecc.com-04.06.2024-12:13:48
Fazilka 1 | Process | Purchase requisition for Submersible mixer | LE22M164-P-WS-WT-PR-2219 | LE22M164-P-WS-WT-PR-2219-A | FFP | Post-order technically cleared | 58 |  |  | fibrein@gmail.com | 21.10.22 | 21.10.22 | 02.12.23 | 05.12.23 | 15.02.24 | 15.02.24 | [6 empty] | 19.02.24 | 22.02.24 | 22.02.24 | T1 | 01.04.24 | FFP | 28.05.24 | 01.06.24 | 07.06.24 | 07.06.24 |  | 22.02.24 | 10.03.24 | 09.05.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:17
Fazilka 1 | Process | Purchase requisition for Submersible mixer | LE22M164-P-WS-WT-PR-2219 | LE22M164-P-WS-WT-PR-2219-B | World water tech | Sent to BU Operations | PR Closed |  |  | wwtechennai@gmail.com | 21.10.22 | 21.10.22 | 09.01.24 | 10.01.24 | [8 empty] | 15.02.24 | 17.02.24 | 22.02.24 | T2 | [7 empty] | 22.02.24 | 10.03.24 | 09.05.24 | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Process | Purchase requisition for Dewatering pump | LE22M164-P-WS-WT-PR-2220 | LE22M164-P-WS-WT-PR-2220-A | AQUA | Sent to BU Operations | 152 |  |  | chennai@aquapumps.com | 07.10.22 | 07.10.22 | 23.01.24 | 12.02.24 | 26.02.24 | 05.03.24 | [6 empty] | 05.03.24 | 05.03.24 | 05.03.24 | T1 | [7 empty] | 05.03.24 | 22.03.24 | 21.05.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:17
Fazilka 1 | Process | Purchase requisition for Dissolving tray | LE22M164-P-WS-WT-PR-2221 | LE22M164-P-WS-WT-PR-2221-A | SITE PROCUREMENT | Regret offer | PR Closed | SITE PROCUREMENT |  |  | 13.10.22 | 13.10.22 | [24 empty] | SNEHA-S@lntecc.com-04.06.2024-12:13:48
Fazilka 1 | Process | Purchase requisition for Trolley | LE22M164-P-WS-WT-PR-2222 | LE22M164-P-WS-WT-PR-2222-A | SITE PROCUREMENT | Regret offer | PR Closed | SITE PROCUREMENT | SITE PROCUREMENT |  | 15.09.22 | 15.09.22 | [24 empty] | SNEHA-S@lntecc.com-04.06.2024-12:13:48
Fazilka 1 | Process | Purchase requisition for Platform weighing machine | LE22M164-P-WS-WT-PR-2223 | LE22M164-P-WS-WT-PR-2223-A | SITE PROCUREMENT | Regret offer | PR Closed | SITE PROCUREMENT |  |  | 17.09.22 | 17.09.22 | [24 empty] | SNEHA-S@lntecc.com-04.06.2024-12:13:48
Fazilka 1 | Process | Purchase requisition for Exhaust fan | LE22M164-P-WS-WT-PR-2224 | LE22M164-P-WS-WT-PR-2224-A | SITE PROCUREMENT | Regret offer | PR Closed | SITE PROCUREMENT |  |  | 13.10.22 | 13.10.22 | [24 empty] | SNEHA-S@lntecc.com-04.06.2024-12:13:48
Fazilka 1 | Process | Purchase requisition for lab equipment | LE22M164-P-WS-WT-PR-2225 | LE22M164-P-WS-WT-PR-2225-A | SITE PROCUREMENT | Regret offer | PR Closed | SITE PROCUREMENT |  |  | 21.10.22 | 21.10.22 | [24 empty] | SNEHA-S@lntecc.com-04.06.2024-12:13:48
Fazilka 1 | Process | Purchase requisition for Rechlorination | LE22M164-P-WS-WT-PR-2226 | LE22M164-P-WS-WT-PR-2226-A | VERITO | Sent to BU Operations | 100 |  |  | jay@veritoengineering.com | 21.10.22 | 19.01.24 | 01.04.24 | 03.04.24 | [8 empty] | 17.04.24 | 20.04.24 | 26.04.24 | T1 | [7 empty] | 26.04.24 | 13.05.24 | 12.07.24 | SNEHA-S@lntecc.com-18.07.2024-17:21:17
Fazilka 1 | Process | Purchase requisition for Service water pumps | LE22M164-P-WS-WT-PR-2227 | LE22M164-P-WS-WT-PR-2227-A | KSB | Pre-order comments issued | 18 |  |  | dhananjay.bidnur@ksb.com | 14.11.23 | 14.11.23 | 29.02.24 | 05.03.24 | 27.03.24 | 29.03.24 | [6 empty] | 04.04.24 | 08.04.24 | 09.04.24 | T1 | 23.05.24 | KSB | 17.07.24 | 17.07.24 |  |  |  | 09.04.24 | 26.04.24 | 25.06.24 | SNEHA-S@lntecc.com-18.07.2024-17:30:55
Fazilka 1 | Process | Purchase requisition for Service water pumps | LE22M164-P-WS-WT-PR-2227 | LE22M164-P-WS-WT-PR-2227-B | KBL | Regret offer | PR Closed |  |  | mohan.kumar@kbl.co.in | 14.11.23 | 14.11.23 | 31.03.24 | 05.04.24 | 07.04.24 | 09.04.24 | [8 empty] | 31.05.24 | [11 empty] | SNEHA-S@lntecc.com-03.07.2024-18:54:03
Fazilka 1 | Mechanical | Dismantling Joints | LE22M164-M-WS-WT-PR-1001 | LE22M164-M-WS-WT-PR-1001-A | Kerijwal Castings | Sent to BU Operations | PR Closed |  |  |  |  | 23.10.23 | 10.11.23 | 13.11.23 | 15.11.23 | 20.11.23 | [6 empty] | 21.11.23 | 21.11.23 | 21.11.23 | T1 | [7 empty] | 21.11.23 | 08.12.23 | 06.02.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Dismantling Joints | LE22M164-M-WS-WT-PR-1001 | LE22M164-M-WS-WT-PR-1001-B | Electrosteel | Regret offer | PR Closed |  |  |  |  | 23.10.23 | [21 empty] | 23.10.23 | 09.11.23 | 08.01.24 | svcn@lntecc.com-02.07.2024-10:51:10
Fazilka 1 | Mechanical | Dismantling Joints | LE22M164-M-WS-WT-PR-1001 | LE22M164-M-WS-WT-PR-1001-C | Technoflux | Sent to BU Operations | PR Closed |  |  |  |  | 23.10.23 | 10.11.23 | 13.11.23 | 15.11.23 | 20.11.23 | [6 empty] | 21.11.23 | 21.11.23 | 21.11.23 | T1 | [7 empty] | 21.11.23 | 08.12.23 | 06.02.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Dismantling Joints | LE22M164-M-WS-WT-PR-1001 | LE22M164-M-WS-WT-PR-1001-D | Precise engineers | Approved by Client | PR Closed |  |  |  |  | 23.10.23 | 22.01.24 | 23.01.24 | 29.01.24 | 30.01.24 | [6 empty] | 20.04.24 | 20.04.24 | 22.04.24 | T1 | 22.04.24 | Precise engineers | 22.04.24 | 23.04.24 | 24.04.24 | 29.04.24 | 30.04.24 | 20.04.24 | 07.05.24 | 21.06.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Dismantling Joints | LE22M164-M-WS-WT-PR-1001 | LE22M164-M-WS-WT-PR-1001-E | Ananth engineers | Sent to BU Operations | PR Closed |  |  |  |  | 23.10.23 | 10.11.23 | 13.11.23 | 15.11.23 | 20.11.23 | [6 empty] | 21.11.23 | 21.11.23 | 21.11.23 | T1 | [7 empty] | 21.11.23 | 08.12.23 | 06.02.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | EOT crane | LE22M164-M-WS-WT-PR-1002 | LE22M164-M-WS-WT-PR-1002-A | Indef | Sent to BU Operations | PR Closed |  |  |  |  | 01.11.23 | 24.11.23 | 27.11.23 | 04.12.23 | 11.12.23 | [6 empty] | 18.12.23 | 18.12.23 | 18.12.23 | T1 | [7 empty] | 18.12.23 | 04.01.24 | 04.03.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | EOT crane | LE22M164-M-WS-WT-PR-1002 | LE22M164-M-WS-WT-PR-1002-B | Eddy | Sent to BU Operations | PR Closed |  |  |  |  | 01.11.23 | 24.11.23 | 27.11.23 | 04.12.23 | 11.12.23 | [6 empty] | 18.12.23 | 18.12.23 | 18.12.23 | T1 | [7 empty] | 18.12.23 | 04.01.24 | 04.03.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | EOT crane | LE22M164-M-WS-WT-PR-1002 | LE22M164-M-WS-WT-PR-1002-C | Reva | Sent to BU Operations | PR Closed |  |  |  |  | 01.11.23 | 24.11.23 | 27.11.23 | 04.12.23 | 11.12.23 | [6 empty] | 18.12.23 | 18.12.23 | 18.12.23 | T1 | [7 empty] | 18.12.23 | 04.01.24 | 04.03.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | EOT crane | LE22M164-M-WS-WT-PR-1002 | LE22M164-M-WS-WT-PR-1002-D | JAPS | Approved by Client | PR Closed |  |  |  |  | 01.11.23 | 24.11.23 | 27.11.23 | 04.12.23 | 11.12.23 | [6 empty] | 18.12.23 | 18.12.23 | 18.12.23 | T1 | 22.12.23 | JAPS | 23.12.23 | 25.12.23 | 26.12.23 | 27.12.23 | 01.02.24 | 18.12.23 | 04.01.24 | 20.02.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | HSC pumps | LE22M164-M-WS-WT-PR-1003 | LE22M164-M-WS-WT-PR-1003-A | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 16.10.23 | 07.11.23 | 07.11.23 | 14.11.23 | 21.11.23 | 17.11.23 | 24.11.23 |  |  |  |  | 20.12.23 | 25.12.23 | 26.12.23 | T1 | [7 empty] | 20.12.23 | 06.01.24 | 06.03.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | HSC pumps | LE22M164-M-WS-WT-PR-1003 | LE22M164-M-WS-WT-PR-1003-B | WILO | Approved by Client | PR Closed |  |  |  |  | 16.10.23 | 07.11.23 | 10.11.23 | 13.11.23 | 15.11.23 | 17.11.23 | 24.11.23 | 30.11.23 | 01.12.23 | 11.12.23 | 18.12.23 | 20.12.23 | 25.12.23 | 26.12.23 | T1 | 19.12.23 | WILO | 25.12.23 | 28.12.23 | 25.12.23 | 27.12.23 | 22.01.24 | 20.12.23 | 06.01.24 | 17.02.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | HSC pumps | LE22M164-M-WS-WT-PR-1003 | LE22M164-M-WS-WT-PR-1003-C | KSB | Sent to BU Operations | PR Closed |  |  |  |  | 16.10.23 | 07.11.23 | 10.11.23 | 13.11.23 | 15.11.23 | 17.11.23 | 24.11.23 | 30.11.23 | 01.12.23 |  |  | 20.12.23 | 25.12.23 | 26.12.23 | T1 | [7 empty] | 20.12.23 | 06.01.24 | 06.03.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Sluice gates | LE22M164-M-WS-WT-PR-1004 | LE22M164-M-WS-WT-PR-1004-A | JASH | Approved by Client | PR Closed |  |  |  |  | 11.09.23 | 25.09.23 | 29.09.23 | 04.10.23 | 09.10.23 | 11.10.23 | 13.10.23 |  |  |  |  | 27.10.23 | 27.10.23 | 27.10.23 | T1 | 02.11.23 | JASH | 06.11.23 | 08.11.23 | 10.11.23 | 12.11.23 | 20.11.23 | 27.10.23 | 13.11.23 | 01.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Sluice gates | LE22M164-M-WS-WT-PR-1004 | LE22M164-M-WS-WT-PR-1004-B | ORIENTAL CASTINGS | Sent to BU Operations | PR Closed |  |  |  |  | 11.09.23 | 26.09.23 | 27.09.23 | 28.09.23 | 30.09.23 | [6 empty] | 28.09.23 | 29.09.23 | 29.09.23 | T1 | [7 empty] | 28.09.23 | 15.10.23 | 14.12.23 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Ventilation fans | LE22M164-M-WS-WT-PR-1005 | LE22M164-M-WS-WT-PR-1005-A | GENVIROTECH | Sent to BU Operations | 111 |  |  |  |  | 05.03.24 | 01.04.24 | 02.04.24 | 04.04.24 | 05.04.24 | 10.04.24 | 11.04.24 |  |  |  |  | 12.04.24 | 13.04.24 | 15.04.24 | T1 | [7 empty] | 12.04.24 | 29.04.24 | 28.06.24 | gopal.samarth@lntecc.com-24.07.2024-16:45:53
Fazilka 1 | Mechanical | Ventilation fans | LE22M164-M-WS-WT-PR-1005 | LE22M164-M-WS-WT-PR-1005-B | SV air systems | Sent to BU Operations | 110 |  |  |  |  | 05.03.24 | 04.04.24 | 05.04.24 | 09.04.24 | 10.04.24 | 15.04.24 | 16.04.24 |  |  |  |  | 12.04.24 | 13.04.24 | 15.04.24 | T1 | [7 empty] | 12.04.24 | 29.04.24 | 28.06.24 | gopal.samarth@lntecc.com-24.07.2024-16:45:53
Fazilka 1 | Mechanical | Ventilation fans | LE22M164-M-WS-WT-PR-1005 | LE22M164-M-WS-WT-PR-1005-C | Nadi air technics | Awaiting pre-offer from vendor | 34 |  |  |  |  | 01.07.24 | [24 empty] | gopal.samarth@lntecc.com-24.07.2024-16:45:53
Fazilka 1 | Mechanical | Ventilation fans | LE22M164-M-WS-WT-PR-1005 | LE22M164-M-WS-WT-PR-1005-D | Tap engineering | Awaiting pre-offer from vendor | 34 |  |  |  |  | 01.07.24 | [24 empty] | gopal.samarth@lntecc.com-24.07.2024-16:45:53
Fazilka 1 | Mechanical | Dewatering pumps | LE22M164-M-WS-WT-PR-1006 | LE22M164-M-WS-WT-PR-1006-A | MBH | Pre-order technically cleared | 51 |  | Naresh | northindustrial@mbhpumps.com |  | 16.03.24 | 30.05.24 | 14.06.24 | [8 empty] | 14.06.24 | 14.06.24 | 14.06.24 | T1 | [7 empty] | 14.06.24 | 01.07.24 | 30.08.24 | gopal.samarth@lntecc.com-24.07.2024-16:45:53
Fazilka 1 | Mechanical | Dewatering pumps | LE22M164-M-WS-WT-PR-1006 | LE22M164-M-WS-WT-PR-1006-B | Aqua pumps | Awaiting pre-offer from vendor | 11 |  |  |  |  | 24.06.24 | 17.07.24 | 18.07.24 | [8 empty] | 18.07.24 | 18.07.24 | 24.07.24 | T1 | [7 empty] | 24.07.24 | 10.08.24 | 09.10.24 | gopal.samarth@lntecc.com-24.07.2024-16:46:17
Fazilka 1 | Mechanical | Butterfly valves | LE22M164-M-WS-WT-PR-1007 | LE22M164-M-WS-WT-PR-1007-A | AVK | Approved by Client | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 20.11.23 | 22.11.23 | 09.10.23 | 13.10.23 |  |  |  |  | 13.11.23 | 14.11.23 | 15.11.23 | T1 | 25.01.24 | AVK | 24.01.24 | 24.01.24 | 24.01.24 | 24.01.24 | 15.02.24 | 13.11.23 | 30.11.23 | 29.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Butterfly valves | LE22M164-M-WS-WT-PR-1007 | LE22M164-M-WS-WT-PR-1007-B | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 09.10.23 | 11.10.23 | 06.12.23 | 09.12.23 |  |  |  |  | 20.10.23 | 21.10.23 | 23.10.23 | T1 | [7 empty] | 20.10.23 | 06.11.23 | 05.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Butterfly valves | LE22M164-M-WS-WT-PR-1007 | LE22M164-M-WS-WT-PR-1007-C | VAG | Sent to BU Operations | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 09.10.23 | 10.10.23 | 18.10.23 | 20.10.23 |  |  |  |  | 20.10.23 | 21.10.23 | 23.10.23 | T1 | [7 empty] | 20.10.23 | 06.11.23 | 05.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Sluice valve | LE22M164-M-WS-WT-PR-1008 | LE22M164-M-WS-WT-PR-1008-A | AVK | Sent to BU Operations | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 20.11.23 | 22.11.23 | 09.10.23 | 13.10.23 |  |  |  |  | 13.11.23 | 14.11.23 | 15.11.23 | . | [7 empty] | 13.11.23 | 30.11.23 | 29.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Sluice valve | LE22M164-M-WS-WT-PR-1008 | LE22M164-M-WS-WT-PR-1008-B | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 09.10.23 | 11.10.23 | 06.12.23 | 09.12.23 |  |  |  |  | 20.10.23 | 21.10.23 | 23.10.23 | T1 | [7 empty] | 20.10.23 | 06.11.23 | 05.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Sluice valve | LE22M164-M-WS-WT-PR-1008 | LE22M164-M-WS-WT-PR-1008-C | VAG | Approved by Client | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 09.10.23 | 10.10.23 | 18.10.23 | 20.10.23 |  |  |  |  | 20.10.23 | 21.10.23 | 23.10.23 | T1 | 25.01.24 | VAG | 24.01.24 | 24.01.24 | 24.01.24 | 24.01.24 | 21.02.24 | 20.10.23 | 06.11.23 | 05.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Dual plate check valve | LE22M164-M-WS-WT-PR-1009 | LE22M164-M-WS-WT-PR-1009-A | AVK | Sent to BU Operations | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 20.11.23 | 22.11.23 | 09.10.23 | 13.10.23 |  |  |  |  | 13.11.23 | 14.11.23 | 15.11.23 | . | [7 empty] | 13.11.23 | 30.11.23 | 29.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Dual plate check valve | LE22M164-M-WS-WT-PR-1009 | LE22M164-M-WS-WT-PR-1009-B | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 09.10.23 | 11.10.23 | 06.12.23 | 09.12.23 |  |  |  |  | 20.10.23 | 21.10.23 | 23.10.23 | T1 | [7 empty] | 20.10.23 | 06.11.23 | 05.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Dual plate check valve | LE22M164-M-WS-WT-PR-1009 | LE22M164-M-WS-WT-PR-1009-C | VAG | Approved by Client | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 09.10.23 | 10.10.23 | 18.10.23 | 20.10.23 |  |  |  |  | 20.10.23 | 21.10.23 | 23.10.23 | T1 | 25.01.24 | VAG | 24.01.24 | 24.01.24 | 24.01.24 | 24.01.24 | 21.02.24 | 20.10.23 | 06.11.23 | 05.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Air valve | LE22M164-M-WS-WT-PR-1010 | LE22M164-M-WS-WT-PR-1010-A | AVK | Approved by Client | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 20.11.23 | 22.11.23 | 09.10.23 | 13.10.23 |  |  |  |  | 13.11.23 | 14.11.23 | 15.11.23 | T1 | 25.01.24 | AVK | 24.01.24 | 24.01.24 | 24.01.24 | 24.01.24 | 15.02.24 | 13.11.23 | 30.11.23 | 29.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Air valve | LE22M164-M-WS-WT-PR-1010 | LE22M164-M-WS-WT-PR-1010-B | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 09.10.23 | 11.10.23 | 06.12.23 | 09.12.23 |  |  |  |  | 20.10.23 | 21.10.23 | 23.10.23 | T1 | [7 empty] | 20.10.23 | 06.11.23 | 05.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Air valve | LE22M164-M-WS-WT-PR-1010 | LE22M164-M-WS-WT-PR-1010-C | VAG | Sent to BU Operations | PR Closed |  |  |  |  | 25.09.23 | 28.09.23 | 30.09.23 | 09.10.23 | 10.10.23 | 18.10.23 | 20.10.23 |  |  |  |  | 20.10.23 | 21.10.23 | 23.10.23 | T1 | [7 empty] | 20.10.23 | 06.11.23 | 05.01.24 | svcn@lntecc.com-03.07.2024-15:08:53
Fazilka 1 | Mechanical | Surge valves | LE22M164-M-WS-WT-PR-1011 | LE22M164-M-WS-WT-PR-1011-A |  | Enquiry yet to float | NA | [26 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-11.07.2024-10:30:15
Fazilka 1 | Mechanical | Surge valves | LE22M164-M-WS-WT-PR-1012 | LE22M164-M-WS-WT-PR-1012-A | AVK | Approved by Client | PR Closed |  |  |  |  | 04.06.24 | 25.06.24 | 25.06.24 | 25.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T1 | 25.06.24 | AVK | 25.06.24 | 25.06.24 | 25.06.24 | 25.06.24 | 03.07.24 |  |  |  | gopal.samarth@lntecc.com-24.07.2024-16:45:53
Fazilka 1 | Instrumentation | Pressure Gauge/ Compound Pressure Gauge | LE22M164-I-WS-WT-PR-5501 | LE22M164-I-WS-WT-PR-5501-A | H Guru | Sent to BU Operations | PR Closed |  | Shyamlal |  | 09.01.23 | 09.01.23 | 27.10.23 | 13.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 13.12.23 | T2 | [7 empty] | 13.12.23 | 30.12.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Pressure Gauge/ Compound Pressure Gauge | LE22M164-I-WS-WT-PR-5501 | LE22M164-I-WS-WT-PR-5501-B | Forbes Marshall | Post-order technically cleared | 20 |  |  |  | 09.01.23 | 09.01.23 | 27.10.23 | 13.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 13.12.23 | T1 | 08.05.24 | Forbes Marshall | 30.05.24 | 01.07.24 | 15.07.24 | 15.07.24 |  | 13.12.23 | 30.12.23 | 07.07.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Pressure Gauge/ Compound Pressure Gauge | LE22M164-I-WS-WT-PR-5501 | LE22M164-I-WS-WT-PR-5501-C | General Instruments | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 27.10.23 | 13.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 13.12.23 | T3 | [7 empty] | 13.12.23 | 30.12.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Pressure Transmitter | LE22M164-I-WS-WT-PR-5503 | LE22M164-I-WS-WT-PR-5503-A | E&H | Sent to BU Operations | PR Closed |  | Ramkumar |  | 09.01.23 | 09.01.23 | 21.09.23 | 28.09.23 | [8 empty] | 21.09.23 | 21.09.23 | 21.09.23 | T2 | [7 empty] | 21.09.23 | 08.10.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Pressure Transmitter | LE22M164-I-WS-WT-PR-5503 | LE22M164-I-WS-WT-PR-5503-B | Siemens | Approved by Client | PR Closed |  | Chandrasekar |  | 09.01.23 | 09.01.23 | 21.09.23 | 22.09.23 | [8 empty] | 22.09.23 | 22.09.23 | 21.09.23 | T1 | 28.09.23 | Siemens | 19.12.23 | 29.12.23 | 29.12.23 | 19.12.23 | 19.12.23 | 21.09.23 | 08.10.23 | 27.11.23 | justin.v@lntecc.com-08.07.2024-12:26:22
Fazilka 1 | Instrumentation | Pressure Transmitter | LE22M164-I-WS-WT-PR-5503 | LE22M164-I-WS-WT-PR-5503-C | Yokogawa | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 21.09.23 | 21.09.23 | [8 empty] | 21.09.23 | 21.09.23 | 21.09.23 | T3 | [7 empty] | 21.09.23 | 08.10.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Float & Board Level Gauge | LE22M164-I-WS-WT-PR-5504 | LE22M164-I-WS-WT-PR-5504-A | Scientific Devices | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 27.11.23 | 05.04.24 | 01.04.24 | 20.04.24 | 01.05.24 | [5 empty] | 01.05.24 | 01.05.24 | 30.05.23 | T2 | [7 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:33:12
Fazilka 1 | Instrumentation | Float & Board Level Gauge | LE22M164-I-WS-WT-PR-5504 | LE22M164-I-WS-WT-PR-5504-B | SBEM | Post-order comments issued | 15 |  |  |  | 09.01.23 | 07.05.23 | 21.05.24 | 21.05.24 | 28.05.24 | 30.05.24 | [6 empty] | 30.05.24 | 28.05.24 | 04.07.24 | T1 | 04.07.24 | SBEM | 19.07.24 | 20.07.24 |  |  |  | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:33:12
Fazilka 1 | Instrumentation | Level Switch | LE22M164-I-WS-WT-PR-5506 | LE22M164-I-WS-WT-PR-5504-C | SBEM | Regret offer | PR Closed |  |  |  | 09.01.23 | 07.05.23 | 21.05.24 | 21.05.24 | 28.05.24 | 30.05.24 | [6 empty] | 30.05.24 | 28.05.24 | 04.07.24 | T1 | 04.07.24 | SBEM | 19.07.24 | 20.07.24 |  |  |  | 10.07.24 |  |  | justin.v@lntecc.com-20.07.2024-14:33:39
Fazilka 1 | Instrumentation | Ultrasonic Level Transmitter | LE22M164-I-WS-WT-PR-5505 | LE22M164-I-WS-WT-PR-5505-A | E&H | Sent to BU Operations | PR Closed |  | Ramkumar |  | 09.01.23 | 09.01.23 | 23.10.23 | 27.10.23 | [8 empty] | 27.10.23 | 27.10.23 | 23.10.23 | T2 | [7 empty] | 23.10.23 | 09.11.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Ultrasonic Level Transmitter | LE22M164-I-WS-WT-PR-5505 | LE22M164-I-WS-WT-PR-5505-B | Siemens | Approved by Client | PR Closed |  | Chandrasekar |  | 09.01.23 | 09.01.23 | 21.09.23 | 27.10.23 | [8 empty] | 27.10.23 | 27.10.23 | 21.09.23 | T1 | 28.09.23 | Siemens | 19.12.23 | 29.12.23 | 29.12.23 | 19.12.23 | 19.12.23 | 21.09.23 | 08.10.23 | 27.11.23 | justin.v@lntecc.com-08.07.2024-12:26:22
Fazilka 1 | Instrumentation | Ultrasonic Level Transmitter | LE22M164-I-WS-WT-PR-5505 | LE22M164-I-WS-WT-PR-5505-C | Yokogawa | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 26.09.23 | 27.10.23 | [8 empty] | 27.10.23 | 27.10.23 | 26.09.23 | T3 | [7 empty] | 26.09.23 | 13.10.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Level Switch - Conductivity Type | LE22M164-I-WS-WT-PR-5506 | LE22M164-I-WS-WT-PR-5506-A | E&H | Pre-order technically cleared | 121 |  |  |  | 09.01.23 | 09.01.23 | 29.01.24 | 20.03.24 | 23.03.24 | 05.04.24 | [6 empty] | 05.04.24 | 05.04.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Level Switch - Conductivity Type | LE22M164-I-WS-WT-PR-5506 | LE22M164-I-WS-WT-PR-5506-B | Scientific Devices | Pre-order technically cleared | 95 |  |  |  | 09.01.23 | 09.01.23 | 27.11.23 | 05.04.24 | 07.03.24 | 20.04.24 | 01.05.24 | [5 empty] | 01.05.24 | 01.05.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Level Switch - Conductivity Type | LE22M164-I-WS-WT-PR-5506 | LE22M164-I-WS-WT-PR-5506-C | Pune Techtrol | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 04.04.24 | 08.04.24 | 26.03.24 | [18 empty] | 10.07.24 | 27.07.24 | 25.09.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Level Switch - Conductivity Type | LE22M164-I-WS-WT-PR-5506 | LE22M164-I-WS-WT-PR-5506-D | SBEM | Pre-order technically cleared | 66 |  |  |  | 09.01.23 | 07.05.23 | 21.05.24 | 21.05.24 | 28.05.24 | 30.05.24 | [6 empty] | 30.05.24 | 28.05.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Loss of Head Transmitter | LE22M164-I-WS-WT-PR-5508 | LE22M164-I-WS-WT-PR-5508-A | Siemens | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 13.02.24 | 20.02.24 | 01.04.24 | 25.03.24 | 28.03.24 | 28.03.24 |  |  |  |  | 28.03.24 | 28.03.24 | 28.03.24 | T3 | [7 empty] | 28.03.24 | 14.04.24 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Loss of Head Transmitter | LE22M164-I-WS-WT-PR-5508 | LE22M164-I-WS-WT-PR-5508-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 08.02.24 | 20.03.24 | 07.03.24 | 03.04.24 | [6 empty] | 03.04.24 | 03.04.24 | 03.04.24 | T2 | [7 empty] | 03.04.24 | 20.04.24 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Loss of Head Transmitter | LE22M164-I-WS-WT-PR-5508 | LE22M164-I-WS-WT-PR-5508-C | E&H | Approved by Client | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 29.01.24 | 20.03.24 | 26.03.24 | 04.04.24 | [6 empty] | 04.04.24 | 04.04.24 | 04.04.24 | T1 | 06.05.24 | E&H | 13.05.24 | 14.05.24 | 17.05.24 | 16.05.24 | 31.05.24 | 04.04.24 | 21.04.24 | 05.07.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Rate of Flow Transmitter | LE22M164-I-WS-WT-PR-5509 | LE22M164-I-WS-WT-PR-5509-A | Siemens | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 13.02.24 | 20.02.24 | 01.04.24 | 25.03.24 | 28.03.24 | 28.03.24 |  |  |  |  | 28.03.24 | 28.03.24 | 28.03.24 | T3 | [7 empty] | 28.03.24 | 14.04.24 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Rate of Flow Transmitter | LE22M164-I-WS-WT-PR-5509 | LE22M164-I-WS-WT-PR-5509-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 08.02.24 | 20.03.24 | 25.03.24 | 03.04.24 | [6 empty] | 03.04.24 | 03.04.24 | 03.04.24 | T2 | [7 empty] | 03.04.24 | 20.04.24 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Rate of Flow Transmitter | LE22M164-I-WS-WT-PR-5509 | LE22M164-I-WS-WT-PR-5509-C | E&H | Approved by Client | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 29.01.24 | 20.03.24 | 20.03.24 | 04.04.24 | [6 empty] | 04.04.24 | 04.04.24 | 04.04.24 | T1 | 06.05.24 | E&H | 13.05.24 | 14.05.24 | 17.05.24 | 16.05.24 | 31.05.24 | 04.04.24 | 21.04.24 | 05.07.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Rotameter | LE22M164-I-WS-WT-PR-5510 | LE22M164-I-WS-WT-PR-5510-A | Eureka | Pre-order technically cleared | 254 |  |  |  | 09.01.23 | 09.01.23 | 31.10.23 | 16.11.23 | 23.11.23 | 24.11.23 | [6 empty] | 24.11.23 | 23.11.23 |  | T3 | [7 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Rotameter | LE22M164-I-WS-WT-PR-5510 | LE22M164-I-WS-WT-PR-5510-B | Scientific Devices | Pre-order technically cleared | 254 |  |  |  | 09.01.23 | 09.01.23 | 10.11.23 | 16.11.23 | 23.11.23 | 24.11.23 | [6 empty] | 24.11.23 | 23.11.23 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | pH Meter | LE22M164-I-WS-WT-PR-5511 | LE22M164-I-WS-WT-PR-5511-A | E&H | Post-order technically cleared | 106 |  | Ramkumar |  | 09.01.23 | 09.01.23 | 17.01.24 | 24.01.24 | [8 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T1 | 02.04.24 | E&H | 10.04.24 | 20.04.24 | 20.04.24 | 10.04.24 |  | 12.02.24 | 29.02.24 | 01.06.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | pH Meter | LE22M164-I-WS-WT-PR-5511 | LE22M164-I-WS-WT-PR-5511-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 11.01.24 | 07.02.24 | 12.02.24 | 14.02.24 | [6 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T2 | [7 empty] | 12.02.24 | 29.02.24 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Turbidity Meter | LE22M164-I-WS-WT-PR-5512 | LE22M164-I-WS-WT-PR-5512-A | E&H | Post-order technically cleared | 106 |  | Ramkumar |  | 09.01.23 | 09.01.23 | 17.01.24 | 24.01.24 | [8 empty] | 12.02.24 | 12.02.24 | 16.04.24 | T1 | 02.04.24 | E&H | 10.04.24 | 20.04.24 | 20.04.24 | 10.04.24 |  | 16.04.24 | 03.05.24 | 01.06.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Turbidity Meter | LE22M164-I-WS-WT-PR-5512 | LE22M164-I-WS-WT-PR-5512-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 11.01.24 | 07.02.24 | 12.02.24 | [7 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T2 | [7 empty] | 12.02.24 | 29.02.24 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Residual Chlorine Analyser | LE22M164-I-WS-WT-PR-5513 | LE22M164-I-WS-WT-PR-5513-A | E&H | Post-order technically cleared | 106 |  | Ramkumar |  | 09.01.23 | 09.01.23 | 17.01.24 | 24.01.24 | [8 empty] | 12.02.24 | 12.02.24 | 16.04.24 | T1 | 02.04.24 | E&H | 10.04.24 | 20.04.24 | 20.04.24 | 10.04.24 |  | 16.04.24 | 03.05.24 | 01.06.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Residual Chlorine Analyser | LE22M164-I-WS-WT-PR-5513 | LE22M164-I-WS-WT-PR-5513-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 11.01.24 | 07.02.24 | 12.02.24 | [7 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T2 | [7 empty] | 12.02.24 | 29.02.24 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Electromagnetic Flow Meter | LE22M164-I-WS-WT-PR-5514 | LE22M164-I-WS-WT-PR-5514-A | E&H | Sent to BU Operations | PR Closed |  | Ramkumar |  | 09.01.23 | 09.01.23 | 10.11.23 | 10.11.23 | [8 empty] | 10.11.23 | 10.11.23 | 10.11.23 | T2 | [7 empty] | 10.11.23 | 27.11.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Electromagnetic Flow Meter | LE22M164-I-WS-WT-PR-5514 | LE22M164-I-WS-WT-PR-5514-B | Siemens | Approved by Client | PR Closed |  | Chandrasekar |  | 09.01.23 | 09.01.23 | 07.09.23 | 12.09.23 | [8 empty] | 21.09.23 | 21.09.23 | 21.09.23 | T1 | 27.09.23 | Siemens | 09.01.24 | 10.01.24 | 10.01.24 | 10.01.24 | 10.01.24 | 21.09.23 | 08.10.23 | 26.11.23 | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Electromagnetic Flow Meter | LE22M164-I-WS-WT-PR-5514 | LE22M164-I-WS-WT-PR-5514-C | Forbes Marshall | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 27.09.23 | 07.11.23 | 08.11.23 | 09.11.23 | [6 empty] | 08.11.23 | 08.11.23 | 08.11.23 | T4 | [7 empty] | 08.11.23 | 25.11.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Electromagnetic Flow Meter | LE22M164-I-WS-WT-PR-5514 | LE22M164-I-WS-WT-PR-5514-D | Yogokawa | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 07.11.23 | 11.11.23 | [10 empty] | 08.11.23 | T3 | [7 empty] | 08.11.23 | 25.11.23 |  | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M164-I-WS-WT-PR-5515 | LE22M164-I-WS-WT-PR-5515-A | Autosys | Pre-order technically cleared | 97 |  |  |  | 09.01.23 | 09.01.23 | 08.11.23 | 15.11.23 | 21.11.23 | 06.12.23 | 18.12.23 | 03.01.24 | 16.01.24 | 24.01.24 |  |  | 29.04.24 | 29.04.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M164-I-WS-WT-PR-5515 | LE22M164-I-WS-WT-PR-5515-B | Centum Controls | Pre-order technically cleared | 106 |  |  |  | 09.01.23 | 09.01.23 | 23.01.24 | 30.01.24 | 15.02.24 | 02.03.24 | 05.03.24 | 19.03.24 | 26.03.24 | 02.04.24 | 20.04.24 |  | 20.04.24 | 20.04.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M164-I-WS-WT-PR-5515 | LE22M164-I-WS-WT-PR-5515-C | Schneider Electric | Pre-order technically cleared | 30 |  | Rushyendhar |  | 09.01.23 | 02.04.24 | 11.04.24 | 16.04.24 | 22.04.24 | 25.04.24 | 06.05.24 | 07.05.24 | 14.05.24 | 15.05.24 | 16.05.24 | 27.05.24 | 05.07.24 | 05.07.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M164-I-WS-WT-PR-5515 | LE22M164-I-WS-WT-PR-5515-D | Sai Applied Technologies | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 07.11.23 | 07.03.24 | 16.04.24 | 17.04.24 | [17 empty] | 10.07.24 | 27.07.24 | 25.09.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M164-I-WS-WT-PR-5515 | LE22M164-I-WS-WT-PR-5515-E | Cotmac | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 11.01.24 | 30.01.24 | [19 empty] | 10.07.24 | 27.07.24 | 25.09.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M164-I-WS-WT-PR-5515 | LE22M164-I-WS-WT-PR-5515-F | Mitsubishi Electric | Pre-order technically cleared | 29 |  | Sudarsan |  | 09.01.23 | 09.01.23 | 28.05.24 | 31.05.24 | 19.06.24 | 27.06.24 | 05.07.24 | 06.07.24 |  |  |  |  | 06.07.24 | 06.07.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Contol & Signal Cables | LE22M164-I-WS-WT-PR-5516 | LE22M164-I-WS-WT-PR-5516-A | Axelon | Pre-order technically cleared | 73 |  |  |  | 09.01.23 | 09.01.23 | 08.01.24 | 18.03.24 | 20.03.24 | 09.05.24 | 15.05.24 | 23.05.24 |  |  |  |  | 23.05.24 | 15.05.24 | [9 empty] | 20.07.24 | 06.08.24 | 05.10.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Contol & Signal Cables | LE22M164-I-WS-WT-PR-5516 | LE22M164-I-WS-WT-PR-5516-B | Polycab | Pre-order technically cleared | 73 |  |  |  | 09.01.23 | 09.01.23 | 08.01.24 | 18.03.24 | 20.03.24 | 09.05.24 | 15.05.24 | 23.05.24 |  |  |  |  | 23.05.24 | 15.05.24 | [9 empty] | 20.07.24 | 06.08.24 | 05.10.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Contol & Signal Cables | LE22M164-I-WS-WT-PR-5516 | LE22M164-I-WS-WT-PR-5516-C | Cords | Pre-order technically cleared | 73 |  |  |  | 09.01.23 | 09.01.23 | 24.02.24 | 15.03.24 | 03.04.24 | 23.05.24 | [6 empty] | 23.05.24 | 03.04.24 | [9 empty] | 20.07.24 | 06.08.24 | 05.10.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Instrumentation | Contol & Signal Cables | LE22M164-I-WS-WT-PR-5516 | LE22M164-I-WS-WT-PR-5516-D | Kei | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 21.02.24 | 15.03.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:07:16
Fazilka 1 | Instrumentation | Contol & Signal Cables | LE22M164-I-WS-WT-PR-5516 | LE22M164-I-WS-WT-PR-5516-E | RPG | Pre-order comments issued | 38 |  |  |  | 09.01.23 | 30.05.24 | 24.06.24 | 27.06.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | justin.v@lntecc.com-20.07.2024-14:30:02
Fazilka 1 | Electrical | Transformers | LE22M164-E-WS-CW-PR-4101 | LE22M164-E-WS-CW-PR-4101-A | Voltamp | Regret offer | PR Closed |  | 9173434252 | ks_vtlchn@voltamptransformers.com |  | 22.12.23 | 28.12.23 | 08.01.24 | 22.01.24 | 25.01.24 | 03.02.24 | 09.02.24 |  |  |  |  | 09.02.24 | 09.02.24 | 09.02.24 | T1 | [7 empty] | 09.02.24 | 26.02.24 | 26.04.24 | muthukumar.r@lntecc.com-01.07.2024-17:33:39
Fazilka 1 | Electrical | Transformers | LE22M164-E-WS-CW-PR-4101 | LE22M164-E-WS-CW-PR-4101-B | Voltech | Post-order technically cleared | 105 |  | 9600095932 | transformers@voltechgroup.com |  | 15.09.23 | 25.09.23 | 12.10.23 | 19.02.24 | 23.02.24 | [6 empty] | 23.02.24 | 23.02.24 | 23.02.24 | T1 | 25.03.24 | Voltech | 05.04.24 | 10.04.24 | 21.04.24 | 21.04.24 |  | 23.02.24 | 11.03.24 | 10.05.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | Transformers | LE22M164-E-WS-CW-PR-4101 | LE22M164-E-WS-CW-PR-4101-C | CGL | Regret offer | PR Closed |  | 7895462894 | agam.kumar@cgglobal.com |  | 25.09.23 | 28.09.23 | 12.10.23 | 27.11.23 | 20.12.23 | 02.01.24 | 09.01.24 |  |  |  |  | 09.01.24 | 09.01.24 | 09.01.24 | T1 | [7 empty] | 09.01.24 | 26.01.24 | 26.03.24 | muthukumar.r@lntecc.com-01.07.2024-17:33:39
Fazilka 1 | Electrical | 11kV Switchyard components | LE22M164-E-WS-CW-PR-4103 | LE22M164-E-WS-CW-PR-4103-A | Dushad Electricals | Pre-order technically cleared | 46 | Vendor name to be finalized by site team. |  |  |  | 16.04.24 | 15.05.24 | 15.05.24 | 15.04.24 | [7 empty] | 19.06.24 | 19.06.24 |  | T1 | [7 empty] | 19.06.24 | 06.07.24 | 04.09.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | 415V LT Switchgear | LE22M164-E-WS-CW-PR-4104 | LE22M164-E-WS-CW-PR-4104-A | SRCS | Post-order technically cleared | 48 |  | 8754013024 | operation@ragavendracontrol.com |  | 11.10.23 | 20.11.23 | 12.01.24 | 22.01.24 | 09.02.24 | 10.02.24 | 12.02.24 | 13.02.24 | 26.02.24 |  |  | 13.02.24 | 26.02.24 | 26.02.24 | T2 | 26.02.24 | SRCS | 15.05.24 | 24.05.24 | 17.06.24 | 17.06.24 |  | 26.02.24 | 14.03.24 | 26.04.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | 415V LT Switchgear | LE22M164-E-WS-CW-PR-4104 | LE22M164-E-WS-CW-PR-4104-B | Coronet | Regret offer | PR Closed |  | 8447476814 | laxman@coronet.in |  | 06.10.23 | 30.11.23 | 08.02.24 | 26.02.24 | 02.03.24 | [6 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T2 | [7 empty] | 02.03.24 | 19.03.24 | 18.05.24 | muthukumar.r@lntecc.com-01.07.2024-17:33:39
Fazilka 1 | Electrical | 415V LT Switchgear | LE22M164-E-WS-CW-PR-4104 | LE22M164-E-WS-CW-PR-4104-C | Universal | Regret offer | PR Closed |  | 9500095075 | deepak@upe.co.in |  | 20.09.23 | 27.09.23 | 20.10.23 | 06.11.23 | 18.11.23 | 07.12.23 | 23.01.24 |  |  |  |  | 23.01.24 | 23.01.24 | 23.01.24 | T2 | [7 empty] | 23.01.24 | 09.02.24 | 09.04.24 | muthukumar.r@lntecc.com-01.07.2024-17:33:39
Fazilka 1 | Electrical | Power and Control Cables & Cable Glands and Lugs | LE22M164-E-WS-CW-PR-4105 | LE22M164-E-WS-CW-PR-4105 |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | HT Termination Kits | LE22M164-E-WS-CW-PR-4106 | LE22M164-E-WS-CW-PR-4106-A | Local vendor | Enquiry yet to float | NA | Vendor name to be finalized by site team. | [25 empty] | 14.08.24 | 31.08.24 | 30.10.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | Diesel Generator | LE22M164-E-WS-CW-PR-4107 | LE22M164-E-WS-CW-PR-4107-A | IEC Genset | Pre-order technically cleared | 227 |  | 9311818808 | niraj.sharma@iecgensets.com |  | 27.09.23 | 03.10.23 | 18.10.23 | [8 empty] | 21.12.23 | 21.12.23 | 21.12.23 | T3 | [7 empty] | 21.12.23 | 07.01.24 | 07.03.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | Diesel Generator | LE22M164-E-WS-CW-PR-4107 | LE22M164-E-WS-CW-PR-4107-B | Sudhir Power Ltd | Pre-order technically cleared | 184 |  | 8800282623 | sarbjeetsingh@sudhirpower.com |  | 03.10.23 | 12.10.23 | 30.10.23 | 22.11.23 | 29.11.23 | 02.01.24 | 08.01.24 | 19.01.24 | 25.01.24 |  |  | 02.02.24 | 02.02.24 | 02.02.24 | T3 | [7 empty] | 02.02.24 | 19.02.24 | 19.04.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | Diesel Generator | LE22M164-E-WS-CW-PR-4107 | LE22M164-E-WS-CW-PR-4107-C | Goel Power Engineers | Pre-order technically cleared | 227 |  | 0222837 7162 | marketing@goelpower.in |  | 03.10.23 | 03.10.23 | 18.10.23 | 21.11.23 | 22.11.23 | 24.11.23 | 11.12.23 | 19.12.23 | 20.12.23 |  |  | 21.12.23 | 21.12.23 | 21.12.23 | T3 | [7 empty] | 21.12.23 | 07.01.24 | 07.03.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | Lighting Materials | LE22M164-E-WS-CW-PR-4108 | LE22M164-E-WS-CW-PR-4108-A | Local vendor | Enquiry yet to float | NA | Vendor name to be finalized by site team. | [25 empty] | 15.08.24 | 01.09.24 | 31.10.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | Earthing & Lightning protection materials with accessories | LE22M164-E-WS-CW-PR-4109 | LE22M164-E-WS-CW-PR-4109-A | Local vendor | Enquiry yet to float | NA | Vendor name to be finalized by site team. | [25 empty] | 15.08.24 | 01.09.24 | 31.10.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | Electrical Safety Items | LE22M164-E-WS-CW-PR-4110 | LE22M164-E-WS-CW-PR-4110-A | Local vendor | Enquiry yet to float | NA | Vendor name to be finalized by site team. | [25 empty] | 22.08.24 | 08.09.24 | 07.11.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | LPBS | LE22M164-E-WS-CW-PR-4111 | LE22M164-E-WS-CW-PR-4111-A | SRCS | Post-order technically cleared | 48 |  | 8754013024 | operation@ragavendracontrol.com |  | 11.10.23 | 20.11.23 | 12.01.24 | 22.01.24 | 09.02.24 | 10.02.24 | 12.02.24 | 13.02.24 | 26.02.24 |  |  | 13.02.24 | 26.02.24 | 26.02.24 | T2 | 26.02.24 | SRCS | 15.05.24 | 24.05.24 | 17.06.24 | 17.06.24 |  | 26.02.24 | 14.03.24 | 26.04.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | LPBS | LE22M164-E-WS-CW-PR-4111 | LE22M164-E-WS-CW-PR-4111-B | CORONET | Regret offer | PR Closed |  | 8447476814 | laxman@coronet.in |  | 06.10.23 | 30.11.23 | 08.02.24 | 26.02.24 | 02.03.24 | [6 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T2 | [7 empty] | 02.03.24 | 19.03.24 | 18.05.24 | muthukumar.r@lntecc.com-01.07.2024-17:33:39
Fazilka 1 | Electrical | LPBS | LE22M164-E-WS-CW-PR-4111 | LE22M164-E-WS-CW-PR-4111-C | Universal | Regret offer | PR Closed |  | 9500095075 | deepak@upe.co.in |  | 20.09.23 | 27.09.23 | 20.10.23 | 06.11.23 | 18.11.23 | 07.12.23 | 23.01.24 |  |  |  |  | 23.01.24 | 23.01.24 | 23.01.24 | T2 | [7 empty] | 23.01.24 | 09.02.24 | 09.04.24 | muthukumar.r@lntecc.com-01.07.2024-17:33:39
Fazilka 1 | Electrical | Cable Trays & its supports | LE22M164-E-WS-CW-PR-4112 | LE22M164-E-WS-CW-PR-4112-A | Local vendor | Enquiry yet to float | NA | Vendor name to be finalized by site team. | [25 empty] | 20.08.24 | 06.09.24 | 05.11.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | HT Panel | LE22M164-E-WS-CW-PR-4113 | LE22M164-E-WS-CW-PR-4113-A | Coronet | Post-order technically cleared | 69 |  | 8447476814 | laxman@coronet.in |  | 06.10.23 | 30.11.23 | 22.01.24 | 29.01.24 | 05.02.24 | [6 empty] | 05.02.24 | 05.02.24 | 05.02.24 | T1 | 12.04.24 | Coronet | 14.05.24 | 14.05.24 | 27.05.24 | 27.05.24 |  | 05.02.24 | 22.02.24 | 22.04.24 | bhuvaneswari.natarajan@lntecc.com-10.07.2024-17:09:26
Fazilka 1 | Electrical | HT Panel | LE22M164-E-WS-CW-PR-4113 | LE22M164-E-WS-CW-PR-4113-B | Universal | Regret offer | PR Closed |  | 95000 95075 | deepak@upe.co.in |  | 20.09.23 | 20.09.23 | 04.10.23 | 14.11.23 | 07.02.24 | 17.02.24 | 19.02.24 |  |  |  |  | 19.02.24 | 19.02.24 | 19.02.24 | T1 | [7 empty] | 19.02.24 | 07.03.24 | 06.05.24 | muthukumar.r@lntecc.com-01.07.2024-17:33:39
Fazilka 1 | Electrical | HT Panel | LE22M164-E-WS-CW-PR-4113 | LE22M164-E-WS-CW-PR-4113-C | HTS | Regret offer | PR Closed |  | 9370797168 | vikas.bhure@htswitchgears.com |  | 11.10.23 | 12.10.23 | 03.11.23 | 21.11.23 | 22.01.24 | [6 empty] | 22.01.24 | 22.01.24 | 22.01.24 | T1 | [7 empty] | 22.01.24 | 08.02.24 | 08.04.24 | muthukumar.r@lntecc.com-01.07.2024-17:33:39
Fazilka 2 | Process | Scraper mechanism for Reactor clarifier | LE22M163-P-WS-WT-PR-2202 | LE22M163-P-WS-WT-PR-2202-A | TRIVENI | Post-order technically cleared | 73 |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 30.11.22 | 30.11.22 | 16.09.23 | 25.09.23 | [8 empty] | 20.11.23 | 20.11.23 | 11.12.23 | T1 | 02.03.24 | TRIVENI | 20.03.24 | 15.05.24 | 23.05.24 | 23.05.24 |  | 11.12.23 | 28.12.23 | 26.02.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Scraper mechanism for Reactor clarifier | LE22M163-P-WS-WT-PR-2202 | LE22M163-P-WS-WT-PR-2202-B | FILSEP | Sent to BU Operations | PR Closed |  | Sivamurgan | filsepengineers@gmail.com | 30.11.22 | 30.11.22 | 06.11.23 | 13.11.23 | [8 empty] | 11.12.23 | 11.12.23 | 11.12.23 | T2 | [7 empty] | 11.12.23 | 28.12.23 | 26.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Air Blower | LE22M163-P-WS-WT-PR-2203 | LE22M163-P-WS-WT-PR-2203-A | KAY | Sent to BU Operations | PR Closed |  | Manish Arya | manish@kayblowers.com | 30.11.22 | 30.11.22 | 05.09.23 | 11.09.23 | [8 empty] | 21.10.23 | 21.10.23 | 18.11.23 | T2 | [7 empty] | 18.11.23 | 05.12.23 | 03.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Air Blower | LE22M163-P-WS-WT-PR-2203 | LE22M163-P-WS-WT-PR-2203-B | EVEREST | Post-order technically cleared | 25 |  |  | Saif.Ali@irco.com | 30.11.22 | 30.11.22 | 13.09.23 | 15.09.23 | [8 empty] | 18.11.23 | 18.11.23 | 18.11.23 | T1 | 26.04.24 | EVEREST | 04.06.24 | 11.06.24 | 06.07.24 | 10.07.24 |  | 18.11.23 | 05.12.23 | 03.02.24 | SNEHA-S@lntecc.com-11.07.2024-16:54:15
Fazilka 2 | Process | Service Water pump | LE22M163-P-WS-WT-PR-2204 | LE22M163-P-WS-WT-PR-2204-A | KSB | Awaiting post-offer from vendor | 73 |  |  | dhananjay.bidnur@ksb.com | 30.11.22 | 30.11.22 | 29.02.24 | 05.03.24 | 27.03.24 | 29.03.24 | [6 empty] | 04.04.24 | 08.04.24 | 09.04.24 | T1 | 23.05.24 | KSB | [5 empty] | 09.04.24 | 26.04.24 | 25.06.24 | SNEHA-S@lntecc.com-11.07.2024-17:26:55
Fazilka 2 | Process | Service Water pump | LE22M163-P-WS-WT-PR-2204 | LE22M163-P-WS-WT-PR-2204-B | KBL | Regret offer | PR Closed |  |  | mohan.kumar@kbl.co.in | 30.11.22 | 30.11.22 | 31.03.24 | 05.04.24 | 07.04.24 | 09.04.24 | [20 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Agitator | LE22M163-P-WS-WT-PR-2205 | LE22M163-P-WS-WT-PR-2205-A | TRIVENI | Regret offer | PR Closed |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 21.11.22 | 21.11.22 | 17.11.23 | 21.11.23 | [22 empty] | SNEHA-S@lntecc.com-17.05.2024-11:56:10
Fazilka 2 | Process | Agitator | LE22M163-P-WS-WT-PR-2205 | LE22M163-P-WS-WT-PR-2205-B | FFP | Post-order technically cleared | 24 |  | Ganesh | fibrein@gmail.com | 21.11.22 | 21.11.22 | 17.11.23 | 21.11.23 | 20.06.24 | 21.06.24 | [6 empty] | 05.02.24 | 05.02.24 | 05.02.24 | T1 | 15.05.24 | FFP | 16.05.24 | 24.05.24 | 10.07.24 | 11.07.24 |  | 05.02.24 | 22.02.24 | 22.04.24 | SNEHA-S@lntecc.com-11.07.2024-17:25:02
Fazilka 2 | Process | WTP Sluice gates | LE22M163-P-WS-WT-PR-2206 | LE22M163-P-WS-WT-PR-2206-B | ORIENTAL | Approved by Client | PR Closed |  | Sanjay Mahensaria | orientalcastings@gmail.com | 22.11.22 | 22.11.22 | 12.09.23 | 15.09.23 | 22.09.23 | 29.09.23 | 06.10.23 | 07.10.23 | 13.10.23 | 13.10.23 |  |  | 13.10.23 | 13.10.23 | 01.11.23 | T1 | 29.11.23 | ORIENTAL | 29.11.23 | 02.12.23 | 20.12.23 | 22.12.23 | 15.04.24 | 01.11.23 | 18.11.23 | 17.01.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Chlorination system | LE22M163-P-WS-WT-PR-2207 | LE22M163-P-WS-WT-PR-2207-A | METITO | Sent to BU Operations | PR Closed |  |  |  | 19.12.22 | 19.12.22 | 25.10.23 | 27.10.23 | 08.11.23 | 17.11.23 | 29.11.23 | 30.11.23 |  |  |  |  | 30.11.23 | 30.11.23 | 01.12.23 | T1 | [7 empty] | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Chlorination system | LE22M163-P-WS-WT-PR-2207 | LE22M163-P-WS-WT-PR-2207-B | CHLOROTECH | Sent to BU Operations | PR Closed |  |  |  | 19.12.22 | 19.12.22 | 15.09.23 | 03.10.23 | 13.10.23 | 18.10.23 | 25.10.23 | 27.10.23 |  |  |  |  | 27.10.23 | 27.10.23 | 01.12.23 | T3 | [7 empty] | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Chlorination system | LE22M163-P-WS-WT-PR-2207 | LE22M163-P-WS-WT-PR-2207-C | ZION | Post-order technically cleared | 125 |  | Deepak Santaram | deepak@ziontech.in | 19.12.22 | 19.12.22 | 08.11.23 | 17.11.23 | 29.11.23 | 30.11.23 | 01.12.23 | [5 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T2 | 11.01.24 | ZION | 11.01.24 | 23.01.24 | 24.03.24 | 01.04.24 |  | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Chlorine Tonners | LE22M163-P-WS-WT-PR-2208 | LE22M163-P-WS-WT-PR-2208-A | METITO | Sent to BU Operations | PR Closed |  |  |  | 28.12.22 | 28.12.22 | 25.10.23 | 27.10.23 | 08.11.23 | 17.11.23 | 29.11.23 | 30.11.23 |  |  |  |  | 30.11.23 | 30.11.23 | 01.12.23 | T1 | [7 empty] | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Chlorine Tonners | LE22M163-P-WS-WT-PR-2208 | LE22M163-P-WS-WT-PR-2208-B | CHLOROTECH | Sent to BU Operations | PR Closed |  |  |  | 28.12.22 | 28.12.22 | 15.09.23 | 03.10.23 | 13.10.23 | 18.10.23 | 25.10.23 | 27.10.23 |  |  |  |  | 27.10.23 | 27.10.23 | 01.12.23 | T3 | [7 empty] | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Chlorine Tonners | LE22M163-P-WS-WT-PR-2208 | LE22M163-P-WS-WT-PR-2208-C | ZION | Post-order technically cleared | 125 |  | Deepak Santaram | deepak@ziontech.in | 28.12.22 | 28.12.22 | 08.11.23 | 17.11.23 | 29.11.23 | 30.11.23 | 01.12.23 | [5 empty] | 01.12.23 | 01.12.23 | 01.12.23 | T2 | 11.01.24 | ZION | 11.01.24 | 23.01.24 | 24.03.24 | 01.04.24 |  | 01.12.23 | 18.12.23 | 16.02.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Sludge thickener | LE22M163-P-WS-WT-PR-2209 | LE22M163-P-WS-WT-PR-2209-A | TRIVENI | Post-order technically cleared | 93 |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 21.11.22 | 21.11.22 | 16.09.23 | 21.09.23 | 27.09.23 | 28.09.23 | [6 empty] | 07.12.23 | 08.12.23 | 08.12.23 | T3 | 14.02.24 | TRIVENI | 14.02.24 | 20.02.24 | 03.05.24 | 03.05.24 |  | 08.12.23 | 25.12.23 | 23.02.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Sludge thickener | LE22M163-P-WS-WT-PR-2209 | LE22M163-P-WS-WT-PR-2209-B | VOLTAS | Sent to BU Operations | PR Closed |  |  | rohankakde@voltas.co | 21.11.22 | 21.11.22 | 30.10.23 | 31.10.23 | 16.11.23 | 18.11.23 | [6 empty] | 18.11.23 | 18.11.23 | 08.12.23 | T1 | [7 empty] | 08.12.23 | 25.12.23 | 23.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Sludge thickener | LE22M163-P-WS-WT-PR-2209 | LE22M163-P-WS-WT-PR-2209-C | SRITECH | Sent to BU Operations | PR Closed |  | Mohan P | mohan@sritechindia.com | 21.11.22 | 21.11.22 | 03.11.23 | 03.11.23 | 06.11.23 | 13.11.23 | 14.11.23 | 14.11.23 |  |  |  |  | 14.11.23 | 14.11.23 | 08.12.23 | T4 | [7 empty] | 08.12.23 | 25.12.23 | 23.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Sludge thickener | LE22M163-P-WS-WT-PR-2209 | LE22M163-P-WS-WT-PR-2209-D | FILSEP | Sent to BU Operations | PR Closed |  | Sivamurgan | filsepengineers@gmail.com | 21.11.22 | 21.11.22 | 06.11.23 | 13.11.23 | 22.11.23 | 24.11.23 | 07.12.23 | 07.12.23 |  |  |  |  | 07.12.23 | 07.12.23 | 08.12.23 | T2 | [7 empty] | 08.12.23 | 25.12.23 | 23.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Filter media | LE22M163-P-WS-WT-PR-2210 | LE22M163-P-WS-WT-PR-2210-A | GLOBAL ADSORBENTS | Regret offer | PR Closed |  |  |  | 19.12.22 | 19.12.22 | 16.09.23 | 20.09.23 | [22 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Rechlorination system | LE22M163-P-WS-WT-PR-2211 | LE22M163-P-WS-WT-PR-2211-A | VERITO | Sent to BU Operations | 100 |  |  |  | 19.01.24 | 19.01.24 | 01.04.24 | 03.04.24 | [8 empty] | 17.04.24 | 20.04.24 | 26.04.24 | T1 | [7 empty] | 26.04.24 | 13.05.24 | 12.07.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Centrifuge | LE22M163-P-WS-WT-PR-2212 | LE22M163-P-WS-WT-PR-2212-A | HILLER | Approved by Client | PR Closed |  | Mitali Ojha | enquiry@hillerindia.com | 30.11.22 | 30.11.22 | 18.07.23 | 18.07.23 | [8 empty] | 03.11.23 | 03.11.23 | 02.12.23 | T1 | 02.01.24 | HILLER | 02.01.24 | 08.01.24 | 03.02.24 | 03.02.24 | 18.05.24 | 02.12.23 | 19.12.23 | 17.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Centrifuge | LE22M163-P-WS-WT-PR-2212 | LE22M163-P-WS-WT-PR-2212-B | ALFA LAVAL | Regret offer | PR Closed |  |  |  | 30.11.22 | 30.11.22 | 11.10.23 | 12.10.23 | [8 empty] | 30.10.23 | 30.10.23 | 02.12.23 | T3 | [7 empty] | 02.12.23 | 19.12.23 | 17.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Centrifuge | LE22M163-P-WS-WT-PR-2212 | LE22M163-P-WS-WT-PR-2212-C | MSEL | Sent to BU Operations | PR Closed |  | Tapan Datta | tapan.datta@msel.co.in | 30.11.22 | 30.11.22 | 20.11.23 | 22.11.23 | [8 empty] | 02.12.23 | 02.12.23 | 02.12.23 | T2 | [7 empty] | 02.12.23 | 19.12.23 | 17.02.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | screw pump | LE22M163-P-WS-WT-PR-2213 | LE22M163-P-WS-WT-PR-2213-A | TUSHACO | Regret offer | PR Closed | Awaiting revised motor documents from vendor |  |  | 28.12.22 | 28.12.22 | 14.02.24 | 20.02.24 | 18.05.24 | 18.05.24 | [20 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | screw pump | LE22M163-P-WS-WT-PR-2213 | LE22M163-P-WS-WT-PR-2213-B | ROTO | Regret offer | PR Closed |  | Anandan Ethiraj | chn1@rotopumps.com | 28.12.22 | 28.12.22 | 14.03.24 | 21.03.24 | 08.04.24 | 08.04.24 | 10.04.24 | 10.04.24 | [18 empty] | SNEHA-S@lntecc.com-17.05.2024-11:56:10
Fazilka 2 | Process | screw pump | LE22M163-P-WS-WT-PR-2213 | LE22M163-P-WS-WT-PR-2213-C | FLOSYS | Sent to BU Operations | 65 |  | Manoj | sales@flosys.in | 28.12.22 | 28.12.22 | 26.04.24 | 06.05.24 | 22.05.24 | [7 empty] | 29.05.24 | 29.05.24 | 31.05.24 | T1 | [7 empty] | 31.05.24 | 17.06.24 | 16.08.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Backwash Reservoir pump | LE22M163-P-WS-WT-PR-2214 | LE22M163-P-WS-WT-PR-2214-A | KBL | Regret offer | PR Closed |  | Mohan Kumar | mohan.kumar@kbl.co.in | 30.11.22 | 30.11.22 | 17.11.23 | 23.11.23 | 24.11.23 | 24.11.23 | [20 empty] | SNEHA-S@lntecc.com-17.05.2024-11:56:10
Fazilka 2 | Process | Backwash Reservoir pump | LE22M163-P-WS-WT-PR-2214 | LE22M163-P-WS-WT-PR-2214-B | KSB | Sent to BU Operations | 90 |  |  | dhananjay.bidnur@ksb.com | 30.11.22 | 30.11.22 | 28.02.24 | 04.03.24 | 19.03.24 | 22.03.24 | 08.04.24 | 08.04.24 |  |  |  |  | 22.04.24 | 24.04.24 | 06.05.24 | T1 | [7 empty] | 06.05.24 | 23.05.24 | 22.07.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Backwash Reservoir pump | LE22M163-P-WS-WT-PR-2214 | LE22M163-P-WS-WT-PR-2214-C | WILO | Sent to BU Operations | 90 |  |  | manikkandan.pr@wilo.com | 30.11.22 | 30.11.22 | 22.02.24 | 04.03.24 | 22.03.24 | 29.03.24 | [6 empty] | 04.04.24 | 05.04.24 | 06.05.24 | T2 | [7 empty] | 06.05.24 | 23.05.24 | 22.07.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Submersible pump | LE22M163-P-WS-WT-PR-2215 | LE22M163-P-WS-WT-PR-2215-A | AQUA | Pre-order technically cleared | 69 |  |  | chennai@aquapumps.com | 30.11.22 | 30.11.22 | 10.04.24 | 24.04.24 | 27.05.24 | 27.05.24 | [6 empty] | 27.05.24 | 27.05.24 | 27.05.24 | T1 | [7 empty] | 27.05.24 | 13.06.24 | 12.08.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Electrical hoist | LE22M163-P-WS-WT-PR-2216 | LE22M163-P-WS-WT-PR-2216-A | Eddy cranes | Regret offer | PR Closed |  | info@eddycranes.in | 22.11.22 | 19.12.23 | 02.01.24 | 04.01.24 | 06.01.24 | 08.01.24 | 08.01.24 | [20 empty] | SNEHA-S@lntecc.com-17.05.2024-11:56:10
Fazilka 2 | Process | Electrical hoist | LE22M163-P-WS-WT-PR-2216 | LE22M163-P-WS-WT-PR-2216-D | Brady | Regret offer | PR Closed |  | srinivasan@bradys.in | 22.11.22 | 17.02.24 | 17.02.24 | [24 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Manual chain pulley block | LE22M163-P-WS-WT-PR-2218 | LE22M163-P-WS-WT-PR-2218-A | BRADYS | Regret offer | PR Closed |  |  | srinivasan@bradys.in | 26.12.22 | 26.12.22 | 14.2.24 | [23 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Manual chain pulley block | LE22M163-P-WS-WT-PR-2218 | LE22M163-P-WS-WT-PR-2218-B | JAPS | Sent to BU Operations | 121 |  |  | sales.japs@gmail.com | 26.12.22 | 26.12.22 | 03.04.24 | 03.04.24 | 04.04.24 | 05.04.24 | [6 empty] | 05.04.24 | 05.04.24 | 05.04.24 | T1 | [7 empty] | 05.04.24 | 22.04.24 | 21.06.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Manual chain pulley block | LE22M163-P-WS-WT-PR-2218 | LE22M163-P-WS-WT-PR-2218-C | Indef | Sent to BU Operations | 72 |  |  | mkm@indef.com | 26.12.22 | 26.12.22 | 16.04.24 | 17.04.24 | 23.04.24 | 15.05.24 | [6 empty] | 20.05.24 | 22.05.24 | 24.05.24 | T2 | [7 empty] | 24.05.24 | 10.06.24 | 09.08.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Dosing pump | LE22M163-P-WS-WT-PR-2219 | LE22M163-P-WS-WT-PR-2219-A | Milton Roy | Sent to BU Operations | PR Closed |  |  | proposal@fluidoze.com | 30.11.22 | 30.11.22 | 02.11.23 | 09.11.23 | [8 empty] | 22.11.23 | 24.11.23 | 15.02.24 | T2 | [7 empty] | 15.02.24 | 03.03.24 | 02.05.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Dosing pump | LE22M163-P-WS-WT-PR-2219 | LE22M163-P-WS-WT-PR-2219-B | Positive Metering | Post-order technically cleared | 106 |  |  | offers1@positivemetering.com | 30.11.22 | 30.11.22 | 01.12.23 | 06.12.23 | 13.02.24 | 13.02.24 | [6 empty] | 15.02.24 | 15.02.24 | 15.02.24 | T1 | 22.03.24 | Positive Metering | 22.03.24 | 29.03.24 | 16.04.24 | 20.04.24 |  | 15.02.24 | 03.03.24 | 02.05.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | DWPE tanks with Agitator | LE22M163-P-WS-WT-PR-2221 | LE22M163-P-WS-WT-PR-2221-A | FFP | Post-order comments issued | 50 |  | Yogesh Shah / Ganesh | fibrein@gmail.com | 28.12.22 | 28.12.22 | 06.03.24 | 15.03.24 | 06.04.24 | 06.04.24 | [6 empty] | 06.04.24 | 06.04.24 | 06.04.24 | T1 | 06.05.24 | FFP | 13.06.24 | 15.06.24 | 18.07.24 |  |  | 06.04.24 | 23.04.24 | 22.06.24 | SNEHA-S@lntecc.com-23.07.2024-10:40:37
Fazilka 2 | Process | Sampling pump | LE22M163-P-WS-WT-PR-2222 | LE22M163-P-WS-WT-PR-2222-A | SITE PROCUREMENT | Regret offer | PR Closed |  |  |  | 21.12.22 | 21.12.22 | [24 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Submersible mixer | LE22M163-P-WS-WT-PR-2223 | LE22M163-P-WS-WT-PR-2223-A | FFP | Post-order technically cleared | 58 |  | Ganesh | fibrein@gmail.com | 19.12.22 | 19.12.22 | 02.12.23 | 05.12.23 | 15.02.24 | 15.02.24 | [6 empty] | 19.02.24 | 22.02.24 | 22.02.24 | T1 | 01.04.24 | FFP | 16.05.24 | 21.05.24 | 07.06.24 | 07.06.24 | 07.06.24 | 22.02.24 | 10.03.24 | 09.05.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Submersible mixer | LE22M163-P-WS-WT-PR-2223 | LE22M163-P-WS-WT-PR-2223-B | SULZER | Sent to BU Operations | PR Closed |  | Dawood Basha | wwtechennai@gmail.com | 19.12.22 | 19.12.22 | 09.01.24 | 10.01.24 | [8 empty] | 15.02.24 | 17.02.24 | 22.02.24 | T2 | [7 empty] | 22.02.24 | 10.03.24 | 09.05.24 | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Dewatering pump | LE22M163-P-WS-WT-PR-2224 | LE22M163-P-WS-WT-PR-2224-A | AQUA | Pre-order technically cleared | 69 |  |  | chennai@aquapumps.com | 27.12.22 | 27.12.22 | 10.04.24 | 24.04.24 | 27.05.24 | 27.05.24 | [6 empty] | 27.05.24 | 27.05.24 | 27.05.24 | T1 | [7 empty] | 27.05.24 | 13.06.24 | 12.08.24 | SNEHA-S@lntecc.com-11.07.2024-16:52:53
Fazilka 2 | Process | Dissolving tray | LE22M163-P-WS-WT-PR-2225 | LE22M163-P-WS-WT-PR-2225-A | SITE PROCUREMENT | Regret offer | PR Closed |  |  |  | 30.11.22 | 30.11.22 | [24 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Trolley | LE22M163-P-WS-WT-PR-2226 | LE22M163-P-WS-WT-PR-2226-A | SITE PROCUREMENT | Regret offer | PR Closed |  |  |  | 29.12.22 | 29.12.22 | [24 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Platform weighing machine | LE22M163-P-WS-WT-PR-2227 | LE22M163-P-WS-WT-PR-2227-A | SITE PROCUREMENT | Regret offer | PR Closed |  |  |  | 28.12.22 | 28.12.22 | [24 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | Exhaust fan | LE22M163-P-WS-WT-PR-2228 | LE22M163-P-WS-WT-PR-2228-A | SITE PROCUREMENT | Regret offer | PR Closed |  |  |  | 29.12.22 | 29.12.22 | [24 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Process | lab equipment | LE22M163-P-WS-WT-PR-2229 | LE22M163-P-WS-WT-PR-2229-A | SITE PROCUREMENT | Regret offer | PR Closed |  |  |  | 30.11.22 | 30.11.22 | [24 empty] | SNEHA-S@lntecc.com-03.07.2024-19:02:30
Fazilka 2 | Mechanical | EOT Crane | LE22M163-M-WS-PR-DC-1002 | LE22M163-M-WS-PR-DC-1002-A | JAPS | Post-order technically cleared | 136 |  | Gaurang Shah 99789 00589 | Jsales.japs@gmail.com |  | 01.12.23 | 29.02.24 | 29.02.24 | [8 empty] | 29.02.24 | 29.02.24 | 29.02.24 | T1 | 29.02.24 | JAPS | 19.03.24 | 19.03.24 | 21.03.24 | 21.03.24 |  | 29.02.24 | 17.03.24 | 29.04.24 | svcn@lntecc.com-26.07.2024-17:40:06
Fazilka 2 | Mechanical | Pump House Valves | LE22M163-M-WS-PR-DC-1003 | LE22M163-M-WS-PR-DC-1003-A | AVK | Post-order technically cleared | 156 |  | Subash 91769 66455 | subhash@avkindia.com |  | 01.12.23 | 30.12.23 | 30.12.23 | [8 empty] | 30.12.23 | 30.12.23 | 30.12.23 | T1 | 30.12.23 | AVK | 01.03.24 | 01.03.24 | 01.03.24 | 01.03.24 |  | 30.12.23 | 16.01.24 | 28.02.24 | svcn@lntecc.com-26.07.2024-17:40:06
Fazilka 2 | Mechanical | Pump House Valves | LE22M163-M-WS-PR-DC-1003 | LE22M163-M-WS-PR-DC-1003-B | VAG | Approved by Client | PR Closed |  | Gopalkrishnan 91769 66478 | N.Gopalakrishnan@vag-group.com |  | 01.12.23 | 10.01.24 | 10.01.24 | [8 empty] | 10.01.24 | 10.01.24 | 10.01.24 | T1 | 10.01.24 | VAG | 28.02.24 | 01.03.24 | 01.03.24 | 01.03.24 | 10.04.24 | 10.01.24 | 27.01.24 | 10.03.24 | svcn@lntecc.com-03.07.2024-15:10:33
Fazilka 2 | Mechanical | Dismantling Joints | LE22M163-M-WS-PR-DC-1004 | LE22M163-M-WS-PR-DC-1004-A | Precise | Post-order technically cleared | 93 |  | Shailendra Mehta 93777 73186 | sjm@vedantagroup.net |  | 01.12.23 | 12.03.24 | 12.03.24 | [8 empty] | 12.03.24 | 12.03.24 | 12.03.24 | T1 | 12.03.24 | Precise | 29.04.24 | 03.05.24 | 03.05.24 | 03.05.24 |  | 12.03.24 | 29.03.24 | 11.05.24 | svcn@lntecc.com-26.07.2024-17:40:06
Fazilka 2 | Mechanical | Sluice Gate | LE22M163-M-WS-PR-SG-1005 | LE22M163-M-WS-PR-DC-1005-A | JASH | Approved by Client | PR Closed |  | Prateek Verma 91-731-6732700 | lpgsouth2@jashindia.com |  | 01.12.23 | 01.12.23 | 01.12.23 | [8 empty] | 18.12.23 | 19.12.23 | 19.12.23 | T1 | 19.12.23 | JASH | 19.12.23 | 19.12.23 | 19.12.23 | 19.12.23 | 15.01.24 | 18.12.23 | 04.01.24 | 17.02.24 | svcn@lntecc.com-03.07.2024-15:10:33
Fazilka 2 | Mechanical | Exhaust Fans | LE22M163-M-WS-PR-VS-1006 | LE22M163-M-WS-PR-DC-1006-A |  | Enquiry yet to float | NA | [26 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-02.07.2024-10:49:01
Fazilka 2 | Mechanical | De watering Pumps | LE22M163-M-WS-PR-DW-1007 | LE22M163-M-WS-PR-DC-1007-A | Aqua | Pre-order comments issued | 9 |  | S.T.Sambandam 8144003131 | chennai@aquapumps.com |  | 05.07.24 | 24.07.24 | 26.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:40:06
Fazilka 2 | Mechanical | Pipe Line Valves | LE22M163-M-WS-PR-DC-1008 | LE22M163-M-WS-PR-DC-1008-A | AVK | Post-order technically cleared | 156 |  | Subash 91769 66455 | subhash@avkindia.com |  | 01.12.23 | 01.12.23 | 01.12.23 | [8 empty] | 30.12.23 | 30.12.23 | 30.12.23 | T1 | 30.12.23 | AVK | 01.03.24 | 01.03.24 | 01.03.24 | 01.03.24 |  | 30.12.23 | 16.01.24 | 28.02.24 | svcn@lntecc.com-26.07.2024-17:40:06
Fazilka 2 | Mechanical | Pipe Line Valves | LE22M163-M-WS-PR-DC-1008 | LE22M163-M-WS-PR-DC-1008-B | VAG | Approved by Client | PR Closed |  | Gopalkrishnan 91769 66478 | N.Gopalakrishnan@vag-group.com |  | 01.12.23 | 01.12.23 | 01.12.23 | [8 empty] | 10.01.24 | 10.01.24 | 10.01.24 | T1 | 10.01.24 | VAG | 28.02.24 | 28.02.24 | 01.03.24 | 01.03.24 | 10.04.24 | 10.01.24 | 27.01.24 | 10.03.24 | svcn@lntecc.com-03.07.2024-15:10:33
Fazilka 2 | Mechanical | Surge Equipments | LE22M163-M-WS-PR-DC-1009 | LE22M163-M-WS-PR-DC-1009-A |  | Enquiry yet to float | NA | [26 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-02.07.2024-10:49:01
Fazilka 2 | Mechanical | HSC Pumps | LE22M163-M-WS-PR-HP-1001 | LE22M163-M-WS-PR-HP-1001-A | KSB | Post-order technically cleared | 92 |  | Dhananjay Diwakar Bidnur 99608 66738 | dhanjay.bidnur@ksb.com |  | 01.12.23 | 04.05.24 | 04.05.24 | [8 empty] | 04.05.24 | 04.05.24 | 04.05.24 | T1 | 04.05.24 | KSB | 04.05.24 | 04.05.24 | 04.05.24 | 04.05.24 |  | 04.05.24 | 21.05.24 | 03.07.24 | svcn@lntecc.com-26.07.2024-17:40:06
Fazilka 2 | Instrumentation | Pressure Gauge/ Compound Pressure Gauge | LE22M163-I-WS-WT-PR-5501 | LE22M163-I-WS-WT-PR-5501-A | H Guru | Sent to BU Operations | PR Closed |  | Shyamlal |  | 09.01.23 | 09.01.23 | 27.10.23 | 13.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 13.12.23 | T2 | [7 empty] | 13.12.23 | 30.12.23 | 28.02.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Pressure Gauge/ Compound Pressure Gauge | LE22M163-I-WS-WT-PR-5501 | LE22M163-I-WS-WT-PR-5501-B | Forbes Marshall | Post-order technically cleared | 20 |  |  |  | 09.01.23 | 09.01.23 | 27.10.23 | 13.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 13.12.23 | T1 | 08.05.24 | Forbes Marshall | 30.05.24 | 01.07.24 | 15.07.24 | 15.07.24 |  | 13.12.23 | 30.12.23 | 28.02.24 | justin.v@lntecc.com-15.07.2024-16:03:13
Fazilka 2 | Instrumentation | Pressure Gauge/ Compound Pressure Gauge | LE22M163-I-WS-WT-PR-5501 | LE22M163-I-WS-WT-PR-5501-C | General Instruments | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 27.10.23 | 13.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 13.12.23 | T3 | [7 empty] | 13.12.23 | 30.12.23 | 28.02.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Pressure Transmitter | LE22M163-I-WS-WT-PR-5502 | LE22M163-I-WS-WT-PR-5502-A | E&H | Sent to BU Operations | PR Closed |  | Ramkumar |  | 09.01.23 | 09.01.23 | 21.09.23 | 28.09.23 | [8 empty] | 21.09.23 | 21.09.23 | 21.09.23 | T2 | [7 empty] | 21.09.23 | 08.10.23 | 07.12.23 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Pressure Transmitter | LE22M163-I-WS-WT-PR-5502 | LE22M163-I-WS-WT-PR-5502-B | Siemens | Approved by Client | PR Closed |  | Chandrasekar |  | 09.01.23 | 09.01.23 | 21.09.23 | 28.09.23 | [8 empty] | 21.09.23 | 21.09.23 | 21.09.23 | T1 | 28.09.23 | Siemens | 19.12.23 | 29.12.23 | 29.12.23 | 19.12.23 | 19.12.23 | 21.09.23 | 08.10.23 | 27.11.23 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Pressure Transmitter | LE22M163-I-WS-WT-PR-5502 | LE22M163-I-WS-WT-PR-5502-C | Yokogawa | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 21.09.23 | 28.09.23 | [8 empty] | 21.09.23 | 21.09.23 | 21.09.23 | T3 | [7 empty] | 21.09.23 | 08.10.23 | 07.12.23 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Float & Board Level Gauge | LE22M163-I-WS-WT-PR-5503 | LE22M163-I-WS-WT-PR-5503-A | Scientific Devices | Pre-order technically cleared | 95 |  |  |  | 09.01.23 | 09.01.23 | 27.11.23 | 05.04.24 | 01.04.24 | 20.04.24 | 01.05.24 | [5 empty] | 01.05.24 | 01.05.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:13
Fazilka 2 | Instrumentation | Float & Board Level Gauge | LE22M163-I-WS-WT-PR-5503 | LE22M163-I-WS-WT-PR-5503-B | SBEM | Pre-order technically cleared | 66 |  |  |  | 09.01.23 | 07.05.24 | 21.05.24 | 21.05.24 | 28.05.24 | 30.05.24 | [6 empty] | 30.05.24 | 28.05.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:13
Fazilka 2 | Instrumentation | Ultrasonic Level Transmitter | LE22M163-I-WS-WT-PR-5504 | LE22M163-I-WS-WT-PR-5504-A | E&H | Sent to BU Operations | PR Closed |  | Ramkumar |  | 09.01.23 | 09.01.23 | 23.10.23 | 27.10.23 | [8 empty] | 27.10.23 | 27.10.23 | 23.10.23 | T2 | [7 empty] | 23.10.23 | 09.11.23 | 08.01.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Ultrasonic Level Transmitter | LE22M163-I-WS-WT-PR-5504 | LE22M163-I-WS-WT-PR-5504-B | Siemens | Approved by Client | PR Closed |  | Chandrasekar |  | 09.01.23 | 09.01.23 | 21.09.23 | 27.10.23 | [8 empty] | 27.10.23 | 27.10.23 | 21.09.23 | T1 | 28.09.23 | Siemens | 19.12.23 | 29.12.23 | 29.12.23 | 19.12.23 | 19.12.23 | 21.09.23 | 08.10.23 | 27.11.23 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Ultrasonic Level Transmitter | LE22M163-I-WS-WT-PR-5504 | LE22M163-I-WS-WT-PR-5504-C | Yokogawa | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 26.09.23 | 27.10.23 | [8 empty] | 27.10.23 | 27.10.23 | 26.09.23 | T3 | [7 empty] | 26.09.23 | 13.10.23 | 12.12.23 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Level Switch - Conductivity Type | LE22M163-I-WS-WT-PR-5505 | LE22M163-I-WS-WT-PR-5505-A | E&H | Pre-order technically cleared | 121 |  |  |  | 09.01.23 | 09.01.23 | 29.01.24 | 20.03.24 | 23.03.24 | 05.04.24 | [6 empty] | 05.04.24 | 05.04.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:13
Fazilka 2 | Instrumentation | Level Switch - Conductivity Type | LE22M163-I-WS-WT-PR-5505 | LE22M163-I-WS-WT-PR-5505-B | Scientific Devices | Pre-order technically cleared | 95 |  |  |  | 09.01.23 | 09.01.23 | 27.11.23 | 05.04.24 | 07.03.24 | 20.04.24 | 01.05.24 | [5 empty] | 01.05.24 | 01.05.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:13
Fazilka 2 | Instrumentation | Level Switch - Conductivity Type | LE22M163-I-WS-WT-PR-5505 | LE22M163-I-WS-WT-PR-5505-C | SBEM | Pre-order technically cleared | 66 |  |  |  | 09.01.23 | 07.05.24 | 21.05.24 | 21.05.24 | 28.05.24 | 30.05.24 | [6 empty] | 30.05.24 | 28.05.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:13
Fazilka 2 | Instrumentation | Loss of Head Transmitter | LE22M163-I-WS-WT-PR-5507 | LE22M163-I-WS-WT-PR-5507-A | Siemens | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 13.02.24 | 20.02.24 | 01.04.24 | 25.03.24 | 28.03.24 | 28.03.24 |  |  |  |  | 28.03.24 | 28.03.24 | 28.03.24 | T3 | [7 empty] | 28.03.24 | 14.04.24 | 13.06.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Loss of Head Transmitter | LE22M163-I-WS-WT-PR-5507 | LE22M163-I-WS-WT-PR-5507-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 08.02.24 | 20.03.24 | 07.03.24 | 03.04.24 | [6 empty] | 03.04.24 | 03.04.24 | 03.04.24 | T2 | [7 empty] | 03.04.24 | 20.04.24 | 19.06.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Loss of Head Transmitter | LE22M163-I-WS-WT-PR-5507 | LE22M163-I-WS-WT-PR-5507-C | E&H | Approved by Client | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 29.01.24 | 20.03.24 | 26.03.24 | 04.04.24 | [6 empty] | 04.04.24 | 04.04.24 | 04.04.24 | T1 | 06.05.24 | E&H | 13.05.24 | 14.05.24 | 17.05.24 | 16.05.24 | 31.05.24 | 04.04.24 | 21.04.24 | 20.06.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Rate of Flow Transmitter | LE22M163-I-WS-WT-PR-5508 | LE22M163-I-WS-WT-PR-5508-A | Siemens | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 13.02.24 | 20.02.24 | 01.04.24 | 25.03.24 | 28.03.24 | 28.03.24 |  |  |  |  | 28.03.24 | 28.03.24 | 28.03.24 | T3 | [7 empty] | 28.03.24 | 14.04.24 | 13.06.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Rate of Flow Transmitter | LE22M163-I-WS-WT-PR-5508 | LE22M163-I-WS-WT-PR-5508-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 08.02.24 | 20.03.24 | 25.03.24 | 03.04.24 | [6 empty] | 03.04.24 | 03.04.24 | 03.04.24 | T2 | [7 empty] | 03.04.24 | 20.04.24 | 19.06.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Rate of Flow Transmitter | LE22M163-I-WS-WT-PR-5508 | LE22M163-I-WS-WT-PR-5508-C | E&H | Approved by Client | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 29.01.24 | 20.03.24 | 20.03.24 | 04.04.24 | [6 empty] | 04.04.24 | 04.04.24 | 04.04.24 | T1 | 06.05.24 | E&H | 13.05.24 | 14.05.24 | 17.05.24 | 16.05.24 | 31.05.24 | 04.04.24 | 21.04.24 | 20.06.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Rotameter | LE22M163-I-WS-WT-PR-5509 | LE22M163-I-WS-WT-PR-5509-A | Eureka | Pre-order technically cleared | 254 |  |  |  | 09.01.23 | 09.01.23 | 31.10.23 | 16.11.23 | 23.11.23 | 24.11.23 | [6 empty] | 24.11.23 | 23.11.23 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | Rotameter | LE22M163-I-WS-WT-PR-5509 | LE22M163-I-WS-WT-PR-5509-B | Scientific Devices | Pre-order technically cleared | 254 |  |  |  | 09.01.23 | 09.01.23 | 10.11.23 | 16.11.23 | 23.11.23 | 24.11.23 | [6 empty] | 24.11.23 | 23.11.23 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | pH Meter | LE22M163-I-WS-WT-PR-5510 | LE22M163-I-WS-WT-PR-5510-A | E&H | Post-order technically cleared | 106 |  | Ramkumar |  | 09.01.23 | 09.01.23 | 17.01.24 | 24.01.24 | [8 empty] | 12.02.24 | 12.02.24 | 16.02.24 | T1 | 02.04.24 | E&H | 10.04.24 | 20.04.24 | 20.04.24 | 10.04.24 |  | 16.02.24 | 04.03.24 | 03.05.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | pH Meter | LE22M163-I-WS-WT-PR-5510 | LE22M163-I-WS-WT-PR-5510-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 11.01.24 | 07.02.24 | 12.02.24 | 14.02.24 | [6 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T2 | [7 empty] | 12.02.24 | 29.02.24 | 29.04.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Turbidity Meter | LE22M163-I-WS-WT-PR-5511 | LE22M163-I-WS-WT-PR-5511-A | E&H | Post-order technically cleared | 106 |  | Ramkumar |  | 09.01.23 | 09.01.23 | 17.01.24 | 24.01.24 | [8 empty] | 12.02.24 | 12.02.24 | 16.02.24 | T1 | 02.04.24 | E&H | 10.04.24 | 20.04.24 | 20.04.24 | 10.04.24 |  | 16.02.24 | 04.03.24 | 03.05.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | Turbidity Meter | LE22M163-I-WS-WT-PR-5511 | LE22M163-I-WS-WT-PR-5511-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 11.01.24 | 07.02.24 | 12.02.24 | 14.02.24 | [6 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T2 | [7 empty] | 12.02.24 | 29.02.24 | 29.04.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Residual Chlorine Analyser | LE22M163-I-WS-WT-PR-5512 | LE22M163-I-WS-WT-PR-5512-A | E&H | Post-order technically cleared | 106 |  | Ramkumar |  | 09.01.23 | 09.01.23 | 17.01.24 | 24.01.24 | [8 empty] | 12.02.24 | 12.02.24 | 16.02.24 | T1 | 02.04.24 | E&H | 10.04.24 | 20.04.24 | 20.04.24 | 10.04.24 |  | 16.02.24 | 04.03.24 | 03.05.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | Residual Chlorine Analyser | LE22M163-I-WS-WT-PR-5512 | LE22M163-I-WS-WT-PR-5512-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 11.01.24 | 07.02.24 | 12.02.24 | 14.02.24 | [6 empty] | 12.02.24 | 12.02.24 | 12.02.24 | T2 | [7 empty] | 12.02.24 | 29.02.24 | 29.04.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Electromagnetic Flow Meter | LE22M163-I-WS-WT-PR-5513 | LE22M163-I-WS-WT-PR-5513-A | E&H | Sent to BU Operations | PR Closed |  | Ramkumar |  | 09.01.23 | 09.01.23 | 10.11.23 | 10.11.23 | [8 empty] | 10.11.23 | 10.11.23 | 10.11.23 | T2 | [7 empty] | 10.11.23 | 27.11.23 | 26.01.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Electromagnetic Flow Meter | LE22M163-I-WS-WT-PR-5513 | LE22M163-I-WS-WT-PR-5513-B | Siemens | Approved by Client | PR Closed |  | Chandrasekar |  | 09.01.23 | 09.01.23 | 07.09.23 | 12.09.23 | [8 empty] | 21.09.23 | 21.09.23 | 21.09.23 | T1 | 27.09.23 | Siemens | 09.01.24 | 10.01.24 | 10.01.24 | 10.01.24 | 10.01.24 | 21.09.23 | 08.10.23 | 26.11.23 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Electromagnetic Flow Meter | LE22M163-I-WS-WT-PR-5513 | LE22M163-I-WS-WT-PR-5513-C | Forbes Marshall | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 27.09.23 | 07.11.23 | 08.11.23 | 09.11.23 | [6 empty] | 08.11.23 | 08.11.23 | 08.11.23 | T4 | [7 empty] | 08.11.23 | 25.11.23 | 24.01.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | Electromagnetic Flow Meter | LE22M163-I-WS-WT-PR-5513 | LE22M163-I-WS-WT-PR-5513-D | Yogokawa | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 07.11.23 | 11.11.23 | [10 empty] | 08.11.23 | T3 | [7 empty] | 08.11.23 | 25.11.23 | 24.01.24 | justin.v@lntecc.com-01.07.2024-15:01:47
Fazilka 2 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M163-I-WS-WT-PR-5514 | LE22M163-I-WS-WT-PR-5514-A | Autosys | Pre-order technically cleared | 97 |  |  |  | 09.01.23 | 09.01.23 | 09.01.23 | 08.11.23 | 15.11.23 | 21.11.23 | 06.12.23 | 18.12.23 | 03.01.24 | 16.01.24 | 24.01.24 |  | 29.04.24 | 29.04.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M163-I-WS-WT-PR-5514 | LE22M163-I-WS-WT-PR-5514-B | Centum Controls | Pre-order technically cleared | 106 |  |  |  | 09.01.23 | 09.01.23 | 23.01.24 | 30.01.24 | 15.02.24 | 02.03.24 | 05.03.24 | 19.03.24 | 26.03.24 | 02.04.24 | 20.04.24 |  | 20.04.24 | 20.04.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M163-I-WS-WT-PR-5514 | LE22M163-I-WS-WT-PR-5514-C | Schneider Electric | Pre-order technically cleared | 31 |  |  |  | 09.01.23 | 02.04.24 | 11.04.24 | 16.04.24 | 22.04.24 | 25.04.24 | 06.05.24 | 07.05.24 | 14.05.24 | 15.05.24 | 16.05.24 | 27.05.24 | 04.07.24 | 04.07.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M163-I-WS-WT-PR-5514 | LE22M163-I-WS-WT-PR-5514-D | Sai Applied Technologies | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 07.11.23 | 07.03.24 | 16.04.24 | 17.04.24 | [17 empty] | 10.07.24 | 27.07.24 | 25.09.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:11:14
Fazilka 2 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M163-I-WS-WT-PR-5514 | LE22M163-I-WS-WT-PR-5514-E | Cotmac | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 11.01.24 | 30.01.24 | [19 empty] | 10.07.24 | 27.07.24 | 25.09.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:11:14
Fazilka 2 | Instrumentation | PLC, RTU & SCADA Accessories | LE22M163-I-WS-WT-PR-5514 | LE22M163-I-WS-WT-PR-5514-F | Mitsubishi Electric | Pre-order technically cleared | 29 |  | Sudarsan |  | 09.01.23 | 09.01.23 | 28.05.24 | 31.05.24 | 19.06.24 | 27.06.24 | 05.07.24 | 06.07.24 |  |  |  |  | 06.07.24 | 06.07.24 | [9 empty] | 10.07.24 | 27.07.24 | 25.09.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | Contol & Signal Cables | LE22M163-I-WS-WT-PR-5515 | LE22M163-I-WS-WT-PR-5515-A | Axelon | Pre-order technically cleared | 30 | Awaiting cable quantity finalization |  |  | 09.01.23 | 09.01.23 | 08.01.24 | 18.03.24 | 20.03.24 | 09.05.24 | 15.05.24 | 05.07.24 |  |  |  |  | 05.07.24 | 05.07.24 | [9 empty] | 20.07.24 | 06.08.24 | 05.10.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | Contol & Signal Cables | LE22M163-I-WS-WT-PR-5515 | LE22M163-I-WS-WT-PR-5515-B | Polycab | Pre-order technically cleared | 30 | Awaiting cable quantity finalization |  |  | 09.01.23 | 09.01.23 | 08.01.24 | 18.03.24 | 20.03.24 | 09.05.24 | 15.05.24 | 05.07.24 |  |  |  |  | 05.07.24 | 05.07.24 | [9 empty] | 20.07.24 | 06.08.24 | 05.10.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | Contol & Signal Cables | LE22M163-I-WS-WT-PR-5515 | LE22M163-I-WS-WT-PR-5515-C | Cords | Pre-order technically cleared | 30 | Awaiting cable quantity finalization |  |  | 09.01.23 | 09.01.23 | 24.02.24 | 15.03.24 | 03.04.24 | 09.05.24 | 15.05.24 | 05.07.24 |  |  |  |  | 05.07.24 | 05.07.24 | [9 empty] | 20.07.24 | 06.08.24 | 05.10.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Instrumentation | Contol & Signal Cables | LE22M163-I-WS-WT-PR-5515 | LE22M163-I-WS-WT-PR-5515-D | Kei | Regret offer | PR Closed |  |  |  | 09.01.23 | 09.01.23 | 21.02.24 | 15.03.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | rajesh.muthuraj@lntecc.com-10.07.2024-16:11:14
Fazilka 2 | Instrumentation | Contol & Signal Cables | LE22M163-I-WS-WT-PR-5515 | LE22M163-I-WS-WT-PR-5515-E | RPG | Pre-order comments issued | 38 |  |  |  | 09.01.23 | 30.05.24 | 24.06.24 | 27.06.24 | [19 empty] | 20.07.24 | 06.08.24 | 05.10.24 | justin.v@lntecc.com-15.07.2024-16:03:14
Fazilka 2 | Electrical | HT & LT Transformers | LE22M163-E-WS-WT-PR-4201 | LE22M163-E-WS-WT-PR-4201-A | ITE | Pre-order technically cleared | 41 | Awaiting, for Fazilka-1 (68MLD) approval from client to make it in line with requirement. | +91-124-4031900 | itegurgaon@gmail.com |  | 19.02.24 | 30.03.24 | 15.04.24 | 24.06.24 | [7 empty] | 24.06.24 | 24.06.24 |  | T1 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | HT & LT Transformers | LE22M163-E-WS-WT-PR-4201 | LE22M163-E-WS-WT-PR-4201-B | Uttam barath | Regret offer | PR Closed | Awaiting, for Fazilka-1 (68MLD) approval from client to make it in line with requirement. | +91-141-2330112 | marketing2@uttam-bharat.com |  | 03.02.24 | 10.02.24 | 13.02.24 | [11 empty] | T1 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | HT & LT Transformers | LE22M163-E-WS-WT-PR-4201 | LE22M163-E-WS-WT-PR-4201-C | Voltech | Pre-order technically cleared | 131 | Awaiting, for Fazilka-1 (68MLD) approval from client to make it in line with requirement. | 9600095932 | transformers@voltechgroup.com |  | 17.02.24 | 19.02.24 | 29.02.24 | 11.03.24 | 26.03.24 | [6 empty] | 26.03.24 | 26.03.24 |  | T1 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | HT Switchgear Panel | LE22M163-E-WS-WT-PR-4203 | LE22M163-E-WS-WT-PR-4203-A | Coronet | Post-order technically cleared | 69 |  | 8447476814 | laxman@coronet.in |  | 06.10.23 | 14.10.23 | 01.11.23 | 24.11.23 | 06.12.23 | 31.01.24 | 12.02.24 |  |  |  |  | 12.02.24 | 12.02.24 | 12.02.24 | T1 | 28.02.24 | Coronet | 21.05.24 | 27.05.24 | 27.05.24 | 27.05.24 |  | 16.08.24 | 02.09.24 | 28.04.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | HT Switchgear Panel | LE22M163-E-WS-WT-PR-4203 | LE22M163-E-WS-WT-PR-4203-B | HTS | Regret offer | PR Closed |  | 9370797168 | vikas.bhure@htswitchgears.com |  | 11.10.23 | 12.10.23 | 06.11.23 | 21.11.23 | 06.12.23 | 18.01.24 | 20.01.24 | 23.01.24 | 24.01.24 | 27.02.24 | 04.03.24 | 04.03.24 | 04.03.24 | 04.03.24 | T1 | [7 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | HT Switchgear Panel | LE22M163-E-WS-WT-PR-4203 | LE22M163-E-WS-WT-PR-4203-C | UPE | Regret offer | PR Closed |  | 95000 95075 | deepak@upe.co.in |  | 20.09.23 | 04.10.23 | 07.02.24 | 17.02.24 | 19.02.24 | [6 empty] | 19.02.24 | 19.02.24 | 19.02.24 | T1 | [7 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | DG set | LE22M163-E-WS-WT-PR-4204 | LE22M163-E-WS-WT-PR-4204-A | GOEL POWER | Pre-order comments issued | 256 | Awaiting, for Fazilka-1 (68MLD) approval from client to make it in line with requirement. |  |  |  | 22.09.23 | 09.10.23 | 18.10.23 | 21.11.23 | 22.11.23 | [9 empty] | T3 | [7 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | DG set | LE22M163-E-WS-WT-PR-4204 | LE22M163-E-WS-WT-PR-4204-B | IEC | Pre-order comments issued | 179 | Awaiting, for Fazilka-1 (68MLD) approval from client to make it in line with requirement. | 9810559597 | rajnish.sharma@iecgensets.com |  | 22.09.23 | 03.10.23 | 09.11.23 | 05.02.24 | 07.02.24 | [9 empty] | T3 | [7 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | DG set | LE22M163-E-WS-WT-PR-4204 | LE22M163-E-WS-WT-PR-4204-C | Sudhir Power | Pre-order technically cleared | 144 | Awaiting, for Fazilka-1 (68MLD) approval from client to make it in line with requirement. |  | tarunbhandari@sudhirpower.com |  | 14.09.23 | 30.10.23 | 08.11.23 | 27.02.24 | 13.03.24 | [6 empty] | 13.03.24 | 13.03.24 |  | T3 | [7 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | HT Cables & Termination Kits | LE22M163-E-WS-WT-PR-4205 | LE22M163-E-WS-WT-PR-4205-B |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | 415V LT Switchgear & APFC | LE22M163-E-WS-WT-PR-4206 | LE22M163-E-WS-WT-PR-4206-A | Coronet | Regret offer | PR Closed |  | 8447476814 | laxman@coronet.in |  | 06.10.23 | 14.10.23 | 30.10.23 | 17.01.24 | 23.01.24 | 03.02.24 | 23.02.24 | 12.03.24 | 15.03.24 |  |  | 26.03.24 | 26.03.24 | 26.03.24 | T2 | [7 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | 415V LT Switchgear & APFC | LE22M163-E-WS-WT-PR-4206 | LE22M163-E-WS-WT-PR-4206-B | SRCS | Post-order comments issued | 34 |  |  | ashok@ragavendracontrol.com |  | 20.09.23 | 09.10.23 | 21.10.23 | 07.11.23 | 17.11.23 | 25.01.24 | 07.02.24 |  |  |  |  | 07.02.24 | 07.02.24 | 06.05.24 | T2 | 06.05.24 | SRCS | 15.05.24 | 01.07.24 |  |  |  | 14.08.24 | 31.08.24 | 05.07.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | 415V LT Switchgear & APFC | LE22M163-E-WS-WT-PR-4206 | LE22M163-E-WS-WT-PR-4206-C | UPE | Regret offer | PR Closed |  | 95000 95075 | deepak@upe.co.in |  | 20.09.23 | 27.09.23 | 20.10.23 | 13.11.23 | 18.11.23 | 17.01.24 | 23.01.24 | 02.02.24 | 23.02.24 | 15.03.24 | 15.03.24 | 02.04.24 | 04.04.24 | 04.04.24 | T2 | [7 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | LT Power and Control Cables | LE22M163-E-WS-WT-PR-4207 | LE22M163-E-WS-WT-PR-4207-A |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | Cable Trays & its supports | LE22M163-E-WS-WT-PR-4208 | LE22M163-E-WS-WT-PR-4208-B |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | Lighting Fixtures | LE22M163-E-WS-WT-PR-4209 | LE22M163-E-WS-WT-PR-4209-C |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | Earthing & Lightning protection materials with accessories | LE22M163-E-WS-WT-PR-4210 | LE22M163-E-WS-WT-PR-4210-A |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | Electrical Safety Items | LE22M163-E-WS-WT-PR-4211 | LE22M163-E-WS-WT-PR-4211-B |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | LPBS | LE22M163-E-WS-WT-PR-4212 | LE22M163-E-WS-WT-PR-4212-C |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | Cable Glands and Lugs | LE22M163-E-WS-WT-PR-4213 | LE22M163-E-WS-WT-PR-4213-A |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | Distribution Board, Switchboards, Sockets & Other Accessories | LE22M163-E-WS-WT-PR-4214 | LE22M163-E-WS-WT-PR-4214-B |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | Lighting pole and Junction Box | LE22M163-E-WS-WT-PR-4215 | LE22M163-E-WS-WT-PR-4215-A |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Fazilka 2 | Electrical | Switchyard Components | LE22M163-E-WS-WT-PR-4217 | LE22M163-E-WS-WT-PR-4217-A |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | muthukumar.r@lntecc.com-10.07.2024-15:39:29
Firozabad WSP | Mechanical | EOT Crane | LE23M598-M-WS-CR-PR-1906 | LE23M598-M-WS-CR-PR-1906-A | Japs | Pre-order technically cleared | 48 | 1. Vendor submitted SG Cranes on 11.01.2024 2. L&T asked for DG Cranes on 11.01.2024 3. DG Cranes offer received from vendor on 12.01.2024 4. L&T Observations sent on 19.02.2024 5. Vendor replied on 20.02.2024 6. Filled in data sheet sent by vendor on 01.03.2024 7.L&T Observations sent on 08.05.2024 8.Compliance received on 15.05.2024 9.L&T Observations sent on 13.06.2024 | 99789 00589 | sales.japs@gmail.com |  | 11.01.24 | 11.01.24 | 08.05.24 | 13.05.24 | 13.06.24 | 14.06.24 | [5 empty] | 17.06.24 | 17.06.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | EOT Crane | LE23M598-M-WS-CR-PR-1906 | LE23M598-M-WS-CR-PR-1906-B | Reva | Pre-order technically cleared | 66 | 1. Observations sent on 19.01.2024 to submit DG cranes 2. Revised offer received on 20.01.2024 3. L&T Observations sent on 19.02.2024 4. Vendor reply received on 24.02.2024 5. L&T Observations sent on 06.03.2024 6. Revised technical offer with filled in data sheet received on 07.03.2024 7.L&T Observations sent on 08.05.2024 | 98994 84751 | south@revacranes.com |  | 11.01.24 | 12.01.24 | 08.05.24 | 11.05.24 | 15.05.24 | 30.05.24 | [5 empty] | 30.05.24 | 30.05.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | EOT Crane | LE23M598-M-WS-CR-PR-1906 | LE23M598-M-WS-CR-PR-1906-C | Indef | Pre-order technically cleared | 20 | 1. L&T Observation to provide DG cranes on 24.01.2024 2. Reminder sent on 14.02.2024 3. Reminder sent on 07.03.2024 4. Technical offer received for DGEOT on 07.03.2024 5. L&T observations sent on 16.03.2024 6. Reminder sent on 26.03.2024 7.Compliance received on 13.06.2024 | 81211 74337 | mkm@indef.com |  | 11.01.24 | 17.01.24 | 16.03.24 | 13.06.24 | 24.06.24 | 25.06.24 | 28.06.24 | 15.07.24 |  |  |  | 15.07.24 | 15.07.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | HSC Pumps | LE23M598-M-WS-CW-PR-1901 | LE23M598-M-WS-CW-PR-1901-E | Andritz | Pre-order comments issued | 9 |  | 73583 86663 | manjunath.valagerepura@andritz.com |  | 16.05.24 | 06.06.24 | 02.07.24 | 24.07.24 | 26.07.24 | [20 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:22
Firozabad WSP | Mechanical | HSC Pumps | LE23M598-M-WS-CW-PR-1901 | LE23M598-M-WS-CW-PR-1901-F | Xylem | Pre-order pending with EDRC | 6 |  | 63589 96864 | shivakumar.natarajan@xylem.com |  | 10.06.24 | 25.06.24 | 03.07.24 | 29.07.24 | [21 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:47
Firozabad WSP | Mechanical | Dewatering Pump | LE23M598-M-WS-DP-PR-1908 | LE23M598-M-WS-DP-PR-1908-A | Aqua Pumps | Regret offer | PR Closed | Regretted | 81440 03131 | chennai@aquapumps.com |  | 16.01.24 | [24 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Dewatering Pump | LE23M598-M-WS-DP-PR-1908 | LE23M598-M-WS-DP-PR-1908-B | Kishor Pumps | Awaiting pre-offer from vendor | 201 | 1. Reminder sent on 23.01.2024 2. Reminder sent on 16.02.2024 3. Reminder sent on 20.02.2024 4. Revised BOQ sent on 27.02.2024 5. Reminder sent on 08.03.2024 6. Mechanical evaluation done, inst comments requested and motor pr to be signed. | 91766 10938 | P.Dixon@kishorpumps.com |  | 16.01.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Dewatering Pump | LE23M598-M-WS-DP-PR-1908 | LE23M598-M-WS-DP-PR-1908-C | MBH Pumps | Pre-order technically cleared | 51 | 1. Additional informations received on 24.01.2024 2. Revised BOQ sent on 27.02.2024 3. Vendor asked for query on 27.02.2024 4. L&T replied on 28.02.2024 5. Vendor provided Rev-1 offer on 28.02.2024 6.Mech done. | 98254 67472 | Parth@mbhpumps.com |  | 16.01.24 | 22.01.24 | 23.05.24 | 01.06.24 | 13.06.24 | 14.06.24 | [5 empty] | 14.06.24 | 14.06.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Dewatering Pump | LE23M598-M-WS-DP-PR-1908 | LE23M598-M-WS-DP-PR-1908-D | Jasco Pump | Pre-order comments issued | 12 | 1. Revised BOQ sent on 27.02.2024 2. Reminder sent on 08.03.2024 3. Revised R1 offer received on 09.03.2024 | 70690 99037 | info@jascopump.com |  | 16.01.24 | 22.01.24 | 03.06.24 | 12.07.24 | 18.07.24 | 22.07.24 | 23.07.24 | [18 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | HSC Pumps | LE23M598-M-WS-HS-PR-1901 | LE23M598-M-WS-HS-PR-1901-A | WPIL | Pre-order comments issued | 33 | 1. Reminder sent on 23.01.2024 2. Offer received on 23.01.2024 3. Revised pump parameters sent on 06.02.2024 4. Remainder sent on 14.02.2024 5. Motor specs requested by vendor on 16.02.2024 6. Motor specifications sent on 16.02.2024 7. Revised offer received on 20.02.2024 8. Revised Specification sent to vendor on 06.03.2024 9. Reminder sent on 16.03.2024 10. Revised offer received on 21.03.2024 11. Observations sent on 09.04.2024 |  | r.chandramohan@wpil.co.in |  | 11.01.24 | 23.01.24 | 09.04.24 | 21.05.24 | 02.07.24 | [20 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | HSC Pumps | LE23M598-M-WS-HS-PR-1901 | LE23M598-M-WS-HS-PR-1901-B | WILO | Pre-order pending with EDRC | 6 | 1. Reminder sent on 23.01.2024 2. Revised Pump parameters sent on 06.02.2024 3. Reminder sent on 14.02.2024 4. Technical offer received on 16.02.2024 5. Revised Specification sent to vendor on 06.03.2024 6. Reminder sent on 16.03.2024 7. Reminder sent on 26.03.2024 | 86800 68301 | manikkandan.pr@wilo.com |  | 11.01.24 | 15.05.24 | 29.06.24 | 29.07.24 | [21 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:47
Firozabad WSP | Mechanical | HSC Pumps | LE23M598-M-WS-HS-PR-1901 | LE23M598-M-WS-HS-PR-1901-C | KBL | Pre-order comments issued | 37 | 1. Reminder sent on 23.01.2024 2. Revised pump parameters sent on 15.02.2024 3. Reminder mail sent on 05.03.2024 4. Revised Specification sent to vendor on 06.03.2024 5. Technical offer received on 08.03.2024 6. Observations sent on 09.04.2024 | 86696 64820 | azharuddin.tamboli@kbl.co.in |  | 11.01.24 | 08.03.24 | 09.04.24 | 17.04.24 | 28.06.24 | [20 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | HSC Pumps | LE23M598-M-WS-HS-PR-1901 | LE23M598-M-WS-HS-PR-1901-D | FLOWMORE | Pre-order comments issued | 11 | 1. Reminder sent on 23.01.2024 2. Offer received on 28.01.2024 3. Revised Pump parameters sent on 06.02.2024 4. Reminder sent on 14.02.2024 5. Revised Offer received on 17.02.2024 6. Revised Specification sent to vendor on 06.03.2024 7. Revised offer received on 09.03.2024 8. L&T Observation sent on 09.04.2024 | 93828 69518 | mkannan@flowmoregroup.co.in |  | 11.01.24 | 28.01.24 | 09.04.24 | 17.05.24 | 28.06.24 | 10.07.24 | 24.07.24 | [18 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Sluice Valves | LE23M598-M-WS-HS-PR-1903-1 | LE23M598-M-WS-HS-PR-1903-1-A | Magwen | Sent to BU Operations | 54 | 1.Offer received on 28.05.2024 2.Observations sent on 01.06.2024 | 9573938553 | naresh.gs@magwen.com |  | 24.05.24 | 28.05.24 | 01.06.24 | 11.06.24 | [7 empty] | 01.06.24 | 01.06.24 | 01.06.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Sluice Valves | LE23M598-M-WS-HS-PR-1903 | LE23M598-M-WS-HS-PR-1903-A | Hawle | Sent to BU Operations | PR Closed | 1. Observations sent on 05.01.2024 2. Reminder sent on 05.02.2024 3. Reply received on 09.02.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 22.11.23 | 14.12.23 | 05.01.24 | 09.02.24 | [7 empty] | 09.02.24 | 09.02.24 | 19.02.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Sluice Valves | LE23M598-M-WS-HS-PR-1903 | LE23M598-M-WS-HS-PR-1903-B | AVK | Approved by Client | PR Closed | 1. Observations sent on 09.01.2024 2. Replies received on 10.01.2024 3. Observations sent on 18.01.2024 4. Replies received on 31.01.2024 5. Observations sent on 09.02.2024 6. Replies received on 12.02.2024 | 91769 66455 | subhash@avkindia.com |  | 22.11.23 | 29.11.23 | 09.01.24 | 10.01.24 | 18.01.24 | 31.01.24 | 09.02.24 | 12.02.24 |  |  |  | 12.02.24 | 12.02.24 | 19.02.24 | T1 | 23.02.24 | AVK | 23.02.24 | 24.02.24 | 04.03.24 | 04.03.24 | 16.03.24 |  |  | 23.04.24 | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Sluice Valves | LE23M598-M-WS-HS-PR-1903 | LE23M598-M-WS-HS-PR-1903-C | Sigmaflow | Sent to BU Operations | PR Closed | 1. L&T Observations sent on 19.02.2024 2. Reply received on 20.02.2024 3. L&T Observation sent on 21.02.2024 4. Reply received on 21.02.2024 5. Technically cleared on 21.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 16.02.24 | 17.02.24 | 19.02.24 | 20.02.24 | 21.02.24 | 21.02.24 | [5 empty] | 21.02.24 | 21.02.24 | 21.02.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Sluice Valves | LE23M598-M-WS-HS-PR-1903 | LE23M598-M-WS-HS-PR-1903-D | VAG | Regret offer | PR Closed | 1. Observations sent on 18.01.2024 2. Reminder sent on 05.02.2024 3. Reminder sent on 09.02.2024 4. Reminder sent on 13.02.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 22.11.23 | 29.11.23 | 18.01.24 | [22 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Air Valves with Isolation Valve | LE23M598-M-WS-HS-PR-1904-1 | LE23M598-M-WS-HS-PR-1904-1-A | Magwen | Pre-order technically rejected | PR Closed | 1.Offer received on 28.05.2024 2.Observations sent on 01.06.2024 | 9573938553 | naresh.gs@magwen.com |  | 24.05.24 | 28.05.24 | 01.06.24 | [22 empty] | rachamalla.nithish@lntecc.com-12.06.2024-11:18:25
Firozabad WSP | Mechanical | Air Valves with Isolation valve | LE23M598-M-WS-HS-PR-1904 | LE23M598-M-WS-HS-PR-1904-A | Hawle | Sent to BU Operations | PR Closed | 1. Observations sent on 05.01.2024 2. Reminder sent on 05.02.2024 3. Reply received on 09.02.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 22.11.23 | 14.12.23 | 05.01.24 | 09.02.24 | [7 empty] | 19.02.24 | 19.02.24 | 19.02.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Air Valves with Isolation valve | LE23M598-M-WS-HS-PR-1904 | LE23M598-M-WS-HS-PR-1904-B | AVK | Approved by Client | PR Closed | 1. Observations sent on 09.01.2024 2. Replies received on 10.01.2024 3. Observations sent on 18.01.2024 4. Replies received on 31.01.2024 5. Observations sent on 09.02.2024 6. Replies received on 12.02.2024 | 91769 66455 | subhash@avkindia.com |  | 22.11.23 | 29.11.23 | 09.01.24 | 10.01.24 | 18.01.24 | 31.01.24 | 09.02.24 | 12.02.24 |  |  |  | 19.02.24 | 19.02.24 | 19.02.24 | T1 | 23.02.24 | AVK | 23.02.24 | 24.02.24 | 04.03.24 | 04.03.24 | 16.03.24 |  |  | 23.04.24 | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Air Valves with Isolation valve | LE23M598-M-WS-HS-PR-1904 | LE23M598-M-WS-HS-PR-1904-C | Sigmaflow | Sent to BU Operations | PR Closed | 1. L&T Observations sent on 19.02.2024 2. Reply received on 20.02.2024 3. L&T Observation sent on 21.02.2024 4. Reply received on 21.02.2024 5. Technically cleared on 21.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 16.02.24 | 17.02.24 | 19.02.24 | 20.02.24 | 21.02.24 | 21.02.24 | [5 empty] | 21.02.24 | 21.02.24 | 21.02.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Air Valves with Isolation valve | LE23M598-M-WS-HS-PR-1904 | LE23M598-M-WS-HS-PR-1904-D | VAG | Regret offer | PR Closed | 1. Observations sent on 18.01.2024 2. Reminder sent on 05.02.2024 3. Reminder sent on 09.02.2024 4. Reminder sent on 13.02.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 22.11.23 | 29.11.23 | [23 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Motorized Sluice Valves | LE23M598-M-WS-PR-VL-1913-1 | LE23M598-M-WS-PR-VL-1913-1-A | Magwen | Sent to BU Operations | 54 | 1.Offer received on 28.05.2024 2.Observations sent on 01.06.2024 | 9573938553 | naresh.gs@magwen.com |  | 24.05.24 | 28.05.24 | 01.06.24 | 11.06.24 | [7 empty] | 01.06.24 | 01.06.24 | 01.06.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Motorized Sluice Valves | LE23M598-M-WS-PR-VL-1913 | LE23M598-M-WS-PR-VL-1913-A | Hawle | Pre-order pending with EDRC | 16 | 1. Reminder sent on 16.03.2024 2. Data sheet sent by vendor on 20.03.2024 3. L&T requested for actuator specifications on 25.03.2024 4. Vendor replied on 28.03.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 17.02.24 | 20.03.24 | 15.05.24 | 30.05.24 | 03.06.24 | 03.06.24 | 06.06.24 | 19.07.24 | [17 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Motorized Sluice Valves | LE23M598-M-WS-PR-VL-1913 | LE23M598-M-WS-PR-VL-1913-B | AVK | Pre-order technically cleared | 90 | 1. L&T Observation sent on 25.03.2024 2. Vendor replied on 25.03.2024 3. L&T Observations sent on 20.04.2024 | 91769 66455 | subhash@avkindia.com |  | 17.02.24 | 23.02.24 | 20.04.24 | 02.05.24 | [7 empty] | 03.05.24 | 06.05.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Motorized Sluice Valves | LE23M598-M-WS-PR-VL-1913 | LE23M598-M-WS-PR-VL-1913-C | VAG | Pre-order comments issued | 37 | 1. L&T Observations for actuator specificiations sent on 11.03.2024 2. Reminder sent on 25.03.2024 3.L&T Observations sent on 28.06.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 17.02.24 | 22.02.24 | 15.05.24 | 21.05.24 | 03.06.24 | 24.06.24 | 28.06.24 | [18 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Dismantling Joints | LE23M598-M-WS-PV-PR-1902 | LE23M598-M-WS-PV-PR-1902-A | Qualitech | Sent to BU Operations | PR Closed | 1. L&T Observation sent on 08-02-2024 2. Revised offer received on 12.02.2024 3. Additional observations sent on 15.02.2024 4. Compliance received on 17.02.2024 5. Technically Cleared on 27.02.2024 | 93147 14916 94141 95835 | kamal.mehta@qualitechgroup.in |  | 20.01.24 | 25.01.24 | 08.02.24 | 12.02.24 | 15.02.24 | 17.02.24 | [5 empty] | 27.02.24 | 27.02.24 | 01.03.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Dismantling Joints | LE23M598-M-WS-PV-PR-1902 | LE23M598-M-WS-PV-PR-1902-B | Surind | Sent to BU Operations | PR Closed | 1. Reminder sent on 03.02.20249 2. Offer received on 16.02.2024 3. Observations sent on 17.02.2024 4. Reminder sent on 26.02.2024 5. Reply received on 27.02.2024 6. Technically cleared on 27.02.2024 | 90070 15744 | info@surind.com |  | 20.01.24 | 16.02.24 | 17.02.24 | 27.02.24 | [7 empty] | 27.02.24 | 27.02.24 | 01.03.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Dismantling Joints | LE23M598-M-WS-PV-PR-1902 | LE23M598-M-WS-PV-PR-1902-C | Sigmaflow | Approved by Client | PR Closed | 1.Observations sent on 08.02.2024 2. Reply received on 09.02.2024 3. Additional observations sent on 15.02.2024 3. Compliance received on 17.02.2024 4. Technically Cleared on 27.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 20.01.24 | 06.02.24 | 08.02.24 | 09.02.24 | 15.02.24 | 17.02.24 | [5 empty] | 27.02.24 | 27.02.24 | 01.03.24 | T1 | 27.04.24 | Sigmaflow | 30.04.24 | 02.05.24 | 02.05.24 | 10.05.24 | 10.05.24 |  |  | 26.06.24 | rachamalla.nithish@lntecc.com-21.05.2024-09:29:10
Firozabad WSP | Mechanical | Dismantling Joints | LE23M598-M-WS-PV-PR-1902 | LE23M598-M-WS-PV-PR-1902-D | Hawle | Sent to BU Operations | PR Closed | 1. Reminder sent on 03.02.2024 2. Reminder sent on 15.02.2024 3. Offer received on 15.02.2024 4. L&T Observation sent on 19.02.2024 5. Reminder sent on 23.02.2024 6. Vendor responded on 23.02.2024 7. Data sheet sent to vendor on 26.02.2024 8. Vendor replied on 01.03.2024 9. Technical clearance on 01.03.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 20.01.24 | 15.02.24 | 19.02.24 | 23.02.24 | 26.02.24 | 01.03.24 | [5 empty] | 01.03.24 | 01.03.24 | 01.03.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Dismantling Joints | LE23M598-M-WS-PV-PR-1902 | LE23M598-M-WS-PV-PR-1902-E | Orbit Engineers | Regret offer | PR Closed | 1. Reminder sent on 03.02.2024 | 78791 45143 | yogesh.orbitengineers@gmail.com |  | 20.01.24 | [24 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Dismantling Joints | LE23M598-M-WS-PV-PR-1902 | LE23M598-M-WS-PV-PR-1902-F | Precise Engineers | Sent to BU Operations | PR Closed | 1.Offer received on 27.05.2024 2. Observations sent on 30.05.2024 3. Compliance received on 03.06.2024 4.Observations sent on 03.06.2024 5.Compliance received on 04.06.2024 6.Observations sent on 06.06.2024 7.Compliance received on 18.06.2024 8.Technical Clearance given on 18.06.2024 | 8905917100 | sjm@vedantagroup.net |  | 21.05.24 | 27.05.24 | 30.05.24 | 03.06.24 | 03.06.24 | 04.06.24 | 06.06.24 | 18.06.24 |  |  |  | 18.06.24 | 18.06.24 | 18.06.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-18.06.2024-14:56:54
Firozabad WSP | Mechanical | Dismantling Joints | LE23M598-M-WS-PV-PR-1902 | LE23M598-M-WS-PV-PR-1902-G | Shiva Industries | Sent to BU Operations | PR Closed | 1.Offer received on 27.05.2024 2.Observations sent on 30.05.2024 3.Compliance received on 03.06.2024 4.Observations sent on 03.06.2024 5.Compliance received on 07.06.2024 6.Technical clearance on 07.06.2024 | 9782357700 | navinebus@yahoo.co.in |  | 21.05.24 | 27.05.24 | 30.05.24 | 03.06.24 | 03.06.24 | 06.06.24 | [5 empty] | 07.06.24 | 07.06.24 | 07.06.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-07.06.2024-11:53:58
Firozabad WSP | Mechanical | Butterfly Valves | LE23M598-M-WS-PV-PR-1905-1 | LE23M598-M-WS-PV-PR-1905-1-A | Magwen | Sent to BU Operations | 53 | 1.Offer received on 28.05.2024 2.Tech clearance on 12.06.2024 | 9573938553 | naresh.gs@magwen.com |  | 24.05.24 | 28.05.24 | 01.06.24 | [8 empty] | 12.06.24 | 12.06.24 | 12.06.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Butterfly Valves | LE23M598-M-WS-PV-PR-1905 | LE23M598-M-WS-PV-PR-1905-A | Hawle | Sent to BU Operations | 75 | 1. L&T asked for actuator specs on 05.02.2024 2. Vendor requested specs for actuator on 09.02.2024 3. Vendor provided actuator docs on 12.02.2024 4. Observations sent on 26.02.2024 5. Reminder sent on 16.03.2024 6. Vendor replied on 16.03.2024 without mechanical 7. Vendor replied on 20.03.2024 for Mechanical 8. E&I Observations sent on 22.03.2024 9. Reply received on 28.03.2024 10. L&T observations sent on 28.03.2024 11. Vendor replied on 04.04.2024 & 05.04.2024 12. L&T observation sent on 11.04.2024 | 99440 74005 | sagaya.prabhu@hawle.in |  | 20.01.24 | 30.01.24 | 26.02.24 | 20.03.24 | 22.03.24 | 28.03.24 | 28.03.24 | 05.04.24 | 11.04.24 | 20.04.24 |  | 19.04.24 | 19.04.24 | 21.05.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Butterfly Valves | LE23M598-M-WS-PV-PR-1905 | LE23M598-M-WS-PV-PR-1905-B | AVK | Sent to BU Operations | 75 | 1. L&T observations sent on 09.02.2024 2. Reply received from vendor on 13.02.2024 3. E&I Observations sent on 15.02.2024 4. Reply received on 21.02.2024 5. L&T Observations sent on 23.04.2024 6. Vendor replied on 24.04.2024 7. L&T Observations sent on 24.04.2024 | 91769 66455 | subhash@avkindia.com |  | 20.01.24 | 31.01.24 | 09.02.24 | 13.02.24 | 15.02.24 | 21.02.24 | 23.04.24 | 24.04.24 | 24.04.24 |  |  | 03.05.24 | 03.05.24 | 21.05.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Butterfly Valves | LE23M598-M-WS-PV-PR-1905 | LE23M598-M-WS-PV-PR-1905-C | VAG | Sent to BU Operations | 75 | 1. Reminder sent on 03.02.2024 2. Reminder sent on 05.03.2024 3. Offer received on 08.03.2024 4. L&T Observations for actuator specificiations sent on 08.03.2024 5. Reminder sent on 02.04.2024 6. Vendor replied on 02.04.2024 7. Reminder sent on 11.04.2024 8. Vendor resent their replies on 12.04.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 20.01.24 | 08.03.24 | 19.04.24 | 21.05.24 | [7 empty] | 21.05.24 | 21.05.24 | 21.05.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:04
Firozabad WSP | Mechanical | Butterfly Valves | LE23M598-M-WS-PV-PR-1905 | LE23M598-M-WS-PV-PR-1905-D | Sigmaflow | Sent to BU Operations | 75 | 1. L&T observations sent on 09.02.2024 2. Reply received from vendor on 15.02.2024 3. Observations sent on 17.02.2024 4. Observations Mail resent on 01.03.2024 5. Vendor confirmation received on 04.03.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 20.01.24 | 23.01.24 | 29.04.24 | [8 empty] | 08.05.24 | 09.05.24 | 21.05.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:05
Firozabad WSP | Mechanical | Butterfly Valves | LE23M598-M-WS-PV-PR-1905 | LE23M598-M-WS-PV-PR-1905-E | Orbit Engineers | Sent to BU Operations | 75 | 1. L&T Observation to provide Actuator on 03.02.2024 2. GA drawing and QAP Sent by vendor on 20.02.2024 3. L&T Observation to provide Circuit diagram for actuators on 28.02.2024 4. Vendor replied with wiring diagram on 04.03.2024 5. Vendor replied again on 06.03.2024 with wiring diagrams | 78791 45143 | yogesh.orbitengineers@gmail.com |  | 20.01.24 | 23.01.24 | 29.04.24 | [8 empty] | 08.05.24 | 08.05.24 | 21.05.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:05
Firozabad WSP | Mechanical | Dual Plate Check Valves | LE23M598-M-WS-PV-PR-1910 | LE23M598-M-WS-PV-PR-1910-A | AVK | Sent to BU Operations | PR Closed | 1. L&T observations sent on 09.02.2024 2. Reply received on 23.02.2024 3. Additional observations sent on 26.02.2024 4. Vendor replied on 26.02.2024 5. Technically cleared on 27.02.2024 | 91769 66455 | subhash@avkindia.com |  | 23.01.24 | 01.02.24 | 09.02.24 | 23.02.24 | 26.02.24 | 26.02.24 | [5 empty] | 27.02.24 | 27.02.24 | 01.03.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-23.05.2024-15:48:01
Firozabad WSP | Mechanical | Dual Plate Check Valves | LE23M598-M-WS-PV-PR-1910 | LE23M598-M-WS-PV-PR-1910-B | VAG | Approved by Client | PR Closed | 1. L&T observations sent on 09.02.2024 2. Reply received on 22.02.2024 3. Data sheet sent to vendor on 26.02.2024 4. Vendor replied on 29.02.2024 5. Technical Clearance on 01.03.2024 | 91000 99176 | G.ArulSelvam@vag-group.com |  | 23.01.24 | 05.02.24 | 09.02.24 | 22.02.24 | 26.02.24 | 29.02.24 | [5 empty] | 01.03.24 | 01.03.24 | 01.03.24 | T1 | 25.04.24 | VAG | 17.05.24 | 20.05.24 | 29.05.24 | 30.05.24 | 30.05.24 |  |  | 24.06.24 | rachamalla.nithish@lntecc.com-03.06.2024-15:21:39
Firozabad WSP | Mechanical | Dual Plate Check Valves | LE23M598-M-WS-PV-PR-1910 | LE23M598-M-WS-PV-PR-1910-C | Sigmaflow | Sent to BU Operations | PR Closed | 1. L&T observations sent on 09.02.2024 2. Reply received on 22.02.2024 3. Technically Cleared on 27.02.2024 | 90733 42195 | jagadesh@sigmaflow.in |  | 23.01.24 | 05.02.24 | 09.02.24 | 22.02.24 | [7 empty] | 27.02.24 | 27.02.24 | 01.03.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-23.05.2024-15:48:01
Firozabad WSP | Mechanical | Dual Plate Check Valves | LE23M598-M-WS-PV-PR-1910 | LE23M598-M-WS-PV-PR-1910-D | Orbit Engineers | Sent to BU Operations | PR Closed | 1. Revised BOQ sent on 09.02.2024 2. Revised offer received on 14.02.2024 3. Technically Cleared on 27.02.2024 | 78791 45143 | yogesh.orbitengineers@gmail.com |  | 23.01.24 | 25.01.24 | 09.02.24 | 14.02.24 | [7 empty] | 27.02.24 | 27.02.24 | 01.03.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-23.05.2024-15:48:01
Firozabad WSP | Mechanical | Zero Velocity Valve | LE23M598-M-WS-PV-PR-1911 | LE23M598-M-WS-PV-PR-1911-A |  | Enquiry yet to float | NA | [29 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Air cushion Valve | LE23M598-M-WS-PV-PR-1912 | LE23M598-M-WS-PV-PR-1912-A |  | Enquiry yet to float | NA | [29 empty] | rachamalla.nithish@lntecc.com-14.05.2024-14:32:23
Firozabad WSP | Mechanical | Sluice Gates | LE23M598-M-WS-SG-PR-1909 | LE23M598-M-WS-SG-PR-1909-A | Jash | Post-order comments issued | 24 | 1. L&T Observations sent on 14.02.2024 2. Reminder sent on 27.02.2024 3. Reply received on 27.02.2024 4. Observation sent on 27.02.2024 for Circuit diagram 5. Reply received from Vendor on 04.03.2024 6. L&T Observation sent on 08.04.2024 7. Vendor replied on 11.04.2024 8. L&T Observations sent on 16.04.2024 9. Vendor replied on 16.04.2024 10. Technical clearance given on 26.04.2024 | 78699 10452 | robin@jashindia.com |  | 12.01.24 | 20.01.24 | 27.02.24 | 04.03.24 | 08.04.24 | 11.04.24 | 16.04.24 | 16.04.24 |  |  |  | 26.04.24 | 26.04.24 | 26.04.24 | T1 | 15.06.24 | Jash | 08.07.24 | 11.07.24 | [5 empty] | 14.08.24 | rachamalla.nithish@lntecc.com-29.07.2024-10:37:05
Firozabad WSP | Mechanical | Sluice Gates | LE23M598-M-WS-SG-PR-1909 | LE23M598-M-WS-SG-PR-1909-B | Oriental Castings | Sent to BU Operations | PR Closed | 1. L&T Observations sent on 17.02.2024 2. Reminder sent on 27.02.2024 3. Vendor replied on 02.03.2024 4. L&T Observation sent on 08.04.2024 5. Vendor replied for actuators on 09.04.2024 6. L&T Observations sent on 09.04.2024 7. Reminder on 16.04.2024 8. Technical clearance given on 26.04.2024 | 98102 05011 | orientalcastings@gmail.com |  | 12.01.24 | 17.01.24 | 17.02.24 | 02.03.24 | 08.04.24 | 18.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 26.04.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-17.06.2024-16:42:29
Firozabad WSP | Mechanical | Exhaust Fans | LE23M598-M-WS-VF-PR-1907 | LE23M598-M-WS-VF-PR-1907-A | Nadi | Pre-order technically cleared | 25 |  | 89398 12409 | satheeshkumar.r@nadiairtechnics.com |  | 03.04.24 | 04.04.24 | 23.05.24 | 23.05.24 | 18.06.24 | 24.06.24 | 09.07.24 | 09.07.24 |  |  |  | 10.07.24 | 10.07.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:05
Firozabad WSP | Mechanical | Exhaust Fans | LE23M598-M-WS-VF-PR-1907 | LE23M598-M-WS-VF-PR-1907-B | Almonard | Awaiting pre-offer from vendor | 123 |  | 99625 13700 | purchase.almonard@gmail.com |  | 03.04.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:37:05
Firozabad WSP | Instrumentation | Pressure Gauge / Compound Gauge | LE23M598-I-WS-WT-PR-5501 | LE23M598-I-WS-WT-PR-5501-A | H Guru | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Pressure Gauge / Compound gauge | LE23M598-I-WS-WT-PR-5501 | LE23M598-I-WS-WT-PR-5501-B | General instruments | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Pressure transmitter | LE23M598-I-WS-WT-PR-5502 | LE23M598-I-WS-WT-PR-5502-A | Siemens | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Pressure transmitter | LE23M598-I-WS-WT-PR-5502 | LE23M598-I-WS-WT-PR-5502-B | ABB | Pre-order pending with EDRC | 65 |  |  |  |  | 07.05.24 | 17.05.24 | 31.05.24 | 31.05.24 | [21 empty] | justin.v@lntecc.com-06.06.2024-18:16:53
Firozabad WSP | Instrumentation | Pressure transmitter | LE23M598-I-WS-WT-PR-5502 | LE23M598-I-WS-WT-PR-5502-C | E&H | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Pressure transmitter | LE23M598-I-WS-WT-PR-5502 | LE23M598-I-WS-WT-PR-5502-D | Vega | Pre-order comments issued | 61 |  |  |  |  | 07.05.24 | 17.05.24 | 04.06.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Float & Board Level gauge | LE23M598-I-WS-WT-PR-5503 | LE23M598-I-WS-WT-PR-5503-A | SBEM | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Float & Board Level gauge | LE23M598-I-WS-WT-PR-5503 | LE23M598-I-WS-WT-PR-5503-B | Pune techtrol | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Ultrasonic level transmitter | LE23M598-I-WS-WT-PR-5504 | LE23M598-I-WS-WT-PR-5504-A | Siemens | Pre-order comments issued | 61 |  |  |  |  | 07.05.24 | 07.05.24 | 21.05.24 | 22.05.24 | 04.06.24 | [20 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Ultrasonic level transmitter | LE23M598-I-WS-WT-PR-5504 | LE23M598-I-WS-WT-PR-5504-B | ABB | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Ultrasonic level transmitter | LE23M598-I-WS-WT-PR-5504 | LE23M598-I-WS-WT-PR-5504-C | E&H | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Ultrasonic level transmitter | LE23M598-I-WS-WT-PR-5504 | LE23M598-I-WS-WT-PR-5504-D | Vega | Pre-order comments issued | 80 |  |  |  |  | 07.05.24 | 15.05.24 | 16.05.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Electromagnectic flow meter | LE23M598-I-WS-WT-PR-5505 | LE23M598-I-WS-WT-PR-5505-A | Krohne | Pre-order comments issued | 61 |  |  |  |  | 07.05.24 | 24.05.24 | 04.06.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Electromagnectic flow meter | LE23M598-I-WS-WT-PR-5505 | LE23M598-I-WS-WT-PR-5505-B | ABB | Pre-order comments issued | 61 |  |  |  |  | 07.05.24 | 18.05.24 | 04.06.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Electromagnectic flow meter | LE23M598-I-WS-WT-PR-5505 | LE23M598-I-WS-WT-PR-5505-C | E&H | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Electromagnectic flow meter | LE23M598-I-WS-WT-PR-5505 | LE23M598-I-WS-WT-PR-5505-D | Siemens | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | pH Meter | LE23M598-I-WS-WT-PR-5506 | LE23M598-I-WS-WT-PR-5506-A | Hach | Pre-order comments issued | 61 |  |  |  |  | 07.05.24 | 09.05.24 | 13.05.24 | 16.05.24 | 04.06.24 | [20 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | pH Meter | LE23M598-I-WS-WT-PR-5506 | LE23M598-I-WS-WT-PR-5506-B | E&H | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | pH Meter | LE23M598-I-WS-WT-PR-5506 | LE23M598-I-WS-WT-PR-5506-C | Emerson | Pre-order comments issued | 83 |  |  |  |  | 07.05.24 | 10.05.24 | 13.05.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Turbidity meter | LE23M598-I-WS-WT-PR-5507 | LE23M598-I-WS-WT-PR-5507-A | Hach | Pre-order comments issued | 61 |  |  |  |  | 07.05.24 | 09.05.24 | 13.05.24 | 16.05.24 | 04.06.24 | [20 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Turbidity meter | LE23M598-I-WS-WT-PR-5507 | LE23M598-I-WS-WT-PR-5507-B | E&H | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Turbidity meter | LE23M598-I-WS-WT-PR-5507 | LE23M598-I-WS-WT-PR-5507-C | Emerson | Pre-order comments issued | 83 |  |  |  |  | 07.05.24 | 10.05.24 | 13.05.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Residual Chlorine Analyzer | LE23M598-I-WS-WT-PR-5508 | LE23M598-I-WS-WT-PR-5508-A | Hach | Pre-order comments issued | 61 |  |  |  |  | 07.05.24 | 09.05.24 | 13.05.24 | 16.05.24 | 04.06.24 | [20 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Residual Chlorine Analyzer | LE23M598-I-WS-WT-PR-5508 | LE23M598-I-WS-WT-PR-5508-B | E&H | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Residual Chlorine Analyzer | LE23M598-I-WS-WT-PR-5508 | LE23M598-I-WS-WT-PR-5508-C | Emerson | Pre-order comments issued | 83 |  |  |  |  | 07.05.24 | 10.05.24 | 13.05.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M598-I-WS-WT-PR-5509 | LE23M598-I-WS-WT-PR-5509-A | SIAS | Pre-order comments issued | 61 | Awaiting PLC I/O finalisation |  |  |  | 07.05.24 | 09.05.24 | 04.06.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M598-I-WS-WT-PR-5509 | LE23M598-I-WS-WT-PR-5509-B | Mitsubishi | Pre-order comments issued | 61 | Awaiting PLC I/O finalisation |  |  |  | 07.05.24 | 14.05.24 | 04.06.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M598-I-WS-WT-PR-5509 | LE23M598-I-WS-WT-PR-5509-C | Schneider | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M598-I-WS-WT-PR-5509 | LE23M598-I-WS-WT-PR-5509-D | Autosys | Pre-order comments issued | 61 | Awaiting PLC I/O finalisation |  |  |  | 07.05.24 | 10.05.24 | 04.06.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M598-I-WS-WT-PR-5509 | LE23M598-I-WS-WT-PR-5509-E | Mirrant | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Instrumentation Control & signal Cables | LE23M598-I-WS-WT-PR-5510 | LE23M598-I-WS-WT-PR-5510-A | Axelon | Pre-order comments issued | 61 | Awaiting finalisation of cable quantity |  |  |  | 07.05.24 | 09.05.24 | 18.05.24 | 19.05.24 | 04.06.24 | [20 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Instrumentation Control & signal Cables | LE23M598-I-WS-WT-PR-5510 | LE23M598-I-WS-WT-PR-5510-B | Cords | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | UPS | LE23M598-I-WS-WT-PR-5511 | LE23M598-I-WS-WT-PR-5511-A | Hitachi | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | UPS | LE23M598-I-WS-WT-PR-5511 | LE23M598-I-WS-WT-PR-5511-B | Vertiv | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | UPS | LE23M598-I-WS-WT-PR-5511 | LE23M598-I-WS-WT-PR-5511-C | Liveline | Pre-order comments issued | 61 | Awaiting load finalisation |  |  |  | 07.05.24 | 17.05.24 | 04.06.24 | [22 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Instrumentation | Solar and Battery system | LE23M598-I-WS-WT-PR-5512 | LE23M598-I-WS-WT-PR-5512-A | SIAS | Awaiting pre-offer from vendor | 89 |  |  |  |  | 07.05.24 | [24 empty] | justin.v@lntecc.com-06.06.2024-18:17:06
Firozabad WSP | Electrical | Transformers | LE23M598-E-WS-CW-PR-4202 | LE23M598-E-WS-CW-PR-4202-A | ITE | Sent to BU Operations | 66 |  | 98991 33500 | sales@indiantransformers.com |  | 20.01.24 | 05.02.24 | 19.2.24 | 23.05.24 | [7 empty] | 28.05.24 | 23.05.24 | 30.05.24 | T1 | [7 empty] | 30.05.24 | 16.06.24 | 15.08.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Transformers | LE23M598-E-WS-CW-PR-4202 | LE23M598-E-WS-CW-PR-4202-B | Uttam Bharat | Sent to BU Operations | 66 |  | 88249 10561 | marketing@uttam-bharat.com |  | 20.01.24 | 25.01.24 | 01.03.24 | 12.03.24 | 20.03.24 | [6 empty] | 02.05.24 | 03.05.24 | 30.05.24 | T1 | [7 empty] | 30.05.24 | 16.06.24 | 15.08.24 | usman.mohideen@lntecc.com-01.07.2024-16:38:24
Firozabad WSP | Electrical | Transformers | LE23M598-E-WS-CW-PR-4202 | LE23M598-E-WS-CW-PR-4202-C | Voltech | Sent to BU Operations | 66 |  | 96000 95932 | ragu.g@voltechgroup.com |  | 20.01.24 | 05.02.24 | 21.02.24 | 27.02.24 | 02.03.24 | 06.03.24 | [5 empty] | 21.03.24 | 21.03.24 | 30.05.24 | T1 | [7 empty] | 30.05.24 | 16.06.24 | 15.08.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Transformers | LE23M598-E-WS-CW-PR-4202 | LE23M598-E-WS-CW-PR-4202-D | Voltamp | Sent to BU Operations | 66 |  | 78618 14751 | ks_vtlchn@voltamptransformers.com |  | 20.01.24 | 24.02.24 | 01.03.24 | [8 empty] | 01.03.24 | 01.03.24 | 30.05.24 | T1 | [7 empty] | 30.05.24 | 16.06.24 | 15.08.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Transformers | LE23M598-E-WS-CW-PR-4202 | LE23M598-E-WS-CW-PR-4202-E | Sai electricals | Sent to BU Operations | 66 |  |  |  |  | 04.05.24 | 09.05.24 | 16.05.24 | 27.05.24 | [7 empty] | 29.05.24 | 27.05.24 | 30.05.24 | T1 | [7 empty] | 30.05.24 | 16.06.24 | 15.08.24 | usman.mohideen@lntecc.com-01.07.2024-16:38:24
Firozabad WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M598-E-WS-CW-PR-4203 | LE23M598-E-WS-CW-PR-4203-A | Sri Ragavendra Controls | Pre-order comments issued | 80 |  | 98947 13024 | ashok@ragavendracontrol.com |  | 03.02.24 | 12.02.24 | 03.05.24 | 16.05.24 | [18 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M598-E-WS-CW-PR-4203 | LE23M598-E-WS-CW-PR-4203-B | Universal Power | Pre-order comments issued | 151 |  | 95000 95075 | deepak@upe.co.in |  | 03.02.24 | 09.02.24 | 16.02.24 | 19.02.24 | 06.03.24 | [17 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M598-E-WS-CW-PR-4203 | LE23M598-E-WS-CW-PR-4203-C | Kontact | Pre-order pending with EDRC | 90 |  | 90878 40000 | vijendra@kontact.in |  | 03.02.24 | 10.02.24 | 19.02.24 | 30.03.24 | 30.04.24 | 06.05.24 | [16 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M598-E-WS-CW-PR-4203 | LE23M598-E-WS-CW-PR-4203-D | Stambh | Pre-order technically cleared | 116 |  | 97920 01030 | rupali@stambhindia.com |  | 03.02.24 | 05.02.24 | 13.02.24 | 27.02.24 | 20.03.24 | [6 empty] | 21.03.24 | 10.04.24 | [9 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | LT Switchgear & Auxillary Panels | LE23M598-E-WS-CW-PR-4203 | LE23M598-E-WS-CW-PR-4203-E | Vivid Electromech | Pre-order technically cleared | 96 |  | 91679 80556 | chennai.sales@vividgroup.in |  | 03.02.24 | 12.02.24 | 17.02.24 | 25.03.24 | 26.03.24 | [6 empty] | 28.03.24 | 30.04.24 | [9 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | DG Sets | LE23M598-E-WS-CW-PR-4204 | LE23M598-E-WS-CW-PR-4204-A | Prime Powergen | Post-order technically cleared | 138 |  | 91001 55773 | chitendar@primepowergen.com |  | 22.01.24 | 24.01.24 | 31.01.24 | 06.02.24 | 14.02.24 | [6 empty] | 26.02.24 | 26.02.24 | 26.02.24 | T1 | 19.03.24 | Prime Powergen | 16.3.24 | 19.3.24 | 16.3.24 | 19.3.24 |  | 11.03.24 | 28.03.24 | 18.05.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | DG Sets | LE23M598-E-WS-CW-PR-4204 | LE23M598-E-WS-CW-PR-4204-B | Jakson | Sent to BU Operations | PR Closed |  | 98369 63737 | ayan.das@jakson.com |  | 30.01.24 | 02.02.24 | 10.3.24 | [8 empty] | 10.3.24 | 5.3.24 | 10.3.24 | T2 | [7 empty] | 11.03.24 | 28.03.24 | 27.05.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | DG Sets | LE23M598-E-WS-CW-PR-4204 | LE23M598-E-WS-CW-PR-4204-C | Greaves Cotton | Sent to BU Operations | PR Closed |  | 70303 11775 | s.banerjee@greavescotton.com |  | 30.01.24 | 09.02.24 | 15.02.24 | 28.02.24 | 28.02.24 | 02.03.24 | [5 empty] | 05.03.24 | 05.03.24 | 05.03.24 | T1 | [7 empty] | 11.03.24 | 28.03.24 | 27.05.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | DG Sets | LE23M598-E-WS-CW-PR-4204 | LE23M598-E-WS-CW-PR-4204-D | IEC | Regret offer | PR Closed |  | 98105 59597 | rajnish.sharma@iecgensets.com |  | 30.01.24 | [21 empty] | 11.03.24 | 28.03.24 | 27.05.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Switchgear, Switchyard | LE23M598-E-WS-CW-PR-4205 | LE23M598-E-WS-CW-PR-4205-A | Universal Power | Pre-order technically cleared | 87 |  | 95000 95075 | deepak@upe.co.in |  | 02.02.24 | 09.02.24 | 14.02.24 | 19.02.24 | 20.03.24 | [6 empty] | 2.5.24 | 2.4.24 | 09.05.24 | [8 empty] | 09.05.24 | 26.05.24 | 25.07.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Switchgear, Switchyard | LE23M598-E-WS-CW-PR-4205 | LE23M598-E-WS-CW-PR-4205-B | Kontact | Pre-order technically cleared | 87 |  | 90878 40000 | vijendra@kontact.in |  | 02.02.24 | 10.02.24 | 19.2.24 | 06.05.24 | 09.05.24 | [6 empty] | 09.05.24 | 09.05.24 | 09.05.24 | [8 empty] | 09.05.24 | 26.05.24 | 25.07.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Switchgear, Switchyard | LE23M598-E-WS-CW-PR-4205 | LE23M598-E-WS-CW-PR-4205-C | Vivid Electromech | Pre-order technically cleared | 87 |  | 91679 80556 | chennai.sales@vividgroup.in |  | 02.02.24 | 12.02.24 | 17.02.24 | 24.02.24 | 21.03.24 | [6 empty] | 30.4.24 | 06.05.24 | 09.05.24 | [8 empty] | 09.05.24 | 26.05.24 | 25.07.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT/LT Power and Control Cable | LE23M598-E-WS-CW-PR-4206 | LE23M598-E-WS-CW-PR-4206-A | Havells | Regret offer | PR Closed |  | 94377 68522 | santosh.swain@havells.com |  | 08.02.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT/LT Power and Control Cable | LE23M598-E-WS-CW-PR-4206 | LE23M598-E-WS-CW-PR-4206-B | KEI | Regret offer | PR Closed |  | 89291 60605 | vincent.kallen@kei-ind.com |  | 08.02.24 | 16.02.24 | [20 empty] | 30.08.24 | 16.09.24 | 15.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT/LT Power and Control Cable | LE23M598-E-WS-CW-PR-4206 | LE23M598-E-WS-CW-PR-4206-C | Axelon | Regret offer | PR Closed |  | 98677 69603 | hardik@axeloninternational.com |  | 08.02.24 | 08.02.24 | [20 empty] | 30.08.24 | 16.09.24 | 15.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT/LT Power and Control Cable | LE23M598-E-WS-CW-PR-4206 | LE23M598-E-WS-CW-PR-4206-D | Monaj Trading | Regret offer | PR Closed |  | 98305 69644 | monajtrading@gmail.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT/LT Power and Control Cable | LE23M598-E-WS-CW-PR-4206 | LE23M598-E-WS-CW-PR-4206-E | Stokes | Regret offer | PR Closed |  | 98401 52061 | sales@stokesglands.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT/LT Power and Control Cable | LE23M598-E-WS-CW-PR-4206 | LE23M598-E-WS-CW-PR-4206-F | Govind Electricals | Regret offer | PR Closed |  | 98401 89014 | sgovindele@gmail.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Cable Termination Kit | LE23M598-E-WS-CW-PR-4207 | LE23M598-E-WS-CW-PR-4207-A | Havells | Regret offer | PR Closed |  | 94377 68522 |  |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Cable Termination Kit | LE23M598-E-WS-CW-PR-4207 | LE23M598-E-WS-CW-PR-4207-B | KEI | Regret offer | PR Closed |  | 89291 60605 | vincent.kallen@kei-ind.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Cable Termination Kit | LE23M598-E-WS-CW-PR-4207 | LE23M598-E-WS-CW-PR-4207-C | Axelon | Regret offer | PR Closed |  | 98677 69603 | hardik@axeloninternational.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Cable Termination Kit | LE23M598-E-WS-CW-PR-4207 | LE23M598-E-WS-CW-PR-4207-D | Monaj Trading | Regret offer | PR Closed |  | 98305 69644 | monajtrading@gmail.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Cable Termination Kit | LE23M598-E-WS-CW-PR-4207 | LE23M598-E-WS-CW-PR-4207-E | Stokes | Regret offer | PR Closed |  | 98401 52061 | sales@stokesglands.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | HT Cable Termination Kit | LE23M598-E-WS-CW-PR-4207 | LE23M598-E-WS-CW-PR-4207-F | Govind Electricals | Regret offer | PR Closed |  | 98401 89014 | sgovindele@gmail.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Glands & Lugs | LE23M598-E-WS-CW-PR-4208 | LE23M598-E-WS-CW-PR-4208-A | Havells | Regret offer | PR Closed |  | 94377 68522 |  |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Glands & Lugs | LE23M598-E-WS-CW-PR-4208 | LE23M598-E-WS-CW-PR-4208-B | KEI | Regret offer | PR Closed |  | 89291 60605 | vincent.kallen@kei-ind.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Glands & Lugs | LE23M598-E-WS-CW-PR-4208 | LE23M598-E-WS-CW-PR-4208-C | Axelon | Regret offer | PR Closed |  | 98677 69603 | hardik@axeloninternational.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Glands & Lugs | LE23M598-E-WS-CW-PR-4208 | LE23M598-E-WS-CW-PR-4208-D | Monaj Trading | Regret offer | PR Closed |  | 98305 69644 | monajtrading@gmail.com |  | 08.02.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Glands & Lugs | LE23M598-E-WS-CW-PR-4208 | LE23M598-E-WS-CW-PR-4208-E | Stokes | Regret offer | PR Closed |  | 98401 52061 | sales@stokesglands.com |  | 08.02.24 | 10.02.24 | [20 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Glands & Lugs | LE23M598-E-WS-CW-PR-4208 | LE23M598-E-WS-CW-PR-4208-F | Govind Electricals | Regret offer | PR Closed |  | 98401 89014 | sgovindele@gmail.com |  | 08.02.24 | 16.02.24 | [20 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Tray & Supports | LE23M598-E-WS-CW-PR-4209 | LE23M598-E-WS-CW-PR-4209-A | Site Procurement | Pre-order technically cleared | 211 | Technical clearance provided |  |  |  | 06.01.24 | 06.01.24 | 06.01.24 | [8 empty] | 06.01.24 | 06.01.24 | [9 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Tray & Supports | LE23M598-E-WS-CW-PR-4209 | LE23M598-E-WS-CW-PR-4209-B |  | Enquiry yet to float | NA |  |  |  |  | 06.01.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Cable Tray & Supports | LE23M598-E-WS-CW-PR-4209 | LE23M598-E-WS-CW-PR-4209-C |  | Enquiry yet to float | NA |  |  |  |  | 06.01.24 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Illumination | LE23M598-E-WS-CW-PR-4210 | LE23M598-E-WS-CW-PR-4210-A |  | Enquiry yet to float | NA | [26 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Illumination | LE23M598-E-WS-CW-PR-4210 | LE23M598-E-WS-CW-PR-4210-B |  | Enquiry yet to float | NA | [26 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Earthing & Lightning Protection | LE23M598-E-WS-CW-PR-4213 | LE23M598-E-WS-CW-PR-4213-A | Site Procurement | Pre-order technically cleared | 222 | Technical clearance provided |  |  |  | 26.12.23 | 26.12.23 | 26.12.23 | [8 empty] | 26.12.23 | 26.12.23 | [9 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Earthing & Lightning Protection | LE23M598-E-WS-CW-PR-4213 | LE23M598-E-WS-CW-PR-4213-B |  | Enquiry yet to float | NA |  |  |  |  | 26.12.23 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Earthing & Lightning Protection | LE23M598-E-WS-CW-PR-4213 | LE23M598-E-WS-CW-PR-4213-C |  | Enquiry yet to float | NA |  |  |  |  | 26.12.23 | [21 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Local Push Button Stations (LPBS) | LE23M598-E-WS-CW-PR-4214 | LE23M598-E-WS-CW-PR-4214-A | Universal Power | Sent to BU Operations | 136 |  | 95000 95075 | deepak@upe.co.in |  | 06.02.24 | 19.02.24 | 19.02.24 | 19.02.24 | [7 empty] | 21.03.24 | 21.03.24 | 21.03.24 | T1 | [7 empty] | 15.05.24 | 01.06.24 | 31.07.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Local Push Button Stations (LPBS) | LE23M598-E-WS-CW-PR-4214 | LE23M598-E-WS-CW-PR-4214-B | Sri Ragavendra Controls | Pre-order technically cleared | 81 |  | 98947 13024 | ashok@ragavendracontrol.com |  | 06.02.24 | 12.02.24 | 03.05.24 | [8 empty] | 15.05.24 | 15.05.24 | [9 empty] | 15.05.24 | 01.06.24 | 31.07.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Firozabad WSP | Electrical | Electrical Safety | LE23M598-E-WS-CW-PR-4216 | LE23M598-E-WS-CW-PR-4216-A | Site Procurement | Pre-order technically cleared | 313 |  |  |  |  | 26.09.23 | 26.09.23 | 26.09.23 | [8 empty] | 26.09.23 | 26.09.23 | [9 empty] | 02.09.24 | 19.09.24 | 18.11.24 | usman.mohideen@lntecc.com-01.07.2024-16:44:58
Ganjam | Process | Clariflocculator mechanism | LE23M379-P-WS-WT-PR-2102 | LE23M379-P-WS-WT-PR-2102-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Air Blower | LE23M379-P-WS-WT-PR-2103 | LE23M379-P-WS-WT-PR-2103-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Agitator | LE23M379-P-WS-WT-PR-2104 | LE23M379-P-WS-WT-PR-2104-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | WTP Sluice gates | LE23M379-P-WS-WT-PR-2105 | LE23M379-P-WS-WT-PR-2105-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Chlorination system | LE23M379-P-WS-WT-PR-2106 | LE23M379-P-WS-WT-PR-2106-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Chlorine Tonners | LE23M379-P-WS-WT-PR-2107 | LE23M379-P-WS-WT-PR-2107-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Filter media | LE23M379-P-WS-WT-PR-2108 | LE23M379-P-WS-WT-PR-2108-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Backwash pump | LE23M379-P-WS-WT-PR-2109 | LE23M379-P-WS-WT-PR-2109-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Submersible pump | LE23M379-P-WS-WT-PR-2110 | LE23M379-P-WS-WT-PR-2110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Electrical hoist | LE23M379-P-WS-WT-PR-2111 | LE23M379-P-WS-WT-PR-2111-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Manual chain pulley block | LE23M379-P-WS-WT-PR-2112 | LE23M379-P-WS-WT-PR-2112-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Dosing pump | LE23M379-P-WS-WT-PR-2113 | LE23M379-P-WS-WT-PR-2113-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Sampling pump | LE23M379-P-WS-WT-PR-2114 | LE23M379-P-WS-WT-PR-2114-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Submersible mixer | LE23M379-P-WS-WT-PR-2115 | LE23M379-P-WS-WT-PR-2115-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Dewatering pump | LE23M379-P-WS-WT-PR-2116 | LE23M379-P-WS-WT-PR-2116-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Dissolving tray | LE23M379-P-WS-WT-PR-2117 | LE23M379-P-WS-WT-PR-2117-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Trolley | LE23M379-P-WS-WT-PR-2118 | LE23M379-P-WS-WT-PR-2118-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Platform weighing machine | LE23M379-P-WS-WT-PR-2119 | LE23M379-P-WS-WT-PR-2119-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Exhaust fan | LE23M379-P-WS-WT-PR-2120 | LE23M379-P-WS-WT-PR-2120-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | lab equipment | LE23M379-P-WS-WT-PR-2121 | LE23M379-P-WS-WT-PR-2121-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Sludge Thickener | LE23M379-P-WS-WT-PR-2122 | LE23M379-P-WS-WT-PR-2122-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | DWPE tanks & Agitators | LE23M379-P-WS-WT-PR-2123 | LE23M379-P-WS-WT-PR-2123-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Centrifuge | LE23M379-P-WS-WT-PR-2124 | LE23M379-P-WS-WT-PR-2124-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Screw pumps | LE23M379-P-WS-WT-PR-2125 | LE23M379-P-WS-WT-PR-2125-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | PACL Unloading cum Transfer pump | LE23M379-P-WS-WT-PR-2126 | LE23M379-P-WS-WT-PR-2126-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Service water pump | LE23M379-P-WS-WT-PR-2127 | LE23M379-P-WS-WT-PR-2127-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Process | Filter Nozzles | LE23M379-P-WS-WT-PR-2128 | LE23M379-P-WS-WT-PR-2128-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | premkumar.nagarajan@lntecc.com
Ganjam | Mechanical | Sluice Gate - CWPH & IBPS | LE20M188-M-WS-CW-PR-1517 | LE20M188-M-WS-CW-PR-1517-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | HSC Pump - CWPH & IBPS | LE23M379-M-WS-CW-PR-1503 | LE23M379-M-WS-CW-PR-1503-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | SLV - CWPH & IBPS | LE23M379-M-WS-CW-PR-1504 | LE23M379-M-WS-CW-PR-1504-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | NRV - CWPH & IBPS | LE23M379-M-WS-CW-PR-1505 | LE23M379-M-WS-CW-PR-1505-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | DJ - CWPH & IBPS | LE23M379-M-WS-CW-PR-1506 | LE23M379-M-WS-CW-PR-1506-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | AV - CWPH & IBPS | LE23M379-M-WS-CW-PR-1507 | LE23M379-M-WS-CW-PR-1507-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | EOT Crane - CWPH & IBPS | LE23M379-M-WS-CW-PR-1509 | LE23M379-M-WS-CW-PR-1509-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | BFV - CWPH & IBPS | LE23M379-M-WS-CW-PR-1510 | LE23M379-M-WS-CW-PR-1510-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | Electric Hoist - CWPH & IBPS | LE23M379-M-WS-CW-PR-1511 | LE23M379-M-WS-CW-PR-1511-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | Submersible Pump - CWPH & IBPS | LE23M379-M-WS-CW-PR-1512 | LE23M379-M-WS-CW-PR-1512-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | Isolation Valve - Pipeline | LE23M379-M-WS-CW-PR-1513 | LE23M379-M-WS-CW-PR-1513-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | AV - Pipeline | LE23M379-M-WS-CW-PR-1514 | LE23M379-M-WS-CW-PR-1514-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | PRV - Pipeline | LE23M379-M-WS-CW-PR-1515 | LE23M379-M-WS-CW-PR-1515-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | FCV - Pipeline | LE23M379-M-WS-CW-PR-1516 | LE23M379-M-WS-CW-PR-1516-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | ACV - Surge Protection Device | LE23M379-M-WS-CW-PR-1518 | LE23M379-M-WS-CW-PR-1518-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | ZVV - Surge Protection Device | LE23M379-M-WS-CW-PR-1519 | LE23M379-M-WS-CW-PR-1519-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | Surge Vessel - Surge Protection Device | LE23M379-M-WS-CW-PR-1520 | LE23M379-M-WS-CW-PR-1520-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | Exhaust fan - Mech | LE23M379-M-WS-CW-PR-1521 | LE23M379-M-WS-CW-PR-1521-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | VT Pump - Intake | LE23M379-M-WS-RW-PR-1501A | LE23M379-M-WS-RW-PR-1501A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | Sluice Gate - Intake | LE23M379-M-WS-RW-PR-1502A | LE23M379-M-WS-RW-PR-1502A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | SLV - Intake | LE23M379-M-WS-RW-PR-1504 | LE23M379-M-WS-RW-PR-1504-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | NRV - Intake | LE23M379-M-WS-RW-PR-1505 | LE23M379-M-WS-RW-PR-1505-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | DJ - Intake | LE23M379-M-WS-RW-PR-1506 | LE23M379-M-WS-RW-PR-1506-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | AV - Intake | LE23M379-M-WS-RW-PR-1507 | LE23M379-M-WS-RW-PR-1507-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | EB - Intake | LE23M379-M-WS-RW-PR-1508 | LE23M379-M-WS-RW-PR-1508-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Mechanical | EOT Crane - Intake | LE23M379-M-WS-RW-PR-1509 | LE23M379-M-WS-RW-PR-1509-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Ganjam | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE23M379-I-WS-WT-PR-5501 | LE23M379-I-WS-WT-PR-5501-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Pressure Switch | LE23M379-I-WS-WT-PR-5502 | LE23M379-I-WS-WT-PR-5502-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Pressure transmitter | LE23M379-I-WS-WT-PR-5503 | LE23M379-I-WS-WT-PR-5503-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Float & Board Level gauge | LE23M379-I-WS-WT-PR-5504 | LE23M379-I-WS-WT-PR-5504-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | level switch - Conductivity type | LE23M379-I-WS-WT-PR-5505 | LE23M379-I-WS-WT-PR-5505-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Ultrasonic level Transmitter | LE23M379-I-WS-WT-PR-5506 | LE23M379-I-WS-WT-PR-5506-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Radar Level Transmitter | LE23M379-I-WS-WT-PR-5507 | LE23M379-I-WS-WT-PR-5507-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Loss of head transmitter | LE23M379-I-WS-WT-PR-5508 | LE23M379-I-WS-WT-PR-5508-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Rate for flow transmitter | LE23M379-I-WS-WT-PR-5509 | LE23M379-I-WS-WT-PR-5509-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Bypass Rotameter | LE23M379-I-WS-WT-PR-5510 | LE23M379-I-WS-WT-PR-5510-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Electromagnectic flow meter | LE23M379-I-WS-WT-PR-5511 | LE23M379-I-WS-WT-PR-5511-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Ultrasonic type Open channel flow transmitter | LE23M379-I-WS-WT-PR-5512 | LE23M379-I-WS-WT-PR-5512-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Battery Operated Flow meter | LE23M379-I-WS-WT-PR-5513 | LE23M379-I-WS-WT-PR-5513-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | pH Meter | LE23M379-I-WS-WT-PR-5514 | LE23M379-I-WS-WT-PR-5514-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Turbidity meter | LE23M379-I-WS-WT-PR-5515 | LE23M379-I-WS-WT-PR-5515-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Residual Chlorine Analyzer | LE23M379-I-WS-WT-PR-5516 | LE23M379-I-WS-WT-PR-5516-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE23M379-I-WS-WT-PR-5517 | LE23M379-I-WS-WT-PR-5517-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | Instrumentation Control & signal Cables | LE23M379-I-WS-WT-PR-5518 | LE23M379-I-WS-WT-PR-5518-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Instrumentation | UPS | LE23M379-I-WS-WT-PR-5519 | LE23M379-I-WS-WT-PR-5519-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | vignesh.c1@lntecc.com
Ganjam | Electrical | CTPT Unit | LE23M379-E-WS-WT-PR-4201 | LE23M379-E-WS-WT-PR-4201-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Poles & conductors | LE23M379-E-WS-WT-PR-4201A | LE23M379-E-WS-WT-PR-4201A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Transformer | LE23M379-E-WS-WT-PR-4203 | LE23M379-E-WS-WT-PR-4203-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | HT Panel | LE23M379-E-WS-WT-PR-4204 | LE23M379-E-WS-WT-PR-4204-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | HT Soft Starter | LE23M379-E-WS-WT-PR-4205 | LE23M379-E-WS-WT-PR-4205-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | DG Set | LE23M379-E-WS-WT-PR-4206 | LE23M379-E-WS-WT-PR-4206-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | LT panels | LE23M379-E-WS-WT-PR-4207 | LE23M379-E-WS-WT-PR-4207-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Bus Duct | LE23M379-E-WS-WT-PR-4208 | LE23M379-E-WS-WT-PR-4208-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | HT VFD | LE23M379-E-WS-WT-PR-4209 | LE23M379-E-WS-WT-PR-4209-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Power and Control Cable | LE23M379-E-WS-WT-PR-4210 | LE23M379-E-WS-WT-PR-4210-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Cable Tray | LE23M379-E-WS-WT-PR-4211 | LE23M379-E-WS-WT-PR-4211-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Lugs & Glands | LE23M379-E-WS-WT-PR-4212 | LE23M379-E-WS-WT-PR-4212-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | HT Termination Kit | LE23M379-E-WS-WT-PR-4212A | LE23M379-E-WS-WT-PR-4212A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | LPBS | LE23M379-E-WS-WT-PR-4213 | LE23M379-E-WS-WT-PR-4213-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Earthing & Lightning Material | LE23M379-E-WS-WT-PR-4214 | LE23M379-E-WS-WT-PR-4214-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Lighting Fixtures | LE23M379-E-WS-WT-PR-4215 | LE23M379-E-WS-WT-PR-4215-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Lighting Materials & accessories | LE23M379-E-WS-WT-PR-4215A | LE23M379-E-WS-WT-PR-4215A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | LDB | LE23M379-E-WS-WT-PR-4215B | LE23M379-E-WS-WT-PR-4215B-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Ganjam | Electrical | Safety Accessories | LE23M379-E-WS-WT-PR-4216 | LE23M379-E-WS-WT-PR-4216-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Gond Devsar | Process | Clariflocculator mechanism | LE20M186-P-002 | LE20M186-P-002-B | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 28.12.22 | 07.01.23 | [8 empty] | 08.07.23 | 08.07.23 | 20.07.23 | [7 empty] | 07.08.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Clariflocculator mechanism | LE20M186-P-002 | LE20M186-P-002-C | Adroit | Approved by Client | PR Closed |  | +91-91790-21490 | shubham@adroitindia.co.in | 29.01.22 | 29.01.22 | 18.05.23 | 18.05.23 | [8 empty] | 18.05.23 | 18.05.23 | 15.07.23 | T1 | 18.09.23 | Adroit | 24.10.23 | 31.10.23 | 20.11.23 | 23.11.23 | 23.11.23 |  |  | 17.11.23 | premkumar.nagarajan@lntecc.com-15.04.2024-10:55:50
Gond Devsar | Process | Air Blower | LE20M186-P-003 | LE20M186-P-003-A | Everest | Sent to BU Operations | PR Closed |  |  |  | 01.10.22 | 01.10.22 | 12.12.22 | 29.12.22 | [8 empty] | 08.02.24 | 08.02.24 | 22.02.24 | [7 empty] | 09.03.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Air Blower | LE20M186-P-003 | LE20M186-P-003-B | kay | Approved by Client | PR Closed | Awaiting client approval | 8572899449 | manish@kayblowers.com | 01.10.22 | 01.10.22 | 14.02.23 | 08.03.23 | [8 empty] | 03.08.23 | 16.02.23 | 02.05.23 | T1 | 07.08.23 | kay | 21.09.23 | 26.09.23 | 26.09.23 | 26.09.23 | 26.09.23 |  |  | 06.10.23 | premkumar.nagarajan@lntecc.com-30.05.2024-10:36:27
Gond Devsar | Process | Air Blower | LE20M186-P-003 | LE20M186-P-003-C | Atlas Copco | Sent to BU Operations | PR Closed |  |  |  | 01.10.22 | 01.10.22 | 08.02.23 | 10.03.23 | [8 empty] | 03.10.23 | 03.10.23 | 23.10.23 | [7 empty] | 02.11.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Agitator | LE20M186-P-004 | LE20M186-P-004-A | Triveni Engineering | Sent to BU Operations | PR Closed |  |  |  | 19.01.22 | 19.01.22 | 09.01.23 | 25.01.23 | [8 empty] | 25.01.23 | 25.01.23 | 09.02.23 | [7 empty] | 24.02.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Agitator | LE20M186-P-004 | LE20M186-P-004-B | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 19.01.22 | 19.01.22 | 28.12.22 | 07.01.23 | [8 empty] | 01.07.23 | 01.07.23 | 17.07.23 | [7 empty] | 31.07.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Agitator | LE20M186-P-004 | LE20M186-P-004-C | Adroit | Approved by Client | PR Closed |  | +91-91790-21490 | shubham@adroitindia.co.in | 19.01.22 | 19.01.22 | 06.04.23 | 06.04.23 | [8 empty] | 05.06.23 | 05.06.23 | 15.07.23 | T1 | 06.10.23 | Adroit | 11.10.23 | 18.10.23 | 15.11.23 | 15.11.23 | 15.11.23 |  |  | 05.12.23 | premkumar.nagarajan@lntecc.com-15.04.2024-10:55:50
Gond Devsar | Process | WTP Sluice gates | LE20M186-P-005 | LE20M186-P-005-A | Oriental | Sent to BU Operations | PR Closed |  |  |  | 19.02.22 | 19.02.22 | 28.08.23 | 15.09.23 | [8 empty] | 15.09.23 | 15.09.23 | 12.10.23 | [7 empty] | 15.10.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | WTP Sluice gates | LE20M186-P-005 | LE20M186-P-005-B | Hindustan water engg | Sent to BU Operations | PR Closed |  |  |  | 19.02.22 | 19.02.22 | 04.10.23 | 03.09.23 | [8 empty] | 15.09.23 | 15.09.23 | 28.09.23 | [7 empty] | 15.10.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | WTP Sluice gates | LE20M186-P-005 | LE20M186-P-005-C | Jash | Approved by Client | PR Closed |  | 72900 40722 | lpgsouth2@jashindia.com | 19.02.22 | 19.02.22 | 08.08.23 | 19.08.23 | [8 empty] | 19.08.23 | 19.08.23 | 12.12.23 | T1 | 16.12.23 | Jash | 10.01.24 | 16.01.24 | 16.01.24 | 16.01.24 | 16.01.24 |  |  | 14.02.24 | premkumar.nagarajan@lntecc.com-15.04.2024-10:55:50
Gond Devsar | Process | Chlorination system | LE20M186-P-006 | LE20M186-P-006-A | Zion | Approved by Client | PR Closed |  | 8094570996 / 9828977765 | deepak@ziontech.in | 10.02.22 | 10.02.22 | 27.04.22 | 16.01.23 | [8 empty] | 16.01.23 | 16.01.23 | 07.04.23 | T1 | 15.07.23 | Zion | 15.07.23 | 15.07.23 | 25.07.23 | 25.07.23 | 25.07.23 |  |  | 13.09.23 | premkumar.nagarajan@lntecc.com-15.04.2024-10:55:50
Gond Devsar | Process | Chlorination system | LE20M186-P-006 | LE20M186-P-006-B | ME INFRA | Sent to BU Operations | PR Closed |  |  |  | 10.02.22 | 10.02.22 | 19.01.23 | 06.03.23 | [8 empty] | 06.03.23 | 06.03.23 | 27.03.23 | [7 empty] | 05.04.23 |  |  |  | premkumar.nagarajan@lntecc.com-28.02.2024-14:05:21
Gond Devsar | Process | Chlorination system | LE20M186-P-006 | LE20M186-P-006-C | Supreme Technologies | Sent to BU Operations | PR Closed |  |  |  | 10.02.22 | 10.02.22 | 07.04.23 | 24.04.23 | [8 empty] | 28.04.23 | 28.04.23 | 17.05.23 | [7 empty] | 28.05.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Air compressor | LE20M186-P-007 | LE20M186-P-007-A | Elgi | Pre-order comments issued | 48 |  |  |  | 10.01.22 | 10.01.22 | 17.09.23 | 21.09.23 | 15.06.24 | 17.06.24 | [9 empty] | T1 | [10 empty] | premkumar.nagarajan@lntecc.com-10.07.2024-16:39:24
Gond Devsar | Process | Air compressor | LE20M186-P-007 | LE20M186-P-007-B | Indo Air | Regret offer | PR Closed | Post order document has been rejected by client | VIJAYA S PILLAI 7359033349 | sales4@indoair.com | 10.01.22 | 10.01.22 | 06.10.23 | 09.10.23 | 13.05.24 | [7 empty] | 13.10.23 | 13.10.23 | 13.10.23 | T3 | 30.03.24 | Indo Air | 19.04.24 | 24.04.24 | 27.05.24 | 27.05.24 |  |  |  | 29.05.24 | premkumar.nagarajan@lntecc.com-10.07.2024-16:39:24
Gond Devsar | Process | Air compressor | LE20M186-P-007 | LE20M186-P-007-C | Atlas copco | Sent to BU Operations | 201 |  |  |  | 10.01.22 | 10.01.22 | 26.12.23 | 28.12.23 | [8 empty] | 16.01.24 | 16.01.24 | 16.01.24 | T2 | [10 empty] | premkumar.nagarajan@lntecc.com-10.07.2024-16:39:24
Gond Devsar | Process | Filter media | LE20M186-P-008 | LE20M186-P-008-A | Dalton Minerals | Approved by Client | PR Closed |  | 011 - 2994 8540 | daltonminerals@gmail.com | 5.02.22 | 05.02.22 | 24.10.23 | 25.10.23 | [8 empty] | 25.10.23 | 25.10.23 | 26.10.23 | T1 | 14.11.23 | Dalton Minerals | 24.11.23 | 27.11.23 | 28.11.23 | 28.11.23 | 28.11.23 |  |  | 13.01.24 | premkumar.nagarajan@lntecc.com-15.04.2024-10:55:50
Gond Devsar | Process | Filter media | LE20M186-P-008 | LE20M186-P-008-B | Maakalyaneshwari | Sent to BU Operations | PR Closed |  |  |  | 5.02.22 | 05.02.22 | 20.10.23 | 21.10.23 | [8 empty] | 21.10.23 | 21.10.23 | 09.11.23 | [7 empty] | 20.11.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Filter media | LE20M186-P-008 | LE20M186-P-008-C | OM Sai minerals | Sent to BU Operations | PR Closed |  |  |  | 5.02.22 | 05.02.22 | 27.10.23 | 27.10.23 | [8 empty] | 27.10.23 | 27.10.23 | 11.11.23 | [7 empty] | 26.11.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Backwash pump | LE20M186-P-009 | LE20M186-P-009-A | Flowmore | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 23.09.23 | 30.09.23 | [8 empty] | 30.09.23 | 30.09.23 | 07.10.23 | [7 empty] | 30.10.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Backwash pump | LE20M186-P-009 | LE20M186-P-009-B | KBL | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 21.09.23 | 26.09.23 | [8 empty] | 26.09.23 | 26.09.23 | 23.10.23 | [7 empty] | 26.10.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Backwash pump | LE20M186-P-009 | LE20M186-P-009-C | WPIL | Approved by Client | PR Closed |  | 07290027621 | design.gzb01@wpil.co.in | 29.01.22 | 29.01.22 | 17.09.23 | 21.10.23 | [8 empty] | 24.11.23 | 24.11.23 | 01.12.23 | T1 | 23.12.23 | WPIL | 23.01.24 | 23.01.24 | 25.01.24 | 25.01.24 | 25.01.24 |  |  | 21.02.24 | premkumar.nagarajan@lntecc.com-15.04.2024-10:55:50
Gond Devsar | Process | Backwash pump | LE20M186-P-009 | LE20M186-P-009-D | KSB | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 10.10.23 | 04.11.23 | [8 empty] | 24.11.23 | 24.11.23 | 13.12.23 | [7 empty] | 24.12.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Backwash pump | LE20M186-P-009 | LE20M186-P-009-E | Wilo | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 08.12.23 | 08.12.23 | [8 empty] | 08.12.23 | 08.12.23 | 26.12.23 | [7 empty] | 07.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Submersible pump | LE20M186-P-010 | LE20M186-P-010-A | KSB | Regret offer | PR Closed | No response from Vendor |  |  | 29.01.22 | 29.01.22 | 22.11.23 | 27.11.23 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-18.07.2024-17:49:45
Gond Devsar | Process | Submersible pump | LE20M186-P-010 | LE20M186-P-010-B | Aqua Pumps | Regret offer | PR Closed | No response from Vendor |  |  | 29.01.22 | 29.01.22 | 19.02.24 | 21.02.24 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-18.07.2024-17:49:45
Gond Devsar | Process | Submersible pump | LE20M186-P-010 | LE20M186-P-010-C | Jasco | Regret offer | PR Closed | No response from Vendor |  |  | 29.01.22 | 29.01.22 | 21.02.24 | 23.02.24 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-18.07.2024-17:49:45
Gond Devsar | Process | Submersible pump | LE20M186-P-010 | LE20M186-P-010-D | MBH | Post-order comments issued | 13 |  |  |  | 29.01.22 | 29.01.22 | 18.01.24 | 25.01.24 | 18.03.24 | 25.03.24 | [6 empty] | 25.03.24 | 25.03.24 | 25.03.24 | T1 | 01.07.24 | MBH | 18.07.24 | 22.07.24 |  |  |  | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-22.07.2024-12:20:14
Gond Devsar | Process | Electrical hoist | LE20M186-P-011 | LE20M186-P-011-A | Indef | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 11.01.23 | 11.08.23 | [8 empty] | 08.12.23 | 08.12.23 | 25.12.23 | [7 empty] | 07.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Electrical hoist | LE20M186-P-011 | LE20M186-P-011-B | Japs | Approved by Client | PR Closed |  | 9978900589 | sales.japs@gmail.com | 29.01.22 | 29.01.22 | 16.09.23 | 09.09.23 | [8 empty] | 12.09.23 | 12.09.23 | 11.01.24 | T1 | 31.01.24 | Japs | 13.02.24 | 20.02.24 | 23.02.24 | 23.02.24 | 23.02.24 |  |  | 31.03.24 | premkumar.nagarajan@lntecc.com-30.05.2024-10:36:27
Gond Devsar | Process | Electrical hoist | LE20M186-P-011 | LE20M186-P-011-C | Safex | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 19.06.23 | 19.09.23 | [8 empty] | 08.12.23 | 08.12.23 | 21.12.23 | [7 empty] | 07.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Electrical hoist | LE20M186-P-011 | LE20M186-P-011-D | Reva | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 16.11.23 | 24.11.23 | [8 empty] | 28.12.23 | 28.12.23 | 31.12.23 | [7 empty] | 27.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Manual chain pulley block | LE20M186-P-012 | LE20M186-P-012-A | Indef | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 11.01.23 | 11.08.23 | [8 empty] | 28.12.23 | 28.12.23 | 20.01.24 | [7 empty] | 27.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Manual chain pulley block | LE20M186-P-012 | LE20M186-P-012-B | Japs | Approved by Client | PR Closed |  | 9978900589 | sales.japs@gmail.com | 29.01.22 | 29.01.22 | 16.09.23 | 08.09.23 | [8 empty] | 12.09.23 | 12.09.23 | 11.01.24 | T1 | 04.02.24 | Japs | 13.02.24 | 20.02.24 | 23.02.24 | 23.02.24 | 23.02.24 |  |  | 04.04.24 | premkumar.nagarajan@lntecc.com-30.05.2024-10:36:27
Gond Devsar | Process | Manual chain pulley block | LE20M186-P-012 | LE20M186-P-012-C | Safex | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 27.01.23 | 19.09.23 | [8 empty] | 28.12.23 | 28.12.23 | 17.01.24 | [7 empty] | 27.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Manual chain pulley block | LE20M186-P-012 | LE20M186-P-012-D | Reva | Sent to BU Operations | PR Closed |  |  |  | 29.01.22 | 29.01.22 | 16.11.23 | 24.11.23 | [8 empty] | 28.12.23 | 28.12.23 | 29.12.23 | [7 empty] | 27.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Dosing pump | LE20M186-P-013 | LE20M186-P-013-A | Positive Metering Pumps | Sent to BU Operations | PR Closed |  |  |  | 19.01.22 | 19.01.22 | 16.01.23 | 25.01.23 | [8 empty] | 01.12.23 | 01.12.23 | 05.12.23 | [7 empty] | 31.12.23 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Dosing pump | LE20M186-P-013 | LE20M186-P-013-B | SR Metering | Approved by Client | PR Closed |  | 8888865119 | sr1@srmetering.com | 19.01.22 | 19.01.22 | 17.11.23 | 04.06.22 | [8 empty] | 01.02.23 | 01.02.23 | 30.01.24 | T1 | 06.02.24 | SR Metering | 04.03.24 | 07.03.24 | 19.03.24 | 19.03.24 | 19.03.24 |  |  | 06.04.24 | premkumar.nagarajan@lntecc.com-30.05.2024-10:36:27
Gond Devsar | Process | Dosing pump | LE20M186-P-013 | LE20M186-P-013-C | Verito | Sent to BU Operations | PR Closed |  |  |  | 19.01.22 | 19.01.22 | 14.11.23 | 20.11.23 | [8 empty] | 06.12.23 | 06.12.23 | 01.01.24 | [7 empty] | 05.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Sampling pump | LE20M186-P-014 | LE20M186-P-014-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 19.02.22 | [24 empty] | premkumar.nagarajan@lntecc.com-06.05.2024-12:16:20
Gond Devsar | Process | Submersible mixer | LE20M186-P-015 | LE20M186-P-015-A | Sulzer World water tech | Approved by Client | PR Closed |  | 9319094421 | wwtechennai@gmail.com | 29.01.22 | 29.01.22 | 12.10.23 | 18.10.23 | [8 empty] | 18.10.23 | 18.10.23 | 18.10.23 | T1 | 15.03.24 | Sulzer World water tech | 07.03.24 | 07.03.24 | 19.03.24 | 19.03.24 | 19.03.24 |  |  | 14.05.24 | premkumar.nagarajan@lntecc.com-30.05.2024-10:36:27
Gond Devsar | Process | Dewatering pump | LE20M186-P-016 | LE20M186-P-016-A | KSB | Regret offer | PR Closed | No response from Vendor |  |  | 29.01.22 | 29.01.22 | 22.11.23 | 27.11.23 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-18.07.2024-17:49:45
Gond Devsar | Process | Dewatering pump | LE20M186-P-016 | LE20M186-P-016-B | Aqua Pumps | Regret offer | PR Closed | No response from Vendor |  |  | 29.01.22 | 29.01.22 | 19.02.24 | 21.02.24 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-18.07.2024-17:49:45
Gond Devsar | Process | Dewatering pump | LE20M186-P-016 | LE20M186-P-016-C | Jasco | Regret offer | PR Closed | No response from Vendor |  |  | 29.01.22 | 29.01.22 | 21.02.24 | 23.02.24 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-18.07.2024-17:49:45
Gond Devsar | Process | Dewatering pump | LE20M186-P-016 | LE20M186-P-016-D | MBH | Post-order comments issued | 13 |  |  |  | 29.01.22 | 29.01.22 | 18.01.24 | 25.01.24 | 18.03.24 | 25.03.24 | [6 empty] | 25.03.24 | 25.03.24 | 25.03.24 | T1 | 01.07.24 | MBH | 18.07.24 | 22.07.24 |  |  |  | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-22.07.2024-12:20:14
Gond Devsar | Process | Trolley | LE20M186-P-017 | LE20M186-P-017-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 19.02.22 | [24 empty] | premkumar.nagarajan@lntecc.com-06.05.2024-12:16:20
Gond Devsar | Process | Platform weighing machine | LE20M186-P-018 | LE20M186-P-018-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 19.02.22 | [24 empty] | premkumar.nagarajan@lntecc.com-06.05.2024-12:16:20
Gond Devsar | Process | Sludge drying bed media | LE20M186-P-019 | LE20M186-P-019-A | Dalton Minerals | Approved by Client | PR Closed |  | 011 - 2994 8540 | daltonminerals@gmail.com | 5.02.22 | 05.02.22 | 24.10.23 | 25.10.23 | [8 empty] | 06.12.23 | 20.09.23 | 26.10.23 | T1 | 01.11.23 | Dalton Minerals | 24.11.23 | 27.11.23 | 28.11.23 | 28.11.23 | 28.11.23 |  |  | 31.12.23 | premkumar.nagarajan@lntecc.com-15.04.2024-10:55:50
Gond Devsar | Process | Sludge drying bed media | LE20M186-P-019 | LE20M186-P-019-B | Maakalyaneshwari | Sent to BU Operations | PR Closed |  |  |  | 5.02.22 | 05.02.22 | 20.10.23 | 21.10.23 | [8 empty] | 06.12.23 | 06.12.23 | 18.12.23 | [7 empty] | 05.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | Sludge drying bed media | LE20M186-P-019 | LE20M186-P-019-C | OM Sai minerals | Sent to BU Operations | PR Closed |  |  |  | 5.02.22 | 05.02.22 | 27.10.23 | 27.10.23 | [8 empty] | 06.12.23 | 06.12.23 | 18.12.23 | [7 empty] | 05.01.24 |  |  |  | premkumar.nagarajan@lntecc.com-19.02.2024-11:15:57
Gond Devsar | Process | lab equipment | LE20M186-P-020 | LE20M186-P-020-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 19.02.22 | [24 empty] | premkumar.nagarajan@lntecc.com-06.05.2024-12:16:20
Gond Devsar | Process | Exhaust fan | LE20M186-P-021 | LE20M186-P-021-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 19.02.22 | [24 empty] | premkumar.nagarajan@lntecc.com-06.05.2024-12:16:20
Gond Devsar | Process | Chlorine tonner | LE20M186-P-022 | LE20M186-P-022-A | Zion | Approved by Client | PR Closed |  | 8094570996 / 9828977765 | deepak@ziontech.in | 19.12.22 | 19.12.22 | 09.01.23 | 16.01.23 | [8 empty] | 16.01.23 | 16.01.23 | 01.03.23 | T1 | 21.06.23 | Zion | 30.06.23 | 15.07.23 | 23.07.23 | 25.07.23 | 25.07.23 |  |  | 20.08.23 | premkumar.nagarajan@lntecc.com-30.05.2024-10:36:27
Gond Devsar | Process | Chlorine tonner | LE20M186-P-022 | LE20M186-P-022-B | ME INFRA | Sent to BU Operations | PR Closed |  |  |  | 19.12.22 | 19.12.22 | 19.01.23 | 06.03.23 | [8 empty] | 06.03.23 | 06.03.23 | 06.03.23 | T2 | [10 empty] | premkumar.nagarajan@lntecc.com-30.05.2024-10:32:09
Gond Devsar | Process | Chlorine tonner | LE20M186-P-022 | LE20M186-P-022-C | Supreme Technologies | Sent to BU Operations | PR Closed |  |  |  | 19.12.22 | 19.12.22 | 07.04.23 | 24.04.23 | [8 empty] | 23.05.23 | 23.05.23 | 23.05.23 | T2 | [6 empty] | 24.05.23 |  |  |  | premkumar.nagarajan@lntecc.com-30.05.2024-10:32:09
Gond Devsar | Process | Rechlorination system | LE20M186-P-023 | LE20M186-P-023-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.04.25 | 17.05.25 | 16.07.25 | premkumar.nagarajan@lntecc.com-02.07.2024-11:17:22
Gond Devsar | Mechanical | Dewatering pump for CWR Pump house | LE20M186-E-012 | LE20M186-E-012-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 283 | Enquiry floated to Jasco/Aqua/MBH |  |  | 26.10.23 | 26.10.23 | [24 empty] | karthiga@lntecc.com
Gond Devsar | Mechanical | VT Pumps | LE20M186-M-001 | LE20M186-M-001-A | KBL | Sent to BU Operations | PR Closed |  |  |  | 26.10.23 | 26.10.23 | 16.11.23 | 18.11.23 | [8 empty] | 20.11.23 | 24.11.23 | 24.11.23 | [7 empty] | 25.11.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Mechanical | VT Pumps | LE20M186-M-001 | LE20M186-M-001-B | WILO | Sent to BU Operations | PR Closed |  |  |  | 26.10.23 | 26.10.23 | 07.11.23 | 15.11.23 | [8 empty] | 23.11.23 | 23.11.23 | 24.11.23 | [7 empty] | 25.11.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Mechanical | VT Pumps | LE20M186-M-001 | LE20M186-M-001-C | WPIL | Approved by Client | PR Closed |  |  |  | 26.10.23 | 26.10.23 | 07.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 21.11.23 | 25.11.23 |  | 25.11.23 | WPIL | 08.12.23 | 15.12.23 | 18.12.23 | 29.12.23 | 05.01.24 |  |  | 24.01.24 | karthiga@lntecc.com
Gond Devsar | Mechanical | Clear Water (HSC) pumps at WTP | LE20M186-M-002 | LE20M186-M-002-A | KBL | Sent to BU Operations | PR Closed |  |  |  | 26.10.23 | 26.10.23 | 31.10.23 | 31.10.23 | [8 empty] | 02.11.23 | 02.11.23 | 24.11.23 | [7 empty] | 30.11.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Mechanical | Clear Water (HSC) pumps at WTP | LE20M186-M-002 | LE20M186-M-002-B | WILO | Sent to BU Operations | PR Closed |  |  |  | 26.10.23 | 16.10.23 | 21.10.23 | 21.10.23 | [8 empty] | 21.10.23 | 29.10.23 | 14.11.23 | [7 empty] | 20.11.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Mechanical | Clear Water (HSC) pumps at WTP | LE20M186-M-002 | LE20M186-M-002-C | WPIL | Approved by Client | PR Closed | Lot-1 MFC Given, Lot-2 : pending with EDRC - Mechanical & Electrical |  |  | 26.10.23 | 26.10.23 | 14.11.23 | 19.11.23 | [8 empty] | 23.11.23 | 28.11.23 | 01.12.23 |  | 13.01.24 | WPIL | 13.01.24 | 15.01.24 | 28.01.24 | 28.01.24 | 30.01.24 |  |  | 13.03.24 | karthiga@lntecc.com-17.02.2024-17:34:01
Gond Devsar | Mechanical | Clear Water (HSC) pumps at WTP | LE20M186-M-002 | LE20M186-M-002-D | KSB | Sent to BU Operations | PR Closed |  |  |  | 26.10.23 | 26.10.23 | 30.10.23 | 31.10.23 | [8 empty] | 07.11.23 | 27.11.23 | 27.11.23 | [7 empty] | 30.11.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Mechanical | Clear Water (HSC) pumps at IBPS Location | LE20M186-M-003 | LE20M186-M-003-A | Wilo | Sent to BU Operations | 173 |  |  |  | 26.10.23 | 26.10.23 | 02.01.24 | 06.01.24 | 12.01.24 | 16.01.24 | 29.01.24 | 30.01.24 |  |  |  |  | 02.02.24 | 08.02.24 | 13.02.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-13.05.2024-16:58:52
Gond Devsar | Mechanical | EOT cranes for Intake, CW-PH at WTP & IBPS'S | LE20M186-M-004 | LE20M186-M-004-A | JAPS | Sent to BU Operations | 135 |  |  |  | 26.10.23 | 30.08.23 | 27.09.23 | 09.10.23 | [8 empty] | 13.10.23 | 17.10.23 | 14.03.24 | T1 | 22.03.24 | [8 empty] | 21.05.24 | rachamalla.nithish@lntecc.com-13.05.2024-16:43:10
Gond Devsar | Mechanical | EOT cranes for Intake, CW-PH at WTP & IBPS'S | LE20M186-M-004 | LE20M186-M-004-B | REVA | Sent to BU Operations | 88 | Electrical-Pending |  |  | 26.10.23 | 10.10.23 | 13.10.23 | 14.10.23 | [8 empty] | 28.11.23 | 15.12.23 | 14.03.24 | T1 | 22.03.24 | REVA | 22.03.24 | 29.03.24 | 06.05.24 | 07.05.24 | 08.05.24 |  |  | 21.05.24 | rachamalla.nithish@lntecc.com-13.05.2024-16:43:10
Gond Devsar | Mechanical | Sluice gate at Intake & CWR at WTP | LE20M186-M-005 | LE20M186-M-005-A | Jash | Approved by Client | PR Closed |  |  |  | 26.10.23 | 26.10.23 | 08.11.23 | 08.12.23 | [8 empty] | 11.12.23 | 11.12.23 | 12.12.23 |  | 17.12.23 | Jash | 26.12.23 | 20.01.24 | 21.01.24 | 22.01.24 | 30.01.24 |  |  | 15.02.24 | karthiga@lntecc.com
Gond Devsar | Mechanical | Sluice gate at Intake & CWR at WTP | LE20M186-M-005 | LE20M186-M-005-B | Hindustan | Sent to BU Operations | PR Closed |  |  |  | 26.10.23 | 14.07.23 | 01.09.23 | 19.09.23 | [8 empty] | 25.09.23 | 29.09.23 | 29.09.23 | [7 empty] | 01.10.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Mechanical | Sluice gate at Intake & CWR at WTP | LE20M186-M-005 | LE20M186-M-005-C | Oriental | Sent to BU Operations | PR Closed |  |  |  | 26.10.23 | 21.08.23 | 30.08.23 | 03.09.23 | [8 empty] | 24.09.23 | 26.09.23 | 26.09.23 | [7 empty] | 29.09.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Mechanical | DJ & EB only for RW-PH,CW-PH, IBPS-1 TO 5 PH, RISING MAIN & OHMBR Inlet &outlets. | LE20M186-M-006 | LE20M186-M-006-A | Precise | Approved by Client | PR Closed |  |  |  | 26.10.23 | 03.09.23 | 19.09.23 | 19.09.23 | [8 empty] | 16.10.23 | 16.10.23 | 19.10.23 |  | 05.11.23 | Precise | 13.11.23 | 13.11.23 | 13.11.23 | 13.11.23 | 18.11.23 |  |  | 04.01.24 | karthiga@lntecc.com
Gond Devsar | Mechanical | DJ & EB only for RW-PH,CW-PH, IBPS-1 TO 5 PH, RISING MAIN & OHMBR Inlet &outlets. | LE20M186-M-006 | LE20M186-M-006-B | Bikaner | Sent to BU Operations | PR Closed |  |  |  | 26.10.23 | 26.10.23 | 05.11.23 | 06.11.23 | [8 empty] | 18.11.23 | 18.11.23 | 20.11.23 | [7 empty] | 25.11.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Mechanical | DJ & EB for CWGM, IBPS-8 & Distribution. | LE20M186-M-007 | LE20M186-M-007-A | PRECISE | Sent to BU Operations | 253 |  |  |  | 26.10.23 | 26.10.23 | 27.10.23 | 16.11.23 | [8 empty] | 17.11.23 | 19.11.23 | 21.11.23 | T1 | [6 empty] | 25.11.23 |  |  |  | lakshmanrao@lntecc.com-04.04.2024-10:47:12
Gond Devsar | Mechanical | Raw water & Clear water Pump house valves | LE20M186-M-008 | LE20M186-M-008-A | AVK | Post-order technically cleared | 223 |  |  |  | 26.10.23 | 26.10.23 | 16.11.23 | 23.11.23 | [8 empty] | 23.11.23 | 23.11.23 | 23.11.23 |  | 23.11.23 | AVK | 24.11.23 | 24.11.23 | 25.11.23 | 04.12.23 | 25.12.23 |  |  | 22.01.24 | sayan.chowdhury@lntecc.com
Gond Devsar | Mechanical | Raw water & Clear water Pump house valves - NRV | LE20M186-M-009 | LE20M186-M-009-A | Sigmaflow | Post-order technically cleared | 290 |  |  |  | 26.10.23 | 09.09.23 | 19.09.23 | 19.09.23 | [8 empty] | 09.10.23 | 14.10.23 | 17.10.23 |  | 17.10.23 | Sigmaflow | 17.10.23 | 17.10.23 | 17.10.23 | 17.10.23 | 19.10.23 |  |  | 16.12.23 | sayan.chowdhury@lntecc.com
Gond Devsar | Mechanical | Distribution valves 52 approved zones + 18 submitted zones | LE20M186-M-010 | LE20M186-M-010-A | AVK | Pre-order technically cleared | 344 |  |  |  | 26.10.23 | 28.05.23 | 27.07.23 | 27.07.23 | [8 empty] | 18.08.23 | 18.08.23 | [8 empty] | 26.08.23 |  |  |  | sayan.chowdhury@lntecc.com
Gond Devsar | Mechanical | CWGM & RISING MAIN valves | LE20M186-M-011 | LE20M186-M-011-A | AVK | Pre-order technically cleared | 253 |  |  |  | 26.10.23 | 26.10.23 | 18.11.23 | 20.11.23 | [8 empty] | 24.11.23 | 24.11.23 | [8 empty] | 25.11.23 |  |  |  | sayan.chowdhury@lntecc.com
Gond Devsar | Mechanical | Dewatering pump for CWR Pump house | LE20M186-M-012 | LE20M186-M-012-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 283 | Enquiry floated to Jasco/MBH/Aqua |  |  | 26.10.23 | 26.10.23 | [24 empty] | karthiga@lntecc.com
Gond Devsar | Mechanical | Ventilation System (Exhaust & Supply) for Clear Water Pump House -01 & 02 & Filter annex building | LE20M186-M-013 | LE20M186-M-013-A | NADI | Approved by Client | PR Closed |  |  |  | 26.10.23 | 07.03.24 | 08.03.24 | 21.03.24 | [8 empty] | 25.03.24 | 25.03.24 | 26.03.24 | T1 | 04.05.24 | NADI | 06.05.24 | 06.05.24 | 07.05.24 | 10.05.24 | 10.05.24 |  |  | 03.07.24 | rachamalla.nithish@lntecc.com-13.05.2024-16:55:18
Gond Devsar | Mechanical | Ventilation System (Exhaust & Supply) for Clear Water Pump House -01 & 02 & Filter annex building | LE20M186-M-013 | LE20M186-M-013-B | POWER VENT SYSTEM | Sent to BU Operations | PR Closed |  |  |  |  | 07.03.24 | 15.03.24 | 21.03.24 | [8 empty] | 25.03.24 | 25.03.24 | 26.03.24 | T2 | [10 empty] | rachamalla.nithish@lntecc.com-13.05.2024-16:55:18
Gond Devsar | Mechanical | Ventilation System (Exhaust & Supply) for Clear Water Pump House -01 & 02 & Filter annex building | LE20M186-M-013 | LE20M186-M-013-C | ALMONARD | Sent to BU Operations | PR Closed |  |  |  |  | 07.03.24 | 15.03.24 | 21.03.24 | [8 empty] | 25.03.24 | 25.03.24 | 26.03.24 | T3 | [10 empty] | rachamalla.nithish@lntecc.com-13.05.2024-16:55:18
Gond Devsar | Mechanical | Pipes & Fittings boq for Intake & CW-PH at WTP, ibps-1 to 5 | LE20M186-M-014 | LE20M186-M-014-A | Vendor Name yet to provide | Sent to BU Operations | 155 | BOQ given to site. Site has to procure those material. Only TC need to give. IBPS-8 only pending |  |  | 26.10.23 | 26.10.23 | 29.02.24 | 02.03.24 | [8 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-23.05.2024-14:08:27
Gond Devsar | Mechanical | Clear Water (HSC) pumps at IBPS Location | LE20M186-M-WS-PR-HSC-1202-2 | LE20M186-M-WS-PR-HSC-1202-2-B | WPIL | Approved by Client | PR Closed |  |  |  |  | 26.10.23 | 30.01.24 | 02.02.24 | 06.02.24 | 13.02.24 | 17.02.24 | 19.02.24 | 20.02.24 | 24.02.24 |  |  | 27.02.24 | 28.02.24 | 01.03.24 | T1 | 11.03.24 | WPIL | 20.03.24 | 22.03.24 | 27.03.24 | 10.05.24 | 10.05.24 |  |  | 10.05.24 | rachamalla.nithish@lntecc.com-13.05.2024-16:58:52
Gond Devsar | Mechanical | Clear Water (HSC) pumps at IBPS Location | LE20M186-M-WS-PR-HSC-1202-2 | LE20M186-M-WS-PR-HSC-1202-2-C | KBL | Sent to BU Operations | PR Closed |  |  |  |  | 26.10.23 | 15.01.24 | 22.01.24 | 30.01.24 | 08.02.24 | 12.02.24 | 19.02.24 |  |  |  |  | 21.02.24 | 23.02.24 | 23.02.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-13.05.2024-16:58:52
Gond Devsar | Mechanical | Clear Water (HSC) pumps at IBPS Location | LE20M186-M-WS-PR-HSC-1202-2 | LE20M186-M-WS-PR-HSC-1202-2-D | FLOWMORE | Regret offer | PR Closed |  |  |  |  | 26.10.23 | [24 empty] | rachamalla.nithish@lntecc.com-13.05.2024-16:58:52
Gond Devsar | Mechanical | Clear Water (HSC) pumps at IBPS Location | LE20M186-M-WS-PR-HSC-1202-2 | LE20M186-M-WS-PR-HSC-1202-2-E | KSB | Regret offer | PR Closed |  |  |  |  | 26.10.23 | [24 empty] | rachamalla.nithish@lntecc.com-13.05.2024-16:58:52
Gond Devsar | Instrumentation | Purchase requisition for Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M186-I-001 | LE20M186-I-001-A | AN instruments | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 20.01.23 | 09.02.23 | 10.02.23 | 10.02.23 | [7 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M186-I-001 | LE20M186-I-001-B | Hguru South | Approved by Client | PR Closed |  |  |  | 27.03.23 | 03.01.23 | 11.01.23 | 24.01.23 | 24.01.23 | [7 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T1 | 19.05.23 | Hguru South | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 |  |  | 18.07.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M186-I-001 | LE20M186-I-001-C | Measurecal | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 27.11.22 | 11.01.23 | 21.01.23 | 21.01.23 | [7 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M186-I-001 | LE20M186-I-001-D | SIAS | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 24.12.22 | 23.01.23 | 11.02.23 | 11.02.23 | [7 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Pressure Switch | LE20M186-I-002 | LE20M186-I-002-A | AN instruments | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 20.01.23 | 09.02.23 | 09.02.23 | 09.02.23 | [7 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Pressure Switch | LE20M186-I-002 | LE20M186-I-002-B | Hguru South | Approved by Client | PR Closed |  |  |  | 27.03.23 | 31.12.22 | 11.01.23 | 24.01.23 | 24.01.23 | [7 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T1 | 19.05.23 | Hguru South | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 | 19.05.23 |  |  | 18.07.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Pressure Switch | LE20M186-I-002 | LE20M186-I-002-C | Measurecal | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 02.12.22 | 11.01.23 | 12.01.23 | 12.01.23 | [7 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Pressure Switch | LE20M186-I-002 | LE20M186-I-002-D | SIAS | Sent to BU Operations | PR Closed |  |  |  | 27.03.23 | 26.11.22 | 23.01.23 | 03.02.23 | 03.02.23 | [7 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Pressure transmitter | LE20M186-I-003 | LE20M186-I-003-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 16.03.23 | 26.11.22 | 14.12.22 | 14.12.22 | 14.12.22 | [7 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Pressure transmitter | LE20M186-I-003 | LE20M186-I-003-B | E&H | Approved by Client | PR Closed |  |  |  | 16.03.23 | 16.09.22 | 12.12.22 | 12.12.22 | 12.12.22 | [7 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T1 | 01.01.23 | E&H | 16.03.23 | 16.03.23 | 16.03.23 | 16.03.23 | 16.03.23 |  |  | 02.03.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Pressure transmitter | LE20M186-I-003 | LE20M186-I-003-C | Honeywell | Sent to BU Operations | PR Closed |  |  |  | 16.03.23 | 25.11.22 | 12.12.22 | 27.12.22 | 27.12.22 | [7 empty] | 28.12.22 | 28.12.22 | 28.12.22 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Float & Board Level gauge | LE20M186-I-004 | LE20M186-I-004-A | Pune Techtrol | Sent to BU Operations | PR Closed |  |  |  | 18.04.23 | 20.12.22 | 16.01.23 | 04.02.23 | 04.02.23 | [7 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Float & Board Level gauge | LE20M186-I-004 | LE20M186-I-004-B | SBEM | Approved by Client | PR Closed |  |  |  | 18.04.23 | 17.11.22 | 16.01.23 | 22.01.23 | 22.01.23 | [7 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T1 | 03.03.23 | SBEM | 03.03.23 | 03.03.23 | 06.03.23 | 06.03.23 | 08.03.23 |  |  | 02.05.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for level switch - Conductivity type | LE20M186-I-005 | LE20M186-I-005-A | Pune Techtrol | Sent to BU Operations | PR Closed |  |  |  | 18.04.23 | 29.12.22 | 16.01.23 | 30.01.23 | 30.01.23 | [7 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for level switch - Conductivity type | LE20M186-I-005 | LE20M186-I-005-B | SBEM | Approved by Client | PR Closed |  |  |  | 18.04.23 | 01.11.22 | 16.01.23 | 17.01.23 | 17.01.23 | [7 empty] | 06.02.23 | 06.02.23 | 06.02.23 | T1 | 09.02.23 | SBEM | 05.03.23 | 07.03.23 | 07.03.23 | 07.03.23 | 08.03.23 |  |  | 10.04.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Ultrasonic level Transmitter | LE20M186-I-006 | LE20M186-I-006-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 30.11.22 | 07.02.23 | 19.02.23 | 19.02.23 | [7 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Ultrasonic level Transmitter | LE20M186-I-006 | LE20M186-I-006-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 24.05.23 | 02.01.24 | 18.01.24 | 18.01.24 | [7 empty] | 01.02.24 | 06.02.24 | 02.03.24 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Ultrasonic level Transmitter | LE20M186-I-006 | LE20M186-I-006-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 13.01.23 | 07.02.23 | 10.02.23 | 10.02.23 | [7 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Datasheet for Ultrasonic level Transmitter | LE20M186-I-006 | LE20M186-I-006-D | EiP Enviro | Approved by Client | PR Closed |  |  |  | 23.07.21 | 24.05.23 | 06.03.23 | 06.03.23 | 06.03.23 | [7 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EiP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Radar Level Transmitter | LE20M186-I-007 | LE20M186-I-007-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 27.11.22 | 07.02.23 | 09.02.23 | 09.02.23 | [7 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Radar Level Transmitter | LE20M186-I-007 | LE20M186-I-007-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 24.05.23 | 02.01.24 | 06.01.24 | 06.01.24 | [7 empty] | 01.02.24 | 02.02.24 | 02.03.24 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Radar Level Transmitter | LE20M186-I-007 | LE20M186-I-007-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 29.12.22 | 07.02.23 | 02.03.23 | 02.03.23 | [7 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Datasheet for Radar Level Transmitter | LE20M186-I-007 | LE20M186-I-007-D | EiP Enviro | Approved by Client | PR Closed |  |  |  | 23.07.21 | 24.05.23 | 06.03.23 | 06.03.23 | 06.03.23 | [7 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EiP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Loss of head transmitter | LE20M186-I-008 | LE20M186-I-008-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 16.03.23 | 24.11.22 | 14.12.22 | 14.12.22 | 14.12.22 | [7 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Loss of head transmitter | LE20M186-I-008 | LE20M186-I-008-B | E&H | Approved by Client | PR Closed |  |  |  | 16.03.23 | 30.10.22 | 12.12.22 | 12.12.22 | 12.12.22 | [7 empty] | 15.12.22 | 15.12.22 | 15.12.22 | T1 | 02.01.23 | E&H | 03.01.23 | 12.01.23 | 12.01.23 | 12.01.23 | 14.01.23 |  |  | 03.03.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Loss of head transmitter | LE20M186-I-008 | LE20M186-I-008-C | Honeywell | Sent to BU Operations | PR Closed |  |  |  | 16.03.23 | 05.12.22 | 12.12.22 | 26.12.22 | 26.12.22 | [7 empty] | 28.12.22 | 28.12.22 | 28.12.22 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Rate for flow transmitter | LE20M186-I-009 | LE20M186-I-009-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 22.01.23 | 07.02.23 | 23.02.23 | 23.02.23 | [7 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Rate for flow transmitter | LE20M186-I-009 | LE20M186-I-009-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 24.05.23 | 02.01.24 | 18.01.24 | 18.01.24 | [7 empty] | 01.02.24 | 29.02.24 | 02.03.24 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Rate for flow transmitter | LE20M186-I-009 | LE20M186-I-009-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 24.01.23 | 07.02.23 | 27.02.23 | 27.02.23 | [7 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Datasheet for Rate for flow transmitter | LE20M186-I-009 | LE20M186-I-009-D | EiP Enviro | Approved by Client | PR Closed |  |  |  | 23.07.21 | 24.05.23 | 06.03.23 | 06.03.23 | 06.03.23 | [7 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EiP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Bypass Rotameter | LE20M186-I-010 | LE20M186-I-010-A | Eureka | Enquiry yet to float | NA |  |  |  | 13.02.23 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Bypass Rotameter | LE20M186-I-010 | LE20M186-I-010-B | Scientific devices | Enquiry yet to float | NA |  |  |  | 13.02.23 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Electromagnectic flow meter | LE20M186-I-011 | LE20M186-I-011-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 29.12.22 | 24.10.22 | 17.11.22 | 18.11.22 | 18.11.22 | [7 empty] | 02.12.22 | 02.12.22 | 02.12.22 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Electromagnectic flow meter | LE20M186-I-011 | LE20M186-I-011-B | Khrone | Approved by Client | PR Closed |  |  |  | 29.12.22 | 06.11.22 | 17.11.22 | 20.11.22 | 20.11.22 | [7 empty] | 02.12.22 | 02.12.22 | 02.12.22 | T1 | 07.02.23 | Khrone | 06.04.23 | 06.04.23 | 06.04.23 | 06.04.23 | 06.04.23 |  |  | 08.04.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Electromagnectic flow meter | LE20M186-I-011 | LE20M186-I-011-C | siemens | Sent to BU Operations | PR Closed |  |  |  | 29.12.22 | 13.11.22 | 17.11.22 | 21.11.22 | 21.11.22 | [7 empty] | 02.12.22 | 02.12.22 | 02.12.22 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Electromagnectic flow meter | LE20M186-I-011 | LE20M186-I-011-D | yokogawa | Sent to BU Operations | PR Closed |  |  |  | 29.12.22 | 28.10.22 | 17.11.22 | 17.11.22 | 17.11.22 | [7 empty] | 02.12.22 | 02.12.22 | 02.12.22 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Ultrasonic type Open channel flow transmitter | LE20M186-I-012 | LE20M186-I-012-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 19.12.22 | 07.02.23 | 28.02.23 | 28.02.23 | [7 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Ultrasonic type Open channel flow transmitter | LE20M186-I-012 | LE20M186-I-012-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 24.05.23 | 02.01.24 | 08.01.24 | 08.01.24 | [7 empty] | 01.02.24 | 22.02.24 | 02.03.24 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Ultrasonic type Open channel flow transmitter | LE20M186-I-012 | LE20M186-I-012-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 24.05.23 | 10.01.23 | 07.02.23 | 22.02.23 | 22.02.23 | [7 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Datasheet for Ultrasonic type Open channel flow transmitter | LE20M186-I-012 | LE20M186-I-012-D | EiP Enviro | Approved by Client | PR Closed |  |  |  | 23.07.21 | 24.05.23 | 06.03.23 | 06.03.23 | 06.03.23 | [7 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EiP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for VTC Flow meter | LE20M186-I-013 | LE20M186-I-013-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for VTC Flow meter | LE20M186-I-013 | LE20M186-I-013-B | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for pH Meter | LE20M186-I-014 | LE20M186-I-014-A | Emerson | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 05.09.23 | 25.09.23 | 29.09.23 | 29.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T1 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for pH Meter | LE20M186-I-014 | LE20M186-I-014-B | HACH | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 30.08.23 | 25.09.23 | 30.09.23 | 30.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for pH Meter | LE20M186-I-014 | LE20M186-I-014-C | ABB | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 24.09.23 | 25.09.23 | 29.09.23 | 29.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for pH Meter | LE20M186-I-014 | LE20M186-I-014-D | E&H | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 13.09.23 | 25.09.23 | 28.09.23 | 28.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Turbidity meter | LE20M186-I-015 | LE20M186-I-015-A | Emerson | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 16.09.23 | 25.09.23 | 01.10.23 | 01.10.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T1 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Turbidity meter | LE20M186-I-015 | LE20M186-I-015-B | HACH | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 23.09.23 | 25.09.23 | 29.09.23 | 29.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Turbidity meter | LE20M186-I-015 | LE20M186-I-015-C | ABB | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 15.09.23 | 25.09.23 | 01.10.23 | 01.10.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Turbidity meter | LE20M186-I-015 | LE20M186-I-015-D | E&H | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 17.09.23 | 25.09.23 | 29.09.23 | 29.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Residual Chlorine Analyzer | LE20M186-I-016 | LE20M186-I-016-A | Emerson | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 23.09.23 | 25.09.23 | 30.09.23 | 30.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T1 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Residual Chlorine Analyzer | LE20M186-I-016 | LE20M186-I-016-B | HACH | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 01.09.23 | 25.09.23 | 02.10.23 | 02.10.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Residual Chlorine Analyzer | LE20M186-I-016 | LE20M186-I-016-C | ABB | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 05.09.23 | 25.09.23 | 25.09.23 | 25.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for Residual Chlorine Analyzer | LE20M186-I-016 | LE20M186-I-016-D | E&H | Sent to BU Operations | 305 |  |  |  | 21.10.23 | 22.09.23 | 25.09.23 | 30.09.23 | 30.09.23 | [7 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M186-I-017 | LE20M186-I-017-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M186-I-017 | LE20M186-I-017-B | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M186-I-017 | LE20M186-I-017-C | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M186-I-017 | LE20M186-I-017-D | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M186-I-017 | LE20M186-I-017-E | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for instrumentation Control & signal Cables | LE20M186-I-018 | LE20M186-I-018-A | Axelon | Sent to BU Operations | PR Closed |  |  |  | 21.07.22 | 21.07.22 | 04.10.22 | 09.01.23 | 09.01.23 | [7 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T2 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for instrumentation Control & signal Cables | LE20M186-I-018 | LE20M186-I-018-B | Cords | Approved by Client | PR Closed |  |  |  | 21.07.22 | 21.07.22 | 04.10.22 | 09.01.23 | 09.01.23 | [7 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T1 | 22.02.23 | Cords | 16.03.23 | 16.03.23 | 16.03.23 | 16.03.23 | 16.03.23 |  |  | 23.04.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for instrumentation Control & signal Cables | LE20M186-I-018 | LE20M186-I-018-C | Delton | Sent to BU Operations | PR Closed |  |  |  | 21.07.22 | 21.07.22 | 04.10.22 | 09.01.23 | 09.01.23 | [7 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T3 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for instrumentation Control & signal Cables | LE20M186-I-018 | LE20M186-I-018-D | Thermo | Sent to BU Operations | PR Closed |  |  |  | 21.07.22 | 21.07.22 | 04.10.22 | 09.01.23 | 09.01.23 | [7 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T4 | [10 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for UPS | LE20M186-I-019 | LE20M186-I-019-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for UPS | LE20M186-I-019 | LE20M186-I-019-B | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for EPABX System | LE20M186-I-020 | LE20M186-I-020-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for EPABX System | LE20M186-I-020 | LE20M186-I-020-B | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Purchase requisition for EPABX System | LE20M186-I-020 | LE20M186-I-020-C | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 21.07.22 | [25 empty] | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Instrumentation | Ultrasonic level transmitter | LE20M186-I-WS-WT-PR-5106 | LE20M186-I-WS-WT-PR-5106-D | EIP Enviro | Approved by Client | PR Closed |  |  |  | 23.07.21 | 24.05.23 | 06.03.23 | 06.03.23 | [8 empty] | 06.05.23 | 06.05.23 | 06.05.23 | T1 | 20.07.23 | EIP Enviro | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 | 20.07.23 |  |  | 18.09.23 | SURENDHAR@lntecc.com-09.07.2024-14:55:28
Gond Devsar | Electrical | Transformer | LE20M186-E-001 | LE20M186-E-001-A | Voltech | Pre-order comments issued | 263 |  |  |  | 25.06.23 | 25.06.23 | 25.09.23 | 05.10.23 | [8 empty] | 15.11.23 | 15.11.23 | [12 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | Transformer | LE20M186-E-001 | LE20M186-E-001-B | Uttam Bharat | Pre-order comments issued | 285 |  |  |  | 25.06.23 | 25.06.23 | 25.09.23 | 30.09.23 | [8 empty] | 24.10.23 | 24.10.23 | [12 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | Transformer | LE20M186-E-001 | LE20M186-E-001-C | Vendor Name yet to provide | Pre-order comments issued | 376 |  |  |  | 25.06.23 | 25.06.23 | 06.07.23 | 08.07.23 | [18 empty] | 25.07.23 |  |  |  | karthiga@lntecc.com
Gond Devsar | Electrical | LT Panel | LE20M186-E-002 | LE20M186-E-002-A | E&E | Pre-order comments issued | 255 |  |  |  | 25.06.23 | 25.06.23 | 13.09.23 | 28.09.23 | [8 empty] | 30.09.23 | 23.11.23 | [12 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | LT Panel | LE20M186-E-002 | LE20M186-E-002-B | BCH | Pre-order comments issued | 270 |  |  |  | 25.06.23 | 25.06.23 | 16.09.23 | 29.09.23 | [8 empty] | 07.11.23 | 08.11.23 | [12 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | LT Panel | LE20M186-E-002 | LE20M186-E-002-C | SRCS | Pre-order technically cleared | 230 |  |  |  | 25.06.23 | 25.06.23 | 03.10.23 | 12.10.23 | [8 empty] | 07.11.23 | 18.12.23 | [12 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | HT Panel | LE20M186-E-003 | LE20M186-E-003-A | UPE | Pre-order comments issued | 264 |  |  |  | 25.06.23 | 25.06.23 | 22.09.23 | 28.09.23 | [8 empty] | 11.11.23 | 14.11.23 | [12 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | HT Panel | LE20M186-E-003 | LE20M186-E-003-B | HTS | Pre-order comments issued | 305 |  |  |  | 25.06.23 | 25.06.23 | 13.09.23 | 28.09.23 | [8 empty] | 01.10.23 | 04.10.23 | [12 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | HT Panel | LE20M186-E-003 | LE20M186-E-003-C | Sawti Switchgear | Pre-order comments issued | 250 |  |  |  | 25.06.23 | 25.06.23 | 10.07.23 | 24.11.23 | [8 empty] | 24.11.23 | 28.11.23 | [12 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | Lighting Fixtures | LE20M186-E-004 | LE20M186-E-004-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order offer evaluation is not required | [28 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | LPBS & LDB | LE20M186-E-005 | LE20M186-E-005-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order offer evaluation is not required | [28 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | AAAC Conductor | LE20M186-E-006 | LE20M186-E-006-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order offer evaluation is not required | [28 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | Control & Relay Panel | LE20M186-E-007 | LE20M186-E-007-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order offer evaluation is not required | [28 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | CT & PT | LE20M186-E-008 | LE20M186-E-008-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order offer evaluation is not required | [28 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | Swicthyard Structures | LE20M186-E-009 | LE20M186-E-009-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order offer evaluation is not required | [28 empty] | sayan.chowdhury@lntecc.com
Gond Devsar | Electrical | HT/ LT Power & Control Cables | LE20M186-E-010 | LE20M186-E-010-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site to Procure | [28 empty] | karthiga@lntecc.com
Gond Devsar | Electrical | Cable Trays & Its accessories | LE20M186-E-011 | LE20M186-E-011-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site to Procure | [28 empty] | karthiga@lntecc.com
Gond Devsar | Electrical | Galns & Lugs | LE20M186-E-013 | LE20M186-E-013-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site to Procure | [28 empty] | karthiga@lntecc.com
Gond Devsar | Electrical | Safety Accessories | LE20M186-E-014 | LE20M186-E-014-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site to Procure | [28 empty] | karthiga@lntecc.com
Guwahati WSS | Process | Flocculator and Inclined Plate Settler scrapper mechanism | LE23M756-P-WS-WT-PR-2002 | LE23M756-P-WS-WT-PR-2002-A | Sritech | Sent to BU Operations | PR Closed |  | P. Mohan |  |  | 25.01.24 | 26.02.24 | 29.02.24 | 07.03.24 | 13.03.24 | 20.03.24 | 21.03.24 | 26.03.24 | 27.03.24 |  |  | 27.03.24 | 27.03.24 | 27.03.24 | T2 | [10 empty] | KUMUTHA@lntecc.com-05.06.2024-17:04:01
Guwahati WSS | Process | Flocculator and Inclined Plate Settler scrapper mechanism | LE23M756-P-WS-WT-PR-2002 | LE23M756-P-WS-WT-PR-2002-B | Shivpad | Regret offer | PR Closed |  |  |  |  | 25.01.24 | 26.02.24 | 29.02.24 | 13.03.24 | 14.03.24 | 19.03.24 | 27.03.24 | [7 empty] | T3 | [10 empty] | KUMUTHA@lntecc.com-20.05.2024-12:11:05
Guwahati WSS | Process | Flocculator and Inclined Plate Settler scrapper mechanism | LE23M756-P-WS-WT-PR-2002 | LE23M756-P-WS-WT-PR-2002-C | Filsep | Post-order comments issued | 11 |  |  |  |  | 25.01.24 | 13.03.24 | 19.03.24 | [8 empty] | 27.03.24 | 27.03.24 | 27.03.24 | T1 | 13.05.24 | Filsep | 13.05.24 | 24.07.24 | [5 empty] | 12.07.24 | KUMUTHA@lntecc.com-24.07.2024-18:44:20
Guwahati WSS | Process | Inclined Plate Settler plate | LE23M756-P-WS-WT-PR-2003 | LE23M756-P-WS-WT-PR-2003-A | Filsep | Sent to BU Operations | 130 |  |  |  |  | 25.01.24 | 21.03.24 | 22.03.24 | [8 empty] | 27.03.24 | 27.03.24 | 27.03.24 | T3 | [10 empty] | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Inclined Plate Settler plate | LE23M756-P-WS-WT-PR-2003 | LE23M756-P-WS-WT-PR-2003-B | Shivpad | Regret offer | PR Closed |  |  |  |  | 25.01.24 | 26.02.24 | 29.02.24 | [8 empty] | 29.02.24 | 29.02.24 | 29.02.24 | T4 | [10 empty] | KUMUTHA@lntecc.com-20.05.2024-11:45:46
Guwahati WSS | Process | Inclined Plate Settler plate | LE23M756-P-WS-WT-PR-2003 | LE23M756-P-WS-WT-PR-2003-C | Cooldeck | Sent to BU Operations | 59 |  |  |  |  | 25.01.24 | 16.04.24 | 24.04.24 | [8 empty] | 07.05.24 | 07.05.24 | 07.05.24 | T1 | 10.05.24 | Cooldeck | 14.05.24 | 06.06.24 | 06.06.24 | 06.06.24 |  |  |  | 09.07.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Inclined Plate Settler plate | LE23M756-P-WS-WT-PR-2003 | LE23M756-P-WS-WT-PR-2003-D | Sangir | Sent to BU Operations | 89 |  |  |  |  | 25.01.24 | 24.04.24 | 25.04.24 | [8 empty] | 07.05.24 | 07.05.24 | 07.05.24 | T2 | [10 empty] | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Air Blower | LE23M756-P-WS-WT-PR-2004 | LE23M756-P-WS-WT-PR-2004-A | Airvac | Sent to BU Operations | PR Closed |  |  |  |  | 28.11.23 | 02.12.23 | 20.12.23 | [8 empty] | 23.02.24 | 23.02.24 | 23.02.24 | T3 | [10 empty] | KUMUTHA@lntecc.com-01.07.2024-15:13:05
Guwahati WSS | Process | Air Blower | LE23M756-P-WS-WT-PR-2004 | LE23M756-P-WS-WT-PR-2004-B | Kay | Post-order technically cleared | 38 |  |  |  |  | 28.11.23 | 02.12.23 | 21.03.24 | [8 empty] | 21.03.24 | 21.03.24 | 21.03.24 | T1 | 17.04.24 | Kay | 03.06.24 | 27.06.24 | 27.06.24 | 27.06.24 |  |  |  | 16.06.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Air Blower | LE23M756-P-WS-WT-PR-2004 | LE23M756-P-WS-WT-PR-2004-C | ACME | Sent to BU Operations | PR Closed |  |  |  |  | 28.11.23 | 27.12.23 | 14.02.24 | [8 empty] | 14.02.24 | 14.02.24 | 14.02.24 | T2 | [10 empty] | KUMUTHA@lntecc.com-01.07.2024-15:13:05
Guwahati WSS | Process | Agitator (Flash Mixer) | LE23M756-P-WS-WT-PR-2005 | LE23M756-P-WS-WT-PR-2005-A | Verito | Post-order technically cleared | 9 |  |  |  |  | 28.11.23 | 30.11.23 | 09.12.23 | [8 empty] | 19.03.24 | 19.03.24 | 19.03.24 | T3 | 15.04.24 | Verito | 15.07.24 | 26.07.24 | 26.07.24 | 26.07.24 |  |  |  |  | KUMUTHA@lntecc.com-26.07.2024-11:07:39
Guwahati WSS | Process | Agitator (Flash Mixer) | LE23M756-P-WS-WT-PR-2005 | LE23M756-P-WS-WT-PR-2005-B | Shivpad | Sent to BU Operations | PR Closed |  |  |  |  | 14.02.24 | 19.12.23 | 29.12.23 | [8 empty] | 23.01.24 | 23.01.24 | 23.01.24 | T2 | [10 empty] | KUMUTHA@lntecc.com-20.05.2024-10:07:30
Guwahati WSS | Process | Agitator (Flash Mixer) | LE23M756-P-WS-WT-PR-2005 | LE23M756-P-WS-WT-PR-2005-C | Adroit | Post-order technically cleared | 54 | Client rejected. Not in approved make list. |  |  |  | 14.02.24 | 29.12.23 | 09.01.24 | [8 empty] | 13.02.24 | 13.02.24 | 13.02.24 | T1 | 15.04.24 | Adroit | 04.05.24 | 11.06.24 | 11.06.24 | 11.06.24 |  |  |  | 14.06.24 | KUMUTHA@lntecc.com-26.07.2024-11:07:39
Guwahati WSS | Process | Agitator (Flash Mixer) | LE23M756-P-WS-WT-PR-2005 | LE23M756-P-WS-WT-PR-2005-D | Triveni | Regret offer | PR Closed |  |  |  |  | 14.02.24 | 29.12.23 | 09.01.24 | [8 empty] | 29.03.24 | 29.03.24 | 29.03.24 | T4 | [10 empty] | KUMUTHA@lntecc.com-20.05.2024-10:06:28
Guwahati WSS | Process | Filter Media | LE23M756-P-WS-WT-PR-2008 | LE23M756-P-WS-WT-PR-2008-A |  | Enquiry yet to float | NA | [26 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-01.07.2024-14:57:58
Guwahati WSS | Process | Sludge drying bed media | LE23M756-P-WS-WT-PR-2009 | LE23M756-P-WS-WT-PR-2009-A |  | Enquiry yet to float | NA | [26 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-01.07.2024-14:58:37
Guwahati WSS | Process | Submersible pump | LE23M756-P-WS-WT-PR-2011 | LE23M756-P-WS-WT-PR-2011-A | MBH | Sent to BU Operations | 124 |  |  |  |  | 29.11.23 | 08.12.23 | 21.12.23 | [8 empty] | 02.04.24 | 02.04.24 | 02.04.24 | T1 | [7 empty] | 18.04.24 | 05.05.24 | 04.07.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Submersible pump | LE23M756-P-WS-WT-PR-2011 | LE23M756-P-WS-WT-PR-2011-B | KSB | Sent to BU Operations | 108 |  |  |  |  | 29.11.23 | 20.12.23 | 04.01.24 | [8 empty] | 18.04.24 | 18.04.24 | 18.04.24 | T2 | [7 empty] | 18.04.24 | 05.05.24 | 04.07.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Manual chain pulley block | LE23M756-P-WS-WT-PR-2013 | LE23M756-P-WS-WT-PR-2013-A | Reva | Regret offer | PR Closed |  |  |  |  | 09.12.23 | 01.02.24 | 16.02.24 | [8 empty] | 30.03.24 | 30.03.24 | 30.03.24 | [8 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-01.07.2024-14:55:36
Guwahati WSS | Process | Nozzles | LE23M756-P-WS-WT-PR-2014 | LE23M756-P-WS-WT-PR-2014-A | VP Engineers | Sent to BU Operations | 169 |  |  |  |  | 01.12.23 | 09.12.23 | 21.12.23 | [8 empty] | 17.02.24 | 17.02.24 | 17.02.24 | T2 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Nozzles | LE23M756-P-WS-WT-PR-2014 | LE23M756-P-WS-WT-PR-2014-B | Guddi Plastcon | Sent to BU Operations | 82 |  |  |  |  | 01.12.23 | 03.05.24 | 03.05.24 | 08.05.24 | 14.05.24 | [6 empty] | 14.05.24 | 14.05.24 | 14.05.24 | T1 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Sampling pump | LE23M756-P-WS-WT-PR-2015 | LE23M756-P-WS-WT-PR-2015-A | NA | Regret offer | PR Closed | Site Procurement. |  |  |  | 01.12.23 | [24 empty] | KUMUTHA@lntecc.com-01.07.2024-15:13:05
Guwahati WSS | Process | Submersible mixer | LE23M756-P-WS-WT-PR-2016 | LE23M756-P-WS-WT-PR-2016-A |  | Enquiry yet to float | NA | Waiting offer from FFP. | [25 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-11.07.2024-12:07:46
Guwahati WSS | Process | Dewatering pump | LE23M756-P-WS-WT-PR-2017 | LE23M756-P-WS-WT-PR-2017-A | Jasco | Sent to BU Operations | 154 |  |  |  |  | 09.12.23 | 04.01.24 | 17.01.24 | [8 empty] | 03.03.24 | 03.03.24 | 03.03.24 | T2 | [7 empty] | 20.05.24 | 06.06.24 | 05.08.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Dewatering pump | LE23M756-P-WS-WT-PR-2017 | LE23M756-P-WS-WT-PR-2017-B | MBH | Sent to BU Operations | 76 |  |  |  |  | 09.12.23 | 04.04.24 | 14.05.24 | 15.05.24 | 20.05.24 | [6 empty] | 20.05.24 | 20.05.24 | 20.05.24 | T1 | [7 empty] | 20.05.24 | 06.06.24 | 05.08.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Trolley | LE23M756-P-WS-WT-PR-2018 | LE23M756-P-WS-WT-PR-2018-A | NA | Regret offer | PR Closed | Site Procurement. |  |  |  | 07.12.23 | [24 empty] | KUMUTHA@lntecc.com-01.07.2024-15:13:05
Guwahati WSS | Process | Potable Water Tank | LE23M756-P-WS-WT-PR-2019 | LE23M756-P-WS-WT-PR-2019-A | NA | Regret offer | PR Closed | Site Procurement. |  |  |  | 29.11.23 | [24 empty] | KUMUTHA@lntecc.com-01.07.2024-15:13:05
Guwahati WSS | Process | Exhaust fans | LE23M756-P-WS-WT-PR-2021 | LE23M756-P-WS-WT-PR-2021-A | NA | Regret offer | PR Closed | Site Procurement. |  |  |  | 19.12.23 | [24 empty] | KUMUTHA@lntecc.com-01.07.2024-15:13:05
Guwahati WSS | Process | Lab equipment | LE23M756-P-WS-WT-PR-2022 | LE23M756-P-WS-WT-PR-2022-A | Lambard Instruchem | Sent to BU Operations | 178 |  |  |  |  | 19.12.23 | 02.01.24 | 08.02.24 | [8 empty] | 08.02.24 | 08.02.24 | 08.02.24 | T1 | [7 empty] | 04.06.24 | 21.06.24 | 20.08.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Air Compressor | LE23M756-P-WS-WT-PR-2023 | LE23M756-P-WS-WT-PR-2023-A | Atlas Copco | Regret offer | PR Closed |  |  |  |  | 29.11.23 | 22.02.24 | 17.04.24 | 15.05.24 | 20.05.24 | 20.05.24 | 21.05.24 | [15 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-01.07.2024-15:06:28
Guwahati WSS | Process | Re chlorination system | LE23M756-P-WS-WT-PR-2024 | LE23M756-P-WS-WT-PR-2024-A | IEC Fabchem | Pre-order comments issued | 30 |  |  |  |  | 12.03.24 | 18.05.24 | 23.05.24 | 04.06.24 | 05.06.24 | 25.06.24 | 05.07.24 | [15 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-26.07.2024-18:24:33
Guwahati WSS | Process | Re chlorination system | LE23M756-P-WS-WT-PR-2024 | LE23M756-P-WS-WT-PR-2024-B | Zion Technologies | Pre-order comments issued | 24 |  |  |  |  | 12.03.24 | 18.06.24 | 26.06.24 | 09.07.24 | 11.07.24 | [17 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-26.07.2024-18:24:33
Guwahati WSS | Process | Re chlorination system | LE23M756-P-WS-WT-PR-2024 | LE23M756-P-WS-WT-PR-2024-C | Luit Minerals | Pre-order comments issued | 9 |  | 9476850502, 6913707510 | support@luitminerals.com |  | 12.03.24 | 08.07.24 | 12.07.24 | 13.07.24 | 20.07.24 | 23.07.24 | 26.07.24 | [18 empty] | KUMUTHA@lntecc.com-26.07.2024-18:24:33
Guwahati WSS | Process | Agitator (Chemical dosing tanks) | LE23M756-P-WS-WT-PR-2025 | LE23M756-P-WS-WT-PR-2025-A | Verito | Pre-order technically cleared | 33 |  | Chetana Badgujar | mailto:verito.offers@veritoengineering.com |  | 16.03.24 | 20.05.24 | 22.05.24 | 23.05.24 | 24.05.24 | [6 empty] | 02.07.24 | 02.07.24 | 02.07.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-24.07.2024-13:01:58
Guwahati WSS | Process | Agitator (Chemical dosing tanks) | LE23M756-P-WS-WT-PR-2025 | LE23M756-P-WS-WT-PR-2025-B | Adroit | Regret offer | PR Closed | Vendor not responding |  |  |  | 16.03.24 | 18.05.24 | 23.05.24 | 04.06.24 | 04.06.24 | [6 empty] | 04.06.24 | 04.06.24 | 04.06.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-11.07.2024-11:57:56
Guwahati WSS | Process | Agitator (Chemical dosing tanks) | LE23M756-P-WS-WT-PR-2025 | LE23M756-P-WS-WT-PR-2025-C | FFP | Pre-order comments issued | 11 |  |  |  |  | 16.03.24 | 11.07.24 | 16.07.24 | 20.07.24 | 24.07.24 | [20 empty] | KUMUTHA@lntecc.com-24.07.2024-13:01:58
Guwahati WSS | Process | Dosing Pumps | LE23M756-P-WS-WT-PR-2026 | LE23M756-P-WS-WT-PR-2026-A | SR Metering | Pre-order technically cleared | 30 |  |  |  |  | 16.03.24 | 03.05.24 | 04.05.24 | 23.05.24 | 24.05.24 | 03.07.24 | 05.07.24 |  |  |  |  | 05.07.24 | 05.07.24 | 05.07.24 | [8 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Dosing Pumps | LE23M756-P-WS-WT-PR-2026 | LE23M756-P-WS-WT-PR-2026-B | Verito | Pre-order technically cleared | 75 |  | Kajol Lalwani | pump.offers@veritoengineering.com |  | 16.03.24 | 03.05.24 | 04.05.24 | 07.05.24 | 18.05.24 | 21.05.24 | 21.05.24 |  |  |  |  | 21.05.24 | 21.05.24 | 21.05.24 | [8 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Dosing Pumps | LE23M756-P-WS-WT-PR-2026 | LE23M756-P-WS-WT-PR-2026-C | Positive Metering | Pre-order technically cleared | 61 |  |  |  |  | 13.05.24 | 13.05.24 | 18.05.24 | 03.06.24 | 04.06.24 | [6 empty] | 04.06.24 | 04.06.24 | 04.06.24 | [8 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Process | Dosing Pumps | LE23M756-P-WS-WT-PR-2026 | LE23M756-P-WS-WT-PR-2026-D | VK Pumps | Regret offer | PR Closed | Vendor not responding |  |  |  | 14.05.24 | 04.06.24 | 05.06.24 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | KUMUTHA@lntecc.com-20.07.2024-18:05:24
Guwahati WSS | Mechanical | Float valves | LE23M756-M-WS-CW-PR-1001 | LE23M756-M-WS-CW-PR-1001-A | Dorot | Pre-order pending with EDRC | 13 |  |  | abhishek.mathur@aquestia.com |  | 18.05.24 | 03.06.24 | 14.06.24 | 22.07.24 | [18 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-24.07.2024-11:44:04
Guwahati WSS | Mechanical | Float valves | LE23M756-M-WS-CW-PR-1001 | LE23M756-M-WS-CW-PR-1001-B | Dalui | Regret offer | PR Closed |  |  | 'nkdalui@gmail.com'; 'daluirabishankar@gmail.com'; 'daluisuman@gmail.com |  | 18.05.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-24.07.2024-11:44:04
Guwahati WSS | Mechanical | Float valves | LE23M756-M-WS-CW-PR-1001 | LE23M756-M-WS-CW-PR-1001-C | VAG | Regret offer | PR Closed |  |  | G.ArulSelvam@vag-group.com |  | 18.05.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-24.07.2024-11:44:04
Guwahati WSS | Mechanical | Dewatering pumps | LE23M756-M-WS-CW-PR-1002 | LE23M756-M-WS-CW-PR-1002-A | AquaPumps | Regret offer | PR Closed |  |  | 'chennai@aquapumps.com' | 11.06.24 | 11.06.24 | [21 empty] | 11.06.24 | 28.06.24 | 27.08.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Dewatering pumps | LE23M756-M-WS-CW-PR-1002 | LE23M756-M-WS-CW-PR-1002-B | Xylem | Regret offer | PR Closed |  | Natarajan, Sivakumar - Xylem | Sivakumar.Natarajan@xylem.com | 11.06.24 | 11.06.24 | [21 empty] | 11.06.24 | 28.06.24 | 27.08.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Dewatering pumps | LE23M756-M-WS-CW-PR-1002 | LE23M756-M-WS-CW-PR-1002-C | KSB | Pre-order comments issued | 23 |  | G, Subramani <Subramani.G@ksb.com> | G, Subramani <Subramani.G@ksb.com> |  | 26.05.24 | 02.07.24 | 12.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-22.07.2024-09:56:06
Guwahati WSS | Mechanical | HSC Pumps | LE23M756-M-WS-CW-PR-1003 | LE23M756-M-WS-CW-PR-1003 | Flowmore | Awaiting pre-offer from vendor | 78 | needs to use existing pump at site |  |  |  | 18.05.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-22.07.2024-09:56:06
Guwahati WSS | Mechanical | Exhaust fans | LE23M756-M-WS-CW-PR-1004 | LE23M756-M-WS-CW-PR-1004-A | Almonard | Regret offer | PR Closed |  | Almonard | purchase.almonard@gmail.com | 12.06.24 | 12.06.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:47:07
Guwahati WSS | Mechanical | Exhaust fans | LE23M756-M-WS-CW-PR-1004 | LE23M756-M-WS-CW-PR-1004-B | Nadiairtechnics | Pre-order technically cleared | 26 |  | SateeshKumar | satheeshkumar.r@nadiairtechnics.com | 12.06.24 | 12.06.24 | 14.06.24 | 26.06.24 | 08.07.24 | 09.07.24 | [6 empty] | 08.07.24 | 08.07.24 | 09.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:47:07
Guwahati WSS | Mechanical | Exhaust fans | LE23M756-M-WS-CW-PR-1004 | LE23M756-M-WS-CW-PR-1004-C | CGGlobal | Regret offer | PR Closed |  | Prakash | prakash.j@cgglobal.com; ajoy.prasad@cgglobal.com; nitin.naik@cgglobal.com | 12.06.24 | 12.06.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-11.07.2024-14:08:39
Guwahati WSS | Mechanical | EOT Crane | LE23M756-M-WS-CW-PR-1005 | LE23M756-M-WS-CW-PR-1005-A | Bradys | Regret offer | PR Closed |  |  | srinivasan@bradys.in |  | 04.05.24 | [21 empty] | 04.05.24 | 21.05.24 | 20.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | EOT Crane | LE23M756-M-WS-CW-PR-1005 | LE23M756-M-WS-CW-PR-1005-B | JAPS | Pre-order technically cleared | 39 |  |  | JAPS PROJECT <sales.japs@gmail.com>; japspro <japspro@yahoo.co.in> |  | 18.05.24 | 03.06.24 | 26.06.24 | [8 empty] | 26.06.24 | 26.06.24 | 26.06.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-11:10:20
Guwahati WSS | Mechanical | EOT Crane | LE23M756-M-WS-CW-PR-1005 | LE23M756-M-WS-CW-PR-1005-C | REVA | Pre-order comments issued | 24 |  |  | 'mkt@revacranes.com' |  | 04.05.24 | 23.05.24 | 26.06.24 | 02.07.24 | 11.07.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-22.07.2024-09:56:06
Guwahati WSS | Mechanical | EOT Crane | LE23M756-M-WS-CW-PR-1005 | LE23M756-M-WS-CW-PR-1005-D | Indef | Regret offer | PR Closed |  |  | Mmkm@indef.com |  | 04.05.24 | [21 empty] | 04.05.24 | 21.05.24 | 20.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | EOT Crane | LE23M756-M-WS-CW-PR-1005 | LE23M756-M-WS-CW-PR-1005-E | Eddy | Regret offer | PR Closed |  |  | insujan@eddycranes.com |  | 04.05.24 | [21 empty] | 04.05.24 | 21.05.24 | 20.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | EOT Crane | LE23M756-M-WS-CW-PR-1005 | LE23M756-M-WS-CW-PR-1005-F | Safex | Pre-order comments issued | 19 |  | Pankaj pandya | pankaj.pandya@safexcranes.co.in |  | 26.06.24 | 03.07.24 | 11.07.24 | 13.07.24 | 16.07.24 | [17 empty] | 15.08.24 | 01.09.24 | 31.10.24 | bnk@lntecc.com-22.07.2024-09:56:06
Guwahati WSS | Mechanical | Dismantling joints | LE23M756-M-WS-CW-PR-1006 | LE23M756-M-WS-CW-PR-1006-A | Precise | Pre-order technically cleared | 66 |  |  | Shailendra Mehta <sjm@vedantagroup.net> |  | 04.05.24 | 08.05.24 | 20.05.24 | [8 empty] | 29.05.24 | 22.05.24 | 30.05.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-11:10:20
Guwahati WSS | Mechanical | Dismantling joints | LE23M756-M-WS-CW-PR-1006 | LE23M756-M-WS-CW-PR-1006-B | SurIndustries | Pre-order technically cleared | 58 |  |  | surindustries <info@surind.com>; Sheikh Mohammed Fayazuddin <fayazaseema@gmail.com> |  | 04.05.24 | 24.05.24 | 28.05.24 | 05.06.24 | 07.06.24 | [6 empty] | 07.06.24 | 07.06.24 | 07.06.24 | T2 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-11:10:20
Guwahati WSS | Mechanical | Dismantling joints | LE23M756-M-WS-CW-PR-1006 | LE23M756-M-WS-CW-PR-1006-C | Electrosteel | Regret offer | PR Closed |  |  | satyendra.kumar@electrosteel.com; anujkr.maurya@electrosteel.com; animikh.banerjee@electrosteel.com; soumayajit.mukherjee@electrosteel.com |  | 04.05.24 | [21 empty] | 04.05.24 | 21.05.24 | 20.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Dismantling joints | LE23M756-M-WS-CW-PR-1006 | LE23M756-M-WS-CW-PR-1006-D | Qualitech | Pre-order technically rejected | PR Closed |  |  | kamal.mehta@qualitechgroup.in |  | 04.05.24 | 06.05.24 | 24.05.24 | 24.05.24 | 14.06.24 | 24.06.24 | 05.07.24 | [15 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-05.07.2024-16:08:22
Guwahati WSS | Mechanical | Dismantling joints | LE23M756-M-WS-CW-PR-1006 | LE23M756-M-WS-CW-PR-1006-E | SigmaFlow | Pre-order technically cleared | 66 |  |  | jagadesh@sigmaflow.in |  | 04.05.24 | 13.05.24 | 20.05.24 | 24.05.24 | [7 empty] | 24.05.24 | 24.05.24 | 30.05.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-11:10:20
Guwahati WSS | Mechanical | PH Valves (DPCV/MBFV/MSV) | LE23M756-M-WS-CW-PR-1007 | LE23M756-M-WS-CW-PR-1007-A | SIGMAFLOW | Pre-order technically cleared | 66 |  |  | jagadesh@sigmaflow.in |  | 30.04.24 | 25.05.24 | 30.05.24 | [8 empty] | 30.05.24 | 30.05.24 | 30.05.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:40:59
Guwahati WSS | Mechanical | PH Valves (DPCV/MBFV/MSV) | LE23M756-M-WS-CW-PR-1007 | LE23M756-M-WS-CW-PR-1007-B | KBL | Pre-order technically cleared | 26 |  | Karthikeyan R <karthikeyan.r@kbl.co.in> | Karthikeyan R <karthikeyan.r@kbl.co.in> |  | 30.04.24 | 08.07.24 | 09.07.24 | [8 empty] | 09.07.24 | 09.07.24 | 09.07.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:40:59
Guwahati WSS | Mechanical | PH Valves (DPCV/MBFV/MSV) | LE23M756-M-WS-CW-PR-1007 | LE23M756-M-WS-CW-PR-1007-C | R&D | Pre-order technically rejected | PR Closed |  | bhupesh@rdmultiples.com | bhupesh@rdmultiples.com |  | 30.04.24 | 28.06.24 | 02.07.24 | 03.07.24 | 06.07.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:40:59
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-A | Hawle | Pre-order technically rejected | PR Closed | Client rejected | Sagayaprabhu | sagaya.prabhu@hawle.in | 26.10.23 | 26.10.23 | 01.11.23 | 03.11.23 | [8 empty] | 09.11.23 | 09.11.23 | 09.11.23 | T1 | 16.11.23 | Hawle | 16.11.23 | 16.11.23 | 16.11.23 | 16.11.23 | 16.11.23 | 26.10.23 | 12.11.23 | 11.01.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-B | KBL | Pre-order technically cleared | 26 |  |  | Karthikeyan R <karthikeyan.r@kbl.co.in> |  | 15.05.24 | 08.07.24 | 09.07.24 | [8 empty] | 09.07.24 | 09.07.24 | 09.07.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:39:39
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-C | IVC | Regret offer | PR Closed |  |  | sudip.ghosh@ivc-valves.com | sudip.ghosh@ivc-valves.com | 15.05.24 | [21 empty] | 15.05.24 | 01.06.24 | 31.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-D | Sigmaflow | Pre-order technically cleared | 66 |  |  | Jagadesh -Sigmaflow <jagadesh@sigmaflow.in> |  | 30.04.24 | 13.05.24 | 20.05.24 | 24.05.24 | [7 empty] | 24.05.24 | 24.05.24 | 30.05.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:38:56
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-E | Jupiter | Pre-order technically cleared | 50 |  |  | ho@jupitervalves.com; chennai@jupitervalves.com | jagadesh@sigmaflow.in | 30.04.24 | 06.06.24 | 15.06.24 | [8 empty] | 14.06.24 | 15.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:38:56
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-F | R&D | Pre-order technically rejected | PR Closed |  |  | bhupesh@rdmultiples.com |  | 30.04.24 | 28.06.24 | 02.07.24 | 03.07.24 | 06.07.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:39:39
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-G | VAG | Regret offer | PR Closed |  |  | G.ArulSelvam@vag-group.com |  | 30.04.24 | [21 empty] | 30.04.24 | 17.05.24 | 16.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-H | AVK | Regret offer | PR Closed |  |  | Subhash S <subhash@avkindia.com> |  | 30.04.24 | [21 empty] | 30.04.24 | 17.05.24 | 16.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Sluice Valves | LE23M756-M-WS-CW-PR-1009 | LE23M756-M-WS-CW-PR-1009-I | Orbit | Pre-order technically cleared | 59 |  |  | yogesh.orbitengineers@gmail.com |  | 30.04.24 | 10.05.24 | 10.05.24 | 16.05.24 | 28.05.24 | 05.06.24 | 06.06.24 |  |  |  |  | 06.06.24 | 05.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:38:56
Guwahati WSS | Mechanical | Flow Control Valve | LE23M756-M-WS-CW-PR-1010 | LE23M756-M-WS-CW-PR-1010-A | AVK | Post-order technically cleared | 267 |  | Subhash | subhash@avkindia.com | 26.10.23 | 26.10.23 | 01.11.23 | 03.11.23 | [8 empty] | 10.11.23 | 10.11.23 | 10.11.23 | T1 | 11.11.23 | AVK | 11.11.23 | 11.11.23 | 11.11.23 | 11.11.23 | 11.11.23 | 10.11.23 | 27.11.23 | 10.01.24 | svcn@lntecc.com-18.07.2024-11:10:20
Guwahati WSS | Mechanical | Butterfly Valves | LE23M756-M-WS-CW-PR-1011 | LE23M756-M-WS-CW-PR-1011-B | AVK | Post-order technically cleared | 267 |  | Subhash | subhash@avkindia.com | 26.10.23 | 26.10.23 | 01.11.23 | 03.11.23 | [8 empty] | 10.11.23 | 10.11.23 | 10.11.23 | T1 | 11.11.23 | AVK | 11.11.23 | 11.11.23 | 11.11.23 | 11.11.23 | 11.11.23 | 10.11.23 | 27.11.23 | 10.01.24 | svcn@lntecc.com-18.07.2024-11:10:20
Guwahati WSS | Mechanical | ACV ( Surge Equipments) | LE23M756-M-WS-CW-PR-1012 | LE23M756-M-WS-CW-PR-1012-A | Flownix | Regret offer | PR Closed |  |  | flownixvalves@gmail.com |  | 18.05.24 | [21 empty] | 18.05.24 | 04.06.24 | 03.08.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | ACV ( Surge Equipments) | LE23M756-M-WS-CW-PR-1012 | LE23M756-M-WS-CW-PR-1012-B | JASH | Pre-order technically rejected | PR Closed |  |  | neeraj@jashindia.com; ashwini@jashindia.com |  | 18.05.24 | 13.06.24 | 11.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:46:02
Guwahati WSS | Mechanical | ACV ( Surge Equipments) | LE23M756-M-WS-CW-PR-1012 | LE23M756-M-WS-CW-PR-1012-C | Sigmaflow | Pre-order technically cleared | 18 |  |  | Jagadesh J <jagadesh@sigmaflow.in> |  | 18.05.24 | 25.05.24 | 17.07.24 | [8 empty] | 16.07.24 | 16.07.24 | 17.07.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:46:02
Guwahati WSS | Mechanical | ACV ( Surge Equipments) | LE23M756-M-WS-CW-PR-1012 | LE23M756-M-WS-CW-PR-1012-D | Jupiter | Awaiting pre-offer from vendor | 78 |  |  | ho@jupitervalves.com; chennai@jupitervalves.com |  | 18.05.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-22.07.2024-09:56:06
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-A | IVC | Regret offer | PR Closed |  |  | sudip.ghosh@ivc-valves.com | Karthikeyan R <karthikeyan.r@kbl.co.in> | 15.05.24 | [21 empty] | 15.05.24 | 01.06.24 | 31.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-B | KBL | Regret offer | PR Closed |  |  | Karthikeyan R <karthikeyan.r@kbl.co.in> |  | 15.05.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:30:56
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-C | Hawle | Pre-order technically rejected | PR Closed | Rejected by client | Sagayaprabhu | sagaya.prabhu@hawle.in | 26.10.23 | 26.10.23 | 01.11.23 | 03.11.23 | [8 empty] | 09.11.23 | 09.11.23 | 09.11.23 | T1 | 16.11.23 | Hawle | 16.11.23 | 16.11.23 | 16.11.23 | 16.11.23 | 16.11.23 | 26.10.23 | 12.11.23 | 11.01.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-D | Sigmaflow | Pre-order technically cleared | 66 |  |  | Jagadesh -Sigmaflow <jagadesh@sigmaflow.in> |  | 30.04.24 | 13.05.24 | 20.05.24 | 24.05.24 | [7 empty] | 24.05.24 | 24.05.24 | 30.05.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:30:56
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-E | Jupiter | Pre-order technically cleared | 50 |  |  | ho@jupitervalves.com; chennai@jupitervalves.com |  | 30.04.24 | 06.06.24 | 15.06.24 | [8 empty] | 14.06.24 | 14.06.24 | 15.06.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:30:56
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-F | R&D | Pre-order technically rejected | PR Closed |  |  | bhupesh@rdmultiples.com |  | 30.04.24 | 28.06.24 | 02.07.24 | 03.07.24 | 06.07.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-11.07.2024-14:08:39
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-G | VAG | Regret offer | PR Closed |  |  | G.ArulSelvam@vag-group.com |  | 30.04.24 | [21 empty] | 30.04.24 | 17.05.24 | 16.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-H | AVK | Regret offer | PR Closed |  |  | Subhash S <subhash@avkindia.com> |  | 30.04.24 | [21 empty] | 30.04.24 | 17.05.24 | 16.07.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | Air Valves | LE23M756-M-WS-CW-PR-1013 | LE23M756-M-WS-CW-PR-1013-I | Orbit | Pre-order technically cleared | 59 |  |  | yogesh.orbitengineers@gmail.com | yogesh.orbitengineers@gmail.com | 30.04.24 | 10.05.24 | 10.05.24 | 16.05.24 | 28.05.24 | 05.06.24 | 06.06.24 |  |  |  |  | 06.06.24 | 05.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:30:56
Guwahati WSS | Mechanical | OHT Valves | LE23M756-M-WS-CW-PR-1014 | LE23M756-M-WS-CW-PR-1014-A | SigmaFlow | Pre-order technically cleared | 66 |  |  | jagadesh@sigmaflow.in |  | 30.04.24 | 25.05.24 | 30.05.24 | [8 empty] | 30.05.24 | 30.05.24 | 30.05.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:42:36
Guwahati WSS | Mechanical | OHT Valves | LE23M756-M-WS-CW-PR-1014 | LE23M756-M-WS-CW-PR-1014-B | KBL | Pre-order technically cleared | 26 |  |  | Karthikeyan R <karthikeyan.r@kbl.co.in> |  | 30.04.24 | 08.07.24 | 09.07.24 | [8 empty] | 09.07.24 | 09.07.24 | 09.07.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:42:36
Guwahati WSS | Mechanical | OHT Valves | LE23M756-M-WS-CW-PR-1014 | LE23M756-M-WS-CW-PR-1014-C | R&D | Pre-order technically rejected | PR Closed |  |  | bhupesh@rdmultiples.com |  | 30.04.24 | 28.06.24 | 02.07.24 | 03.07.24 | 06.07.24 | [6 empty] | 30.05.24 | 30.05.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:42:36
Guwahati WSS | Mechanical | ZVV (Surge Equipments) | LE23M756-M-WS-CW-PR-1016 | LE23M756-M-WS-CW-PR-1016-A | Flownix | Regret offer | PR Closed |  |  | flownixvalves@gmail.com |  | 18.05.24 | [21 empty] | 18.05.24 | 04.06.24 | 03.08.24 | svcn@lntecc.com-02.07.2024-10:17:02
Guwahati WSS | Mechanical | ZVV (Surge Equipments) | LE23M756-M-WS-CW-PR-1016 | LE23M756-M-WS-CW-PR-1016-B | Jash | Pre-order technically rejected | PR Closed |  |  | neeraj@jashindia.com; ashwini@jashindia.com |  | 18.05.24 | 13.06.24 | 11.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:46:02
Guwahati WSS | Mechanical | ZVV (Surge Equipments) | LE23M756-M-WS-CW-PR-1016 | LE23M756-M-WS-CW-PR-1016-C | Sigmaflow | Pre-order technically cleared | 18 |  |  | Jagadesh J <jagadesh@sigmaflow.in> |  | 18.05.24 | 25.05.24 | 17.07.24 | [8 empty] | 16.07.24 | 17.07.24 | 17.07.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-20.07.2024-16:46:02
Guwahati WSS | Mechanical | ZVV (Surge Equipments) | LE23M756-M-WS-CW-PR-1016 | LE23M756-M-WS-CW-PR-1016-D | Jupiter | Awaiting pre-offer from vendor | 78 |  |  | ho@jupitervalves.com; chennai@jupitervalves.com |  | 18.05.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-22.07.2024-09:56:06
Guwahati WSS | Instrumentation | Ultrasonic flowmeter | LE23M756-I-WS-WT-PR-5501 | LE23M756-I-WS-WT-PR-5501-A | SIEMENS | Sent to BU Operations | 58 |  |  |  |  | 20.05.24 | 25.05.24 | 30.05.24 | [8 empty] | 05.06.24 | 06.06.24 | 07.06.24 | T1 | [7 empty] | 07.06.24 | 24.06.24 | 23.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Ultrasonic flowmeter | LE23M756-I-WS-WT-PR-5501 | LE23M756-I-WS-WT-PR-5501-B | E&H | Sent to BU Operations | 59 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | [8 empty] | 05.06.24 | 06.06.24 | 06.06.24 | T2 | [7 empty] | 06.06.24 | 23.06.24 | 22.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Ultrasonic flowmeter | LE23M756-I-WS-WT-PR-5501 | LE23M756-I-WS-WT-PR-5501-C | ABB | Sent to BU Operations | 55 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | [8 empty] | 07.06.24 | 08.06.24 | 10.06.24 | T3 | [7 empty] | 10.06.24 | 27.06.24 | 26.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Electromagnetic flowmeter | LE23M756-I-WS-WT-PR-5502 | LE23M756-I-WS-WT-PR-5502-A | SIEMENS | Sent to BU Operations | 51 |  |  |  |  | 20.05.24 | 25.05.24 | 30.05.24 | [8 empty] | 12.06.24 | 13.06.24 | 14.06.24 | T1 | [7 empty] | 14.06.24 | 01.07.24 | 30.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Electromagnetic flowmeter | LE23M756-I-WS-WT-PR-5502 | LE23M756-I-WS-WT-PR-5502-B | E&H | Sent to BU Operations | 51 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | [8 empty] | 12.06.24 | 13.06.24 | 14.06.24 | T1 | [7 empty] | 14.06.24 | 01.07.24 | 30.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Electromagnetic flowmeter | LE23M756-I-WS-WT-PR-5502 | LE23M756-I-WS-WT-PR-5502-C | ABB | Sent to BU Operations | 51 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | [8 empty] | 11.06.24 | 13.06.24 | 14.06.24 | T2 | [7 empty] | 14.06.24 | 01.07.24 | 30.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Ultrasonic level transmitter | LE23M756-I-WS-WT-PR-5503 | LE23M756-I-WS-WT-PR-5503-A | SIEMENS | Sent to BU Operations | 51 |  |  |  |  | 20.05.24 | 25.05.24 | 30.05.24 | [8 empty] | 12.06.24 | 13.06.24 | 14.06.24 | T3 | [7 empty] | 14.06.24 | 01.07.24 | 30.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Ultrasonic level transmitter | LE23M756-I-WS-WT-PR-5503 | LE23M756-I-WS-WT-PR-5503-B | E&H | Pre-order comments issued | 60 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | [19 empty] | 10.07.24 | 27.07.24 | 25.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Ultrasonic level transmitter | LE23M756-I-WS-WT-PR-5503 | LE23M756-I-WS-WT-PR-5503-C | ABB | Sent to BU Operations | 30 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | [8 empty] | 04.07.24 | 04.07.24 | 05.07.24 | T1 | [7 empty] | 11.07.24 | 28.07.24 | 26.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:15:57
Guwahati WSS | Instrumentation | Pressure Transmitter | LE23M756-I-WS-WT-PR-5504 | LE23M756-I-WS-WT-PR-5504-A | SIEMENS | Sent to BU Operations | 39 |  |  |  |  | 20.05.24 | 25.05.24 | 30.05.24 | [8 empty] | 21.06.24 | 25.06.24 | 26.06.24 | T3 | [7 empty] | 04.07.24 | 21.07.24 | 19.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:17:38
Guwahati WSS | Instrumentation | Pressure Transmitter | LE23M756-I-WS-WT-PR-5504 | LE23M756-I-WS-WT-PR-5504-B | E&H | Sent to BU Operations | 48 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | [8 empty] | 14.06.24 | 15.06.24 | 17.06.24 | T1 | [7 empty] | 17.06.24 | 04.07.24 | 02.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Pressure Transmitter | LE23M756-I-WS-WT-PR-5504 | LE23M756-I-WS-WT-PR-5504-C | ABB | Sent to BU Operations | 48 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | [8 empty] | 14.06.24 | 15.06.24 | 17.06.24 | T2 | [7 empty] | 17.06.24 | 04.07.24 | 02.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Float and Board level gauge | LE23M756-I-WS-WT-PR-5505 | LE23M756-I-WS-WT-PR-5505-A | SBEM | Sent to BU Operations | 31 |  |  |  |  | 20.05.24 | 03.06.24 | 04.06.24 | [8 empty] | 02.07.24 | 03.07.24 | 04.07.24 | T1 | [7 empty] | 03.07.24 | 20.07.24 | 18.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:19:56
Guwahati WSS | Instrumentation | Float and Board level gauge | LE23M756-I-WS-WT-PR-5505 | LE23M756-I-WS-WT-PR-5505-B | PUNE TECHTROL | Sent to BU Operations | 39 |  |  |  |  | 20.05.24 | 04.06.24 | 05.06.24 | 11.06.24 | [7 empty] | 21.06.24 | 25.06.24 | 26.06.24 | T2 | [7 empty] | 03.07.24 | 20.07.24 | 18.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:21:56
Guwahati WSS | Instrumentation | Pressure gauge | LE23M756-I-WS-WT-PR-5506 | LE23M756-I-WS-WT-PR-5506-A | HGURU | Sent to BU Operations | 53 |  |  |  |  | 20.05.24 | 03.06.24 | 04.06.24 | 12.06.24 | [7 empty] | 07.06.24 | 10.06.24 | 11.06.24 | T2 | [7 empty] | 10.07.24 | 27.07.24 | 25.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:21:56
Guwahati WSS | Instrumentation | Pressure gauge | LE23M756-I-WS-WT-PR-5506 | LE23M756-I-WS-WT-PR-5506-B | GIC | Sent to BU Operations | 45 |  |  |  |  | 20.05.24 | 06.06.24 | 13.06.24 | 14.06.24 | [7 empty] | 17.06.24 | 19.06.24 | 20.06.24 | T1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | PLC & SCADA | LE23M756-I-WS-WT-PR-5507 | LE23M756-I-WS-WT-PR-5507-A | Schneider Electric | Sent to BU Operations | 138 |  |  |  |  | 12.03.24 | 16.03.24 | 19.03.24 | [8 empty] | 19.03.24 | 19.03.24 | 19.03.24 | T1 | [7 empty] | 19.03.24 | 05.04.24 | 04.06.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | PLC & SCADA | LE23M756-I-WS-WT-PR-5507 | LE23M756-I-WS-WT-PR-5507-B | SIAS | Sent to BU Operations | 138 |  |  |  |  | 12.03.24 | 16.03.24 | 19.03.24 | [8 empty] | 19.03.24 | 19.03.24 | 19.03.24 | T2 | [7 empty] | 19.03.24 | 05.04.24 | 04.06.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | PLC & SCADA | LE23M756-I-WS-WT-PR-5507 | LE23M756-I-WS-WT-PR-5507-C | AUTOSYS | Pre-order technically rejected | PR Closed |  |  |  |  | 09.05.24 | 10.05.24 | 14.05.24 | [22 empty] | vignesh.c1@lntecc.com-01.07.2024-12:25:31
Guwahati WSS | Instrumentation | Cables | LE23M756-I-WS-WT-PR-5508 | LE23M756-I-WS-WT-PR-5508 | GEMSCAB | Sent to BU Operations | 51 |  |  |  |  | 20.05.24 | 25.05.24 | 03.06.24 | [8 empty] | 12.06.24 | 13.06.24 | 14.06.24 | T1 | [7 empty] | 14.06.24 | 01.07.24 | 30.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Cables | LE23M756-I-WS-WT-PR-5508 | LE23M756-I-WS-WT-PR-5508-B | Axelon | Sent to BU Operations | 51 |  |  |  |  | 20.05.24 | 25.05.24 | 03.06.24 | [8 empty] | 12.06.24 | 13.06.24 | 14.06.24 | T2 | [7 empty] | 14.06.24 | 01.07.24 | 30.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | UPS & Battery | LE23M756-I-WS-WT-PR-5509 | LE23M756-I-WS-WT-PR-5509-A | HIREL | Awaiting pre-offer from vendor | 76 |  |  |  |  | 20.05.24 | [21 empty] | 25.07.24 | 11.08.24 | 10.10.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | UPS & Battery | LE23M756-I-WS-WT-PR-5509 | LE23M756-I-WS-WT-PR-5509-B | VERTIV | Awaiting pre-offer from vendor | 76 |  |  |  |  | 20.05.24 | [21 empty] | 25.07.24 | 11.08.24 | 10.10.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Rate of flow transmitter | LE23M756-I-WS-WT-PR-5510 | LE23M756-I-WS-WT-PR-5510-A | E & H | Sent to BU Operations | 27 |  |  |  |  | 20.05.24 | 04.07.24 | 07.07.24 | [8 empty] | 06.07.24 | 06.07.24 | 08.07.24 | T3 | [7 empty] | 11.07.24 | 28.07.24 | 26.09.24 | vignesh.c1@lntecc.com-08.07.2024-17:26:37
Guwahati WSS | Instrumentation | Rate of flow transmitter | LE23M756-I-WS-WT-PR-5510 | LE23M756-I-WS-WT-PR-5510-B | SIEMENS | Sent to BU Operations | 55 |  |  |  |  | 20.05.24 | 25.05.24 | 03.06.24 | [8 empty] | 05.06.24 | 07.06.24 | 10.06.24 | T1 | [7 empty] | 10.06.24 | 27.06.24 | 26.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Instrumentation | Rate of flow transmitter | LE23M756-I-WS-WT-PR-5510 | LE23M756-I-WS-WT-PR-5510-C | ABB | Sent to BU Operations | 54 |  |  |  |  | 20.05.24 | 25.05.24 | 03.06.24 | [8 empty] | 06.06.24 | 08.06.24 | 11.06.24 | T2 | [7 empty] | 11.06.24 | 28.06.24 | 27.08.24 | vignesh.c1@lntecc.com-08.07.2024-17:13:19
Guwahati WSS | Electrical | Transformer | LE23M756-E-WS-CW-PR-4202 | LE23M756-E-WS-CW-PR-4202-A | Indian | Pre-order comments issued | 69 |  |  |  |  | 10.05.24 | 23.05.24 | 27.05.24 | [19 empty] | 22.07.24 | 08.08.24 | 07.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Transformer | LE23M756-E-WS-CW-PR-4202 | LE23M756-E-WS-CW-PR-4202-B | Vardhman | Pre-order comments issued | 50 |  |  |  |  | 10.05.24 | 22.05.24 | 23.05.24 | 11.06.24 | 15.06.24 | [17 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Transformer | LE23M756-E-WS-CW-PR-4202 | LE23M756-E-WS-CW-PR-4202-C | Voltech | Pre-order comments issued | 58 |  |  |  |  | 10.05.24 | 21.05.24 | 23.05.24 | 30.05.24 | 07.06.24 | [17 empty] | 24.07.24 | 10.08.24 | 09.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Switchgear System | LE23M756-E-WS-CW-PR-4203 | LE23M756-E-WS-CW-PR-4203-A | Ragavendra | Pre-order technically cleared | 25 |  |  |  |  | 13.05.24 | 06.06.24 | 11.06.24 |  | 10.07.24 | [6 empty] | 10.07.24 | 10.07.24 | [9 empty] | 25.07.24 | 11.08.24 | 10.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:53:15
Guwahati WSS | Electrical | Switchgear system | LE23M756-E-WS-CW-PR-4203 | LE23M756-E-WS-CW-PR-4203-B | Universal | Pre-order technically cleared | 25 |  |  |  |  | 13.05.24 | 24.05.24 | 06.06.24 | 18.06.24 | 10.07.24 | [6 empty] | 10.07.24 | 10.07.24 | [9 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:53:15
Guwahati WSS | Electrical | Switchgear System | LE23M756-E-WS-CW-PR-4203 | LE23M756-E-WS-CW-PR-4203-C | Voltech | Pre-order technically cleared | 25 |  |  |  |  | 15.05.24 | 27.05.24 | 06.06.24 |  | 10.07.24 | [6 empty] | 10.07.24 | 10.07.24 | [9 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:53:15
Guwahati WSS | Electrical | Power and Control Cables | LE23M756-E-WS-CW-PR-4204 | LE23M756-E-WS-CW-PR-4204-A | Gemscab | Regret offer | PR Closed |  |  |  |  | 14.05.24 | 15.05.24 | 05.06.24 | [8 empty] | 05.06.24 | [13 empty] | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:01:37
Guwahati WSS | Electrical | Power and Control Cables | LE23M756-E-WS-CW-PR-4204 | LE23M756-E-WS-CW-PR-4204-B | Axelon | Sent to BU Operations | 38 |  |  |  |  | 14.05.24 | 15.05.24 | 05.06.24 | [8 empty] | 05.06.24 | 05.06.24 | 27.06.24 | t2 | [7 empty] | 27.06.24 | 14.07.24 | 12.09.24 | usman.mohideen@lntecc.com-11.07.2024-09:53:15
Guwahati WSS | Electrical | Power and Control Cables | LE23M756-E-WS-CW-PR-4204 | LE23M756-E-WS-CW-PR-4204-C | Cords | Sent to BU Operations | 38 |  |  |  |  | 14.05.24 | 21.05.24 | 05.06.24 | 11.06.24 | [7 empty] | 05.06.24 | 11.06.24 | 27.06.24 | t2 | [7 empty] | 27.06.24 | 14.07.24 | 12.09.24 | usman.mohideen@lntecc.com-11.07.2024-09:53:15
Guwahati WSS | Electrical | Lighting materials | LE23M756-E-WS-CW-PR-4205 | LE23M756-E-WS-CW-PR-4205-A | Monaj Trading | Awaiting pre-offer from vendor | 82 |  |  |  |  | 14.05.24 | [21 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Lighting materials | LE23M756-E-WS-CW-PR-4205 | LE23M756-E-WS-CW-PR-4205-B | Stokes | Awaiting pre-offer from vendor | 82 |  |  |  |  | 14.05.24 | [21 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Earthing & Lightning System | LE23M756-E-WS-CW-PR-4206 | LE23M756-E-WS-CW-PR-4206-A | Monaj Trading | Awaiting pre-offer from vendor | 82 |  |  |  |  | 14.05.24 | [21 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Earthing & Lightning System | LE23M756-E-WS-CW-PR-4206 | LE23M756-E-WS-CW-PR-4206-B | Stokes | Awaiting pre-offer from vendor | 82 |  |  |  |  | 14.05.24 | [21 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Cables Glands & Lugs | LE23M756-E-WS-WT-PR-4207 | LE23M756-E-WS-WT-PR-4207-A | Monaj Trading | Awaiting pre-offer from vendor | 82 |  |  |  |  | 14.05.24 | [21 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Cables Glands & Lugs | LE23M756-E-WS-WT-PR-4207 | LE23M756-E-WS-WT-PR-4207-B | Stokes | Awaiting pre-offer from vendor | 82 |  |  |  |  | 14.05.24 | [21 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Cable Trays & Accessories | LE23M756-E-WS-WT-PR-4208 | LE23M756-E-WS-WT-PR-4208-A | Monaj Trading | Awaiting pre-offer from vendor | 82 |  |  |  |  | 14.05.24 | [21 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Guwahati WSS | Electrical | Cable Trays & Accessories | LE23M756-E-WS-WT-PR-4208 | LE23M756-E-WS-WT-PR-4208-B | Stokes | Awaiting pre-offer from vendor | 82 |  |  |  |  | 14.05.24 | [21 empty] | 07.08.24 | 24.08.24 | 23.10.24 | usman.mohideen@lntecc.com-11.07.2024-09:52:43
Hubballi | Process | Raw water quality Report | LE200351-P-WS-WT-PR-2001 | LE200351-P-WS-WT-PR-2001 | PR Closed | Regret offer | PR Closed |  |  |  |  | 17.04.20 | [24 empty] | THENNARASU@lntecc.com-04.06.2024-11:22:53
Hubballi | Process | Clariflocculator Mechanism | LE200351-P-WS-WT-PR-2002 | LE200351-P-WS-WT-PR-2002-A | SRITECH | Post-order technically cleared | 251 |  |  |  |  | 06.11.20 | 21.01.23 | 24.02.23 | 10.03.23 | 17.04.23 | 02.06.23 | [5 empty] | 17.04.23 | 02.06.23 | 02.06.23 | T1 | 31.08.23 | SRITECH | 11.09.23 | 04.10.23 | 22.11.23 | 27.11.23 |  |  |  | 30.10.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Clariflocculator Mechanism | LE200351-P-WS-WT-PR-2002 | LE200351-P-WS-WT-PR-2002-B | SHIVPAD | Regret offer | PR Closed |  |  |  |  | 06.11.20 | 10.01.23 | 13.01.23 | [22 empty] | THENNARASU@lntecc.com-20.05.2024-09:59:53
Hubballi | Process | Clariflocculator Mechanism | LE200351-P-WS-WT-PR-2002 | LE200351-P-WS-WT-PR-2002-C | TRIVENI | Sent to BU Operations | PR Closed |  |  |  |  | 06.11.20 | 29.12.22 | 20.01.23 | 03.02.23 | 08.02.23 | 09.03.23 | 03.06.23 |  |  |  |  | 09.03.23 | 03.06.23 | 03.06.23 | T2 | [10 empty] | THENNARASU@lntecc.com-20.05.2024-10:00:00
Hubballi | Process | Clariflocculator Mechanism | LE200351-P-WS-WT-PR-2002 | LE200351-P-WS-WT-PR-2002-D | ADROIT | Sent to BU Operations | PR Closed |  |  |  |  | 06.11.20 | 02.03.23 | 02.03.23 | 09.05.23 | 19.06.23 | 22.06.23 | 06.07.23 |  |  |  |  | 22.06.23 | 06.07.23 | 06.07.23 | T3 | [10 empty] | THENNARASU@lntecc.com-20.05.2024-10:00:00
Hubballi | Process | Air Blower | LE200351-P-WS-WT-PR-2003 | LE200351-P-WS-WT-PR-2003-A | ACME | Regret offer | PR Closed | REJECTED |  |  |  | 06.11.20 | 06.01.23 | 12.01.23 | 23.02.23 | 01.03.23 | 13.09.23 | 16.06.23 | 19.09.23 | 29.09.23 |  |  | 07.08.23 | 24.08.23 | 24.08.23 | T1 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:10:48
Hubballi | Process | Air Blower | LE200351-P-WS-WT-PR-2003 | LE200351-P-WS-WT-PR-2003-B | KAY | Sent to BU Operations | 346 |  |  |  |  | 06.11.20 | 23.01.23 | 31.01.23 | 03.03.23 | 03.06.23 | 03.06.23 | 13.06.23 | 07.08.23 | 24.08.23 |  |  | 07.08.23 | 24.08.23 | 24.08.23 | T1 | 24.08.23 | KAY | [7 empty] | 23.10.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Air Blower | LE200351-P-WS-WT-PR-2003 | LE200351-P-WS-WT-PR-2003-C | ATLAS COPCO | Regret offer | PR Closed | REJECTED |  |  |  | 06.11.20 | 23.01.23 | 01.02.23 | 09.03.23 | 03.06.23 | 19.07.23 | 08.08.23 |  |  |  |  | 19.07.23 | 08.08.23 | 08.08.23 | T1 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:10:48
Hubballi | Process | Air Blower | LE200351-P-WS-WT-PR-2003 | LE200351-P-WS-WT-PR-2003-D | EVEREST | Sent to BU Operations | 234 |  |  |  |  | 06.11.20 | 30.05.23 | 22.06.23 | 12.12.23 | 14.12.23 | 05.01.23 | 10.01.23 | 09.02.23 | 17.02.23 |  |  | 09.02.23 | 17.02.23 | 17.02.23 | T1 | 17.02.23 | EVEREST | [7 empty] | 18.04.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Agitator | LE200351-P-WS-WT-PR-2004 | LE200351-P-WS-WT-PR-2004-A | SHIVPAD | Sent to BU Operations | PR Closed |  |  |  |  | 06.11.20 | 10.01.23 | 13.01.23 | 04.02.23 | 07.02.23 | [6 empty] | 04.02.23 | 07.02.23 | 07.02.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:11:55
Hubballi | Process | Agitator | LE200351-P-WS-WT-PR-2004 | LE200351-P-WS-WT-PR-2004-B | TRIVENI | Regret offer | PR Closed |  |  |  |  | 06.11.20 | 29.12.23 | 29.12.23 | [8 empty] | 29.12.23 | 29.12.23 | [12 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:29:02
Hubballi | Process | Agitator | LE200351-P-WS-WT-PR-2004 | LE200351-P-WS-WT-PR-2004-C | VERITO | Regret offer | PR Closed |  |  |  |  | 06.11.20 | 19.01.23 | 04.02.23 | 28.02.23 | 01.03.23 | [6 empty] | 28.02.23 | 01.03.23 | [12 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:29:02
Hubballi | Process | Agitator | LE200351-P-WS-WT-PR-2004 | LE200351-P-WS-WT-PR-2004-D | SRITECH | Post-order technically cleared | 310 |  |  |  |  | 06.11.20 | 07.01.23 | 27.01.23 | 17.04.23 | 08.05.23 | [6 empty] | 17.04.23 | 08.05.23 | 08.05.23 | T1 | 22.08.23 | SRITECH | 04.09.23 | 07.09.23 | 25.09.23 | 29.09.23 |  |  |  | 21.10.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Agitator | LE200351-P-WS-WT-PR-2004 | LE200351-P-WS-WT-PR-2004-E | ADROIT | Sent to BU Operations | PR Closed |  |  |  |  | 06.11.20 | 02.03.23 | 02.03.23 | 09.05.23 | 19.06.23 | 22.06.23 | 06.07.23 |  |  |  |  | 22.06.23 | 06.07.23 | 06.07.23 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:11:55
Hubballi | Process | WTP Sluice Gates | LE200351-P-WS-WT-PR-2005 | LE200351-P-WS-WT-PR-2005-A | ORIENTAL | Sent to BU Operations | PR Closed |  |  |  |  | 21.11.20 | 11.01.23 | 03.02.23 | 13.02.23 | 14.02.23 | [6 empty] | 13.02.23 | 14.02.23 | 14.02.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:13:20
Hubballi | Process | WTP Sluice Gates | LE200351-P-WS-WT-PR-2005 | LE200351-P-WS-WT-PR-2005-B | JASH | Post-order technically cleared | 246 |  |  |  |  | 21.11.20 | 12.01.23 | 19.01.23 | 01.02.23 | 04.02.23 | 17.02.23 | 03.03.23 | 04.05.23 | 08.05.23 |  |  | 04.05.23 | 08.05.23 | 08.05.23 | T1 | 31.07.23 | JASH | 04.08.23 | 13.09.23 | 28.11.23 | 02.12.23 |  |  |  | 29.09.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | WTP Sluice Gates | LE200351-P-WS-WT-PR-2005 | LE200351-P-WS-WT-PR-2005-C | SIGMA FLOW | Sent to BU Operations | PR Closed |  |  |  |  | 21.11.20 | 12.01.23 | 04.02.23 | 15.02.23 | 18.03.23 | 22.04.23 | 28.04.23 |  |  |  |  | 22.04.23 | 28.04.23 | 28.04.23 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:13:20
Hubballi | Process | Chlorination System | LE200351-P-WS-WT-PR-2006 | LE200351-P-WS-WT-PR-2006-D | CHLOROTECH | Sent to BU Operations | PR Closed |  |  |  |  | 27.11.20 | 10.11.22 | 22.12.22 | 31.12.22 | 20.02.23 | 03.03.23 | 10.03.23 | 21.03.23 |  |  |  | 10.03.23 | 21.03.23 | 10.03.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:15:45
Hubballi | Process | Chlorination System | LE200351-P-WS-WT-PR-2006 | LE200351-P-WS-WT-PR-2006-E | ZION | Post-order technically cleared | 62 |  |  |  |  | 27.11.20 | 29.12.22 | 10.02.23 | 06.04.23 | 14.04.23 | 18.04.23 | 19.04.23 |  |  |  |  | 18.04.23 | 19.04.23 | 19.04.23 | T1 | 15.11.23 | ZION | 29.01.23 | 14.02.24 | 29.05.24 | 03.06.24 |  |  |  | 14.01.24 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Chlorination System | LE200351-P-WS-WT-PR-2006 | LE200351-P-WS-WT-PR-2006-F | TOSHCON | Regret offer | PR Closed |  |  |  |  | 27.11.20 | 21.02.22 | 01.03.23 | [8 empty] | 21.02.22 | 01.03.23 | [12 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:29:02
Hubballi | Process | Chlorine Tonners | LE200351-P-WS-WT-PR-2007 | LE200351-P-WS-WT-PR-2007-A | ZION | Sent to BU Operations | 473 |  |  |  |  | 27.11.20 | 29.12.22 | 10.02.23 | 06.04.23 | 14.04.23 | 18.04.23 | 19.04.23 |  |  |  |  | 18.04.23 | 19.04.23 | 19.04.23 | T1 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Filter media | LE200351-P-WS-WT-PR-2008 | LE200351-P-WS-WT-PR-2008-A | Shakun Minerals | Pre-order technically cleared | 57 |  |  |  |  | 09.02.24 | 31.05.24 | 07.06.24 | 08.06.24 | 08.06.24 | [6 empty] | 08.06.24 | 08.06.24 |  | T1 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Nozzles | LE200351-P-WS-WT-PR-2009 | LE200351-P-WS-WT-PR-2009-A | GUDDI PLASTCON | Post-order technically cleared | 459 |  |  |  |  | 07.11.20 | 06.01.23 | 21.01.23 | [8 empty] | 06.01.23 | 21.01.23 | 21.01.23 | T1 | 03.05.23 | GUDDI PLASTCON | 03.05.23 | 03.05.23 | 03.05.23 | 03.05.23 |  |  |  | 02.07.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Nozzles | LE200351-P-WS-WT-PR-2009 | LE200351-P-WS-WT-PR-2009-B | VP ENGINEERS | Sent to BU Operations | PR Closed |  |  |  |  | 07.11.20 | 21.10.23 | 29.12.23 | 30.12.23 | 31.12.23 | [6 empty] | 30.12.23 | 31.12.23 | 30.12.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:17:10
Hubballi | Process | Sludge Drying Bed Media | LE200351-P-WS-WT-PR-2010 | LE200351-P-WS-WT-PR-2010-A | Shakum Minerals | Pre-order technically cleared | 57 |  |  |  |  | 09.02.24 | 31.05.24 | 07.06.24 | 08.06.24 | 08.06.24 | [6 empty] | 08.06.24 | 08.06.24 |  | T1 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Backwash Pump | LE200351-P-WS-WT-PR-2011 | LE200351-P-WS-WT-PR-2011-A | WILO | Regret offer | PR Closed |  |  |  |  | 11.11.20 | 29.12.22 | 01.03.23 | [8 empty] | 29.12.22 | 01.03.23 | [12 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:29:02
Hubballi | Process | Backwash Pump | LE200351-P-WS-WT-PR-2011 | LE200351-P-WS-WT-PR-2011-B | KSB | Sent to BU Operations | PR Closed |  |  |  |  | 11.11.20 | 24.04.23 | 02.05.23 | 23.05.23 | 27.05.23 | 14.07.23 | 08.08.23 |  |  |  |  | 14.07.23 | 08.08.23 | 14.07.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:19:36
Hubballi | Process | Backwash Pump | LE200351-P-WS-WT-PR-2011 | LE200351-P-WS-WT-PR-2011-C | ANDRITZ | Post-order technically cleared | 209 |  |  |  |  | 11.11.20 | 20.07.23 | 04.08.23 | [8 empty] | 20.07.23 | 04.08.23 | 20.07.23 | T1 | 11.10.23 | ANDRITZ | 21.10.23 | 23.11.23 | 12.12.23 | 08.01.24 |  |  |  | 10.12.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Submersible Pump | LE200351-P-WS-WT-PR-2012 | LE200351-P-WS-WT-PR-2012-A | JASCO | Regret offer | PR Closed |  |  |  |  | 07.11.20 | 30.01.23 | 04.02.23 | [8 empty] | 30.01.23 | 04.02.23 | [12 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:26:43
Hubballi | Process | Submersible Pump | LE200351-P-WS-WT-PR-2012 | LE200351-P-WS-WT-PR-2012-B | KSB | Sent to BU Operations | 262 |  |  |  |  | 07.11.20 | 10.03.23 | 28.03.23 | 13.04.23 | 14.04.23 | 26.04.23 | 08.05.23 | 31.10.23 | 16.11.23 |  |  | 31.10.23 | 16.11.23 | 31.10.23 | T1 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Submersible Pump | LE200351-P-WS-WT-PR-2012 | LE200351-P-WS-WT-PR-2012-C | MBH | Pre-order technically cleared | 73 |  |  |  |  | 07.11.20 | 04.04.24 | 30.04.24 | 14.05.24 | 23.05.24 | [6 empty] | 04.04.24 | 30.04.24 | [12 empty] | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Electrical Hoist | LE200351-P-WS-WT-PR-2013 | LE200351-P-WS-WT-PR-2013-A | JAPS | Post-order technically cleared | 165 |  |  |  |  | 30.11.20 | 23.01.23 | 27.01.23 | 19.07.23 | 22.08.23 | [6 empty] | 19.07.23 | 22.08.23 | 19.07.23 | T1 | 11.10.23 | JAPS | 27.10.23 | 27.10.23 | 15.02.24 | 21.02.24 |  |  |  | 10.12.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Electrical Hoist | LE200351-P-WS-WT-PR-2013 | LE200351-P-WS-WT-PR-2013-B | INDEF | Sent to BU Operations | PR Closed |  |  |  |  | 30.11.20 | 03.02.23 | 06.02.23 | 21.02.23 | 03.03.23 | [6 empty] | 21.02.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:22:56
Hubballi | Process | Manual Chain Pulley Block | LE200351-P-WS-WT-PR-2014 | LE200351-P-WS-WT-PR-2014-A | JAPS | Post-order technically cleared | 165 |  |  |  |  | 30.11.20 | 23.01.23 | 27.01.23 | 19.07.23 | 22.08.23 | 24.08.23 | 04.09.23 |  |  |  |  | 24.08.23 | 04.09.23 | 04.09.23 | T1 | 11.10.23 | JAPS | 27.10.23 | 27.10.23 | 15.02.24 | 21.02.24 |  |  |  | 10.12.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Manual Chain Pulley Block | LE200351-P-WS-WT-PR-2014 | LE200351-P-WS-WT-PR-2014-B | INDEF | Sent to BU Operations | PR Closed |  |  |  |  | 30.11.20 | 03.02.23 | 06.02.23 | 21.02.23 | 03.03.23 | [6 empty] | 21.02.23 | 03.03.23 | 03.03.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:22:56
Hubballi | Process | Dosing Pump | LE200351-P-WS-WT-PR-2015 | LE200351-P-WS-WT-PR-2015-A | POSITIVE METERING | Sent to BU Operations | PR Closed |  |  |  |  | 20.11.20 | 21.01.23 | 21.01.23 | 02.02.23 | 04.02.23 | 06.02.23 | 06.02.23 |  |  |  |  | 06.02.23 | 06.02.23 | 06.02.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:24:28
Hubballi | Process | Dosing Pump | LE200351-P-WS-WT-PR-2015 | LE200351-P-WS-WT-PR-2015-B | VK PUMPS | Sent to BU Operations | PR Closed |  |  |  |  | 20.11.20 | 29.12.22 | 12.01.23 | 14.02.23 | 16.02.23 | 23.02.23 | 27.02.23 |  |  |  |  | 23.02.23 | 27.02.23 | 23.02.23 | T3 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:24:28
Hubballi | Process | Dosing Pump | LE200351-P-WS-WT-PR-2015 | LE200351-P-WS-WT-PR-2015-C | SR METERING | Sent to BU Operations | PR Closed |  |  |  |  | 20.11.20 | 22.12.22 | 20.01.23 | 30.01.23 | 30.01.23 | [6 empty] | 30.01.23 | 30.01.23 | 30.01.23 | T4 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:24:28
Hubballi | Process | Dosing Pump | LE200351-P-WS-WT-PR-2015 | LE200351-P-WS-WT-PR-2015-D | VERITO | Post-order technically cleared | 439 |  |  |  |  | 20.11.20 | 13.02.23 | 13.02.23 | 16.02.23 | 16.02.23 | [6 empty] | 16.02.23 | 16.02.23 | 16.02.23 | T1 | 15.04.23 | VERITO | 15.04.23 | 19.04.23 | 22.05.23 | 23.05.23 |  |  |  | 14.06.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Sampling Pump | LE200351-P-WS-WT-PR-2016 | LE200351-P-WS-WT-PR-2016-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 20.11.20 | [24 empty] | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Submersible Mixer | LE200351-P-WS-WT-PR-2017 | LE200351-P-WS-WT-PR-2017-A | SULZER | Sent to BU Operations | PR Closed |  |  |  |  | 07.11.20 | 20.01.23 | 04.02.23 | [8 empty] | 20.01.23 | 04.02.23 | 04.02.23 | T2 | [10 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:26:43
Hubballi | Process | Submersible Mixer | LE200351-P-WS-WT-PR-2017 | LE200351-P-WS-WT-PR-2017-B | FFP | Post-order technically cleared | 337 |  |  |  |  | 07.11.20 | 06.02.23 | 08.02.23 | 06.07.23 | 07.07.23 | [6 empty] | 06.07.23 | 07.07.23 | 07.07.23 | T1 | 31.07.23 | FFP | 02.08.23 | 28.08.23 | 28.08.23 | 02.09.23 |  |  |  | 29.09.23 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Dewatering Pump | LE200351-P-WS-WT-PR-2018 | LE200351-P-WS-WT-PR-2018-A | JASCO | Regret offer | PR Closed |  |  |  |  | 06.11.20 | 30.01.23 | 04.02.23 | [8 empty] | 30.01.23 | 04.02.23 | [12 empty] | deepak.choudhary@lntecc.com-20.05.2024-10:29:02
Hubballi | Process | Dewatering Pump | LE200351-P-WS-WT-PR-2018 | LE200351-P-WS-WT-PR-2018-B | KSB | Sent to BU Operations | 262 |  |  |  |  | 06.11.20 | 10.03.23 | 28.03.23 | 13.04.23 | 14.04.23 | 26.04.23 | 08.05.23 | 31.10.23 | 16.11.23 |  |  | 31.10.23 | 16.11.23 | 16.11.23 | T1 | [10 empty] | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Dewatering Pump | LE200351-P-WS-WT-PR-2018 | LE200351-P-WS-WT-PR-2018-C | MBH | Pre-order technically cleared | 73 |  |  |  |  | 06.11.20 | 04.04.24 | 30.04.24 | 14.05.24 | 23.05.24 | [6 empty] | 04.04.24 | 30.04.24 | [12 empty] | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Process | Trolley | LE200351-P-WS-WT-PR-2019 | LE200351-P-WS-WT-PR-2019-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 11.11.20 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:37:30
Hubballi | Process | Platform Weighing Machine | LE200351-P-WS-WT-PR-2020 | LE200351-P-WS-WT-PR-2020-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 21.11.20 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:38:13
Hubballi | Process | Dissolving Tray | LE200351-P-WS-WT-PR-2021 | LE200351-P-WS-WT-PR-2021-A | NA | Regret offer | PR Closed | Site procurement |  |  |  | 06.11.20 | [24 empty] | THENNARASU@lntecc.com-20.06.2024-11:47:26
Hubballi | Process | Exhaust Fan | LE200351-P-WS-WT-PR-2022 | LE200351-P-WS-WT-PR-2022-A | PR Deleted | Regret offer | PR Closed |  |  |  |  | 04.06.24 | [24 empty] | THENNARASU@lntecc.com-04.06.2024-11:27:44
Hubballi | Process | Laboratory Equipment | LE200351-P-WS-WT-PR-2023 | LE200351-P-WS-WT-PR-2023-A | EIE Instruments | Post-order technically cleared | 82 | mail confirmation given |  |  |  | 27.11.20 | 15.04.24 | 25.04.24 | 06.05.24 | 14.05.24 | [6 empty] | 14.05.24 | 14.05.24 | 14.05.24 | T1 | 14.05.24 | EIE Instruments | 14.05.24 | 14.05.24 | 14.05.24 | 14.05.24 |  |  |  | 13.07.24 | THENNARASU@lntecc.com-11.07.2024-11:45:46
Hubballi | Mechanical | EOT Cranes | LE200351-M-WS-CR-PR-1265 | LE200351-M-WS-CR-PR-1265-A | JAPS | Pre-order technically cleared | 48 |  | 9825019138 | sales.japs@gmail.com |  | 02.04.21 | 25.01.24 | 02.04.24 | 15.06.24 | 17.06.24 | [6 empty] | 15.06.24 | 15.06.24 | 17.06.24 | T1 | [7 empty] | 15.06.24 | 02.07.24 | 31.08.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | EOT Cranes | LE200351-M-WS-CR-PR-1265 | LE200351-M-WS-CR-PR-1265-B | REVA cranes | Pre-order technically cleared | 13 |  | 9899484744 | south@revacranes.com | 02.04.21 | 01.07.24 | 01.07.24 | 02.07.24 | 03.07.24 | 08.07.24 | 20.07.24 | 22.07.24 |  |  |  |  | 22.07.24 | 20.07.24 | 22.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-16:55:22
Hubballi | Mechanical | HSC Pumps | LE200351-M-WS-CWPR-1263 | LE200351-M-WS-CWPR-1263-A | WPIL | Post-order technically cleared | 256 |  | 33 4052 6000 | s.sen@wpil.co.in |  | 31.03.21 | 16.08.23 | 24.08.23 | [8 empty] | 30.08.23 | 30.08.23 | 30.08.23 | T1 | 30.08.23 | WPIL | 07.10.23 | 16.10.23 | 22.11.23 | 22.11.23 |  | 30.08.23 | 16.09.23 | 29.10.23 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | Dewatering Pumps | LE200351-M-WS-DW-PR-1263 | LE200351-M-WS-DW-PR-1263-A | Aqua | Pre-order comments issued | 10 |  | S.T.Sambandam 8144003131 | chennai@aquapumps.com |  | 05.07.24 | 23.07.24 | 25.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:00:24
Hubballi | Mechanical | Dewatering Pumps | LE200351-M-WS-DW-PR-1263 | LE200351-M-WS-DW-PR-1263-B | Jasco | Pre-order technically cleared | 9 |  | Arvish Modi 7069099037 | hyd@jascopump.com |  | 29.06.24 | 09.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [10 empty] | svcn@lntecc.com-26.07.2024-17:00:24
Hubballi | Mechanical | Exhaust Fans | LE200351-M-WS-EF-PR-1264 | LE200351-M-WS-EF-PR-1264-A |  | Enquiry yet to float | NA | [26 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-15:02:53
Hubballi | Mechanical | Pump house valves | LE200351-M-WS-VL-PR-1266 | LE200351-M-WS-VL-PR-1266-A | AVK | Post-order technically cleared | 78 |  | 91769 66455 | subhash@avkindia.com |  | 02.04.21 | 30.10.23 | 08.11.23 | [8 empty] | 08.11.23 | 08.11.23 | 08.11.23 | T1 | 08.11.23 | AVK | 09.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  | 08.11.23 | 25.11.23 | 07.01.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | DJ | LE200351-M-WS-VL-PR-1266 | LE200351-M-WS-VL-PR-1266-B | Electrosteel | Post-order technically cleared | 78 |  |  | satyendra.kumar@electrosteel.com; anujkr.maurya@electrosteel.com; animikh.banerjee@electrosteel.com; soumayajit.mukherjee@electrosteel.com |  | 02.04.21 | 30.10.23 | 08.11.23 | [8 empty] | 08.11.23 | 08.11.23 | 08.11.23 | T1 | 08.11.23 | Electrosteel | 09.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  | 08.11.23 | 25.11.23 | 07.01.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | DPCV | LE200351-M-WS-VL-PR-1266 | LE200351-M-WS-VL-PR-1266-C | R&D | Post-order technically cleared | 240 |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 02.04.21 | 17.06.23 | 17.06.23 | [8 empty] | 05.08.23 | 05.08.23 | 05.08.23 | T1 | 30.09.23 | R&D | 30.11.23 | 07.12.23 | 08.12.23 | 08.12.23 |  | 05.08.23 | 22.08.23 | 21.10.23 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | Pipe Line Valves | LE200351-M-WS-VL-PR-1267 | LE200351-M-WS-VL-PR-1267-A | MAGWEN | Approved by Client | PR Closed |  | 91769 66481 |  |  | 07.11.22 | 08.11.22 | 08.11.22 | [8 empty] | 09.11.22 | 09.11.22 | 10.11.22 | T1 | 10.11.22 | MAGWEN | 17.11.22 | 23.11.22 | 23.11.22 | 23.11.22 | 29.11.22 | 09.11.22 | 26.11.22 | 09.01.23 | svcn@lntecc.com-03.07.2024-15:02:13
Hubballi | Mechanical | PRV | LE200351-M-WS-VL-PR-1267 | LE200351-M-WS-VL-PR-1267-B | Dorot | Post-order technically cleared | 123 |  | 91769 66464 | abhishek.mathur@aquestia.com |  | 06.11.23 | 18.12.23 | 18.12.23 | [8 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T1 | 02.03.24 | Dorot | 02.04.24 | 02.04.24 | 03.04.24 | 03.04.24 |  | 02.03.24 | 19.03.24 | 01.05.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | Sluice Gate | LE200351-M-WS-VL-PR-1268 | LE200351-M-WS-VL-PR-1268-A | JASH | Pre-order technically cleared | 58 |  | 91-72900 40772 | lpgsouth2@jashindia.com |  | 28.10.20 | 07.03.24 | 07.06.24 | [8 empty] | 07.06.24 | 07.03.24 | 07.03.24 | T1 | [7 empty] | 07.06.24 | 24.06.24 | 23.08.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | Sluice Gate | LE200351-M-WS-VL-PR-1268 | LE200351-M-WS-VL-PR-1268-B | IVC | Regret offer | PR Closed |  | Sudip Ghosh | sudip.ghosh@ivc-valves.com |  | 28.10.20 | 23.01.24 | [20 empty] | 28.10.20 | 14.11.20 | 13.01.21 | svcn@lntecc.com-02.07.2024-10:55:34
Hubballi | Mechanical | VT pumps-Intake | LE200351-M-WS-VT-PR-1261 | LE200351-M-WS-VT-PR-1261-A | WILO | Approved by Client | PR Closed |  | 86800 68301 | manikkandan.pr@wilo.com |  | 31.03.21 | 06.02.23 | 09.02.23 | [8 empty] | 15.02.24 | 15.02.24 | 15.02.24 | T1 | 15.02.24 | WILO | 11.01.24 | 18.02.24 | 18.02.24 | 18.02.24 | 29.03.24 | 15.02.24 | 03.03.24 | 15.04.24 | svcn@lntecc.com-03.07.2024-15:02:13
Hubballi | Mechanical | VT pumps | LE200351-M-WS-VT-PR-1261 | LE200351-M-WS-VT-PR-1261-B | KBL | Approved by Client | PR Closed |  | 86696 64820 | azharuddin.tamboli@kbl.co.in |  | 31.03.21 | 06.02.23 | 09.02.23 | [8 empty] | 15.02.24 | 15.02.24 | 15.02.24 | T1 | 15.02.24 | KBL | 11.01.24 | 18.02.24 | 18.02.24 | 18.02.24 | 29.03.24 | 15.02.24 | 03.03.24 | 15.04.24 | svcn@lntecc.com-03.07.2024-15:02:13
Hubballi | Mechanical | Surge Equipments (ZVV) | LE200354-M-WS-CW-PR-1200 | LE200354-M-WS-CW-PR-1200-A | JASH | Post-order technically cleared | 144 |  | 91-72900 40772 | lpgsouth2@jashindia.com |  | 07.12.23 | 12.02.24 | 04.03.24 | [8 empty] | 04.03.24 | 04.03.24 | 04.03.24 | T1 | 06.03.24 | JASH | 12.03.24 | 13.03.24 | 13.03.24 | 13.03.24 |  | 04.03.24 | 21.03.24 | 05.05.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | Surge Equipments | LE200354-M-WS-CW-PR-1201 | LE200354-M-WS-CW-PR-1201-A | SigmaFlow | Sent to BU Operations | 178 |  | Jagadesh | jagadesh@sigmaflow.in |  | 07.12.23 | 31.01.24 | 08.02.24 | [8 empty] | 08.02.24 | 08.02.24 | 08.02.24 | T1 | [7 empty] | 08.02.24 | 25.02.24 | 25.04.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | Surge Equipments(ACV) | LE200354-M-WS-CW-PR-1203 | LE200354-M-WS-CW-PR-1203-A | AVK | Post-order technically cleared | 135 |  | 91769 66455 | subhash@avkindia.com |  | 07.12.23 | 31.01.24 | 08.02.24 | [8 empty] | 08.02.24 | 08.02.24 | 08.02.24 | T1 | 12.03.24 | AVK | 13.03.24 | 22.03.24 | 22.03.24 | 22.03.24 |  | 08.02.24 | 25.02.24 | 25.04.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | FCV | LE200354-M-WS-CW-PR-1269 | LE200354-M-WS-CW-PR-1269-A | AVK | Post-order technically cleared | 172 |  | 91769 66455 | subhash@avkindia.com |  | 03.07.23 | 10.07.23 | 10.07.23 | [8 empty] | 09.02.24 | 09.02.24 | 09.02.24 | T1 | 09.02.24 | AVK | 13.02.24 | 14.02.24 | 14.02.24 | 14.02.24 |  | 09.02.24 | 26.02.24 | 09.04.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Mechanical | ELSR/GLSR Valves | LE200354-M-WS-CW-PR-1270 | LE200354-M-WS-CW-PR-1270-A | R&D | Post-order technically cleared | 92 |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 06.06.23 | 09.02.24 | 12.02.24 | [8 empty] | 17.04.24 | 17.04.24 | 17.04.24 | T1 | 17.04.24 | R&D | 04.05.24 | 04.05.24 | 04.05.24 | 04.05.24 |  | 17.04.24 | 04.05.24 | 16.06.24 | svcn@lntecc.com-26.07.2024-16:51:04
Hubballi | Instrumentation | Electromagnetic Flowmeter | LE200351-I-WS-PR-EF-5201 | LE200351-I-WS-PR-EF-5201-A | Khrone | Approved by Client | PR Closed |  | Diliban | dilibanr@forbesmarshall.com | 02.03.22 | 02.03.22 | 07.03.22 | 14.03.22 | 18.03.22 | [7 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T1 | 21.05.24 | Khrone | 06.08.22 | 18.08.22 | 18.08.22 | 18.08.22 | 01.04.24 | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Electromagnetic Flowmeter | LE200351-I-WS-PR-EF-5201 | LE200351-I-WS-PR-EF-5201-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 02.03.22 | 02.03.22 | 15.03.22 | 15.03.22 | 16.06.22 | [7 empty] | 16.06.22 | 16.06.22 | 20.03.22 | T2 | [7 empty] | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Electromagnetic Flowmeter | LE200351-I-WS-PR-EF-5201 | LE200351-I-WS-PR-EF-5201-C | ABB | Sent to BU Operations | PR Closed |  | Krishnakishore | krishna.kishore@in.abb.com | 02.03.22 | 02.03.22 | 07.03.22 | 14.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Electromagnetic Flowmeter | LE200351-I-WS-PR-EF-5201 | LE200351-I-WS-PR-EF-5201-D | Siemens | Sent to BU Operations | PR Closed |  | Guruswamy Keerthi | keerthi.guruswamy.ext@siemens.com | 02.03.22 | 02.03.22 | 08.03.22 | 14.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T4 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Float and Board Level Indicator | LE200351-I-WS-PR-FB-5205 | LE200351-I-WS-PR-FB-5205-A | SBEM | Sent to BU Operations | 40 |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 05.03.22 | 29.09.23 | 25.03.24 | 08.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T1 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Float and Board Level Indicator | LE200351-I-WS-PR-FB-5205 | LE200351-I-WS-PR-FB-5205-B | Pune Techtrol | Pre-order technically rejected | PR Closed |  | Shanmugasundari | sales.techtrol@measurecon.co.in | 01.01.22 | 05.03.22 | 19.02.24 | 25.03.24 | [22 empty] | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Float and Board Level Indicator | LE200351-I-WS-PR-FB-5205 | LE200351-I-WS-PR-FB-5205-C | Scientific Devices | Sent to BU Operations | 40 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 05.03.22 | 16.11.23 | 25.03.24 | 10.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T2 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Ultrasonic Level Transmitter | LE200351-I-WS-PR-LT-5203 | LE200351-I-WS-PR-LT-5203-A | Eximp | Sent to BU Operations | PR Closed |  | Jayakrishnan Pallath | Jayakrishnan.Pallath@eximpinc.com | 03.03.22 | 03.03.22 | 14.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 17.03.22 | 17.03.22 | 20.03.22 | T1 | [7 empty] | 17.03.22 | 03.04.22 | 02.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Ultrasonic Level Transmitter | LE200351-I-WS-PR-LT-5203 | LE200351-I-WS-PR-LT-5203-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 03.03.22 | 03.03.22 | 09.03.22 | 18.03.22 | [8 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T2 | [7 empty] | 28.03.22 | 14.04.22 | 13.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Ultrasonic Level Transmitter | LE200351-I-WS-PR-LT-5203 | LE200351-I-WS-PR-LT-5203-C | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 03.03.22 | 03.03.22 | 08.03.22 | 16.03.22 | [8 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Ultrasonic Level Transmitter | LE200351-I-WS-PR-LT-5203 | LE200351-I-WS-PR-LT-5203-D | Siemens | Post-order technically cleared | 683 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 03.03.22 | 03.03.22 | 16.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T4 | 30.08.22 | Siemens | 20.09.22 | 21.09.22 | 21.09.22 | 21.09.22 |  | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | PLC & SCADA | LE200351-I-WS-PR-PL-5516 | LE200351-I-WS-PR-PL-5516-A | Schnedier | Sent to BU Operations | 317 |  | Rusheyandr | rushyendhar.repalli@se.com | 01.01.22 | 30.07.22 | 30.06.23 | 01.07.23 | 10.08.23 | [7 empty] | 22.09.23 | 22.09.23 | 22.09.23 | T1 | [7 empty] | 22.09.23 | 09.10.23 | 08.12.23 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | PLC & SCADA | LE200351-I-WS-PR-PL-5516 | LE200351-I-WS-PR-PL-5516-B | Honeywell | Sent to BU Operations | 258 |  | Vinod Janarthan | vinod.janarthan@Honeywell.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 13.11.23 | [7 empty] | 17.11.23 | 20.11.23 | 20.11.23 | T2 | [7 empty] | 17.11.23 | 04.12.23 | 02.02.24 | mehernani@lntecc.com-11.07.2024-13:05:14
Hubballi | Instrumentation | PLC & SCADA | LE200351-I-WS-PR-PL-5516 | LE200351-I-WS-PR-PL-5516-C | Mitsubushi | Pre-order technically rejected | PR Closed |  | Sudarsan.Gupta | Sudarsan.Gupta@asia.meap.com | 01.01.22 | 30.07.22 | 13.12.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | PLC & SCADA | LE200351-I-WS-PR-PL-5516 | LE200351-I-WS-PR-PL-5516-D | Sai applied technologies pvt limited | Pre-order technically rejected | PR Closed |  | Sweta Parvatiya | mktg@saiapplied.com | 01.01.22 | 30.07.22 | 01.11.23 | [23 empty] | mehernani@lntecc.com-14.05.2024-15:08:03
Hubballi | Instrumentation | UPS | LE200351-I-WS-PR-UP-5518 | LE200351-I-WS-PR-UP-5518-A | Hitachi hirel | Sent to BU Operations | 55 | Technical clearance given. However final clearance shall be given after PLC vendor finalization |  | balakumaran_s@hitachi-hirel.com | 01.01.22 | 29.05.24 | 05.06.24 | 05.06.24 | [8 empty] | 08.06.24 | 08.06.24 | 10.06.24 | T1 | [7 empty] | 08.06.24 | 25.06.24 | 24.08.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | UPS | LE200351-I-WS-PR-UP-5518 | LE200351-I-WS-PR-UP-5518-B | Liveline India | Sent to BU Operations | 55 | Technical clearance given. However final clearance shall be given after PLC vendor finalization |  | sales2@livelineindia.com |  | 29.05.24 | 30.05.24 | 30.05.24 | [8 empty] | 08.06.24 | 08.06.24 | 10.06.24 | T2 | [7 empty] | 10.06.24 | 27.06.24 | 26.08.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | UPS | LE200351-I-WS-PR-UP-5518 | LE200351-I-WS-PR-UP-5518-C | Vertiv | Pre-order pending with EDRC | 30 |  |  | K.Shivakumar@vertiv.com |  | 29.11.23 | 05.07.24 | [20 empty] | 12.07.24 | 29.07.24 | 27.09.24 | mehernani@lntecc.com-08.07.2024-17:24:45
Hubballi | Instrumentation | Water meter | LE200351-I-WS-PR-WT-5523 | LE200351-I-WS-PR-WT-5523-A | vENUS | Approved by Client | PR Closed |  | A S JAYARAMA | gm_venusmeters@yahoo.com |  | 20.01.24 | 20.01.24 | 31.01.24 | [8 empty] | 16.02.24 | 16.02.24 | 18.02.24 | T1 | 15.05.24 | vENUS | 14.03.24 | 15.03.24 | 15.03.24 | 15.03.24 | 13.05.24 | 16.02.24 | 04.03.24 | 03.05.24 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Pressure transmitter | LE200351-I-WS-WT-PR-5202 | LE200351-I-WS-WT-PR-5202-A | Eximp | Sent to BU Operations | PR Closed |  | Jayakrishnan Pallath | Jayakrishnan.Pallath@eximpinc.com | 03.03.22 | 03.03.22 | 14.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 17.03.22 | 17.03.22 | 20.03.22 | T1 | [7 empty] | 17.03.22 | 03.04.22 | 02.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Pressure transmitter | LE200351-I-WS-WT-PR-5202 | LE200351-I-WS-WT-PR-5202-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 03.03.22 | 03.03.22 | 09.03.22 | 18.03.22 | [8 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T2 | [7 empty] | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Pressure transmitter | LE200351-I-WS-WT-PR-5202 | LE200351-I-WS-WT-PR-5202-C | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 03.03.22 | 03.03.22 | 08.03.22 | 16.03.22 | [8 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Pressure transmitter | LE200351-I-WS-WT-PR-5202 | LE200351-I-WS-WT-PR-5202-D | Siemens | Post-order technically cleared | 683 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 03.03.22 | 03.03.22 | 16.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T4 | 30.08.22 | Siemens | 20.09.22 | 21.09.22 | 21.09.22 | 21.09.22 |  | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Pressure Gauge | LE200351-I-WS-WT-PR-5501 | LE200351-I-WS-WT-PR-5501-A | Hguru | Sent to BU Operations | 207 |  | H Guru | info@hgurusouth.com | 01.01.22 | 30.07.22 | 08.11.23 | 10.01.24 | [8 empty] | 10.01.24 | 10.01.24 | 10.01.24 | T1 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Pressure Gauge | LE200351-I-WS-WT-PR-5501 | LE200351-I-WS-WT-PR-5501-B | Scientific devices | Sent to BU Operations | 207 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 30.07.22 | 16.11.23 | 10.01.24 | [8 empty] | 10.01.24 | 10.01.24 | 10.01.24 | T2 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Pressure Gauge | LE200351-I-WS-WT-PR-5501 | LE200351-I-WS-WT-PR-5501-C | GIC | Regret offer | PR Closed |  | Dinabandhu Bhatta | gicchennai@general-gauges.com | 01.01.22 | 30.07.22 | 14.11.23 | 15.11.23 | [22 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | Pressure Gauge | LE200351-I-WS-WT-PR-5501 | LE200351-I-WS-WT-PR-5501-D | Forbes marshall | Sent to BU Operations | 132 |  | R, DILIBAN. | dilibanr@forbesmarshall.com | 01.01.22 | 30.07.22 | 20.11.23 | 10.01.24 | 19.02.24 | [7 empty] | 25.03.24 | 25.03.24 | 25.03.24 | T3 | [7 empty] | 25.03.24 | 11.04.24 | 10.06.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Ultrasonic Flow transmitter | LE200351-I-WS-WT-PR-5507 | LE200351-I-WS-WT-PR-5507-A | SBEM | Pre-order technically rejected | PR Closed |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 30.07.22 | 29.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | Ultrasonic Flow transmitter | LE200351-I-WS-WT-PR-5507 | LE200351-I-WS-WT-PR-5507-B | Siemens | Sent to BU Operations | 132 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 01.01.22 | 30.07.22 | 09.11.23 | 14.12.23 | 25.03.24 | [7 empty] | 25.03.24 | 25.03.24 | 25.03.24 | T1 | [7 empty] | 25.03.24 | 11.04.24 | 10.06.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Rate of flowmeter | LE200351-I-WS-WT-PR-5509 | LE200351-I-WS-WT-PR-5509-A | SBEM | Pre-order technically rejected | PR Closed |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 30.07.22 | 29.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | Rate of flowmeter | LE200351-I-WS-WT-PR-5509 | LE200351-I-WS-WT-PR-5509-B | Siemens | Sent to BU Operations | 234 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 01.01.22 | 30.07.22 | 09.11.23 | 14.12.23 | [8 empty] | 14.12.23 | 14.12.23 | 14.12.23 | T1 | [7 empty] | 25.03.24 | 11.04.24 | 10.06.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Bypass Rotameter | LE200351-I-WS-WT-PR-5510 | LE200351-I-WS-WT-PR-5510-A | Scientific devices | Sent to BU Operations | 211 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 30.07.22 | 16.11.23 | 06.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 06.01.24 | T1 | [7 empty] | 06.01.24 | 23.01.24 | 23.03.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Bypass Rotameter | LE200351-I-WS-WT-PR-5510 | LE200351-I-WS-WT-PR-5510-B | Eureka | Sent to BU Operations | 211 |  | S.Kumar | chennaioffice@eurekaflow.com | 01.01.22 | 30.07.22 | 24.11.23 | 06.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 06.01.24 | T2 | [7 empty] | 06.01.24 | 23.01.24 | 23.03.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Ph Analyser | LE200351-I-WS-WT-PR-5511 | LE200351-I-WS-WT-PR-5511-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Ph Analyser | LE200351-I-WS-WT-PR-5511 | LE200351-I-WS-WT-PR-5511-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | Ph Analyser | LE200351-I-WS-WT-PR-5511 | LE200351-I-WS-WT-PR-5511-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-14.05.2024-15:08:03
Hubballi | Instrumentation | Ph Analyser | LE200351-I-WS-WT-PR-5511 | LE200351-I-WS-WT-PR-5511-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 01.02.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Ph Analyser | LE200351-I-WS-WT-PR-5511 | LE200351-I-WS-WT-PR-5511-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 20.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Ph Analyser | LE200351-I-WS-WT-PR-5511 | LE200351-I-WS-WT-PR-5511-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | Turbidity Analyser | LE200351-I-WS-WT-PR-5512 | LE200351-I-WS-WT-PR-5512-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Turbidity Analyser | LE200351-I-WS-WT-PR-5512 | LE200351-I-WS-WT-PR-5512-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | Turbidity Analyser | LE200351-I-WS-WT-PR-5512 | LE200351-I-WS-WT-PR-5512-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-14.05.2024-15:08:03
Hubballi | Instrumentation | Turbidity Analyser | LE200351-I-WS-WT-PR-5512 | LE200351-I-WS-WT-PR-5512-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 01.02.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Turbidity Analyser | LE200351-I-WS-WT-PR-5512 | LE200351-I-WS-WT-PR-5512-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 20.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | Turbidity Analyser | LE200351-I-WS-WT-PR-5512 | LE200351-I-WS-WT-PR-5512-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | RCL Analyser | LE200351-I-WS-WT-PR-5513 | LE200351-I-WS-WT-PR-5513-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | RCL Analyser | LE200351-I-WS-WT-PR-5513 | LE200351-I-WS-WT-PR-5513-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | RCL Analyser | LE200351-I-WS-WT-PR-5513 | LE200351-I-WS-WT-PR-5513-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-14.05.2024-15:08:03
Hubballi | Instrumentation | RCL Analyser | LE200351-I-WS-WT-PR-5513 | LE200351-I-WS-WT-PR-5513-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 01.02.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | RCL Analyser | LE200351-I-WS-WT-PR-5513 | LE200351-I-WS-WT-PR-5513-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 20.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-17:25:22
Hubballi | Instrumentation | RCL Analyser | LE200351-I-WS-WT-PR-5513 | LE200351-I-WS-WT-PR-5513-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | Battery Operated Datalogger | LE200351-I-WS-WT-PR-5519 | LE200351-I-WS-WT-PR-5519-A | Enviro | Sent to BU Operations | PR Closed |  | Sharad | Water.div@envirosafety.in | 25.08.22 | 29.08.22 | 03.09.22 | 16.09.22 | 19.09.22 | 19.09.22 | [6 empty] | 10.05.23 | 10.05.23 | 16.05.23 | T2 | [7 empty] | 10.05.23 | 27.05.23 | 26.07.23 | mehernani@lntecc.com-01.07.2024-17:16:17
Hubballi | Instrumentation | Battery Operated Datalogger | LE200351-I-WS-WT-PR-5519 | LE200351-I-WS-WT-PR-5519-B | GSV Microtech | Post-order technically cleared | 232 |  | Manikandan A | sales@gsv-microtech.com | 25.08.22 | 29.08.22 | 16.06.23 | 04.08.23 | [8 empty] | 04.08.23 | 04.08.23 | 10.08.23 | T1 | 20.10.23 | GSV Microtech | 02.12.23 | 15.12.23 | 16.12.23 | 16.12.23 |  | 04.08.23 | 21.08.23 | 20.10.23 | mehernani@lntecc.com-01.07.2024-17:16:17
Hubballi | Instrumentation | Instrumentation Cables | LE21M351-I-WS-PR-CA-5517 | LE21M351-I-WS-PR-CA-5517-A | Cords | Sent to BU Operations | 40 |  |  | hp@cordscable.com | 01.01.22 | 29.05.24 | 11.06.24 | 17.06.24 | 22.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 22.06.24 | T1 | [7 empty] | 22.06.24 | 09.07.24 | 07.09.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Instrumentation Cables | LE21M351-I-WS-PR-CA-5517 | LE21M351-I-WS-PR-CA-5517-B | PVESPL | Regret offer | PR Closed |  |  | pvespl@vashiisl.com |  | 29.05.24 | 09.06.24 | 10.06.24 | [22 empty] | mehernani@lntecc.com-08.07.2024-14:29:47
Hubballi | Instrumentation | Instrumentation Cables | LE21M351-I-WS-PR-CA-5517 | LE21M351-I-WS-PR-CA-5517-C | Gemscab | Sent to BU Operations | 40 |  |  | mrawoof@gemscab.com |  | 11.06.24 | 19.06.24 | 19.06.24 | [8 empty] | 25.06.24 | 25.06.24 | 22.06.24 | T2 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Vibration Monitoring System | LE21M351-I-WS-WT-VMS-5521 | LE21M351-I-WS-WT-VMS-5521-A | Preipolar | Pre-order technically rejected | PR Closed |  | Sivanesh G | sivanesh@preipolar.com | 01.01.22 | 16.09.23 | 16.11.23 | [23 empty] | mehernani@lntecc.com-07.06.2024-15:52:14
Hubballi | Instrumentation | Vibration Monitoring System | LE21M351-I-WS-WT-VMS-5521 | LE21M351-I-WS-WT-VMS-5521-B | Centum | Sent to BU Operations | 233 |  | Akhil suresh | akhil@centumcontrols.com | 01.01.22 | 16.09.23 | 29.11.23 | 15.12.23 | [8 empty] | 15.12.23 | 15.12.23 | 15.12.23 | T1 | [7 empty] | 15.12.23 | 01.01.24 | 01.03.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Instrumentation | Vibration Monitoring System | LE21M351-I-WS-WT-VMS-5521 | LE21M351-I-WS-WT-VMS-5521-C | Forbes marshall | Sent to BU Operations | 233 |  | Pallavi Gajbhiye | pgajbhiye@forbesmarshall.com | 01.01.22 | 16.09.23 | 29.11.23 | 15.12.23 | [8 empty] | 15.12.23 | 15.12.23 | 15.12.23 | T2 | [7 empty] | 15.12.23 | 01.01.24 | 01.03.24 | mehernani@lntecc.com-11.07.2024-13:04:28
Hubballi | Electrical | Transformer | LE200351-E-WS-CW-PR-4101 | LE200351-E-WS-CW-PR-4101-A | Voltech | Pre-order comments issued | 272 |  |  |  |  | 21.10.23 | 30.10.23 | 01.11.23 | 06.11.23 | [10 empty] | T1 | [7 empty] | 08.08.24 | 25.08.24 | 24.10.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:26
Hubballi | Electrical | Transformer | LE200351-E-WS-CW-PR-4101 | LE200351-E-WS-CW-PR-4101-B | Shilchar | Regret offer | PR Closed |  |  |  |  | 29.04.24 | 03.05.24 | 08.05.24 | [11 empty] | T1 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Transformer | LE200351-E-WS-CW-PR-4101 | LE200351-E-WS-CW-PR-4101-C | Telawne | Regret offer | PR Closed |  |  |  |  | 21.10.23 | 31.10.23 | 01.11.23 | 06.11.23 | 13.11.23 | [9 empty] | T1 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Transformer | LE200351-E-WS-CW-PR-4101 | LE200351-E-WS-CW-PR-4101-D | Uttam Bharath | Regret offer | PR Closed |  |  |  |  | 21.10.23 | 26.10.23 | 04.11.23 | [11 empty] | T1 | [7 empty] | 08.08.24 | 25.08.24 | 24.10.24 | muthukumar.r@lntecc.com-17.07.2024-13:58:22
Hubballi | Electrical | HT Switchgear | LE200351-E-WS-CW-PR-4103 | LE200351-E-WS-CW-PR-4103-A | Universal | Regret offer | PR Closed |  |  |  |  | 20.04.24 | 28.04.24 | 30.04.24 | [8 empty] | 04.05.24 | 06.05.24 |  | T1 | [7 empty] | 12.07.24 | 29.07.24 | 27.09.24 | muthukumar.r@lntecc.com-10.07.2024-15:29:46
Hubballi | Electrical | HT Switchgear | LE200351-E-WS-CW-PR-4103 | LE200351-E-WS-CW-PR-4103-B | Lotus | Pre-order technically cleared | 39 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | 11.06.24 |  |  |  |  | 04.05.24 | 26.06.24 |  | T1 | [7 empty] | 25.07.24 | 11.08.24 | 10.10.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:26
Hubballi | Electrical | HT Switchgear | LE200351-E-WS-CW-PR-4103 | LE200351-E-WS-CW-PR-4103-C | Sun Shine | Pre-order technically cleared | 48 |  |  |  |  | 23.04.24 | 17.05.24 | 18.05.24 | 10.06.24 | 11.06.24 | [6 empty] | 17.06.24 | 17.06.24 |  | T1 | [7 empty] | 25.07.24 | 11.08.24 | 10.10.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:26
Hubballi | Electrical | HT Switchgear | LE200351-E-WS-CW-PR-4103 | LE200351-E-WS-CW-PR-4103-D | Kontact | Pre-order comments issued | 74 |  |  | estimation@kontact.in |  | 02.03.24 | 18.05.24 | 22.05.24 | [19 empty] | 08.08.24 | 25.08.24 | 24.10.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:26
Hubballi | Electrical | HT Soft Starters | LE200351-E-WS-CW-PR-4104 | LE200351-E-WS-CW-PR-4104-A | Lecon | Regret offer | PR Closed |  |  |  |  | 02.03.24 | 18.03.24 | 20.03.24 | [8 empty] | 23.03.24 | 24.04.24 | 24.04.24 | T2 | [7 empty] | 08.08.24 | 25.08.24 | 24.10.24 | muthukumar.r@lntecc.com-17.07.2024-13:59:45
Hubballi | Electrical | HT Soft Starters | LE200351-E-WS-CW-PR-4104 | LE200351-E-WS-CW-PR-4104-B | Jaya Shree | Post-order technically cleared | 33 |  |  |  |  | 23.02.24 | 27.03.24 | 01.04.24 | 02.04.24 | 03.04.24 | [6 empty] | 07.05.24 | 10.05.24 | 24.04.24 | T2 | 24.04.24 | Jaya Shree | 19.06.24 | 25.06.24 | 02.07.24 | 02.07.24 |  | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-13:59:45
Hubballi | Electrical | HT Capacitors | LE200351-E-WS-CW-PR-4105 | LE200351-E-WS-CW-PR-4105-A | Madhav Capacitors | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 31.03.24 | 10.04.24 | 23.04.24 | 24.04.24 | [6 empty] | 26.04.24 | 27.04.24 | 27.04.24 | T2 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | HT Capacitors | LE200351-E-WS-CW-PR-4105 | LE200351-E-WS-CW-PR-4105-B | Lecon | Post-order technically cleared | 50 |  |  |  |  | 23.02.24 | 27.02.24 | 28.02.24 | 08.03.24 | 20.03.24 | [6 empty] | 22.04.24 | 23.04.24 | 23.04.24 | T2 | 27.05.24 | Lecon | 27.05.24 | 10.06.24 | 17.06.24 | 15.06.24 |  | 16.08.24 | 02.09.24 | 26.07.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT Capacitors | LE200351-E-WS-CW-PR-4105 | LE200351-E-WS-CW-PR-4105-C | Shreem | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 26.02.24 | 19.03.24 | 26.04.24 | 29.04.24 | [6 empty] | 29.04.24 | 02.05.24 | 02.05.24 | T2 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | HT Cable Termination Kits & LT Cable Lugs and Glands | LE200351-E-WS-CW-PR-4106 | LE200351-E-WS-CW-PR-4106-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T1 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | HT Cable Termination Kits & LT Cable Lugs and Glands | LE200351-E-WS-CW-PR-4106 | LE200351-E-WS-CW-PR-4106-B | Govind Electricals | Awaiting pre-offer from vendor | 86 |  |  |  |  | 10.05.24 | [13 empty] | T1 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LT Switchgear and Auxiliary Panels | LE200351-E-WS-CW-PR-4107 | LE200351-E-WS-CW-PR-4107-A | Lotus | Pre-order technically cleared | 46 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | 10.06.24 |  |  |  |  | 10.06.24 | 19.06.24 |  | T2 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LT Switchgear and Auxiliary Panels | LE200351-E-WS-CW-PR-4107 | LE200351-E-WS-CW-PR-4107-B | Sunshine | Pre-order technically cleared | 48 |  |  |  |  | 05.03.24 | 17.05.24 | 18.05.24 | 10.06.24 | 11.06.24 | [6 empty] | 11.06.24 | 17.06.24 |  | T2 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LT Switchgear and Auxiliary Panels | LE200351-E-WS-CW-PR-4107 | LE200351-E-WS-CW-PR-4107-C | SRCS | Pre-order comments issued | 55 |  | 8754013024 | project@ragavendracontrol.com |  | 05.03.24 | 22.05.24 | 10.06.24 | [8 empty] | 10.06.24 |  |  | T2 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT and LT Power and Control Cables | LE200351-E-WS-CW-PR-4108 | LE200351-E-WS-CW-PR-4108-A | Gemscab | Pre-order technically cleared | 83 |  |  |  |  | 02.03.24 | 11.03.24 | 30.04.24 | 04.05.24 | 07.05.24 | [6 empty] | 10.05.24 | 13.05.24 |  | T1 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT and LT Power and Control Cables | LE200351-E-WS-CW-PR-4108 | LE200351-E-WS-CW-PR-4108-B | Axelon | Pre-order technically cleared | 87 |  |  |  |  | 02.03.24 | 02.05.24 | 07.05.24 | 08.05.24 | [7 empty] | 08.05.24 | 09.05.24 |  | T1 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT and LT Power and Control Cables | LE200351-E-WS-CW-PR-4108 | LE200351-E-WS-CW-PR-4108-C | Vishal | Pre-order technically cleared | 87 |  |  |  |  | 30.04.24 | 02.05.24 | 07.05.24 | 08.05.24 | [7 empty] | 08.05.24 | 09.05.24 |  | T1 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT and LT Power and Control Cables | LE200351-E-WS-CW-PR-4108 | LE200351-E-WS-CW-PR-4108-D | Havells | Regret offer | PR Closed |  |  |  |  | 30.04.24 | [13 empty] | T1 | [10 empty] | muthukumar.r@lntecc.com-07.06.2024-17:41:03
Hubballi | Electrical | HT and LT Power and Control Cables | LE200351-E-WS-CW-PR-4108 | LE200351-E-WS-CW-PR-4108-E | KEI | Regret offer | PR Closed |  |  |  |  | 17.05.24 | [13 empty] | T1 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Cable Trays and Supports | LE200351-E-WS-CW-PR-4109 | LE200351-E-WS-CW-PR-4109-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T3 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Cable Trays and Supports | LE200351-E-WS-CW-PR-4109 | LE200351-E-WS-CW-PR-4109-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 |  |  |  |  | 06.06.24 | 06.06.24 |  | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Lighting Fixtures | LE200351-E-WS-CW-PR-4110 | LE200351-E-WS-CW-PR-4110-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T3 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Lighting Fixtures | LE200351-E-WS-CW-PR-4110 | LE200351-E-WS-CW-PR-4110-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 |  |  |  |  | 06.06.24 | 06.06.24 |  | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Earthing and Its Accessories | LE200351-E-WS-CW-PR-4111 | LE200351-E-WS-CW-PR-4111-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T3 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Earthing and Its Accessories | LE200351-E-WS-CW-PR-4111 | LE200351-E-WS-CW-PR-4111-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 |  |  |  |  | 06.06.24 | 06.06.24 |  | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | NGR | LE200351-E-WS-CW-PR-4112 | LE200351-E-WS-CW-PR-4112-A | RSI switchgear | Pre-order comments issued | 54 |  |  |  |  | 17.05.24 | 11.06.24 | 11.06.24 | [11 empty] | T2 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | NGR | LE200351-E-WS-CW-PR-4112 | LE200351-E-WS-CW-PR-4112-B | National Resistors | Pre-order technically cleared | 57 |  |  |  |  | 17.05.24 | 04.06.24 | 08.06.24 | [8 empty] | 08.06.24 | 08.06.24 |  | T2 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Electrical Safety Items | LE200351-E-WS-CW-PR-4113 | LE200351-E-WS-CW-PR-4113-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T3 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Electrical Safety Items | LE200351-E-WS-CW-PR-4113 | LE200351-E-WS-CW-PR-4113-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 |  |  |  |  | 06.06.24 | 06.06.24 |  | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LPBS | LE200351-E-WS-CW-PR-4114 | LE200351-E-WS-CW-PR-4114-A | Lotus | Pre-order technically cleared | 55 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 10.06.24 | 10.06.24 | 10.06.24 | T3 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-13:59:45
Hubballi | Electrical | LPBS | LE200351-E-WS-CW-PR-4114 | LE200351-E-WS-CW-PR-4114-B | Sunshine | Pre-order technically cleared | 54 |  |  |  |  | 05.03.24 | 17.05.24 | 18.05.24 | 10.06.24 | 11.06.24 | [6 empty] | 11.06.24 | 11.06.24 | 11.06.24 | T3 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-13:58:22
Hubballi | Electrical | LPBS | LE200351-E-WS-CW-PR-4114 | LE200351-E-WS-CW-PR-4114-C | SRCS | Pre-order technically cleared | 55 |  |  |  |  | 05.03.24 | 22.05.24 | 10.06.24 | [8 empty] | 10.06.24 | 10.06.24 | 10.06.24 | T3 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-13:58:22
Hubballi | Electrical | LDB | LE200351-E-WS-CW-PR-4116 | LE200351-E-WS-CW-PR-4116-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T2 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | LDB | LE200351-E-WS-CW-PR-4116 | LE200351-E-WS-CW-PR-4116-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T2 |  |  |  |  | 06.06.24 | 06.06.24 |  | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Switchboards, Sockets and other accessories | LE200351-E-WS-CW-PR-4117 | LE200351-E-WS-CW-PR-4117-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T3 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Switchboards, Sockets and other accessories | LE200351-E-WS-CW-PR-4117 | LE200351-E-WS-CW-PR-4117-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 |  |  |  |  | 06.06.24 | 06.06.24 |  | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Lighting Poles and Junction Boxes | LE200351-E-WS-CW-PR-4118 | LE200351-E-WS-CW-PR-4118-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T2 | [10 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Lighting Poles and Junction Boxes | LE200351-E-WS-CW-PR-4118 | LE200351-E-WS-CW-PR-4118-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T2 |  |  |  |  | 06.06.24 | 06.06.24 |  | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Battery, Battery Charger and DCDB | LE200351-E-WS-CW-PR-4119 | LE200351-E-WS-CW-PR-4119-A | Liveline | Pre-order comments issued | 79 |  |  |  |  | 23.02.24 | 01.05.24 | 17.05.24 | [11 empty] | T3 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Battery, Battery Charger and DCDB | LE200351-E-WS-CW-PR-4119 | LE200351-E-WS-CW-PR-4119-B | Voltech | Pre-order technically cleared | 81 |  |  |  |  | 23.02.24 | 24.02.24 | 15.04.24 | 20.04.24 | 25.04.24 | [6 empty] | 07.05.24 | 15.05.24 |  | T3 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Switchyard equipments | LE200351-E-WS-CW-PR-4120 | LE200351-E-WS-CW-PR-4120-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | Switchyard equipments | LE200351-E-WS-CW-PR-4120 | LE200351-E-WS-CW-PR-4120-B | Govind Electricals | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [18 empty] | 06.06.24 | 06.06.24 |  |  |  |  | ananthakrishnan.krishnan@lntecc.com-10.06.2024-09:33:45
Hubballi | Electrical | MV VFD | LE200351-E-WS-CW-PR-4124 | LE200351-E-WS-CW-PR-4124-A | Temic | Pre-order technically cleared | 68 |  | 9952935915 | Sreekarthick.Rangaswamy@tmeic.in |  | 29.04.24 | 03.05.24 | 18.05.24 | 24.05.24 | 28.05.24 | [6 empty] | 28.05.24 | 28.05.24 |  | T2 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | MV VFD | LE200351-E-WS-CW-PR-4124 | LE200351-E-WS-CW-PR-4124-B | Hitachi | Pre-order technically cleared | 23 |  | 9789979389 | j_pandurangan@hitachi-hirel.com |  | 29.04.24 | 30.04.24 | 18.05.24 | 21.05.24 | 28.04.24 | [6 empty] | 12.07.24 | 12.07.24 |  | T2 | [7 empty] | 16.08.24 | 02.09.24 | 01.11.24 | muthukumar.r@lntecc.com-17.07.2024-14:02:35
Hubballi | Electrical | Transformer | LE200357-E-WS-CW-PR-4002 | LE200357-E-WS-CW-PR-4002-A | Voltech | Pre-order comments issued | 272 |  |  |  |  | 21.10.23 | 30.10.23 | 01.11.23 | 06.11.23 | [10 empty] | T1 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Transformer | LE200357-E-WS-CW-PR-4002 | LE200357-E-WS-CW-PR-4002-B | Shilchar | Pre-order comments issued | 88 |  |  |  |  | 29.04.24 | 03.05.24 | 08.05.24 | [19 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Transformer | LE200357-E-WS-CW-PR-4002 | LE200357-E-WS-CW-PR-4002-C | Telawne | Pre-order comments issued | 265 |  |  |  |  | 21.10.23 | 31.10.23 | 01.11.23 | 06.11.23 | 13.11.23 | [17 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Transformer | LE200357-E-WS-CW-PR-4002 | LE200357-E-WS-CW-PR-4002-D | Uttam Bharath | Pre-order comments issued | 274 |  |  |  |  | 21.10.23 | 26.10.23 | 04.11.23 | [11 empty] | T1 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | DG Set | LE200357-E-WS-CW-PR-4003 | LE200357-E-WS-CW-PR-4003-A | Prime power | Regret offer | PR Closed |  |  |  |  | 17.05.24 | 18.05.24 | 21.05.24 | 29.05.24 | 10.06.24 | [6 empty] | 08.06.24 | 10.06.24 | 20.06.24 | t1 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-14:03:44
Hubballi | Electrical | DG Set | LE200357-E-WS-CW-PR-4003 | LE200357-E-WS-CW-PR-4003-B | Power Icad | Regret offer | PR Closed |  |  |  |  | 17.05.24 | 28.05.24 | 10.06.24 | [8 empty] | 08.06.24 | 10.06.24 | 20.06.24 | t1 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-14:03:44
Hubballi | Electrical | HT Switchgear | LE200357-E-WS-CW-PR-4005 | LE200357-E-WS-CW-PR-4005-A | Universal | Regret offer | PR Closed |  |  |  |  | 20.04.24 | 28.04.24 | 30.04.24 | [8 empty] | 04.05.24 | 06.05.24 | [12 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | HT Switchgear | LE200357-E-WS-CW-PR-4005 | LE200357-E-WS-CW-PR-4005-B | Lotus | Sent to BU Operations | 45 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | 20.06.24 | t1 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT Switchgear | LE200357-E-WS-CW-PR-4005 | LE200357-E-WS-CW-PR-4005-C | Sun Shine | Pre-order technically cleared | 73 |  |  |  |  | 23.04.24 | 17.05.24 | 18.05.24 | [8 empty] | 23.05.24 | 23.05.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT Soft Starters | LE200357-E-WS-CW-PR-4006 | LE200357-E-WS-CW-PR-4006-A | Lecon | Regret offer | PR Closed |  |  |  |  | 02.03.24 | 18.03.24 | 20.03.24 | [8 empty] | 23.03.24 | 24.04.24 | 24.05.24 | T1 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-14:03:44
Hubballi | Electrical | HT Soft Starters | LE200357-E-WS-CW-PR-4006 | LE200357-E-WS-CW-PR-4006-B | Jaya Shree | Post-order technically cleared | 33 |  |  |  |  | 23.02.24 | 27.03.24 | 01.04.24 | 02.04.24 | 03.04.24 | [6 empty] | 07.05.24 | 10.05.24 | 24.05.24 | T1 | 24.05.24 | Jaya Shree | 19.06.24 | 25.06.24 | 02.07.24 | 02.07.24 |  | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-14:03:44
Hubballi | Electrical | HT Capacitors | LE200357-E-WS-CW-PR-4007 | LE200357-E-WS-CW-PR-4007-A | Madhav Capacitors | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 31.03.24 | 10.04.24 | 23.04.24 | 24.04.24 | [6 empty] | 26.04.24 | 27.04.24 | 27.04.24 | T2 | [10 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | HT Capacitors | LE200357-E-WS-CW-PR-4007 | LE200357-E-WS-CW-PR-4007-B | Lecon | Post-order comments issued | 61 |  |  |  |  | 23.02.24 | 27.02.24 | 28.02.24 | 08.03.24 | 20.03.24 | [6 empty] | 22.04.24 | 23.04.24 | 23.04.24 | T2 | 27.05.24 | Lecon | 27.05.24 | 04.06.24 |  |  |  | 05.09.24 | 22.09.24 | 26.07.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT Capacitors | LE200357-E-WS-CW-PR-4007 | LE200357-E-WS-CW-PR-4007-C | Shreem | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 26.02.24 | 19.03.24 | 26.04.24 | 29.04.24 | [6 empty] | 29.04.24 | 02.05.24 | 02.05.24 | T2 | [10 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | HT CABLE TERMINATION KITS & LT CABLE LUGS AND GLANDS | LE200357-E-WS-CW-PR-4008 | LE200357-E-WS-CW-PR-4008-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | HT CABLE TERMINATION KITS & LT CABLE LUGS AND GLANDS | LE200357-E-WS-CW-PR-4008 | LE200357-E-WS-CW-PR-4008-B | Govind Electricals | Pre-order technically cleared | 50 |  |  |  |  | 10.05.24 | 15.06.24 | 15.06.24 | [8 empty] | 15.06.24 | 15.06.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LT Switchgear and Auxiliary Panels | LE200357-E-WS-CW-PR-4009 | LE200357-E-WS-CW-PR-4009-A | Lotus | Sent to BU Operations | 45 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | 20.06.24 | t1 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LT Switchgear and Auxiliary Panels | LE200357-E-WS-CW-PR-4009 | LE200357-E-WS-CW-PR-4009-B | Sunshine | Pre-order technically cleared | 57 |  |  |  |  | 05.03.24 | 17.05.24 | 18.05.24 | [8 empty] | 08.06.24 | 08.06.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LT Switchgear and Auxiliary Panels | LE200357-E-WS-CW-PR-4009 | LE200357-E-WS-CW-PR-4009-C | SRCS | Awaiting pre-offer from vendor | 45 |  |  |  |  | 05.03.24 | 20.06.24 | [20 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-A | Gemscab | Pre-order technically cleared | 83 |  |  |  |  | 02.03.24 | 11.03.24 | 30.04.24 | 04.05.24 | 07.05.24 | [6 empty] | 10.05.24 | 13.05.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-B | Axelon | Pre-order technically cleared | 87 |  |  |  |  | 02.03.24 | 02.05.24 | 07.05.24 | 08.05.24 | [7 empty] | 08.05.24 | 09.05.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-C | Vishal | Pre-order technically cleared | 87 |  |  |  |  | 30.04.24 | 02.05.24 | 07.05.24 | 08.05.24 | [7 empty] | 08.05.24 | 09.05.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-D | Havells | Regret offer | PR Closed |  |  |  |  | 30.04.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | HT and LT Power and Control Cables | LE200357-E-WS-CW-PR-4010 | LE200357-E-WS-CW-PR-4010-E | KEI | Pre-order comments issued | 40 |  |  |  |  | 17.05.24 | 20.06.24 | 25.06.24 | [19 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Cable Trays and Supports | LE200357-E-WS-CW-PR-4011 | LE200357-E-WS-CW-PR-4011-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | Cable Trays and Supports | LE200357-E-WS-CW-PR-4011 | LE200357-E-WS-CW-PR-4011-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 31.05.24 | [8 empty] | 06.06.24 | 06.06.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Earthing and Its Accessories | LE200357-E-WS-CW-PR-4013 | LE200357-E-WS-CW-PR-4013-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | Earthing and Its Accessories | LE200357-E-WS-CW-PR-4013 | LE200357-E-WS-CW-PR-4013-B | Govind Electricals | Pre-order technically cleared | 65 |  |  |  |  | 10.05.24 | 27.05.24 | 31.05.24 | [8 empty] | 31.05.24 | 31.05.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | NGR | LE200357-E-WS-CW-PR-4014 | LE200357-E-WS-CW-PR-4014-A | RSI switchgear | Pre-order technically cleared | 48 |  |  |  |  | 17.05.24 | 14.06.24 | 17.06.24 | [8 empty] | 17.06.24 | 17.06.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | NGR | LE200357-E-WS-CW-PR-4014 | LE200357-E-WS-CW-PR-4014-B | National Resistors | Pre-order technically cleared | 57 |  |  |  |  | 17.05.24 | 04.06.24 | 08.06.24 | [8 empty] | 08.06.24 | 08.06.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Electrical Safety Items | LE200357-E-WS-CW-PR-4015 | LE200357-E-WS-CW-PR-4015-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | Electrical Safety Items | LE200357-E-WS-CW-PR-4015 | LE200357-E-WS-CW-PR-4015-B | Govind Electricals | Pre-order technically cleared | 65 |  |  |  |  | 10.05.24 | 27.05.24 | 31.05.24 | [8 empty] | 31.05.24 | 31.05.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LPBS | LE200357-E-WS-CW-PR-4016 | LE200357-E-WS-CW-PR-4016-A | Lotus | Pre-order technically cleared | 92 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LPBS | LE200357-E-WS-CW-PR-4016 | LE200357-E-WS-CW-PR-4016-B | Sunshine | Pre-order technically cleared | 57 |  |  |  |  | 05.03.24 | 17.05.24 | 18.05.24 | [8 empty] | 08.06.24 | 08.06.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LPBS | LE200357-E-WS-CW-PR-4016 | LE200357-E-WS-CW-PR-4016-C | SRCS | Awaiting pre-offer from vendor | 152 |  |  |  |  | 05.03.24 | [21 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Battery, Battery Charger and DCDB | LE200357-E-WS-CW-PR-4020 | LE200357-E-WS-CW-PR-4020-A | Liveline | Pre-order technically cleared | 51 |  |  |  |  | 23.02.24 | 01.05.24 | 04.05.24 | 12.06.24 | 14.06.24 | [6 empty] | 14.06.24 | 14.06.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Battery, Battery Charger and DCDB | LE200357-E-WS-CW-PR-4020 | LE200357-E-WS-CW-PR-4020-B | Voltech | Pre-order technically cleared | 81 |  |  |  |  | 23.02.24 | 24.02.24 | 15.04.24 | 20.04.24 | 25.04.24 | [6 empty] | 07.05.24 | 15.05.24 | [9 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Switchyard equipments | LE200357-E-WS-CW-PR-4021 | LE200357-E-WS-CW-PR-4021-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | Switchyard equipments | LE200357-E-WS-CW-PR-4021 | LE200357-E-WS-CW-PR-4021-B | Govind Electricals | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | Lighting Fixtures | LE200357-E-WS-CW-PR-4212 | LE200357-E-WS-CW-PR-4212-A | Monaj Trading | Awaiting pre-offer from vendor | 86 |  |  |  |  | 10.05.24 | [21 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Lighting Fixtures | LE200357-E-WS-CW-PR-4212 | LE200357-E-WS-CW-PR-4212-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | LDB | LE200357-E-WS-CW-PR-4218 | LE200357-E-WS-CW-PR-4218-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | LDB | LE200357-E-WS-CW-PR-4218 | LE200357-E-WS-CW-PR-4218-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Lighting Poles and Junction Boxes | LE200357-E-WS-CW-PR-4219 | LE200357-E-WS-CW-PR-4219-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | Lighting Poles and Junction Boxes | LE200357-E-WS-CW-PR-4219 | LE200357-E-WS-CW-PR-4219-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 05.09.24 | 22.09.24 | 21.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Hubballi | Electrical | Switchboards, Sockets and other accessories | LE200357-E-WS-CW-PR-4222 | LE200357-E-WS-CW-PR-4222-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [24 empty] | usman.mohideen@lntecc.com-26.06.2024-09:25:51
Hubballi | Electrical | Switchboards, Sockets and other accessories | LE200357-E-WS-CW-PR-4222 | LE200357-E-WS-CW-PR-4222-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 12.09.24 | 29.09.24 | 28.11.24 | muthukumar.r@lntecc.com-17.07.2024-12:40:27
Jalandhar | Process | Scraper mechanism Reactor clarifier. | LE200809-P-WS-WT-PR-2202 | LE200809-P-WS-WT-PR-2202-A | Triveni | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 17.04.21 | 13.02.23 | 15.02.23 | [8 empty] | 15.02.23 | 15.02.23 | 15.02.23 | T1 | 18.08.23 | Triveni | 18.08.23 | 22.08.23 | 21.11.23 | 21.11.23 | 21.11.23 |  |  | 17.10.23 | premkumar.nagarajan@lntecc.com-02.05.2024-16:53:35
Jalandhar | Process | Air Blower | LE200809-P-WS-WT-PR-2203 | LE200809-P-WS-WT-PR-2203-A | Kay Blower | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 20.03.21 | 05.01.23 | 06.01.23 | [8 empty] | 06.01.23 | 06.01.23 | 06.01.23 | T1 | 13.03.23 | Kay Blower | 13.03.23 | 14.03.23 | 14.03.23 | 14.03.23 | 14.03.23 |  |  | 12.05.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Air Compressor | LE200809-P-WS-WT-PR-2204 | LE200809-P-WS-WT-PR-2204-A | Atlascopco | Approved by Client | PR Closed |  |  |  |  | 23.04.21 | 07.10.22 | 17.10.22 | [8 empty] | 17.10.22 | 17.10.22 | 17.10.22 | T1 | 10.01.23 | Atlascopco | 10.01.23 | 17.01.23 | 17.01.23 | 17.01.23 | 17.01.23 |  |  | 11.03.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Agitator | LE200809-P-WS-WT-PR-2205 | LE200809-P-WS-WT-PR-2205-A | FFP | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 23.04.21 | 09.01.23 | 18.02.23 | [8 empty] | 18.02.23 | 18.02.23 | 18.02.23 | T1 | 05.04.23 | FFP | 05.04.23 | 06.04.23 | 06.04.23 | 06.04.23 | 06.04.23 |  |  | 04.06.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | WTP Sluice gates | LE200809-P-WS-WT-PR-2206 | LE200809-P-WS-WT-PR-2206-A | Jash | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 23.04.21 | 09.07.21 | 14.07.21 | [8 empty] | 14.07.21 | 14.07.21 | 14.07.21 | T1 | 03.04.23 | Jash | 24.05.23 | 29.05.23 | 29.05.23 | 29.05.23 | 29.05.23 |  |  | 02.06.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Process | Chlorination system | LE200809-P-WS-WT-PR-2207 | LE200809-P-WS-WT-PR-2207-A | Zion | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 30.04.21 | 13.03.23 | 15.03.23 | [8 empty] | 15.03.23 | 15.03.23 | 15.03.23 | T1 | 10.07.23 | Zion | 18.07.23 | 18.07.23 | 18.07.23 | 18.07.23 | 18.07.23 |  |  | 08.09.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Process | Chlorine Tonners | LE200809-P-WS-WT-PR-2208 | LE200809-P-WS-WT-PR-2208-A | Zion | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 27.03.21 | 13.03.23 | 15.03.23 | [8 empty] | 15.03.23 | 15.03.23 | 15.03.23 | T1 | 10.07.23 | Zion | 18.07.23 | 18.07.23 | 18.07.23 | 18.07.23 | 18.07.23 |  |  | 08.09.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Process | Sludge thickener | LE200809-P-WS-WT-PR-2209 | LE200809-P-WS-WT-PR-2209-A | Triveni | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 17.04.21 | 13.02.23 | 13.02.23 | [8 empty] | 13.02.23 | 13.02.23 | 13.02.23 | T1 | 13.02.23 | Triveni | 28.04.23 | 04.05.23 | 04.05.23 | 04.05.23 | 04.05.23 |  |  | 14.04.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Filter media | LE200809-P-WS-WT-PR-2210 | LE200809-P-WS-WT-PR-2210-A | Dalton | Approved by Client | PR Closed |  |  |  |  | 27.03.21 | 01.03.23 | 06.03.23 | [8 empty] | 06.03.23 | 06.03.23 | 06.03.23 | T1 | 06.03.23 | Dalton | 31.03.23 | 03.04.23 | 03.04.23 | 03.04.23 | 03.04.23 |  |  | 05.05.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Nozzles | LE200809-P-WS-WT-PR-2211 | LE200809-P-WS-WT-PR-2211-A | Guddi Plastron | Approved by Client | PR Closed |  |  |  |  | 20.03.21 | 28.06.21 | 05.07.21 | [8 empty] | 05.07.21 | 05.07.21 | 05.07.21 | T1 | 05.07.21 | Guddi Plastron | 13.09.21 | 20.09.21 | 20.09.21 | 20.09.21 | 20.09.21 |  |  | 03.09.21 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Centrifuge | LE200809-P-WS-WT-PR-2212 | LE200809-P-WS-WT-PR-2212-A | McNally Sayaji | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 20.03.21 | 16.11.23 | 16.11.23 | [8 empty] | 16.11.23 | 16.11.23 | 16.11.23 | T1 | 22.11.23 | McNally Sayaji | 22.11.23 | 23.11.23 | 23.11.23 | 23.11.23 | 23.11.23 |  |  | 21.01.24 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Process | screw pump | LE200809-P-WS-WT-PR-2213 | LE200809-P-WS-WT-PR-2213-A | Circor Tushaco | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 09.04.21 | 14.03.23 | 14.03.23 | [8 empty] | 14.03.23 | 14.03.23 | 14.03.23 | T1 | 14.03.23 | Circor - Tushaco | 10.05.23 | 18.05.23 | 18.05.23 | 18.05.23 | 18.05.23 |  |  | 13.05.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Backwash Reservoir pump | LE200809-P-WS-WT-PR-2214 | LE200809-P-WS-WT-PR-2214-A | Wilo | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 20.03.21 | 15.03.233 | 17.03.23 | [8 empty] | 02.05.23 | 02.05.23 | 02.05.23 | T1 | 08.06.23 | Wilo | 10.07.23 | 11.07.23 | 11.07.23 | 11.07.23 | 11.07.23 |  |  | 07.08.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Process | Submersible pump | LE200809-P-WS-WT-PR-2215 | LE200809-P-WS-WT-PR-2215-A | Aqua | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 30.04.21 | 22.12.22 | 26.12.22 | [8 empty] | 26.12.22 | 26.12.22 | 26.12.22 | T1 | 13.03.23 | Aqua(jasco) | 09.05.23 | 10.05.23 | 10.05.23 | 10.05.23 | 10.05.23 |  |  | 12.05.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Electrical hoist | LE200809-P-WS-WT-PR-2216 | LE200809-P-WS-WT-PR-2216-A | Reva | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 07.05.21 | 03.11.22 | 09.11.22 | [8 empty] | 09.11.22 | 09.11.22 | 09.11.22 | T1 | 09.11.22 | Reva (japs) | 27.03.23 | 21.04.23 | 21.04.23 | 21.04.23 | 21.04.23 |  |  | 08.01.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Crane | LE200809-P-WS-WT-PR-2217 | LE200809-P-WS-WT-PR-2217-A | Reva | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 07.05.21 | 20.07.21 | 02.08.21 | [8 empty] | 02.08.21 | 02.08.21 | 02.08.21 | T1 | 02.08.21 | Reva (japs) | 27.03.23 | 21.04.23 | 21.04.23 | 21.04.23 | 21.04.23 |  |  | 01.10.21 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Manual chain pulley block | LE200809-P-WS-WT-PR-2218 | LE200809-P-WS-WT-PR-2218-A | Reva | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 07.05.21 | 20.07.21 | 02.08.21 | [8 empty] | 02.08.21 | 02.08.21 | 02.08.21 | T1 | 02.08.21 | Reva (japs) | 27.03.23 | 21.04.23 | 21.04.23 | 21.04.23 | 21.04.23 |  |  | 01.10.21 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Dosing pump | LE200809-P-WS-WT-PR-2219 | LE200809-P-WS-WT-PR-2219-A | Post Cleared | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 09.04.21 | 11.10.21 | 19.10.21 | [8 empty] | 19.10.21 | 19.10.21 | 19.10.21 | T1 | 19.10.21 | Post Cleared (positive metering pumps) | 26.04.23 | 28.04.23 | 28.04.23 | 28.04.23 | 28.04.23 |  |  | 18.12.21 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Chemical transfer pump - Liquid alum | LE200809-P-WS-WT-PR-2220 | LE200809-P-WS-WT-PR-2220-A | Sj industries | Approved by Client | PR Closed |  |  |  |  | 20.03.21 | 12.12.23 | 13.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 13.12.23 | T1 | 09.01.24 | Sj industries | 15.04.24 | 20.01.24 | 22.04.24 | 22.04.24 | 22.04.24 |  |  | 09.03.24 | premkumar.nagarajan@lntecc.com-02.05.2024-17:41:20
Jalandhar | Process | DWPE tanks | LE200809-P-WS-WT-PR-2221 | LE200809-P-WS-WT-PR-2221-A | FFP | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 27.03.21 | 23.06.21 | 05.07.21 | [8 empty] | 05.07.21 | 05.07.21 | 05.07.21 | T1 | 05.07.21 | FFP | 09.03.23 | 10.03.23 | 10.03.23 | 10.03.23 | 10.03.23 |  |  | 03.09.21 | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Sampling pump | LE200809-P-WS-WT-PR-2222 | LE200809-P-WS-WT-PR-2222-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 27.03.21 | [24 empty] | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Submersible mixer | LE200809-P-WS-WT-PR-2223 | LE200809-P-WS-WT-PR-2223-A | Sulzer | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 23.04.21 | 17.01.23 | 21.03.23 | [8 empty] | 21.03.23 | 21.03.23 | 21.03.23 | T1 | 21.03.23 | Sulzer | 29.03.23 | 29.03.23 | 29.03.23 | 29.03.23 | 29.03.23 |  |  | 20.05.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Process | Dewatering pump | LE200809-P-WS-WT-PR-2224 | LE200809-P-WS-WT-PR-2224-A | Aqua Pumps | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 23.04.21 | 30.01.23 | 10.02.23 | [8 empty] | 14.03.23 | 14.03.23 | 14.03.23 | T1 | 14.03.23 | Aqua Pumps | 09.05.23 | 10.05.23 | 10.05.23 | 10.05.23 | 10.05.23 |  |  | 13.05.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Process | Dissolving tray | LE200809-P-WS-WT-PR-2225 | LE200809-P-WS-WT-PR-2225-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 27.03.21 | [24 empty] | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Trolley | LE200809-P-WS-WT-PR-2226 | LE200809-P-WS-WT-PR-2226-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 27.03.21 | [24 empty] | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Platm weighing machine | LE200809-P-WS-WT-PR-2227 | LE200809-P-WS-WT-PR-2227-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 27.03.21 | [24 empty] | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Exhaust fan | LE200809-P-WS-WT-PR-2228 | LE200809-P-WS-WT-PR-2228-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 27.03.21 | [24 empty] | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | lab equipment | LE200809-P-WS-WT-PR-2229 | LE200809-P-WS-WT-PR-2229-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 27.03.21 | [24 empty] | premkumar.nagarajan@lntecc.com-02.05.2024-17:02:03
Jalandhar | Process | Flocculator mechanism | LE200809-P-WS-WT-PR-2230 | LE200809-P-WS-WT-PR-2230-A | Triveni | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 30.04.21 | 17.11.22 | 06.12.22 | [8 empty] | 06.12.22 | 06.12.22 | 06.12.22 | T1 | 17.06.23 | Triveni | 29.06.23 | 07.07.23 | 07.07.23 | 07.07.23 | 07.07.23 |  |  | 16.08.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Process | Rechlorination system | LE200809-P-WS-WT-PR-2231 | LE200809-P-WS-WT-PR-2231-A | Zion | Approved by Client | PR Closed | Manufacturing cleared |  |  |  | 20.03.21 | 09.06.23 | 14.06.23 | [8 empty] | 14.06.23 | 14.06.23 | 14.06.23 | T1 | 25.08.23 | Zion | 26.09.23 | 26.09.23 | 26.09.23 | 26.09.23 | 26.09.23 |  |  | 24.10.23 | premkumar.nagarajan@lntecc.com-02.05.2024-17:34:07
Jalandhar | Instrumentation | Instrumentation Control & signal Cables | LE200809-I-WS-PR-CA-5516 | LE200809-I-WS-PR-CA-5516-A | Delton cables | Enquiry yet to float | NA |  | 9500038879 | arvind@deltoncables.com | [23 empty] | 18.09.24 | 05.10.24 | 04.12.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Instrumentation Control & signal Cables | LE200809-I-WS-PR-CA-5516 | LE200809-I-WS-PR-CA-5516-B | Cords cable | Enquiry yet to float | NA |  | 9849487072 | jus@cordscable.com | [23 empty] | 18.09.24 | 05.10.24 | 04.12.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Instrumentation Control & signal Cables | LE200809-I-WS-PR-CA-5516 | LE200809-I-WS-PR-CA-5516-C | Thermo cable | Enquiry yet to float | NA |  | 9840038225 | balaji@thermocables.com | [23 empty] | 18.09.24 | 05.10.24 | 04.12.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Level switch - Conductivity type | LE200809-I-WS-PR-CL-5504 | LE200809-I-WS-PR-CL-5504-A | SBEM | Post-order technically cleared | 90 | PO issue date has issues in the portal | 86818 98929 | rajesh.p@sbem.co.in | 12.04.21 | 01.04.23 | 03.04.23 | 03.04.23 | [8 empty] | 29.04.23 | 29.04.23 | 01.05.23 | T1 | 06.05.24 | SBEM | 08.04.24 | 08.04.24 | 08.04.24 | 08.04.24 |  | 17.07.24 | 03.08.24 | 05.07.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:41
Jalandhar | Instrumentation | Level switch - Conductivity type | LE200809-I-WS-PR-CL-5504 | LE200809-I-WS-PR-CL-5504-B | Pune Techtrol | Sent to BU Operations | PR Closed | PO issue date has issues in the portal | 94455 65336 | sales.techtrol@measurecon.co.in | 12.04.21 | 01.04.23 | 03.04.23 | 03.04.23 | [8 empty] | 19.04.23 | 19.04.23 | 01.05.23 | T2 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Electromagnectic flow meter | LE200809-I-WS-PR-FM-5500 | LE200809-I-WS-PR-FM-5500-A | Siemens | Sent to BU Operations | PR Closed |  | NA | keerthi.guruswamy.ext@siemens.com | 12.04.21 | 08.09.21 | 10.09.21 | 10.09.21 | [8 empty] | 11.09.21 | 11.09.21 | 15.09.21 | T2 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Electromagnectic flow meter | LE200809-I-WS-PR-FM-5500 | LE200809-I-WS-PR-FM-5500-B | Khrone | Approved by Client | PR Closed | PO issue date has issues in the portal | 99897 25626 | dilibanr@forbesmarshall.com | 12.04.21 | 05.03.23 | 30.03.23 | 30.03.23 | [8 empty] | 24.05.23 | 24.05.23 | 28.05.23 | T1 | 06.05.24 | Khrone | 11.06.23 | 11.06.23 | 14.06.23 | 14.06.23 | 15.08.23 | 17.07.24 | 03.08.24 | 05.07.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Electromagnectic flow meter | LE200809-I-WS-PR-FM-5500 | LE200809-I-WS-PR-FM-5500-C | Yokogawa | Regret offer | PR Closed |  | 93430 35952 | p.ramkumar@yokogawa.com | 12.04.21 | 08.06.23 | [21 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Loss of head transmitter | LE200809-I-WS-PR-LH-5510 | LE200809-I-WS-PR-LH-5510-A | E&H | Enquiry yet to float | NA |  | 97909 52907 | hari.narayan@endress.com | 12.04.21 | 01.04.23 | 05.04.23 | 28.04.23 | [8 empty] | 11.07.23 | 06.07.23 | 10.07.23 | T1 | 06.05.24 | E&H |  |  |  | 08.05.23 |  | 30.08.24 | 16.09.24 | 05.07.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Loss of head transmitter | LE200809-I-WS-PR-LH-5510 | LE200809-I-WS-PR-LH-5510-B | Siemens | Enquiry yet to float | NA |  | NA | keerthi.guruswamy.ext@siemens.com | 12.04.21 | 01.04.23 | 28.04.23 | 20.08.21 | [8 empty] | 01.09.21 | 11.07.23 | 15.07.23 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Loss of head transmitter | LE200809-I-WS-PR-LH-5510 | LE200809-I-WS-PR-LH-5510-C | ABB | Enquiry yet to float | NA |  | 99667 75348 | krishna.kishore@in.abb.com | 12.04.21 | 15.08.21 | 20.08.21 | 11.09.23 | [8 empty] | 29.09.23 | 01.09.21 | 05.09.21 | T3 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Float & Board Level gauge | LE200809-I-WS-PR-LI-5505 | LE200809-I-WS-PR-LI-5505-A | SBEM | Post-order technically cleared | 90 | PO issue date has issues in the portal | 86818 98929 | rajesh.p@sbem.co.in | 12.04.21 | 01.04.23 | 11.09.23 | 11.09.23 | [8 empty] | 29.04.23 | 29.04.23 | 01.05.23 | T1 | 06.05.24 | SBEM | 08.04.24 | 08.04.24 | 08.04.24 | 08.04.24 |  | 17.07.24 | 03.08.24 | 05.07.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:41
Jalandhar | Instrumentation | Float & Board Level gauge | LE200809-I-WS-PR-LI-5505 | LE200809-I-WS-PR-LI-5505-B | Pune Techtrol | Sent to BU Operations | PR Closed |  | 94455 65336 | sales.techtrol@measurecon.co.in | 12.04.21 | 01.04.23 | 11.09.23 | 11.09.23 | [8 empty] | 19.04.23 | 19.04.23 | 01.05.23 | T2 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Turbidity Analyzer | LE200809-I-WS-PR-NT-5513 | LE200809-I-WS-PR-NT-5513-A | HACH | Pre-order comments issued | 31 |  | 81236 00656 | mohanraj.elumalai@hach.com |  | 01.09.23 | 11.09.23 | 11.09.23 | 26.06.24 | 04.07.24 | [17 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:41
Jalandhar | Instrumentation | Turbidity Analyzer | LE200809-I-WS-PR-NT-5513 | LE200809-I-WS-PR-NT-5513-B | E&H | Sent to BU Operations | 68 |  | 97909 52907 | hari.narayan@endress.com |  | 01.09.23 | 11.09.23 | 11.09.23 | [8 empty] | 30.09.23 | 28.05.24 | 28.05.24 | T1 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:41
Jalandhar | Instrumentation | Turbidity Analyzer | LE200809-I-WS-PR-NT-5513 | LE200809-I-WS-PR-NT-5513-C | ABB | Enquiry yet to float | NA |  | 99667 75348 | krishna.kishore@in.abb.com |  |  |  | 07.06.23 | [8 empty] | 16.11.23 | [10 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE200809-I-WS-PR-PC-5519 | LE200809-I-WS-PR-PC-5519-A | Schneider | Sent to BU Operations | PR Closed |  | 97009 53031 | rushyendhar.repalli@se.com | 12.04.21 | 15.08.23 | 11.09.23 | 11.09.23 | [8 empty] | 29.09.23 | 29.09.23 | 06.10.23 | T1 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE200809-I-WS-PR-PC-5519 | LE200809-I-WS-PR-PC-5519-B | SIAS | Sent to BU Operations | PR Closed |  | 8012468923 | nandhinik@sias.in | 12.04.21 | 15.08.23 | 11.09.23 | 11.09.23 | [8 empty] | 03.10.23 | 03.10.23 | 04.10.23 | T4 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE200809-I-WS-PR-PC-5519 | LE200809-I-WS-PR-PC-5519-C | SATPL | Post-order technically cleared | 74 | PO issue date has issues in the portal | 7698007206 | meet.makwana@saiapplied.com | 12.04.21 | 15.08.23 | 11.09.23 | 11.09.23 | [8 empty] | 24.10.23 | 24.10.23 | 24.10.23 | T2 | 06.05.24 | SATPL | 09.11.23 | 28.11.23 | 23.04.24 | 22.05.24 |  | 17.07.24 | 03.08.24 | 05.07.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE200809-I-WS-PR-PC-5519 | LE200809-I-WS-PR-PC-5519-D | ICAM | Sent to BU Operations | PR Closed |  | 9838777959 | isales2@icamsystems.com | 12.04.21 | 15.08.23 | 11.09.23 | 11.09.23 | [8 empty] | 04.10.23 | 04.10.23 | 06.10.23 | T3 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE200809-I-WS-PR-PC-5519 | LE200809-I-WS-PR-PC-5519-E | Autosys | Sent to BU Operations | PR Closed |  | NA | mgrengg@autosysindia.in | 12.04.21 | 15.08.23 | 11.09.23 | 11.09.23 | [8 empty] | 30.09.23 | 30.09.23 | 04.10.23 | T5 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE200809-I-WS-PR-PG-5508 | LE200809-I-WS-PR-PG-5508-A | HGuru | Approved by Client | PR Closed | PO issue date has issues in the portal | 8296294809 | info@hgurusouth.com | 12.04.21 | 01.06.23 | 07.06.23 | 07.06.23 | [8 empty] | 16.11.23 | 16.11.23 | 20.11.23 | T1 | 06.05.24 | HGuru | 12.12.23 | 12.12.23 | 14.12.23 | 14.12.23 | 05.01.24 | 17.07.24 | 03.08.24 | 05.07.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | pH Meter | LE200809-I-WS-PR-PH-5512 | LE200809-I-WS-PR-PH-5512-A | HACH | Pre-order comments issued | 31 |  | 81236 00656 | mohanraj.elumalai@hach.com |  | 01.09.23 | 11.09.23 | 11.09.23 | 26.06.24 | 04.07.24 | [17 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | pH Meter | LE200809-I-WS-PR-PH-5512 | LE200809-I-WS-PR-PH-5512-B | E&H | Sent to BU Operations | 68 |  | 97909 52907 | hari.narayan@endress.com |  | 01.09.23 | 11.09.23 | 11.09.23 | [8 empty] | 30.09.23 | 28.05.24 | 28.05.24 | T1 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | pH Meter | LE200809-I-WS-PR-PH-5512 | LE200809-I-WS-PR-PH-5512-C | ABB | Enquiry yet to float | NA |  | 99667 75348 | krishna.kishore@in.abb.com |  |  |  | 28.04.23 | [8 empty] | 11.07.23 | [10 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Pressure Switch | LE200809-I-WS-PR-PS-5501 | LE200809-I-WS-PR-PS-5501 | HGuru | Approved by Client | PR Closed | PO issue date has issues in the portal | 8296294809 | info@hgurusouth.com | 12.04.21 | 01.06.23 | 07.06.23 | 07.06.23 | [8 empty] | 16.11.23 | 16.11.23 | 20.11.23 | T1 | 06.05.24 | HGuru | 12.12.23 | 12.12.23 | 14.12.23 | 14.12.23 | 05.01.24 | 30.08.24 | 16.09.24 | 05.07.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Residual Chlorine analyzer | LE200809-I-WS-PR-RC-5514 | LE200809-I-WS-PR-RC-5514-A | HACH | Pre-order comments issued | 31 |  | 81236 00656 | mohanraj.elumalai@hach.com |  | 01.09.23 | 11.09.23 | 11.09.23 | 26.06.24 | 04.07.24 | [17 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | Residual Chlorine analyzer | LE200809-I-WS-PR-RC-5514 | LE200809-I-WS-PR-RC-5514-B | E&H | Sent to BU Operations | 68 |  | 97909 52907 | hari.narayan@endress.com |  | 01.09.23 | 11.09.23 | 11.09.23 | [8 empty] | 30.09.23 | 28.05.24 | 28.05.24 | T1 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | Residual Chlorine analyzer | LE200809-I-WS-PR-RC-5514 | LE200809-I-WS-PR-RC-5514-C | ABB | Enquiry yet to float | NA |  | 99667 75348 | krishna.kishore@in.abb.com | [23 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Rate for flow transmitter | LE200809-I-WS-PR-RF-5511 | LE200809-I-WS-PR-RF-5511-A | E&H | Approved by Client | PR Closed |  | 97909 52907 | hari.narayan@endress.com | 12.04.21 | 01.04.23 | 05.04.23 | 05.04.23 | [8 empty] | 06.07.23 | 06.07.23 | 10.07.23 | T1 | 06.05.24 | E&H | 16.01.24 | 16.01.24 | 20.01.23 | 20.01.23 | 20.01.23 | 17.07.24 | 03.08.24 | 05.07.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Rate for flow transmitter | LE200809-I-WS-PR-RF-5511 | LE200809-I-WS-PR-RF-5511-B | Siemens | Sent to BU Operations | PR Closed |  | NA | keerthi.guruswamy.ext@siemens.com | 12.04.21 | 01.04.23 | 28.04.23 | 28.04.23 | [8 empty] | 11.07.23 | 11.07.23 | 15.07.23 | T2 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Rate for flow transmitter | LE200809-I-WS-PR-RF-5511 | LE200809-I-WS-PR-RF-5511-C | ABB | Sent to BU Operations | PR Closed |  | 99667 75348 | krishna.kishore@in.abb.com | 12.04.21 | 15.08.21 | 20.08.21 | 20.08.21 | [8 empty] | 11.07.23 | 01.09.21 | 05.09.21 | T3 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Bypass Rotameter | LE200809-I-WS-PR-RM-5509 | LE200809-I-WS-PR-RM-5509 -A | Eureka | Enquiry yet to float | NA |  | 63795 45974 | chennaioffice@eurekaflow.com | [23 empty] | 30.08.24 | 16.09.24 | 15.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Bypass Rotameter | LE200809-I-WS-PR-RM-5509 | LE200809-I-WS-PR-RM-5509 -B | Scientific Devices | Enquiry yet to float | NA |  | 80971 39097 | info@scientificdevices.org | [23 empty] | 30.08.24 | 16.09.24 | 15.11.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Ultrasonic type Open channel flow transmitter | LE200809-I-WS-PR-UF-5503 | LE200809-I-WS-PR-UF-5503-A | E&H | Approved by Client | PR Closed |  | 97909 52907 | hari.narayan@endress.com | 12.04.21 | 01.04.23 | 05.04.23 | 05.04.23 | [8 empty] | 06.07.23 | 06.07.23 | 10.07.23 | T1 | 06.05.24 | E&H | 16.01.24 | 16.01.24 | 20.01.23 | 20.01.23 | 20.01.23 | 17.07.24 | 03.08.24 | 05.07.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Ultrasonic type Open channel flow transmitter | LE200809-I-WS-PR-UF-5503 | LE200809-I-WS-PR-UF-5503-B | Siemens | Sent to BU Operations | PR Closed |  | NA | keerthi.guruswamy.ext@siemens.com | 12.04.21 | 01.04.23 | 28.04.23 | 28.04.23 | [8 empty] | 11.07.23 | 11.07.23 | 15.07.23 | T2 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Ultrasonic type Open channel flow transmitter | LE200809-I-WS-PR-UF-5503 | LE200809-I-WS-PR-UF-5503-C | ABB | Sent to BU Operations | PR Closed |  | 99667 75348 | krishna.kishore@in.abb.com | 12.04.21 | 15.08.21 | 20.08.21 | 20.08.21 | [8 empty] | 01.09.21 | 01.09.21 | 05.09.21 | T3 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Ultrasonic level transmitter | LE200809-I-WS-PR-UF-5506 | LE200809-I-WS-PR-UF-5506-A | E&H | Post-order technically cleared | 90 | PO issue date has issues in the portal | 97909 52907 | hari.narayan@endress.com | 12.04.21 | 01.04.23 | 05.04.23 | 05.04.23 | [8 empty] | 06.07.23 | 06.07.23 | 10.07.23 | T1 | 06.05.24 | E&H | 04.05.23 | 04.05.23 | 08.05.23 | 08.05.23 |  | 17.07.24 | 03.08.24 | 05.07.24 | sooryaprakash.t@lntecc.com-11.07.2024-11:56:42
Jalandhar | Instrumentation | Ultrasonic level transmitter | LE200809-I-WS-PR-UF-5506 | LE200809-I-WS-PR-UF-5506-B | Siemens | Sent to BU Operations | PR Closed |  | NA | keerthi.guruswamy.ext@siemens.com | 12.04.21 | 01.04.23 | 28.04.23 | 28.04.23 | [8 empty] | 11.07.23 | 11.07.23 | 15.07.23 | T2 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | Ultrasonic level transmitter | LE200809-I-WS-PR-UF-5506 | LE200809-I-WS-PR-UF-5506-C | ABB | Regret offer | PR Closed |  | 99667 75348 | krishna.kishore@in.abb.com | 12.04.21 | 15.08.21 | 20.08.21 | 20.08.21 | [8 empty] | 01.09.21 | 01.09.21 | 05.09.21 | T3 | [7 empty] | 17.07.24 | 03.08.24 | 02.10.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | UPS | LE200809-I-WS-PR-UP-5518 | LE200809-I-WS-PR-UP-5518-A | Vertiv | Enquiry yet to float | NA |  | 9841974315 | K.Shivakumar@vertiv.com | [23 empty] | 18.09.24 | 05.10.24 | 04.12.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Instrumentation | UPS | LE200809-I-WS-PR-UP-5518 | LE200809-I-WS-PR-UP-5518-B | Hitachi Hirel | Enquiry yet to float | NA |  | 9789979384 | b_ramasamy@hitachi-hirel.com | [23 empty] | 18.09.24 | 05.10.24 | 04.12.24 | sooryaprakash.t@lntecc.com-10.07.2024-15:37:21
Jalandhar | Electrical | Transformer | LE200809-E-WS-WT-PR-4002 | LE200809-E-WS-WT-PR-4002-A | Crompton Greaves | Sent to BU Operations | PR Closed |  |  |  |  | 02.08.23 | 09.08.23 | 17.08.23 | 22.08.23 | 13.09.23 | 16.09.23 | [5 empty] | 29.09.23 | 30.09.23 | 03.10.23 | T1 | [7 empty] | 30.09.23 | 17.10.23 | 16.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | Transformer | LE200809-E-WS-WT-PR-4002 | LE200809-E-WS-WT-PR-4002-B | Kirloskar | Post-order technically cleared | 268 |  |  |  |  | 02.08.23 | 04.08.23 | 17.08.23 | 23.08.23 | 07.09.23 | 07.10.23 | 13.10.23 |  |  |  |  | 14.10.23 | 16.10.23 | 16.10.23 | T1 | 19.10.23 | Kirloskar | 26.10.23 | 04.11.23 | 06.11.23 | 10.11.23 |  | 16.10.23 | 02.11.23 | 18.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | Transformer | LE200809-E-WS-WT-PR-4002 | LE200809-E-WS-WT-PR-4002-C | Nucon | Sent to BU Operations | PR Closed |  |  |  |  | 02.08.23 | 09.08.23 | 17.08.23 | 22.08.23 | 12.09.23 | 05.09.23 | [5 empty] | 28.09.23 | 29.09.23 | 03.10.23 | T1 | [7 empty] | 29.09.23 | 16.10.23 | 15.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | Transformer | LE200809-E-WS-WT-PR-4002 | LE200809-E-WS-WT-PR-4002-D | Voltamp | Sent to BU Operations | PR Closed |  |  |  |  | 02.08.23 | 04.08.23 | 17.08.23 | 23.08.23 | 06.09.23 | 08.09.23 | [5 empty] | 04.10.23 | 05.10.23 | 16.10.23 | T1 | [7 empty] | 05.10.23 | 22.10.23 | 21.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | HT Switchgear | LE200809-E-WS-WT-PR-4003 | LE200809-E-WS-WT-PR-4003-A | Symatic | Sent to BU Operations | PR Closed |  |  |  |  | 02.08.23 | 07.08.23 | 17.08.23 | 12.10.23 | [7 empty] | 12.10.23 | 14.10.23 | 16.10.23 | T2 | [7 empty] | 14.10.23 | 31.10.23 | 30.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | HT Switchgear | LE200809-E-WS-WT-PR-4003 | LE200809-E-WS-WT-PR-4003-B | UPE | Post-order technically cleared | 268 |  |  |  |  | 02.08.23 | 11.10.23 | 12.10.23 | [8 empty] | 13.10.23 | 14.10.23 | 16.10.23 | T2 | 19.10.23 | UPE | 21.10.23 | 04.11.23 | 06.11.23 | 10.11.23 |  | 14.10.23 | 31.10.23 | 18.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | HT Switchgear | LE200809-E-WS-WT-PR-4003 | LE200809-E-WS-WT-PR-4003-C | CG | Sent to BU Operations | PR Closed |  |  |  |  | 02.08.23 | 05.10.23 | 09.10.23 | 11.10.23 | [7 empty] | 17.10.23 | 18.10.23 | 18.10.23 | T2 | [7 empty] | 18.10.23 | 04.11.23 | 03.01.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | Switchyard Components | LE200809-E-WS-WT-PR-4004 | LE200809-E-WS-WT-PR-4004-A | Local Vendor | Sent to BU Operations | 183 | The Vendor name is finalized in site only. So, it is entered as Local vendor. |  |  |  | 04.12.23 | 06.12.23 | 11.12.23 | [8 empty] | 19.01.24 | 22.01.24 | 03.02.24 | T3 | [7 empty] | 22.01.24 | 08.02.24 | 08.04.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | LT Switchgear and Auxiliary Panels | LE200809-E-WS-WT-PR-4005 | LE200809-E-WS-WT-PR-4005-A | SRCS | Post-order technically cleared | 233 |  |  |  |  | 12.09.23 | 13.09.23 | 11.10.23 | 07.11.23 | 08.11.23 | [6 empty] | 14.11.23 | 13.11.23 | 27.11.23 | T2 | 08.12.23 | SRCS | 09.12.23 | 12.12.23 | 13.12.23 | 15.12.23 |  | 13.11.23 | 30.11.23 | 29.01.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | LT Switchgear and Auxiliary Panels | LE200809-E-WS-WT-PR-4005 | LE200809-E-WS-WT-PR-4005-B | Voltech | Post-order technically cleared | 233 |  |  |  |  | 12.09.23 | 20.09.23 | 11.10.23 | 15.11.23 | 18.11.23 | [6 empty] | 23.11.23 | 24.11.23 | 27.11.23 | T2 | 08.12.23 | Voltech | 09.12.23 | 11.12.23 | 12.12.23 | 15.12.23 |  | 24.11.23 | 11.12.23 | 06.02.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | LT Switchgear and Auxiliary Panels | LE200809-E-WS-WT-PR-4005 | LE200809-E-WS-WT-PR-4005-C | RST | Sent to BU Operations | PR Closed |  |  |  |  | 12.09.23 | 19.09.23 | 11.10.23 | [8 empty] | 16.11.23 | 17.11.23 | 27.11.23 | T2 | [7 empty] | 17.11.23 | 04.12.23 | 02.02.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | LPBS | LE200809-E-WS-WT-PR-4006 | LE200809-E-WS-WT-PR-4006-A | SRCS | Approved by Client | PR Closed |  |  |  |  | 12.09.23 | 13.09.23 | 11.10.23 | 07.11.23 | 08.11.23 | [6 empty] | 14.11.23 | 13.11.23 | 27.11.23 | T2 | 08.12.23 | SRCS | 09.12.23 | 12.12.23 | 13.12.23 | 15.12.23 | 27.12.23 | 13.11.23 | 30.11.23 | 29.01.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | LPBS | LE200809-E-WS-WT-PR-4006 | LE200809-E-WS-WT-PR-4006-B | Voltech | Approved by Client | PR Closed |  |  |  |  | 12.09.23 | 20.09.23 | 11.10.23 | 15.11.23 | 18.11.23 | [6 empty] | 23.11.23 | 24.11.23 | 27.11.23 | T2 | 08.12.23 | Voltech | 09.12.23 | 11.12.23 | 12.12.23 | 15.12.23 | 27.12.23 | 24.11.23 | 11.12.23 | 06.02.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | LPBS | LE200809-E-WS-WT-PR-4006 | LE200809-E-WS-WT-PR-4006-C | RST | Sent to BU Operations | PR Closed |  |  |  |  | 12.09.23 | 19.09.23 | 11.10.23 | [8 empty] | 16.11.23 | 17.11.23 | 27.11.23 | T2 | [7 empty] | 17.11.23 | 04.12.23 | 02.02.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | Busduct | LE200809-E-WS-WT-PR-4007 | LE200809-E-WS-WT-PR-4007-A | Star Drive | Post-order technically cleared | 110 |  | Suji | suji@stardrive.in |  | 11.12.23 | 18.12.23 | 21.12.23 | [8 empty] | 21.12.23 | 21.12.23 | 21.12.23 | T1 | 21.12.23 | Star Drive | 16.04.24 | 16.04.24 | 16.04.24 | 16.04.24 |  | 21.12.23 | 07.01.24 | 19.02.24 | rajesh.r1@lntecc.com-01.07.2024-18:18:12
Jalandhar | Electrical | DG Set | LE200809-E-WS-WT-PR-4008 | LE200809-E-WS-WT-PR-4008-A | Goel Power | Pre-order technically cleared | 223 |  |  |  |  | 22.09.23 | 03.10.23 | 18.10.23 | 21.11.23 | 22.11.23 | 19.12.23 | [5 empty] | 22.12.23 | 25.12.23 | [9 empty] | 25.12.23 | 11.01.24 | 11.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | DG Set | LE200809-E-WS-WT-PR-4008 | LE200809-E-WS-WT-PR-4008-B | IEC Genset | Pre-order technically cleared | 223 |  |  |  |  | 22.09.23 | 03.10.23 | 18.10.23 | 27.10.23 | 22.11.23 | 20.12.23 | [5 empty] | 25.12.23 | 25.12.23 | [9 empty] | 25.12.23 | 11.01.24 | 11.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | DG Set | LE200809-E-WS-WT-PR-4008 | LE200809-E-WS-WT-PR-4008-C | Perfect Genset | Regret offer | PR Closed |  |  |  |  | 22.09.23 | 06.10.23 | 18.10.23 | [22 empty] | ananthakrishnan.krishnan@lntecc.com-03.06.2024-11:54:29
Jalandhar | Electrical | DG Set | LE200809-E-WS-WT-PR-4008 | LE200809-E-WS-WT-PR-4008-D | Sudhir power | Pre-order technically cleared | 223 |  |  |  |  | 22.09.23 | 03.10.23 | 30.10.23 | 20.11.23 | 22.11.23 | 21.12.23 | [5 empty] | 23.12.23 | 25.12.23 | [9 empty] | 25.12.23 | 11.01.24 | 11.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | HT & LT Power and Control Cables | LE200809-E-WS-WT-PR-4009 | LE200809-E-WS-WT-PR-4009-A | Cords Cable | Post-order technically cleared | 174 | For LT cables, this vendor is finalized. |  |  |  | 09.12.23 | 14.12.23 | 18.12.23 | [8 empty] | 22.12.23 | 25.12.23 | 30.12.23 | T3 | 03.01.24 | Cords Cable | 08.01.24 | 09.01.24 | 19.01.24 | 12.02.24 |  | 25.12.23 | 11.01.24 | 03.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | HT & LT Power and Control Cables | LE200809-E-WS-WT-PR-4009 | LE200809-E-WS-WT-PR-4009-B | Havells | Sent to BU Operations | PR Closed |  |  |  |  | 09.12.23 | 26.12.23 | 27.12.23 | [8 empty] | 28.12.23 | 28.12.23 | 30.12.23 | T3 | [7 empty] | 28.12.23 | 14.01.24 | 14.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | HT & LT Power and Control Cables | LE200809-E-WS-WT-PR-4009 | LE200809-E-WS-WT-PR-4009-C | KEI | Post-order technically cleared | 173 | For HT cables, this vendor is finalized. |  |  |  | 09.12.23 | 14.12.23 | 15.12.23 | [8 empty] | 29.12.23 | 30.12.23 | 30.12.23 | T3 | 04.01.24 | KEI | 09.01.24 | 19.01.24 | 29.01.24 | 13.02.24 |  | 30.12.23 | 16.01.24 | 04.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:38
Jalandhar | Electrical | HT & LT Power and Control Cables | LE200809-E-WS-WT-PR-4009 | LE200809-E-WS-WT-PR-4009-D | Polycab | Sent to BU Operations | PR Closed |  |  |  |  | 09.12.23 | 12.12.23 | 18.12.23 | [8 empty] | 27.12.23 | 28.12.23 | 30.12.23 | T3 | [7 empty] | 28.12.23 | 14.01.24 | 14.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:39
Jalandhar | Electrical | Cable Trays and its supports | LE200809-E-WS-WT-PR-4010 | LE200809-E-WS-WT-PR-4010-A | Local Vendor | Sent to BU Operations | 183 | The Vendor name is finalized in site only. So, it is entered as Local vendor. |  |  |  | 04.12.23 | 06.12.23 | 11.12.23 | [8 empty] | 19.01.24 | 22.01.24 | 03.02.24 | T3 | [7 empty] | 22.01.24 | 08.02.24 | 08.04.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:39
Jalandhar | Electrical | Cable Termination Kit | LE200809-E-WS-WT-PR-4011 | LE200809-E-WS-WT-PR-4011-A | Local Vendor | Sent to BU Operations | 183 | The Vendor name is finalized in site only. So, it is entered as Local vendor. |  |  |  | 04.12.23 | 06.12.23 | 11.12.23 | [8 empty] | 19.01.24 | 22.01.24 | 03.02.24 | T3 | [7 empty] | 22.01.24 | 08.02.24 | 08.04.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:39
Jalandhar | Electrical | Earthing and Lightning System | LE200809-E-WS-WT-PR-4013 | LE200809-E-WS-WT-PR-4013-A | Local Vendor | Sent to BU Operations | 183 | The Vendor name is finalized in site only. So, it is entered as Local vendor. |  |  |  | 04.12.23 | 06.12.23 | 11.12.23 | [8 empty] | 19.01.24 | 22.01.24 | 03.02.24 | T3 | [7 empty] | 22.01.24 | 08.02.24 | 08.04.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:39
Jalandhar | Electrical | Lighting System | LE200809-E-WS-WT-PR-4012 | LE200809-E-WS-WT-PR-4014-A | Govind Electricals | Sent to BU Operations | 184 |  |  |  |  | 07.12.23 | 11.12.23 | 15.12.23 | 02.01.24 | 04.01.24 | [6 empty] | 15.01.24 | 19.01.24 | 02.02.24 | T3 | [7 empty] | 19.01.24 | 05.02.24 | 05.04.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:39
Jalandhar | Electrical | Electrical Safety Accessories and equipments | LE200809-E-WS-WT-PR-4015 | LE200809-E-WS-WT-PR-4015-A | Local Vendor | Sent to BU Operations | 183 | The Vendor name is finalized in site only. So, it is entered as Local vendor. |  |  |  | 04.12.23 | 06.12.23 | 11.12.23 | [8 empty] | 19.01.24 | 22.01.24 | 03.02.24 | T3 | [7 empty] | 22.01.24 | 08.02.24 | 08.04.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-16:31:39
Jharsuguda | Process | Clariflocculator Mechanism | LE190742-P-001 | LE190742-P-001-A | Sritech | Post-order technically cleared | 159 |  |  |  | 26.09.23 | 26.09.23 | 26.09.23 | 06.10.23 | [8 empty] | 06.10.23 | 07.10.23 | 13.11.23 | T1 | 07.12.23 | Sritech | 08.12.23 | 20.02.24 | 02.03.24 | 27.02.24 |  |  |  | 05.02.24 | PVVKSG@lntecc.com-23.07.2024-11:35:52
Jharsuguda | Process | Air Blower | LE190742-P-002 | LE190742-P-002-A | ACME | Post-order pending with EDRC | 12 |  |  |  | 25.12.23 | 25.12.23 | 17.01.24 | 08.02.24 | 21.02.24 | 26.02.24 | 11.03.24 | 16.03.24 |  |  |  |  | 03.04.24 | 22.03.24 | 03.04.24 | T2 | 24.06.24 | ACME | 12.07.24 | 17.07.24 |  | 23.07.24 |  |  |  | 23.08.24 | PVVKSG@lntecc.com-23.07.2024-11:35:52
Jharsuguda | Process | Air Blower | LE190742-P-002 | LE190742-P-002-B | KAY | Sent to BU Operations | PR Closed |  | Biplab Ghoshal, Engineer - Sales & service, Ph. no. 9832474430 | kolkata@kayblowers.com | 25.12.23 | 25.12.23 | 17.01.24 | 08.02.24 | 08.03.24 | 16.03.24 | 29.03.24 | 23.04.24 | 16.05.24 | 23.05.24 |  |  | 29.05.24 | 27.05.24 | 29.05.24 | T1 | [10 empty] | PVVKSG@lntecc.com-17.07.2024-15:02:29
Jharsuguda | Process | Agitator | LE190742-P-003 | LE190742-P-003-A | Milton Roy | Regret offer | PR Closed | Items already procured at site |  |  | 19.05.23 | 19.05.23 | 15.06.23 | 22.06.23 | [22 empty] | PVVKSG@lntecc.com-16.05.2024-15:41:48
Jharsuguda | Process | Agitator | LE190742-P-003 | LE190742-P-003-B | JP Sons | Regret offer | PR Closed | Items already procured at site |  |  | 19.05.23 | 19.05.23 | 26.02.24 | [23 empty] | PVVKSG@lntecc.com-16.05.2024-15:41:48
Jharsuguda | Process | Agitator | LE190742-P-003 | LE190742-P-003-C | Ceecons | Regret offer | PR Closed | Items already procured at site |  |  | 19.05.23 | 19.05.23 | 15.06.23 | 21.06.23 | [22 empty] | PVVKSG@lntecc.com-16.05.2024-15:41:48
Jharsuguda | Process | Agitator | LE190742-P-003 | LE190742-P-003-D | Shivpad | Sent to BU Operations | 23 |  | 9003243278 | ragavendar@shivpad.com |  | 15.05.24 | 27.05.24 | 27.06.24 | [8 empty] | 12.07.24 | 03.07.24 | 12.07.24 | T1 | [7 empty] | 12.07.24 | 29.07.24 | 27.09.24 | PVVKSG@lntecc.com-23.07.2024-11:35:52
Jharsuguda | Process | Chlorination system | LE190742-P-004 | LE190742-P-004-A | Toshcon | Post-order technically cleared | 68 |  | Prem Prakash, DGM - Sales. Phone: +91-145-2971131/2/3, 9314397727 | metering2@toshcon.com | 28.09.22 | 28.09.22 | 23.08.23 | 24.08.23 | [8 empty] | 24.10.23 | 21.11.23 | 21.11.23 | T1 | 22.11.23 | Toshcon | 24.11.23 | 05.02.24 | 31.05.24 | 28.05.24 |  |  |  | 21.01.24 | PVVKSG@lntecc.com-23.07.2024-11:35:52
Jharsuguda | Process | Backwash pump | LE190742-P-005 | LE190742-P-005-A | Wilo | Sent to BU Operations | PR Closed |  |  |  | 22.05.23 | 22.05.23 | 05.10.23 | 11.10.23 | [8 empty] | 18.10.23 | 20.10.23 | 03.11.23 | T1 | [6 empty] | 19.11.23 |  |  |  | PVVKSG@lntecc.com-12.06.2024-10:36:48
Jharsuguda | Process | Backwash pump | LE190742-P-005 | LE190742-P-005-B | MBH | Pre-order technically rejected | PR Closed |  |  |  | 22.05.23 | 22.05.23 | 29.09.23 | 06.10.23 | [8 empty] | 11.10.23 | 12.10.23 | [12 empty] | karthiga@lntecc.com-14.05.2024-18:03:55
Jharsuguda | Process | Backwash pump | LE190742-P-005 | LE190742-P-005-C | KBL | Regret offer | PR Closed | Not considered for finalization as Vendor not responding |  |  | 22.05.23 | 22.05.23 | 15.06.23 | 17.06.23 | [22 empty] | PVVKSG@lntecc.com-16.05.2024-15:41:49
Jharsuguda | Process | Backwash pump | LE190742-P-005 | LE190742-P-005-D | Flow More | Post-order pending with EDRC | 12 |  | KANNAN. M Sr. MANAGER - MARKETING TEL NO 044 42857673: MOBILE NO :9382869518/9444210348 EMAIL : mkannan@flowmoregroup.co.in | MADMKT@FLOWMOREGROUP.COM, mkannan@flowmoregroup.co.in, | 22.05.23 | 22.05.23 | 23.09.23 | 27.09.23 | [8 empty] | 27.09.23 | 28.09.23 | 17.10.23 | T2 | 24.05.24 | Flow More | 24.06.24 | 18.07.24 |  | 23.07.24 |  |  |  | 23.07.24 | PVVKSG@lntecc.com-23.07.2024-11:40:53
Jharsuguda | Process | Submersible pump | LE190742-P-006 | LE190742-P-006-A | AQUA | Post-order comments issued | 17 |  | S.T.Sambandam -8144003131 | chennai@aquapumps.com | 29.02.24 | 29.02.24 | 11.03.24 | 26.03.24 | 04.04.24 | 26.04.24 | 16.05.24 | 23.05.24 | 03.06.24 |  |  |  | 05.06.24 | 03.06.24 | 05.06.24 | T3 | 21.06.24 | AQUA | 12.07.24 | 18.07.24 | [5 empty] | 20.08.24 | PVVKSG@lntecc.com-23.07.2024-11:35:53
Jharsuguda | Process | Submersible pump | LE190742-P-006 | LE190742-P-006-B | MBH | Sent to BU Operations | PR Closed |  | Naresh B Koul - 99200 13772 | northindustrial@mbhpumps.com |  | 20.03.24 | 27.03.24 | 09.04.24 | 15.04.24 | 26.04.24 | 30.04.24 | 14.05.24 | 23.05.24 | 23.05.24 | 24.05.24 |  | 24.05.24 | 24.05.24 | 05.06.24 | T1 | [10 empty] | PVVKSG@lntecc.com-25.06.2024-17:44:25
Jharsuguda | Process | Submersible pump | LE190742-P-006 | LE190742-P-006-C | Jasco | Sent to BU Operations | PR Closed |  | Arvish Modi -7069099037 | hyd@jascopump.com |  | 20.03.24 | 28.03.24 | 09.04.24 | 15.04.24 | 26.04.24 | 06.05.24 | 15.05.24 | 18.05.24 | 23.05.24 |  |  | 23.05.24 | 23.05.24 | 05.06.24 | T2 | [10 empty] | PVVKSG@lntecc.com-25.06.2024-17:44:25
Jharsuguda | Process | Electrical hoist | LE190742-P-007 | LE190742-P-007-A | Brady | Approved by Client | PR Closed |  |  |  | 29.02.20 | 29.02.20 | 17.06.20 | 21.07.20 | [8 empty] | 27.10.20 | 27.10.20 | 12.03.21 | T1 | 17.03.21 | Brady | 26.04.21 | 06.07.21 | 20.08.21 | 20.08.21 | 20.08.21 |  |  | 16.05.21 | PVVKSG@lntecc.com-16.05.2024-15:41:49
Jharsuguda | Process | Manual chain pulley block | LE190742-P-008 | LE190742-P-008-A | Brady | Approved by Client | PR Closed |  |  |  | 25.02.20 | 25.02.20 | 17.06.20 | 21.07.20 | [8 empty] | 27.10.20 | 27.10.20 | 19.12.20 | T1 | 08.01.21 | Brady | 26.04.21 | 06.07.21 | 20.08.21 | 20.08.21 | 20.08.21 |  |  | 09.03.21 | PVVKSG@lntecc.com-16.05.2024-15:41:49
Jharsuguda | Process | Dosing pump | LE190742-P-009 | LE190742-P-009-A | SR Metering | Awaiting post-offer from vendor | 13 |  |  |  |  | 29.02.24 | 01.03.24 | 08.03.24 | 13.03.24 | 21.03.24 | 22.03.24 | 04.04.24 | 04.04.24 | 24.04.24 |  |  | 24.04.24 | 04.04.24 | 01.06.24 | T1 | 22.07.24 | SR Metering | [8 empty] | PVVKSG@lntecc.com-23.07.2024-11:21:57
Jharsuguda | Process | Dosing pump | LE190742-P-009 | LE190742-P-009-B | Verito | Sent to BU Operations | PR Closed |  | Kajol Lalwani - 7600552286 | pump.offers@veritoengineering.com |  | 22.03.24 | 22.03.24 | 04.04.24 | 10.04.24 | 24.04.24 | 06.05.24 | 14.05.24 |  |  |  |  | 23.05.24 | 16.05.24 | 01.06.24 | T2 | [10 empty] | PVVKSG@lntecc.com-22.07.2024-14:45:42
Jharsuguda | Process | Dosing pump | LE190742-P-009 | LE190742-P-009-C | Positive Metering | Sent to BU Operations | PR Closed |  | Swati Rane – Asst. Manager-Sales & Marketing. Commercial - +91 9940084899 Technical - +91 9552590842 (Sr. Manager Proposal & Engineering) Landline : 91 253 6613216 | ofrp@positivemetering.com |  | 22.03.24 | 13.04.24 | 24.04.24 | 02.05.24 | 24.05.24 | 29.05.24 | 29.05.24 | 30.05.24 |  |  |  | 01.06.24 | 30.05.24 | 01.06.24 | T3 | [10 empty] | PVVKSG@lntecc.com-22.07.2024-14:45:42
Jharsuguda | Process | Sampling pump | LE190742-P-010 | LE190742-P-010-A | S J Industries | Awaiting post-offer from vendor | 12 |  |  |  | 29.02.24 | 29.02.24 | 01.03.24 | 08.03.24 | 09.03.24 | 16.03.24 | 16.03.24 | [5 empty] | 16.03.24 | 16.03.24 | 16.03.24 | T1 | 23.07.24 | S J Industries | [8 empty] | PVVKSG@lntecc.com-23.07.2024-11:35:53
Jharsuguda | Process | Submersible mixer | LE190742-P-011 | LE190742-P-011-A | FFP | Post-order technically cleared | 48 |  | Bhauso | fibrein@gmail.com | 09.11.23 | 09.11.23 | 16.11.23 | 21.11.23 | [8 empty] | 11.11.23 | 16.11.23 | 06.12.23 | T1 | 08.05.24 | FFP | 17.05.24 | 23.05.24 | 25.06.24 | 17.06.24 |  |  |  | 07.07.24 | PVVKSG@lntecc.com-23.07.2024-11:35:53
Jharsuguda | Process | Dewatering pump | LE190742-P-012 | LE190742-P-012-A | MBH | Sent to BU Operations | PR Closed |  | Naresh B Koul - 99200 13772 | northindustrial@mbhpumps.com | 29.02.24 | 20.03.24 | 27.03.24 | 09.04.24 | 15.04.24 | 26.04.24 | 02.05.24 | 14.05.24 | 23.05.24 | 23.05.24 | 24.05.24 |  | 24.05.24 | 24.05.24 | 05.06.24 | T1 | [10 empty] | PVVKSG@lntecc.com-25.06.2024-17:44:25
Jharsuguda | Process | Dewatering pump | LE190742-P-012 | LE190742-P-012-B | AQUA | Post-order comments issued | 17 |  | S.T.Sambandam-8144003131 | chennai@aquapumps.com |  | 29.02.24 | 11.03.24 | 26.03.24 | 04.04.24 | 26.04.24 | 16.05.24 | 23.05.24 | 03.06.24 |  |  |  | 05.06.24 | 03.06.24 | 05.06.24 | T3 | 21.06.24 | AQUA | 12.07.24 | 18.07.24 | [5 empty] | 20.08.24 | PVVKSG@lntecc.com-23.07.2024-11:35:53
Jharsuguda | Process | Dewatering pump | LE190742-P-012 | LE190742-P-012-C | Jasco | Sent to BU Operations | PR Closed |  | Arvish Modi -7069099037 | hyd@jascopump.com |  | 20.03.24 | 28.03.24 | 09.04.24 | 15.04.24 | 26.04.24 | 06.05.24 | 15.05.24 | 18.05.24 | 23.05.24 |  |  | 23.05.24 | 23.05.24 | 05.06.24 | T2 | [10 empty] | PVVKSG@lntecc.com-25.06.2024-17:44:25
Jharsuguda | Process | WTP Sluice gates | LE190742-P-013 | LE190742-P-013-A | Oriental | Sent to BU Operations | PR Closed |  |  |  | 20.03.23 | 20.03.23 | 19.05.23 | 20.05.23 | [8 empty] | 23.05.23 | 25.05.23 | 23.06.23 | T1 | [10 empty] | PVVKSG@lntecc.com-16.05.2024-15:41:49
Jharsuguda | Process | WTP Sluice gates | LE190742-P-013 | LE190742-P-013-B | Fluid Control Equipments | Approved by Client | PR Closed |  |  |  | 20.03.23 | 20.03.23 | 01.06.23 | 01.06.23 | [8 empty] | 02.06.23 | 02.06.23 | 06.10.23 | T2 | 22.11.23 | Fluid Control Equipments | 30.11.23 | 21.12.23 | 06.01.24 | 06.01.24 | 02.03.24 |  |  | 21.01.24 | PVVKSG@lntecc.com-16.05.2024-15:41:49
Jharsuguda | Process | Sludge Thickener | LE190742-P-014 | LE190742-P-014-A | Sritech | Post-order technically cleared | 172 |  |  |  | 26.09.23 | 26.09.23 | 30.09.23 | 07.10.23 | [8 empty] | 09.10.23 | 09.10.23 | 31.10.23 | T1 | 26.11.23 | Sritech | 10.02.24 | 13.02.24 | 15.02.24 | 14.02.24 |  |  |  | 25.01.24 | PVVKSG@lntecc.com-23.07.2024-11:35:53
Jharsuguda | Process | Filter media | LE190742-P-015 | LE190742-P-015-A | Maa Kaleswari | Regret offer | PR Closed | Site Procurement. Cluster SCM released PO. |  |  | 30.09.22 | 30.09.22 | [24 empty] | PVVKSG@lntecc.com-21.05.2024-10:30:35
Jharsuguda | Process | DWPE tanks | LE190742-P-016 | LE190742-P-016-A | FFPO | Awaiting post-offer from vendor | 12 |  |  |  | 02.12.23 | 02.12.23 | 08.12.23 | 27.12.23 | 20.02.24 | 12.03.24 | 13.03.24 | 18.03.24 |  |  |  |  | 04.04.24 | 24.03.24 | 04.04.24 | T1 | 23.07.24 | FFPO | [8 empty] | PVVKSG@lntecc.com-23.07.2024-11:35:53
Jharsuguda | Process | Centrifuge | LE190742-P-017 | LE190742-P-017-A | Hiller | Awaiting post-offer from vendor | 16 |  |  |  | 22.05.23 | 22.05.23 | 16.06.23 | 16.06.23 | [8 empty] | 11.07.23 | 28.09.23 | 16.10.23 | T1 | 19.07.24 | Hiller | [8 empty] | PVVKSG@lntecc.com-23.07.2024-11:21:57
Jharsuguda | Process | Centrifuge | LE190742-P-017 | LE190742-P-017-B | SKS Decanter | Regret offer | PR Closed |  |  |  | 22.05.23 | 22.05.23 | 29.09.23 | 07.10.23 | 02.07.24 | [7 empty] | 09.10.23 | 09.10.23 | 19.10.23 | T2 | 10.06.24 | SKS Decanter | 13.06.24 | 28.06.24 | 11.07.24 | 11.07.24 |  |  |  | 09.08.24 | PVVKSG@lntecc.com-23.07.2024-11:35:53
Jharsuguda | Process | Screw pumps | LE190742-P-018 | LE190742-P-018-A | Flosys Pumps | Awaiting post-offer from vendor | 13 |  | Jagadeesan.P -9361303055 | sales@flosys.in | 29.02.24 | 29.02.24 | 12.03.24 | 26.03.24 | 03.04.24 | 25.04.24 | [6 empty] | 25.04.24 | 04.05.24 | 20.05.24 | T3 | 22.07.24 | Flosys Pumps | [8 empty] | PVVKSG@lntecc.com-23.07.2024-11:21:57
Jharsuguda | Process | Screw pumps | LE190742-P-018 | LE190742-P-018-B | Rotomac | Sent to BU Operations | PR Closed |  | Srinivasalu -9500165366 / 9380014111 | chennai@rotomac.org |  | 20.03.24 | 25.03.24 | 28.03.24 | 30.03.24 | 15.04.24 | 16.04.24 | 25.04.24 |  |  |  |  | 26.04.24 | 26.04.24 | 20.05.24 | T1 | [10 empty] | PVVKSG@lntecc.com-22.07.2024-14:45:42
Jharsuguda | Process | Screw pumps | LE190742-P-018 | LE190742-P-018-C | Positive | Regret offer | PR Closed | Rejected. | Ratna Kandekar -9922507044 | ratnak@positivemetering.com |  | 20.03.24 | 25.03.24 | 28.03.24 | 08.04.24 | 15.04.24 | 18.04.24 | 29.04.24 | [5 empty] | 29.04.24 |  | T2 | [10 empty] | PVVKSG@lntecc.com-20.05.2024-18:30:11
Jharsuguda | Process | Screw pumps | LE190742-P-018 | LE190742-P-018-D | Allweiler | Regret offer | PR Closed |  |  |  |  | 20.03.24 | 03.04.24 | [23 empty] | PVVKSG@lntecc.com-16.05.2024-15:41:49
Jharsuguda | Process | Screw pumps | LE190742-P-018 | LE190742-P-018-E | Verito | Regret offer | PR Closed |  |  |  |  | 20.03.24 | 30.03.24 | [23 empty] | PVVKSG@lntecc.com-16.05.2024-15:41:49
Jharsuguda | Process | Dissolving tray | LE190742-P-019 | LE190742-P-019-A | NA | Regret offer | PR Closed | Site Procurement. |  |  | 30.09.22 | 30.09.22 | [24 empty] | PVVKSG@lntecc.com-21.05.2024-10:31:29
Jharsuguda | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE190742-I-WS-WT-PR-5101 | LE190742-I-WS-WT-PR-5101-A | AN instruments | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE190742-I-WS-WT-PR-5101 | LE190742-I-WS-WT-PR-5101-B | SIAS | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE190742-I-WS-WT-PR-5101 | LE190742-I-WS-WT-PR-5101-C | Measurecal | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE190742-I-WS-WT-PR-5101 | LE190742-I-WS-WT-PR-5101-D | Hguru South | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T1 | 30.12.21 | Hguru South | 14.01.22 | 19.01.22 | 20.01.22 | 24.01.22 | 25.01.22 |  |  | 28.02.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Pressure Switch | LE190742-I-WS-WT-PR-5102 | LE190742-I-WS-WT-PR-5102-A | AN instruments | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Pressure Switch | LE190742-I-WS-WT-PR-5102 | LE190742-I-WS-WT-PR-5102-B | Hguru South | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Pressure Switch | LE190742-I-WS-WT-PR-5102 | LE190742-I-WS-WT-PR-5102-C | Measurecal | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Pressure Switch | LE190742-I-WS-WT-PR-5102 | LE190742-I-WS-WT-PR-5102-D | HGURU | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T1 | 30.12.21 | HGURU | 14.01.22 | 19.01.22 | 23.01.22 | 24.01.22 | 25.01.22 |  |  | 28.02.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Float & Board Level gauge | LE190742-I-WS-WT-PR-5103 | LE190742-I-WS-WT-PR-5103-A | Pune Techtrol | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 19.12.21 | 20.12.21 | [8 empty] | 25.12.21 | 25.12.21 | 26.12.21 | T1 | 08.01.22 | Pune Techtrol | 10.01.22 | 15.01.22 | 16.01.22 | 20.01.22 | 21.01.22 |  |  | 09.03.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Float & Board Level gauge | LE190742-I-WS-WT-PR-5103 | LE190742-I-WS-WT-PR-5103-B | SBEM | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 19.12.21 | 20.12.21 | [8 empty] | 25.12.21 | 25.12.21 | 26.12.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | level switch - Conductivity type | LE190742-I-WS-WT-PR-5104 | LE190742-I-WS-WT-PR-5104-A | SBEM | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 19.12.21 | 20.12.21 | [8 empty] | 25.12.21 | 25.12.21 | 26.12.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | level switch - Conductivity type | LE190742-I-WS-WT-PR-5104 | LE190742-I-WS-WT-PR-5104-B | Pune Techtrol | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 19.12.21 | 20.12.21 | [8 empty] | 25.12.21 | 25.12.21 | 26.12.21 | T1 | 03.01.22 | Pune Techtrol | 10.01.22 | 15.01.22 | 17.01.22 | 20.01.22 | 21.01.22 |  |  | 04.03.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Ultrasonic level Transmitter | LE190742-I-WS-WT-PR-5105 | LE190742-I-WS-WT-PR-5105-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Ultrasonic level Transmitter | LE190742-I-WS-WT-PR-5105 | LE190742-I-WS-WT-PR-5105-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Ultrasonic level Transmitter | LE190742-I-WS-WT-PR-5105 | LE190742-I-WS-WT-PR-5105-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Ultrasonic level Transmitter | LE190742-I-WS-WT-PR-5105 | LE190742-I-WS-WT-PR-5105-D | Siemens | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T1 | 12.09.21 | Siemens | 13.09.21 | 18.09.21 | 18.09.21 | 23.09.21 | 24.09.21 |  |  | 11.11.21 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Radar Level Transmitter | LE190742-I-WS-WT-PR-5106 | LE190742-I-WS-WT-PR-5106-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Radar Level Transmitter | LE190742-I-WS-WT-PR-5106 | LE190742-I-WS-WT-PR-5106-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Radar Level Transmitter | LE190742-I-WS-WT-PR-5106 | LE190742-I-WS-WT-PR-5106-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Radar Level Transmitter | LE190742-I-WS-WT-PR-5106 | LE190742-I-WS-WT-PR-5106-D | Siemens | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T1 | 01.09.21 | Siemens | 13.09.21 | 18.09.21 | 22.09.21 | 23.09.21 | 24.09.21 |  |  | 31.10.21 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Loss of head transmitter | LE190742-I-WS-WT-PR-5107 | LE190742-I-WS-WT-PR-5107-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Loss of head transmitter | LE190742-I-WS-WT-PR-5107 | LE190742-I-WS-WT-PR-5107-B | E&H | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Loss of head transmitter | LE190742-I-WS-WT-PR-5107 | LE190742-I-WS-WT-PR-5107-C | Siemens | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T1 | 02.09.21 | Siemens | 13.09.21 | 18.09.21 | 18.09.21 | 23.09.21 | 24.09.21 |  |  | 01.11.21 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Rate for flow transmitter | LE190742-I-WS-WT-PR-5108 | LE190742-I-WS-WT-PR-5108-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Rate for flow transmitter | LE190742-I-WS-WT-PR-5108 | LE190742-I-WS-WT-PR-5108-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Rate for flow transmitter | LE190742-I-WS-WT-PR-5108 | LE190742-I-WS-WT-PR-5108-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Rate for flow transmitter | LE190742-I-WS-WT-PR-5108 | LE190742-I-WS-WT-PR-5108-D | Siemens | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T1 | 06.09.21 | Siemens | 13.09.21 | 18.09.21 | 18.09.21 | 23.09.21 | 24.09.21 |  |  | 05.11.21 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Bypass Rotameter | LE190742-I-WS-WT-PR-5109 | LE190742-I-WS-WT-PR-5109-A | Eureka | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 08.05.21 | 09.05.21 | [8 empty] | 14.05.21 | 14.05.21 | 15.05.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Bypass Rotameter | LE190742-I-WS-WT-PR-5109 | LE190742-I-WS-WT-PR-5109-B | Scientific devices | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 08.05.21 | 09.05.21 | [8 empty] | 14.05.21 | 14.05.21 | 15.05.21 | T1 | 18.05.21 | Scientific devices | 30.05.21 | 04.06.21 | 04.06.21 | 09.06.21 | 10.06.21 |  |  | 17.07.21 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Electromagnectic flow meter | LE190742-I-WS-WT-PR-5110 | LE190742-I-WS-WT-PR-5110-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 13.06.21 | 14.06.21 | [8 empty] | 19.06.21 | 19.06.21 | 20.06.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Electromagnectic flow meter | LE190742-I-WS-WT-PR-5110 | LE190742-I-WS-WT-PR-5110-B | Khrone | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 13.06.21 | 14.06.21 | [8 empty] | 19.06.21 | 19.06.21 | 20.06.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Electromagnectic flow meter | LE190742-I-WS-WT-PR-5110 | LE190742-I-WS-WT-PR-5110-C | siemens | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 13.06.21 | 14.06.21 | [8 empty] | 19.06.21 | 19.06.21 | 20.06.21 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Electromagnectic flow meter | LE190742-I-WS-WT-PR-5110 | LE190742-I-WS-WT-PR-5110-D | E&H | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 13.06.21 | 14.06.21 | [8 empty] | 19.06.21 | 19.06.21 | 20.06.21 | T1 | 24.06.21 | E&H | 05.07.21 | 10.07.21 | 10.07.21 | 15.07.21 | 16.07.21 |  |  | 23.08.21 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Ultrasonic type Open channel flow transmitter | LE190742-I-WS-WT-PR-5111 | LE190742-I-WS-WT-PR-5111-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Ultrasonic type Open channel flow transmitter | LE190742-I-WS-WT-PR-5111 | LE190742-I-WS-WT-PR-5111-B | Electronet | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Ultrasonic type Open channel flow transmitter | LE190742-I-WS-WT-PR-5111 | LE190742-I-WS-WT-PR-5111-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Ultrasonic type Open channel flow transmitter | LE190742-I-WS-WT-PR-5111 | LE190742-I-WS-WT-PR-5111-D | Siemens | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 22.08.21 | 23.08.21 | [8 empty] | 28.08.21 | 28.08.21 | 29.08.21 | T1 | 07.09.21 | Siemens | 13.09.21 | 18.09.21 | 20.09.21 | 23.09.21 | 24.09.21 |  |  | 06.11.21 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Pressure transmitter | LE190742-I-WS-WT-PR-5112 | LE190742-I-WS-WT-PR-5112-E | ABB | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Pressure transmitter | LE190742-I-WS-WT-PR-5112 | LE190742-I-WS-WT-PR-5112-F | E&H | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Pressure transmitter | LE190742-I-WS-WT-PR-5112 | LE190742-I-WS-WT-PR-5112-G | HGURU | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 23.12.21 | 24.12.21 | [8 empty] | 29.12.21 | 29.12.21 | 30.12.21 | T1 | 09.01.22 | HGURU | 14.01.22 | 19.01.22 | 23.01.22 | 24.01.22 | 25.01.22 |  |  | 10.03.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | pH Meter | LE190742-I-WS-WT-PR-5113 | LE190742-I-WS-WT-PR-5113-A | Emerson | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | pH Meter | LE190742-I-WS-WT-PR-5113 | LE190742-I-WS-WT-PR-5113-B | HACH | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | pH Meter | LE190742-I-WS-WT-PR-5113 | LE190742-I-WS-WT-PR-5113-C | ABB | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | pH Meter | LE190742-I-WS-WT-PR-5113 | LE190742-I-WS-WT-PR-5113-D | Emerson | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T1 | 18.04.22 | Emerson | 22.04.22 | 27.04.22 | 01.05.22 | 02.05.22 | 03.05.22 |  |  | 17.06.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Turbidity meter | LE190742-I-WS-WT-PR-5114 | LE190742-I-WS-WT-PR-5114-A | Emerson | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Turbidity meter | LE190742-I-WS-WT-PR-5114 | LE190742-I-WS-WT-PR-5114-B | HACH | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Turbidity meter | LE190742-I-WS-WT-PR-5114 | LE190742-I-WS-WT-PR-5114-C | ABB | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Turbidity meter | LE190742-I-WS-WT-PR-5114 | LE190742-I-WS-WT-PR-5114-D | Emerson | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T1 | 14.04.22 | Emerson | 22.04.22 | 27.04.22 | 01.05.22 | 02.05.22 | 03.05.22 |  |  | 13.06.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Residual Chlorine Analyzer | LE190742-I-WS-WT-PR-5115 | LE190742-I-WS-WT-PR-5115-A | Emerson | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Residual Chlorine Analyzer | LE190742-I-WS-WT-PR-5115 | LE190742-I-WS-WT-PR-5115-B | HACH | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Residual Chlorine Analyzer | LE190742-I-WS-WT-PR-5115 | LE190742-I-WS-WT-PR-5115-C | ABB | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Residual Chlorine Analyzer | LE190742-I-WS-WT-PR-5115 | LE190742-I-WS-WT-PR-5115-D | Emerson | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 31.03.22 | 01.04.22 | [8 empty] | 06.04.22 | 06.04.22 | 07.04.22 | T1 | 10.04.22 | Emerson | 22.04.22 | 27.04.22 | 30.04.22 | 02.05.22 | 03.05.22 |  |  | 09.06.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE190742-I-WS-WT-PR-5117 | LE190742-I-WS-WT-PR-5117-A | Autosys | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 08.05.21 | 09.05.21 | [8 empty] | 14.05.21 | 14.05.21 | 15.05.21 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE190742-I-WS-WT-PR-5117 | LE190742-I-WS-WT-PR-5117-B | SIAS | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 08.05.21 | 09.05.21 | [8 empty] | 14.05.21 | 14.05.21 | 15.05.21 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE190742-I-WS-WT-PR-5117 | LE190742-I-WS-WT-PR-5117-C | COTMAC | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 08.05.21 | 09.05.21 | [8 empty] | 14.05.21 | 14.05.21 | 15.05.21 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE190742-I-WS-WT-PR-5117 | LE190742-I-WS-WT-PR-5117-D | Mitsubishi | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 08.05.21 | 09.05.21 | [8 empty] | 14.05.21 | 14.05.21 | 15.05.21 | T5 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE190742-I-WS-WT-PR-5117 | LE190742-I-WS-WT-PR-5117-E | Schneider | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 08.05.21 | 09.05.21 | [8 empty] | 14.05.21 | 14.05.21 | 15.05.21 | T1 | 23.05.21 | Schneider | 30.05.21 | 04.06.21 | 06.06.21 | 09.06.21 | 10.06.21 |  |  | 22.07.21 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | instrumentation Control & signal Cables | LE190742-I-WS-WT-PR-5118 | LE190742-I-WS-WT-PR-5118-A | Axelon | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 09.07.22 | 10.07.22 | [8 empty] | 15.07.22 | 15.07.22 | 16.07.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | instrumentation Control & signal Cables | LE190742-I-WS-WT-PR-5118 | LE190742-I-WS-WT-PR-5118-B | Cords | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 09.07.22 | 10.07.22 | [8 empty] | 15.07.22 | 15.07.22 | 16.07.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | instrumentation Control & signal Cables | LE190742-I-WS-WT-PR-5118 | LE190742-I-WS-WT-PR-5118-C | Delton | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 09.07.22 | 10.07.22 | [8 empty] | 15.07.22 | 15.07.22 | 16.07.22 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | instrumentation Control & signal Cables | LE190742-I-WS-WT-PR-5118 | LE190742-I-WS-WT-PR-5118-D | Thermo | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 09.07.22 | 10.07.22 | [8 empty] | 15.07.22 | 15.07.22 | 16.07.22 | T1 | 23.07.22 | Thermo | 31.07.22 | 05.08.22 | 07.08.22 | 10.08.22 | 11.08.22 |  |  | 21.09.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | UPS | LE190742-I-WS-WT-PR-5119 | LE190742-I-WS-WT-PR-5119-A | Vertiv | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 30.06.22 | 01.07.22 | [8 empty] | 06.07.22 | 06.07.22 | 07.07.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | UPS | LE190742-I-WS-WT-PR-5119 | LE190742-I-WS-WT-PR-5119-B | LiveLine | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 30.06.22 | 01.07.22 | [8 empty] | 06.07.22 | 06.07.22 | 07.07.22 | T1 | 13.07.22 | LiveLine | 22.07.22 | 27.07.22 | 31.07.22 | 01.08.22 | 02.08.22 |  |  | 11.09.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Battery Operated Flowmeter | LE190742-I-WS-WT-PR-5120 | LE190742-I-WS-WT-PR-5120-A | Khrone | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 11.08.22 | 12.08.22 | [8 empty] | 17.08.22 | 17.08.22 | 18.08.22 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Battery Operated Flowmeter | LE190742-I-WS-WT-PR-5120 | LE190742-I-WS-WT-PR-5120-B | siemens | Sent to BU Operations | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 11.08.22 | 12.08.22 | [8 empty] | 17.08.22 | 17.08.22 | 18.08.22 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Instrumentation | Battery Operated Flowmeter | LE190742-I-WS-WT-PR-5120 | LE190742-I-WS-WT-PR-5120-C | ABB | Approved by Client | PR Closed |  |  |  | 10.08.20 | 10.08.20 | 11.08.22 | 12.08.22 | [8 empty] | 17.08.22 | 17.08.22 | 18.08.22 | T1 | 23.08.22 | ABB | 02.09.22 | 07.09.22 | 11.09.22 | 12.09.22 | 13.09.22 |  |  | 22.10.22 | sooryaprakash.t@lntecc.com-03.05.2024-12:20:00
Jharsuguda | Electrical | LT Cable | LE-1904742-E-WS-WT-PR-4008 | LE-1904742-E-WS-WT-PR-4008-B | Havells | Approved by Client | PR Closed |  |  |  | 27.10.22 | 21.02.21 | 23.11.21 | 21.12.21 | [8 empty] | 15.11.21 | 23.11.21 | 23.11.21 |  | 07.12.21 | Havells | 22.12.21 | 22.12.21 | 22.12.21 | 22.12.21 | 22.12.21 |  |  | 05.02.22 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | LT Cable | LE-1904742-E-WS-WT-PR-4008 | LE-1904742-E-WS-WT-PR-4008-C | KEI | Sent to BU Operations | PR Closed |  |  |  | 27.10.22 | 29.12.20 | 11.10.21 | 28.10.21 | [8 empty] | 19.11.21 | 19.11.21 | 19.11.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | LT Cable | LE-1904742-E-WS-WT-PR-4008 | LE-1904742-E-WS-WT-PR-4008-D | Purva Vasi | Sent to BU Operations | PR Closed |  |  |  | 27.10.22 | 17.12.20 | 10.10.21 | 28.10.21 | [8 empty] | 15.11.21 | 15.11.21 | 15.11.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | VFD | LE190742-E-001 | LE190742-E-001-A | Hitachi | Approved by Client | PR Closed |  |  |  | 18.10.22 | 18.10.22 | 04.09.23 | 05.10.23 | [8 empty] | 05.10.23 | 09.10.23 | 09.10.23 |  | 09.10.23 | Hitachi | 06.12.23 | 01.02.24 | 05.02.24 | 05.02.24 | 05.02.24 |  |  | 08.12.23 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | VFD | LE190742-E-001 | LE190742-E-001-B | ABB | Sent to BU Operations | PR Closed |  |  |  | 18.10.22 | 18.10.22 | 05.09.23 | 06.09.23 | [8 empty] | 18.10.23 | 19.10.23 | 19.10.23 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Transformer | LE190742-E-WS-WT-PR-4003 | LE190742-E-WS-WT-PR-4003-A | PETE | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 01.08.21 | 02.09.21 | 03.09.21 | [8 empty] | 07.09.21 | 07.09.21 | 07.09.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Transformer | LE190742-E-WS-WT-PR-4003 | LE190742-E-WS-WT-PR-4003-B | TBEA | Approved by Client | PR Closed |  |  |  | 26.9.22 | 26.09.22 | 03.02.23 | 03.02.23 | [8 empty] | 09.02.23 | 09.02.23 | 09.02.23 |  | 25.04.23 | TBEA | 18.05.23 | 18.05.23 | 06.07.23 | 06.07.23 | 6.7.23 |  |  | 24.06.23 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Transformer | LE190742-E-WS-WT-PR-4003 | LE190742-E-WS-WT-PR-4003-C | Uttam Bharat | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 17.04.21 | 24.08.21 | 26.08.21 | [8 empty] | 09.02.23 | 09.02.23 | 09.02.23 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Transformer | LE190742-E-WS-WT-PR-4003 | LE190742-E-WS-WT-PR-4003-D | Vardhman | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 02.07.21 | 15.11.21 | 18.11.21 | [8 empty] | 02.12.21 | 02.12.21 | 02.12.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Transformer | LE190742-E-WS-WT-PR-4003 | LE190742-E-WS-WT-PR-4003-E | Voltech | Sent to BU Operations | PR Closed |  |  |  | 26.9.22 | 26.08.20 | 25.08.21 | 26.08.21 | [8 empty] | 27.12.21 | 27.12.21 | 27.12.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | DG Set | LE190742-E-WS-WT-PR-4005 | LE190742-E-WS-WT-PR-4005-A | IEC | Approved by Client | PR Closed |  |  |  | 20.2.20 | 20.02.20 | 21.03.20 | 21.03.20 | [8 empty] | 21.03.20 | 21.03.20 | 21.03.20 |  | 06.05.20 | IEC | 05.08.20 | 21.08.20 | 15.12.20 | 15.12.20 | 15.12.20 |  |  | 05.07.20 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | LDB & LPBS | LE190742-E-WS-WT-PR-4007 | LE190742-E-WS-WT-PR-4007-A | AEPL | Approved by Client | PR Closed |  |  |  | 25.10.22 | 25.10.22 | 28.10.22 | 05.11.22 | [8 empty] | 12.12.22 | 12.12.22 | 12.12.22 |  | 02.06.23 | AEPL | 23.11.23 | 14.12.23 | 15.12.23 | 18.12.23 | 18.12.23 |  |  | 01.08.23 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | LT Cable | LE190742-E-WS-WT-PR-4008 | LE190742-E-WS-WT-PR-4008-A | Vishal | Sent to BU Operations | 989 |  |  |  | 27.10.22 | 19.01.21 | 13.10.21 | 28.10.21 | [8 empty] | 01.11.21 | 19.11.21 | 19.11.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | HT Panel | LE190742-E-WS-WT-PR-4014 | LE190742-E-WS-WT-PR-4014-A | Universal | Pre-order technically cleared | 465 |  |  |  | 28.10.22 | 28.10.22 | 25.01.23 | 25.01.23 | [8 empty] | 27.04.23 | 27.04.23 | 27.04.23 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | HT Panel | LE190742-E-WS-WT-PR-4014 | LE190742-E-WS-WT-PR-4014-B | HTS | Pre-order technically cleared | 507 |  |  |  | 28.10.22 | 28.10.22 | 23.02.23 | 10.03.23 | [8 empty] | 16.03.23 | 16.03.23 | 16.03.23 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | HT Panel | LE190742-E-WS-WT-PR-4014 | LE190742-E-WS-WT-PR-4014-C | UPE | Pre-order technically cleared | 978 |  |  |  | 28.10.22 | 05.01.21 | 20.11.21 | 22.11.21 | [8 empty] | 30.11.21 | 30.11.21 | 30.11.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Conductor | LE190742-E-WS-WT-PR-4020 | LE190742-E-WS-WT-PR-4020-A | Cabcon | Sent to BU Operations | 957 |  |  |  | 10.6.21 | 10.06.21 | 21.12.21 | 21.12.21 | [8 empty] | 21.12.21 | 21.12.21 | 21.12.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Conductor | LE190742-E-WS-WT-PR-4020 | LE190742-E-WS-WT-PR-4020-B | Galaxy | Sent to BU Operations | 957 |  |  |  | 10.6.21 | 10.06.21 | 21.12.21 | 21.12.21 | [8 empty] | 21.12.21 | 21.12.21 | 21.12.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Conductor | LE190742-E-WS-WT-PR-4020 | LE190742-E-WS-WT-PR-4020-C | Gupta | Sent to BU Operations | 957 |  |  |  | 10.6.21 | 10.06.21 | 21.12.21 | 21.12.21 | [8 empty] | 21.12.21 | 21.12.21 | 21.12.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | Transformer | LE190742-E-WS-WT-PR-4043 | LE190742-E-WS-WT-PR-4043-A | Voltech | Approved by Client | PR Closed |  |  |  | 26.9.22 | 03.12.20 | 25.08.21 | 26.08.21 | [8 empty] | 27.12.21 | 27.12.21 | 27.12.21 |  | 30.01.23 | Voltech | 16.02.23 | 16.02.23 | 16.02.23 | 16.02.23 | 16.2.23 |  |  | 31.03.23 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | LT Panel | LE190742-E-WS-WT-PR-4104 | LE190742-E-WS-WT-PR-4104-A | EAP | Sent to BU Operations | PR Closed |  |  |  | 14.10.22 | 14.10.22 | 23.12.22 | 17.04.23 | [8 empty] | 20.04.23 | 20.04.23 | 20.04.23 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | LT Panel | LE190742-E-WS-WT-PR-4104 | LE190742-E-WS-WT-PR-4104-B | SRCS | Approved by Client | PR Closed |  |  |  | 14.10.22 | 14.10.22 | 19.12.22 | 12.04.23 | [8 empty] | 26.07.23 | 26.07.23 | 26.07.23 |  | 20.08.23 | SRCS | 22.05.23 | 23.06.23 | 14.08.23 | 14.08.23 | 14.8.23 |  |  | 19.10.23 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | LT Panel | LE190742-E-WS-WT-PR-4104 | LE190742-E-WS-WT-PR-4104-C | UPE | Sent to BU Operations | PR Closed |  |  |  | 14.10.22 | 14.10.22 | 25.01.23 | 12.04.23 | [8 empty] | 21.04.23 | 21.04.23 | 21.04.23 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | LT Panel | LE190742-E-WS-WT-PR-4104 | LE190742-E-WS-WT-PR-4104-D | Voltech | Sent to BU Operations | PR Closed |  |  |  | 14.10.22 | 06.01.21 | 20.06.21 | 13.10.21 | [8 empty] | 13.10.21 | 13.10.21 | 13.10.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | VFD | LE190742-E-WS-WT-PR-4114 | LE190742-E-WS-WT-PR-4114-C | TMEIC | Sent to BU Operations | 292 |  |  |  | 18.10.22 | 18.10.22 | 25.07.23 | 16.09.23 | [8 empty] | 17.10.23 | 17.10.23 | 17.10.23 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | PCVCB | LE190742-E-WS-WT-PR-4115 | LE190742-E-WS-WT-PR-4115-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 19.10.22 | 07.05.21 | 01.10.21 | 04.10.21 | [8 empty] | 27.10.21 | 27.10.21 | 27.10.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | PCVCB | LE190742-E-WS-WT-PR-4115 | LE190742-E-WS-WT-PR-4115-B | CGL | Approved by Client | PR Closed |  |  |  | 19.10.22 | 19.10.22 | 25.10.22 | 28.10.22 | [8 empty] | 10.11.22 | 10.11.22 | 10.11.22 |  | 10.11.22 | CGL | 22.08.21 | 30.03.22 | 03.05.22 | 03.05.22 | 3.5.22 |  |  | 09.01.23 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | C&R | LE190742-E-WS-WT-PR-4140 | LE190742-E-WS-WT-PR-4140-A | POPULAR | Approved by Client | PR Closed |  |  |  | 19.10.22 | 29.12.20 | 28.08.21 | 31.08.21 | [8 empty] | 30.09.21 | 30.09.21 | 30.09.21 |  | 03.10.21 | POPULAR | 29.01.22 | 08.02.22 | 30.03.22 | 30.03.22 | 30.3.22 |  |  | 02.12.21 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | CT&PT | LE190742-E-WS-WT-PR-4141 | LE190742-E-WS-WT-PR-4141-A | Kalpa | Sent to BU Operations | PR Closed |  |  |  | 19.10.22 | 07.08.21 | 26.08.21 | 26.08.21 | [8 empty] | 30.09.21 | 30.09.21 | 30.09.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | CT&PT | LE190742-E-WS-WT-PR-4141 | LE190742-E-WS-WT-PR-4141-B | Mehru | Approved by Client | PR Closed |  |  |  | 19.10.22 | 15.01.21 | 30.09.21 | 30.09.21 | [8 empty] | 30.09.21 | 30.09.21 | 30.09.21 |  | 09.12.21 | Mehru | 21.02.22 | 11.03.22 | 30.03.22 | 30.03.22 | 30.3.22 |  |  | 07.02.22 | karthik.ajithkumar@lntecc.com
Jharsuguda | Electrical | CT&PT | LE190742-E-WS-WT-PR-4141 | LE190742-E-WS-WT-PR-4141-C | Pragati | Sent to BU Operations | PR Closed |  |  |  | 19.10.22 | 18.07.21 | 01.11.21 | 01.11.21 | [8 empty] | 22.11.21 | 22.11.21 | 22.11.21 | [11 empty] | karthik.ajithkumar@lntecc.com
Kalburgi | Process | Flocculator and Inclined Plate Settler scrapper mechanism | LE200354-P-WS-WT-PR-2252 | LE200354-P-WS-WT-PR-2252-A | Sritech | Pre-order technically cleared | 58 |  |  |  |  | 05.10.21 | 24.04.24 | 03.05.24 | 07.05.24 | 22.05.24 | 29.05.24 | 01.06.24 | 07.06.24 | 07.06.24 |  |  | 07.06.24 | 07.06.24 | 07.06.24 | [8 empty] | 07.06.24 | 24.06.24 | 23.08.24 | KUMUTHA@lntecc.com-01.07.2024-14:36:35
Kalburgi | Process | Air Blower | LE200354-P-WS-WT-PR-2253 | LE200354-P-WS-WT-PR-2253-A | Everest | Post-order technically cleared | 166 |  |  |  |  | 24.09.21 | 24.08.23 | 05.09.23 | 04.10.23 | 04.10.23 | [6 empty] | 04.10.23 | 04.10.23 | 04.10.23 | T1 | 05.10.23 | Everest | 05.10.23 | 07.10.23 | 20.02.24 | 20.02.24 |  |  |  | 04.12.23 | KUMUTHA@lntecc.com-01.06.2024-13:57:06
Kalburgi | Process | Agitator | LE200354-P-WS-WT-PR-2254 | LE200354-P-WS-WT-PR-2254-A | Verito | Post-order technically cleared | 87 | Awaiting for 3D Drawing |  |  |  | 24.09.21 | 19.10.23 | 25.10.23 | 07.11.23 | 08.11.23 | 09.11.23 | 18.11.23 |  |  |  |  | 09.11.23 | 09.11.23 | 18.11.23 | T1 | 20.12.23 | Verito | 20.12.23 | 03.01.24 | 16.02.24 | 16.02.24 | 09.05.24 |  |  | 18.02.24 | KUMUTHA@lntecc.com-27.06.2024-16:46:43
Kalburgi | Process | Sluice gate | LE200354-P-WS-WT-PR-2255 | LE200354-P-WS-WT-PR-2255-A | IVC | Post-order comments issued | 50 |  |  |  |  | 30.11.20 | 24.11.23 | 07.12.22 | 03.01.24 | 12.01.24 | 16.01.24 | 16.01.24 | 17.01.24 | 10.04.24 |  |  | 10.04.24 | 10.04.24 | 10.04.24 | T1 | 19.04.24 | IVC | 09.05.24 | 15.06.24 | [5 empty] | 18.06.24 | KUMUTHA@lntecc.com-15.07.2024-18:45:56
Kalburgi | Process | Sluice gate | LE200354-P-WS-WT-PR-2255 | LE200354-P-WS-WT-PR-2255-B | Jash | Regret offer | PR Closed |  |  |  |  | 30.11.20 | 03.04.24 | 04.04.24 | 06.04.24 | 10.04.24 | [20 empty] | hari.thinakaran@lntecc.com-20.05.2024-10:26:43
Kalburgi | Process | Chlorination System | LE200354-P-WS-WT-PR-2256 | LE200354-P-WS-WT-PR-2256-A | Chennai Chloro System | Pre-order technically rejected | PR Closed |  |  |  |  | 04.10.21 | 19.01.24 | 06.02.24 | 20.04.24 | 03.05.24 | 08.05.24 | 24.05.24 | 15.06.24 | 19.06.24 | 08.07.24 | 15.07.24 | 15.07.24 | 15.07.24 | 15.07.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-15.07.2024-17:19:54
Kalburgi | Process | Chlorination System | LE200354-P-WS-WT-PR-2256 | LE200354-P-WS-WT-PR-2256-B | Zion Technologies | Pre-order technically cleared | 47 |  |  |  |  | 04.10.21 | 12.06.24 | 14.06.24 | 14.06.24 | 18.06.24 | [6 empty] | 18.06.24 | 18.06.24 | 18.06.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-15.07.2024-17:19:54
Kalburgi | Process | Chlorine tonner | LE200354-P-WS-WT-PR-2257 | LE200354-P-WS-WT-PR-2257-A | Chennai Chloro System | Pre-order technically rejected | PR Closed |  |  |  |  | 04.10.21 | 20.04.24 | 03.05.24 | 08.07.24 | 15.07.24 | [6 empty] | 15.07.24 | 15.07.24 | 15.07.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-15.07.2024-17:20:53
Kalburgi | Process | Chlorine tonner | LE200354-P-WS-WT-PR-2257 | LE200354-P-WS-WT-PR-2257-B | Zion Technologies | Pre-order technically cleared | 47 |  |  |  |  | 04.10.21 | 12.06.24 | 14.06.24 | 14.06.24 | 18.06.24 | [6 empty] | 18.06.24 | 18.06.24 | 18.06.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-15.07.2024-17:20:53
Kalburgi | Process | Filter Media | LE200354-P-WS-WT-PR-2258 | LE200354-P-WS-WT-PR-2258-A | Kalimati Carbon | Pre-order technically cleared | 75 |  |  |  |  | 24.09.21 | 04.03.24 | 14.03.24 | 13.05.24 | 13.05.24 | 21.05.24 | 21.05.24 |  |  |  |  | 21.05.24 | 21.05.24 | 21.05.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-05.07.2024-18:26:49
Kalburgi | Process | Filter Media | LE200354-P-WS-WT-PR-2258 | LE200354-P-WS-WT-PR-2258-B | Dalton Minerals | Pre-order technically cleared | 100 |  |  |  |  | 24.09.21 | 20.03.24 | 27.03.24 | 02.04.24 | 02.04.24 | 11.04.24 | 12.04.24 | 22.04.24 | 26.04.24 |  |  | 22.04.24 | 22.04.24 | 26.04.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-05.07.2024-18:26:49
Kalburgi | Process | Filter Media | LE200354-P-WS-WT-PR-2258 | LE200354-P-WS-WT-PR-2258-C | Shakun Minerals | Pre-order comments issued | 30 |  |  |  |  | 24.09.21 | 27.05.24 | 30.05.24 | 05.07.24 | 05.07.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-05.07.2024-18:26:49
Kalburgi | Process | Nozzles | LE200354-P-WS-WT-PR-2259 | LE200354-P-WS-WT-PR-2259-A | Guddi Plastcon | Post-order technically cleared | 55 |  |  |  |  | 04.10.21 | 26.09.23 | 05.10.23 | 31.10.23 | 01.11.23 | 20.12.23 | 20.12.23 |  |  |  |  | 20.12.23 | 20.12.23 | 20.12.23 | T1 | 20.12.23 | Guddi Plastcon | 03.01.24 | 05.01.24 | 22.02.24 | 22.02.24 | 10.06.24 |  |  | 18.02.24 | KUMUTHA@lntecc.com-27.06.2024-16:45:48
Kalburgi | Process | Sludge Drying Bed Media | LE200354-P-WS-WT-PR-2260 | LE200354-P-WS-WT-PR-2260-A | Kalimati Carbon | Pre-order technically cleared | 75 |  |  |  |  | 24.09.21 | 04.03.24 | 14.03.24 | 13.05.24 | 13.05.24 | 21.05.24 | 21.05.24 |  |  |  |  | 21.05.24 | 21.05.24 | 21.05.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-05.07.2024-18:28:49
Kalburgi | Process | Sludge Drying Bed Media | LE200354-P-WS-WT-PR-2260 | LE200354-P-WS-WT-PR-2260-B | Dalton Minerals | Pre-order technically cleared | 100 |  |  |  |  | 24.09.21 | 20.03.24 | 27.03.24 | 02.04.24 | 02.04.24 | 11.04.24 | 12.04.24 | 22.04.24 | 26.04.24 |  |  | 22.04.24 | 22.04.24 | 26.04.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-05.07.2024-18:28:49
Kalburgi | Process | Sludge Drying Bed Media | LE200354-P-WS-WT-PR-2260 | LE200354-P-WS-WT-PR-2260-C | Shakun Minerals | Pre-order comments issued | 30 |  |  |  |  | 24.09.21 | 27.05.24 | 30.05.24 | 05.07.24 | 05.07.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-05.07.2024-18:28:49
Kalburgi | Process | Backwash Pump | LE200354-P-WS-WT-PR-2261 | LE200354-P-WS-WT-PR-2261-A | Wilo | Regret offer | PR Closed | Not Responding |  |  |  | 24.09.21 | 21.08.23 | 22.08.23 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-09.07.2024-12:53:17
Kalburgi | Process | Backwash Pump | LE200354-P-WS-WT-PR-2261 | LE200354-P-WS-WT-PR-2261-B | MBH | Pre-order technically rejected | PR Closed |  |  |  |  | 24.09.21 | 21.08.23 | 23.08.23 | 06.09.23 | 08.09.23 | 11.10.23 | 12.10.23 | [15 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-01.07.2024-14:46:59
Kalburgi | Process | Backwash Pump | LE200354-P-WS-WT-PR-2261 | LE200354-P-WS-WT-PR-2261-C | KSB | Pre-order technically cleared | 17 |  |  |  |  | 24.09.21 | 04.03.24 | 05.03.24 | 28.03.24 | 29.03.24 | 18.04.24 | 30.04.24 |  |  |  |  | 18.04.24 | 18.04.24 | 30.04.24 | T1 | 15.07.24 | KSB | 16.07.24 | 18.07.24 |  |  |  | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-18.07.2024-12:57:48
Kalburgi | Process | Backwash Pump | LE200354-P-WS-WT-PR-2261 | LE200354-P-WS-WT-PR-2261-D | Andritz | Pre-order technically rejected | PR Closed |  |  |  |  | 24.09.21 | 12.06.24 | 14.06.24 | 24.06.24 | 24.06.24 | 09.07.24 | 09.07.24 | 10.07.24 | 10.07.24 |  |  | 10.07.24 | 10.07.24 | 10.07.24 | [8 empty] | 31.07.24 | 17.08.24 | 16.10.24 | KUMUTHA@lntecc.com-18.07.2024-12:57:48
Kalburgi | Process | Submersible Pump | LE200354-P-WS-WT-PR-2262 | LE200354-P-WS-WT-PR-2262-A | MBH | Pre-order technically cleared | 45 |  |  |  |  | 14.03.24 | 01.06.24 | 03.06.24 | 10.06.24 | 11.06.24 | 20.06.24 | 20.06.24 |  |  |  |  | 20.06.24 | 20.06.24 | 20.06.24 | [8 empty] | 20.06.24 | 07.07.24 | 05.09.24 | KUMUTHA@lntecc.com-25.07.2024-12:17:25
Kalburgi | Process | Submersible Pump | LE200354-P-WS-WT-PR-2262 | LE200354-P-WS-WT-PR-2262-B | Jasco | Pre-order comments issued | 10 |  |  |  |  | 14.03.24 | 09.07.24 | 25.07.24 | [22 empty] | KUMUTHA@lntecc.com-25.07.2024-12:17:25
Kalburgi | Process | Electric Hoist | LE200354-P-WS-WT-PR-2263 | LE200354-P-WS-WT-PR-2263-A | Japs | Post-order technically cleared | 75 |  |  |  |  | 30.11.20 | 26.09.23 | 07.10.23 | 17.10.23 | 19.10.23 | [6 empty] | 12.10.23 | 12.10.23 | 19.10.23 | T1 | 19.10.23 | Japs | 19.01.24 | 21.05.24 | 21.05.24 | 21.05.24 |  |  |  | 18.12.23 | KUMUTHA@lntecc.com-21.05.2024-18:10:29
Kalburgi | Process | Manual Chain Pulley Block | LE200354-P-WS-WT-PR-2264 | LE200354-P-WS-WT-PR-2264-A | Japs | Post-order technically cleared | 75 |  |  |  |  | 30.11.20 | 26.09.23 | 07.10.23 | 17.10.23 | 19.10.23 | [6 empty] | 12.10.23 | 12.10.23 | 19.10.23 | T1 | 19.10.23 | Japs | 04.04.24 | 21.05.24 | 21.05.24 | 21.05.24 |  |  |  | 18.12.23 | KUMUTHA@lntecc.com-01.06.2024-13:57:07
Kalburgi | Process | Dosing Pump | LE200354-P-WS-WT-PR-2265 | LE200354-P-WS-WT-PR-2265-A | SR Metering | Post-order technically cleared | 87 |  |  |  |  | 04.10.21 | 21.08.23 | 24.08.23 | 28.08.23 | 31.08.23 | [6 empty] | 28.08.23 | 28.08.23 | 31.08.23 | T1 | 31.08.23 | SR Metering | 13.11.23 | 08.12.23 | 10.01.24 | 10.01.24 | 09.05.24 |  |  | 30.10.23 | KUMUTHA@lntecc.com-27.06.2024-16:47:56
Kalburgi | Process | Sampling Pump | LE200354-P-WS-WT-PR-2266 | LE200354-P-WS-WT-PR-2266-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 03.01.24 | [24 empty] | KUMUTHA@lntecc.com-07.06.2024-14:12:56
Kalburgi | Process | Submersible Mixer | LE200354-P-WS-WT-PR-2267 | LE200354-P-WS-WT-PR-2267-A | ABS | Post-order technically cleared | 38 |  |  |  |  | 04.10.21 | 27.02.24 | 14.03.24 | 03.04.24 | 03.04.24 | [6 empty] | 03.04.24 | 03.04.24 | 03.04.24 | T1 | 15.05.24 | ABS | 01.06.24 | 27.06.24 | 27.06.24 | 27.06.24 |  |  |  | 14.07.24 | KUMUTHA@lntecc.com-27.06.2024-16:43:03
Kalburgi | Process | Dewatering Pump | LE200354-P-WS-WT-PR-2268 | LE200354-P-WS-WT-PR-2268-A | MBH | Post-order technically cleared | 58 |  |  |  |  | 31.10.20 | 31.10.23 | 10.11.23 | 17.01.24 | 06.02.24 | 12.02.24 | 23.02.24 |  |  |  |  | 23.02.24 | 23.02.24 | 23.02.24 | T1 | 21.05.24 | MBH | 21.05.24 | 07.06.24 | 07.06.24 | 07.06.24 |  |  |  | 20.07.24 | KUMUTHA@lntecc.com-07.06.2024-11:29:56
Kalburgi | Process | Dissolving tray | LE200354-P-WS-WT-PR-2269 | LE200354-P-WS-WT-PR-2269-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 12.11.20 | [24 empty] | KUMUTHA@lntecc.com-07.06.2024-14:15:25
Kalburgi | Process | Trolley | LE200354-P-WS-WT-PR-2270 | LE200354-P-WS-WT-PR-2270-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 13.11.20 | [24 empty] | KUMUTHA@lntecc.com-07.06.2024-14:17:50
Kalburgi | Process | Platform weighing machine | LE200354-P-WS-WT-PR-2271 | LE200354-P-WS-WT-PR-2271-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 13.11.20 | [24 empty] | KUMUTHA@lntecc.com-07.06.2024-14:16:43
Kalburgi | Process | Exhaust fan | LE200354-P-WS-WT-PR-2272 | LE200354-P-WS-WT-PR-2272-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 30.11.20 | [24 empty] | KUMUTHA@lntecc.com-07.06.2024-14:14:12
Kalburgi | Process | Lab Equipments | LE200354-P-WS-WT-PR-2273 | LE200354-P-WS-WT-PR-2273-A | NA | Regret offer | PR Closed | Site Procurement |  |  |  | 30.11.20 | [24 empty] | KUMUTHA@lntecc.com-07.06.2024-14:21:00
Kalburgi | Process | Inclined Plate Settler plate | LE200354-P-WS-WT-PR-2274 | LE200354-P-WS-WT-PR-2274-A | Sritech | Pre-order technically cleared | 58 |  |  |  |  | 05.10.21 | 24.04.24 | 03.05.24 | 07.06.24 | 07.06.24 | [6 empty] | 07.06.24 | 07.06.24 | 07.06.24 | [8 empty] | 07.06.24 | 24.06.24 | 23.08.24 | KUMUTHA@lntecc.com-01.07.2024-14:41:18
Kalburgi | Process | Inclined Plate Settler plate | LE200354-P-WS-WT-PR-2274 | LE200354-P-WS-WT-PR-2274-B | Cooldeck | Pre-order technically cleared | 81 |  |  |  |  | 05.10.21 | 22.04.24 | 02.05.24 | 04.05.24 | 15.05.24 | [6 empty] | 04.05.24 | 04.05.24 | 15.05.24 | [8 empty] | 07.06.24 | 24.06.24 | 23.08.24 | KUMUTHA@lntecc.com-01.07.2024-14:41:18
Kalburgi | Mechanical | EOT Cranes | LE200354-M-WS-CR-PR-1333 | LE200354-M-WS-CR-PR-1333-A | JAPS | Post-order pending with EDRC | 19 |  | 9825019138 | sales.japs@gmail.com |  | 02.04.21 | 25.01.24 | 10.06.24 | 15.06.24 | [7 empty] | 17.06.24 | 17.06.24 | 17.06.24 | T1 | 16.07.24 | JAPS | 16.07.24 |  |  |  |  | 17.06.24 | 04.07.24 | 02.09.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | EOT Cranes | LE200354-M-WS-CR-PR-1333 | LE200354-M-WS-CR-PR-1333-B | REVA cranes | Regret offer | PR Closed |  | Amita Shah 9899484744 | mkt@revacranes.com, crm@revacranes.com,south@revacranes.com |  | 27.06.24 | 01.07.24 | 02.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Dewatering Pumps | LE200354-M-WS-DW-PR-1337 | LE200354-M-WS-DW-PR-1337-A | Aqua | Pre-order technically cleared | 9 |  | S.T.Sambandam 8144003131 | chennai@aquapumps.com |  | 05.07.24 | 23.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T2 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:05:10
Kalburgi | Mechanical | Dewatering Pumps | LE200354-M-WS-DW-PR-1337 | LE200354-M-WS-DW-PR-1337-B | JASCO | Pre-order technically cleared | 9 |  | Arvish Modi 7069099037 | mailto:hyd@jascopump.com |  | 29.06.24 | 09.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [10 empty] | svcn@lntecc.com-26.07.2024-17:05:30
Kalburgi | Mechanical | HSC Pumps | LE200354-M-WS-HC-PR-1331 | LE200354-M-WS-HC-PR-1331-A | WPIL | Post-order technically cleared | 256 |  | 33 4052 6000 | s.sen@wpil.co.in |  | 31.03.21 | 16.08.23 | 24.08.23 | [8 empty] | 30.08.23 | 30.08.23 | 30.08.23 | T1 | 30.08.23 | WPIL | 07.10.23 | 16.10.23 | 22.11.23 | 22.11.23 |  | 30.08.23 | 16.09.23 | 29.10.23 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Pipe Line Valves | LE200354-M-WS-LV-PR-1335 | LE200354-M-WS-LV-PR-1335-A | MAGWEN | Approved by Client | PR Closed |  | 91769 66481 |  |  | 07.11.22 | 08.11.22 | 08.11.22 | [8 empty] | 09.11.22 | 09.11.22 | 10.11.22 | T1 | 10.11.22 | MAGWEN | 17.11.22 | 23.11.22 | 23.11.22 | 23.11.22 | 29.11.22 | 09.11.22 | 26.11.22 | 09.01.23 | svcn@lntecc.com-03.07.2024-10:40:14
Kalburgi | Mechanical | PRV | LE200354-M-WS-LV-PR-1335 | LE200354-M-WS-LV-PR-1335-B | Dorot | Post-order technically cleared | 123 |  | 91769 66464 | abhishek.mathur@aquestia.com |  | 06.11.23 | 06.11.23 | 18.12.23 | [8 empty] | 02.03.24 | 02.03.24 | 02.03.24 | T1 | 07.03.24 | Dorot | 02.04.24 | 03.04.24 | 03.04.24 | 03.04.24 | 03.04.24 | 02.03.24 | 19.03.24 | 06.05.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Pump house valves | LE200354-M-WS-PV-PR-1334 | LE200354-M-WS-PV-PR-1334-A | AVK | Post-order technically cleared | 78 |  | 91769 66455 | subhash@avkindia.com |  | 02.04.21 | 08.11.23 | 08.11.23 | [8 empty] | 08.11.23 | 08.11.23 | 08.11.23 | T1 | 08.12.23 | AVK | 09.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  | 08.11.23 | 25.11.23 | 24.01.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | DJ | LE200354-M-WS-PV-PR-1334 | LE200354-M-WS-PV-PR-1334-B | Electrosteel | Post-order technically cleared | 78 |  |  | satyendra.kumar@electrosteel.com; anujkr.maurya@electrosteel.com; animikh.banerjee@electrosteel.com; soumayajit.mukherjee@electrosteel.com |  | 02.04.21 | 02.04.21 | 30.10.23 | [8 empty] | 08.11.23 | 08.11.23 | 08.11.23 | T1 | 08.12.23 | Electrosteel | 09.05.24 | 18.05.24 | 18.05.24 | 18.05.24 |  | 08.11.23 | 25.11.23 | 24.01.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | DPCV | LE200354-M-WS-PV-PR-1334 | LE200354-M-WS-PV-PR-1334-C | R&D | Post-order technically cleared | 240 |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 02.04.21 | 02.04.21 | 17.06.23 | [8 empty] | 05.08.23 | 05.08.23 | 05.08.23 | T1 | 30.09.23 | R&D | 30.11.23 | 07.12.23 | 08.12.23 | 08.12.23 |  | 05.08.23 | 22.08.23 | 21.10.23 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Sluice Gate | LE200354-M-WS-SG-PR-1332 | LE200354-M-WS-SG-PR-1332-A | JASH | Pre-order technically cleared | 58 |  | 91-72900 40772 | lpgsouth2@jashindia.com |  | 28.10.20 | 28.10.20 | 07.03.24 | 07.03.24 | 07.06.24 | [6 empty] | 07.06.24 | 07.03.24 | 07.06.24 | T1 | [7 empty] | 07.06.24 | 24.06.24 | 23.08.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Sluice Gate | LE200354-M-WS-SG-PR-1332 | LE200354-M-WS-SG-PR-1332-B | IVC | Regret offer | PR Closed |  | Sudip Ghosh | sudip.ghosh@ivc-valves.com |  | 28.10.20 | 28.10.20 | 23.01.24 | [19 empty] | 28.10.20 | 14.11.20 | 13.01.21 | svcn@lntecc.com-02.07.2024-10:54:26
Kalburgi | Mechanical | ELSR Valves | LE200354-M-WS-SG-PR-1342 | LE200354-M-WS-SG-PR-1342-A | R&D | Approved by Client | PR Closed |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 12.12.20 | 09.02.24 | 12.02.24 | [8 empty] | 17.04.24 | 17.04.24 | 17.04.24 | T1 | 20.04.24 | R&D | 04.05.24 | 04.05.24 | 04.05.24 | 04.05.24 | 19.05.24 | 17.04.24 | 04.05.24 | 19.06.24 | svcn@lntecc.com-03.07.2024-10:40:14
Kalburgi | Mechanical | WTP Valves | LE200354-M-WS-SG-PR-1343 | LE200354-M-WS-SG-PR-1343-A | R&D | Pre-order technically cleared | 48 |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 30.05.24 | 30.05.24 | 17.06.24 | [8 empty] | 14.06.24 | 17.06.24 | 17.06.24 | [8 empty] | 14.06.24 | 01.07.24 | 30.08.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | FCV | LE200354-M-WS-SG-PR-1344 | LE200354-M-WS-SG-PR-1344-A | AVK | Post-order technically cleared | 177 |  | 91769 66455 | subhash@avkindia.com |  | 10.07.23 | 03.07.23 | 03.07.23 | [8 empty] | 09.02.24 | 09.02.24 | 09.02.24 | T1 | 01.08.23 | AVK | 04.08.23 | 09.08.23 | 09.08.23 | 09.08.23 |  | 09.02.24 | 26.02.24 | 30.09.23 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Surge Equipments | LE200354-M-WS-SV-PR-1336 | LE200354-M-WS-SV-PR-1336-A | Sigmaflow | Post-order technically cleared | 135 |  | Jagadesh | jagadesh@sigmaflow.in |  | 12.07.23 | 31.01.24 | 08.02.24 | [8 empty] | 08.02.24 | 08.02.24 | 08.02.24 | T1 | 12.03.24 | Sigmaflow | 13.03.24 | 22.03.24 | 22.03.24 | 22.03.24 |  | 08.02.24 | 25.02.24 | 25.04.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Surge Equipments | LE200354-M-WS-SV-PR-1336 | LE200354-M-WS-SV-PR-1336-B | AVK | Post-order technically cleared | 135 |  | 91769 66455 | subhash@avkindia.com |  | 12.07.23 | 12.12.23 | 16.12.23 | [8 empty] | 08.02.24 | 08.02.24 | 08.02.24 | T1 | 12.03.24 | AVK | 13.03.24 | 22.03.24 | 22.03.24 | 22.03.24 |  | 08.02.24 | 25.02.24 | 25.04.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | VT pumps-Intake | LE200354-M-WS-VT-PR-1330 | LE200354-M-WS-VT-PR-1330-A | WILO | Approved by Client | PR Closed |  | 86800 68301 | manikkandan.pr@wilo.com |  | 31.03.21 | 06.02.23 | 09.02.23 | [8 empty] | 15.02.24 | 15.02.24 | 15.02.24 | T1 | 15.02.24 | WILO | 16.02.24 | 18.02.24 | 18.02.24 | 18.02.24 | 29.03.24 | 15.02.24 | 03.03.24 | 15.04.24 | svcn@lntecc.com-03.07.2024-10:40:14
Kalburgi | Mechanical | VT pumps | LE200354-M-WS-VT-PR-1330 | LE200354-M-WS-VT-PR-1330-B | KBL | Approved by Client | PR Closed |  | 86696 64820 | azharuddin.tamboli@kbl.co.in |  | 31.03.21 | 06.02.23 | 09.02.23 | [8 empty] | 15.02.24 | 15.02.24 | 15.02.24 | T1 | 15.02.24 | KBL | 16.02.24 | 18.02.24 | 18.02.24 | 18.02.24 | 29.03.24 | 15.02.24 | 03.03.24 | 15.04.24 | svcn@lntecc.com-03.07.2024-10:40:14
Kalburgi | Mechanical | Exhaust Fans | LE200354-M-WS-VT-PR-1338 | LE200354-M-WS-VT-PR-1338-A |  | Enquiry yet to float | NA | [26 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-03.07.2024-14:56:08
Kalburgi | Mechanical | Submersible Pumps | LE200354-M-WS-VT-PR-1339 | LE200354-M-WS-VT-PR-1339-A | WPIL | Sent to BU Operations | 256 | Post order cleared. HSC pump converted to submersible pump. Submersible pumps NOT CLEARED for WPIL. | 33 4052 6000 | s.sen@wpil.co.in |  | 11.07.23 | 16.08.23 | 24.08.23 | [8 empty] | 30.08.23 | 30.08.23 | 30.08.23 | T1 | 01.09.23 | WPIL | 07.10.23 | 16.10.23 | 22.11.23 | 22.11.23 |  | 30.08.23 | 16.09.23 | 31.10.23 | svcn@lntecc.com-26.07.2024-17:31:00
Kalburgi | Mechanical | Submersible Pumps | LE200354-M-WS-VT-PR-1339 | LE200354-M-WS-VT-PR-1339-B | Aqua | Pre-order technically cleared | 10 |  | S.T.Sambandam 8144003131 | chennai@aquapumps.com |  | 05.07.24 | 23.07.24 | 25.07.24 | [8 empty] | 25.07.24 | 25.07.24 | 25.07.24 | T2 | [10 empty] | svcn@lntecc.com-26.07.2024-17:31:00
Kalburgi | Mechanical | Submersible Pumps | LE200354-M-WS-VT-PR-1339 | LE200354-M-WS-VT-PR-1339-C | JASCO | Pre-order technically cleared | 9 |  | Arvish Modi 7069099037 | mailto:hyd@jascopump.com |  | 29.06.24 | 09.07.24 | 26.07.24 | [8 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [10 empty] | svcn@lntecc.com-26.07.2024-17:31:00
Kalburgi | Mechanical | Submersible Pumps | LE200354-M-WS-VT-PR-1339 | LE200354-M-WS-VT-PR-1339-D | MBH Pumps | Pre-order technically cleared | 7 |  | Naresh Koul 99200 13772 | northindustrial@mbhpumps.com |  | 28.07.24 | 05.07.24 | 11.07.24 | 19.07.24 | 25.07.24 | [6 empty] | 25.07.24 | 25.07.24 | 25.07.24 | T3 | [10 empty] | svcn@lntecc.com-26.07.2024-17:31:00
Kalburgi | Mechanical | Stop lock Gate | LE200354-M-WS-VT-PR-1340 | LE200354-M-WS-VT-PR-1340-A | Triveni | Pre-order technically cleared | 26 |  | Gaurav Dhiman +91 9953317091 | gauravdhiman@projects.trivenigroup.com |  | 17.06.24 | 08.07.24 | 09.07.24 | [8 empty] | 09.07.24 | 08.07.24 | 09.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Stop lock Gate | LE200354-M-WS-VT-PR-1340 | LE200354-M-WS-VT-PR-1340-B | JASH | Pre-order technically cleared | 33 |  | 9826644554 | iipgmarketing@jashindia.com | 11.03.23 | 17.06.24 | 24.06.24 | 02.07.24 | [8 empty] | 02.07.24 | 02.07.24 | 02.07.24 | T1 | [7 empty] | 02.07.24 | 19.07.24 | 17.09.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Trash rack | LE200354-M-WS-VT-PR-1341 | LE200354-M-WS-VT-PR-1341-A | Triveni | Pre-order technically cleared | 26 |  | Gaurav Dhiman +91 9953317091 | gauravdhiman@projects.trivenigroup.com |  | 17.06.24 | 08.07.24 | 09.07.24 | [8 empty] | 09.07.24 | 08.07.24 | 09.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Mechanical | Trash rack | LE200354-M-WS-VT-PR-1341 | LE200354-M-WS-VT-PR-1341-B | JASH | Pre-order technically cleared | 33 |  | 9826644554 | iipgmarketing@jashindia.com | 11.03.23 | 17.06.24 | 24.06.24 | 02.07.24 | [8 empty] | 02.07.24 | 02.07.24 | 02.07.24 | T1 | [7 empty] | 02.07.24 | 19.07.24 | 17.09.24 | svcn@lntecc.com-26.07.2024-17:03:10
Kalburgi | Instrumentation | Float and Board Level Indicator | LE200354-I-WS-PR-FB-5117 | LE200354-I-WS-PR-FB-5117-A | SBEM | Sent to BU Operations | 40 |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 05.03.22 | 29.09.23 | 25.03.24 | 08.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T1 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | Float and Board Level Indicator | LE200354-I-WS-PR-FB-5117 | LE200354-I-WS-PR-FB-5117-B | Pune Techtrol | Pre-order technically rejected | PR Closed |  | Shanmugasundari | sales.techtrol@measurecon.co.in | 01.01.22 | 05.03.22 | 19.02.24 | 25.03.24 | [22 empty] | mehernani@lntecc.com-01.07.2024-16:32:29
Kalburgi | Instrumentation | Float and Board Level Indicator | LE200354-I-WS-PR-FB-5117 | LE200354-I-WS-PR-FB-5117-C | Scientific Devices | Sent to BU Operations | 40 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 05.03.22 | 16.11.23 | 25.03.24 | 10.06.24 | [7 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T2 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | PLC & SCADA | LE200354-I-WS-PR-PL-5516 | LE200354-I-WS-PR-PL-5516-A | Schnedier | Sent to BU Operations | 317 |  | Rusheyandr | rushyendhar.repalli@se.com | 01.01.22 | 30.07.22 | 30.06.23 | 01.07.23 | 10.08.23 | [7 empty] | 22.09.23 | 22.09.23 | 22.09.23 | T1 | [7 empty] | 22.09.23 | 09.10.23 | 08.12.23 | mehernani@lntecc.com-11.07.2024-13:07:41
Kalburgi | Instrumentation | PLC & SCADA | LE200354-I-WS-PR-PL-5516 | LE200354-I-WS-PR-PL-5516-B | Honeywell | Sent to BU Operations | 258 |  | Vinod Janarthan | vinod.janarthan@Honeywell.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 13.11.23 | [7 empty] | 17.11.23 | 17.11.23 | 20.11.23 | T2 | [7 empty] | 17.11.23 | 04.12.23 | 02.02.24 | mehernani@lntecc.com-11.07.2024-12:52:47
Kalburgi | Instrumentation | PLC & SCADA | LE200354-I-WS-PR-PL-5516 | LE200354-I-WS-PR-PL-5516-C | Mitsubushi | Pre-order technically rejected | PR Closed |  | Sudarsan.Gupta | Sudarsan.Gupta@asia.meap.com | 01.01.22 | 30.07.22 | 13.12.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | PLC & SCADA | LE200354-I-WS-PR-PL-5516 | LE200354-I-WS-PR-PL-5516-D | Sai applied technologies pvt limited | Pre-order technically rejected | PR Closed |  | Sweta Parvatiya | mktg@saiapplied.com | 01.01.22 | 30.07.22 | 01.11.23 | [23 empty] | mehernani@lntecc.com-14.05.2024-14:49:06
Kalburgi | Instrumentation | UPS | LE200354-I-WS-PR-UP-5518 | LE200354-I-WS-PR-UP-5518-A | Liveline India | Sent to BU Operations | 55 | Technical clearance given. However final clearance shall be given after PLC vendor finalization |  | sales2@livelineindia.com | 01.01.22 | 29.05.24 | 30.05.24 | 30.05.24 | [8 empty] | 10.06.24 | 10.06.24 | 10.06.24 | T1 | [7 empty] | 10.06.24 | 27.06.24 | 26.08.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | UPS | LE200354-I-WS-PR-UP-5518 | LE200354-I-WS-PR-UP-5518-B | Hitachihirel | Sent to BU Operations | 55 | Technical clearance given. However final clearance shall be given after PLC vendor finalization |  | balakumaran_s@hitachi-hirel.com |  | 29.05.24 | 05.06.24 | 05.06.24 | [8 empty] | 08.06.24 | 08.06.24 | 10.06.24 | T1 | [7 empty] | 08.06.24 | 25.06.24 | 24.08.24 | mehernani@lntecc.com-11.07.2024-12:52:47
Kalburgi | Instrumentation | UPS | LE200354-I-WS-PR-UP-5518 | LE200354-I-WS-PR-UP-5518-C | Vertiv | Pre-order pending with EDRC | 30 |  |  | K.Shivakumar@vertiv.com |  | 29.11.23 | 05.07.24 | [20 empty] | 12.07.24 | 29.07.24 | 27.09.24 | mehernani@lntecc.com-11.07.2024-12:29:21
Kalburgi | Instrumentation | Pressure transmitter | LE200354-I-WS-WT-PR-5103 | LE200354-I-WS-WT-PR-5103-A | Eximp | Sent to BU Operations | PR Closed |  | Jayakrishnan Pallath | Jayakrishnan.Pallath@eximpinc.com | 03.03.22 | 03.03.22 | 14.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 17.03.22 | 17.03.22 | 20.03.22 | T4 | [7 empty] | 17.03.22 | 03.04.22 | 02.06.22 | mehernani@lntecc.com-01.07.2024-16:13:31
Kalburgi | Instrumentation | Pressure transmitter | LE200354-I-WS-WT-PR-5103 | LE200354-I-WS-WT-PR-5103-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 03.03.22 | 03.03.22 | 09.03.22 | 18.03.22 | [8 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T2 | [7 empty] | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-16:13:31
Kalburgi | Instrumentation | Pressure transmitter | LE200354-I-WS-WT-PR-5103 | LE200354-I-WS-WT-PR-5103-C | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 03.03.22 | 03.03.22 | 08.03.22 | 16.03.22 | [8 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-16:13:31
Kalburgi | Instrumentation | Pressure transmitter | LE200354-I-WS-WT-PR-5103 | LE200354-I-WS-WT-PR-5103-D | Siemens | Post-order technically cleared | 683 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 03.03.22 | 03.03.22 | 16.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T1 | 14.09.22 | Siemens | 20.09.22 | 21.09.22 | 21.09.22 | 21.09.22 |  | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-11.07.2024-12:52:46
Kalburgi | Instrumentation | Electromagnetic Flowmeter | LE200354-I-WS-WT-PR-5114 | LE200354-I-WS-WT-PR-5114-A | Khrone | Approved by Client | PR Closed |  | Diliban | dilibanr@forbesmarshall.com | 02.03.22 | 02.03.22 | 07.03.22 | 14.03.22 | 18.03.22 | [7 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T1 | 30.08.22 | Khrone | 06.08.22 | 18.08.22 | 18.08.22 | 18.08.22 | 01.04.24 | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-16:12:16
Kalburgi | Instrumentation | Electromagnetic Flowmeter | LE200354-I-WS-WT-PR-5114 | LE200354-I-WS-WT-PR-5114-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 02.03.22 | 02.03.22 | 15.03.22 | 15.03.22 | 16.06.22 | [7 empty] | 16.06.22 | 16.06.22 | 20.03.22 | T2 | [7 empty] | 18.03.22 | 04.04.22 | 03.06.22 | mehernani@lntecc.com-01.07.2024-16:12:16
Kalburgi | Instrumentation | Electromagnetic Flowmeter | LE200354-I-WS-WT-PR-5114 | LE200354-I-WS-WT-PR-5114-C | ABB | Sent to BU Operations | PR Closed |  | Krishnakishore | krishna.kishore@in.abb.com | 02.03.22 | 02.03.22 | 07.03.22 | 14.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-16:12:16
Kalburgi | Instrumentation | Electromagnetic Flowmeter | LE200354-I-WS-WT-PR-5114 | LE200354-I-WS-WT-PR-5114-D | Siemens | Sent to BU Operations | PR Closed |  | Guruswamy Keerthi | keerthi.guruswamy.ext@siemens.com | 02.03.22 | 02.03.22 | 08.03.22 | 14.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T4 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-16:12:16
Kalburgi | Instrumentation | Pressure Gauge | LE200354-I-WS-WT-PR-5501 | LE200354-I-WS-WT-PR-5501-A | Hguru | Sent to BU Operations | 207 |  | H Guru | info@hgurusouth.com | 01.01.22 | 30.07.22 | 08.11.23 | 10.01.24 | [8 empty] | 10.01.24 | 10.01.24 | 10.01.24 | T1 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | mehernani@lntecc.com-11.07.2024-12:52:47
Kalburgi | Instrumentation | Pressure Gauge | LE200354-I-WS-WT-PR-5501 | LE200354-I-WS-WT-PR-5501-B | Scientific devices | Sent to BU Operations | 207 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 30.07.22 | 16.11.23 | 10.01.24 | [8 empty] | 10.01.24 | 10.01.24 | 10.01.24 | T2 | [7 empty] | 10.01.24 | 27.01.24 | 27.03.24 | mehernani@lntecc.com-11.07.2024-12:52:47
Kalburgi | Instrumentation | Pressure Gauge | LE200354-I-WS-WT-PR-5501 | LE200354-I-WS-WT-PR-5501-C | GIC | Regret offer | PR Closed |  | Dinabandhu Bhatta | gicchennai@general-gauges.com | 01.01.22 | 30.07.22 | 14.11.23 | 14.11.23 | [22 empty] | mehernani@lntecc.com-11.06.2024-09:11:27
Kalburgi | Instrumentation | Pressure Gauge | LE200354-I-WS-WT-PR-5501 | LE200354-I-WS-WT-PR-5501-D | Forbes marshall | Sent to BU Operations | 132 |  | R, DILIBAN. | dilibanr@forbesmarshall.com | 01.01.22 | 30.07.22 | 20.11.23 | 10.01.24 | 19.02.24 | [7 empty] | 25.03.24 | 25.03.24 | 25.03.24 | T3 | [7 empty] | 25.03.24 | 11.04.24 | 10.06.24 | mehernani@lntecc.com-11.07.2024-12:52:47
Kalburgi | Instrumentation | Ultrasonic Flow transmitter | LE200354-I-WS-WT-PR-5507 | LE200354-I-WS-WT-PR-5507-A | SBEM | Pre-order technically rejected | PR Closed |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 30.07.22 | 29.09.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | Ultrasonic Flow transmitter | LE200354-I-WS-WT-PR-5507 | LE200354-I-WS-WT-PR-5507-B | Siemens | Sent to BU Operations | 132 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 01.01.22 | 30.07.22 | 09.11.23 | 14.12.23 | 25.03.24 | [7 empty] | 25.03.24 | 25.03.24 | 25.03.24 | T1 | [7 empty] | 25.03.24 | 11.04.24 | 10.06.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | Rate of flowmeter | LE200354-I-WS-WT-PR-5509 | LE200354-I-WS-WT-PR-5509-A | SBEM | Pre-order technically rejected | PR Closed |  | Rajesh | rajesh.p@sbem.co.in | 01.01.22 | 30.07.22 | 29.09.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | Rate of flowmeter | LE200354-I-WS-WT-PR-5509 | LE200354-I-WS-WT-PR-5509-B | Siemens | Sent to BU Operations | 234 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 01.01.22 | 30.07.22 | 09.11.23 | 14.12.23 | [8 empty] | 14.12.23 | 14.12.23 | 14.12.23 | T1 | [8 empty] | 28.07.24 | 26.09.24 | mehernani@lntecc.com-11.07.2024-12:52:47
Kalburgi | Instrumentation | Bypass Rotameter | LE200354-I-WS-WT-PR-5510 | LE200354-I-WS-WT-PR-5510-A | Scientific devices | Sent to BU Operations | 211 |  | Shaheen | info@scientificdevices.org | 01.01.22 | 30.07.22 | 16.11.23 | 06.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 06.01.24 | T1 | [7 empty] | 06.01.24 | 23.01.24 | 23.03.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | Bypass Rotameter | LE200354-I-WS-WT-PR-5510 | LE200354-I-WS-WT-PR-5510-B | Eureka | Sent to BU Operations | 211 |  | S.Kumar | chennaioffice@eurekaflow.com | 01.01.22 | 30.07.22 | 24.11.23 | 06.01.24 | [8 empty] | 06.01.24 | 06.01.24 | 06.01.24 | T2 | [7 empty] | 06.01.24 | 23.01.24 | 23.03.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | Ph Analyser | LE200354-I-WS-WT-PR-5511 | LE200354-I-WS-WT-PR-5511-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-16:19:32
Kalburgi | Instrumentation | Ph Analyser | LE200354-I-WS-WT-PR-5511 | LE200354-I-WS-WT-PR-5511-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | Ph Analyser | LE200354-I-WS-WT-PR-5511 | LE200354-I-WS-WT-PR-5511-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-14.05.2024-14:49:06
Kalburgi | Instrumentation | Ph Analyser | LE200354-I-WS-WT-PR-5511 | LE200354-I-WS-WT-PR-5511-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 10.03.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-11.07.2024-12:52:46
Kalburgi | Instrumentation | Ph Analyser | LE200354-I-WS-WT-PR-5511 | LE200354-I-WS-WT-PR-5511-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 16.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-16:19:32
Kalburgi | Instrumentation | Ph Analyser | LE200354-I-WS-WT-PR-5511 | LE200354-I-WS-WT-PR-5511-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | Turbidity Analyser | LE200354-I-WS-WT-PR-5512 | LE200354-I-WS-WT-PR-5512-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-16:25:07
Kalburgi | Instrumentation | Turbidity Analyser | LE200354-I-WS-WT-PR-5512 | LE200354-I-WS-WT-PR-5512-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | Turbidity Analyser | LE200354-I-WS-WT-PR-5512 | LE200354-I-WS-WT-PR-5512-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-14.05.2024-14:49:06
Kalburgi | Instrumentation | Turbidity Analyser | LE200354-I-WS-WT-PR-5512 | LE200354-I-WS-WT-PR-5512-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 10.03.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-11.07.2024-12:52:47
Kalburgi | Instrumentation | Turbidity Analyser | LE200354-I-WS-WT-PR-5512 | LE200354-I-WS-WT-PR-5512-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 16.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-16:25:07
Kalburgi | Instrumentation | Turbidity Analyser | LE200354-I-WS-WT-PR-5512 | LE200354-I-WS-WT-PR-5512-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | RCL Analyser | LE200354-I-WS-WT-PR-5513 | LE200354-I-WS-WT-PR-5513-A | Xylem | Sent to BU Operations | PR Closed |  | Tanishq Raj | tanishq@errandenterprises.com | 01.01.22 | 30.07.22 | 31.10.23 | 01.11.23 | 02.11.23 | 02.11.23 | 04.11.23 | [5 empty] | 04.11.23 | 04.11.23 | 07.11.23 | T2 | [7 empty] | 04.11.23 | 21.11.23 | 20.01.24 | mehernani@lntecc.com-01.07.2024-16:23:09
Kalburgi | Instrumentation | RCL Analyser | LE200354-I-WS-WT-PR-5513 | LE200354-I-WS-WT-PR-5513-B | Yukogawa | Pre-order technically rejected | PR Closed |  | Ramkumar | p.ramkumar@yokogawa.com | 01.01.22 | 30.07.22 | 04.09.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | RCL Analyser | LE200354-I-WS-WT-PR-5513 | LE200354-I-WS-WT-PR-5513-C | Hach | Pre-order technically rejected | PR Closed |  | Mohan | mohanraj.elumalai@hach.com | 01.01.22 | 30.07.22 | 13.04.23 | [23 empty] | mehernani@lntecc.com-14.05.2024-14:49:06
Kalburgi | Instrumentation | RCL Analyser | LE200354-I-WS-WT-PR-5513 | LE200354-I-WS-WT-PR-5513-D | E&H | Post-order technically cleared | 80 |  | Harinarayan | hari.narayan@endress.com | 01.01.22 | 30.07.22 | 25.05.23 | 26.05.23 | 02.06.23 | 02.06.23 | 07.09.23 | [5 empty] | 07.09.23 | 07.09.23 | 10.09.23 | T1 | 10.03.24 | E&H | 10.04.24 | 16.05.24 | 16.05.24 | 16.05.24 |  | 07.09.23 | 24.09.23 | 23.11.23 | mehernani@lntecc.com-11.07.2024-12:52:47
Kalburgi | Instrumentation | RCL Analyser | LE200354-I-WS-WT-PR-5513 | LE200354-I-WS-WT-PR-5513-E | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 01.01.22 | 30.07.22 | 13.03.24 | 13.03.24 | 13.03.24 | 14.03.24 | 14.03.24 | 15.03.24 |  |  |  |  | 15.03.24 | 15.03.24 | 16.03.24 | T3 | [7 empty] | 15.03.24 | 01.04.24 | 31.05.24 | mehernani@lntecc.com-01.07.2024-16:23:09
Kalburgi | Instrumentation | RCL Analyser | LE200354-I-WS-WT-PR-5513 | LE200354-I-WS-WT-PR-5513-F | Emerson | Pre-order technically rejected | PR Closed |  | Vinod Tony | Vinod.Tony@Emerson.com | 01.01.22 | 30.07.22 | 01.12.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | Battery Operated Datalogger | LE200354-I-WS-WT-PR-5519 | LE200354-I-WS-WT-PR-5519-A | Enviro | Sent to BU Operations | PR Closed |  | Sharad | Water.div@envirosafety.in | 25.08.22 | 29.08.22 | 03.09.22 | 16.09.22 | 19.09.22 | 19.09.22 | [6 empty] | 10.05.23 | 10.05.23 | 14.08.23 | T2 | [7 empty] | 10.05.23 | 27.05.23 | 26.07.23 | mehernani@lntecc.com-01.07.2024-16:27:20
Kalburgi | Instrumentation | Battery Operated Datalogger | LE200354-I-WS-WT-PR-5519 | LE200354-I-WS-WT-PR-5519-B | GSV Microtech | Post-order technically cleared | 232 |  | Manikandan A | sales@gsv-microtech.com | 25.08.22 | 29.08.22 | 16.06.23 | 04.08.23 | [8 empty] | 04.08.23 | 04.08.23 | 14.08.23 | T1 | 20.10.23 | GSV Microtech | 02.12.23 | 16.12.23 | 16.12.23 | 16.12.23 |  | 04.08.23 | 21.08.23 | 20.10.23 | mehernani@lntecc.com-11.07.2024-12:52:46
Kalburgi | Instrumentation | Cables | LE21M354-I-WS-PR-CA-5517 | LE21M354-I-WS-PR-CA-5517-A | Cords | Sent to BU Operations | 40 |  |  | hp@cordscable.com |  | 29.05.24 | 11.06.24 | 17.06.24 | 22.06.24 | [7 empty] | 22.06.24 | 22.06.24 | 25.06.24 | T1 | [7 empty] | 22.06.24 | 09.07.24 | 07.09.24 | mehernani@lntecc.com-11.07.2024-12:52:46
Kalburgi | Instrumentation | Cables | LE21M354-I-WS-PR-CA-5517 | LE21M354-I-WS-PR-CA-5517-B | PVESPL | Regret offer | PR Closed |  |  | pvespl@vashiisl.com |  | 29.05.24 | 09.06.24 | 11.06.24 | [22 empty] | mehernani@lntecc.com-11.07.2024-12:29:21
Kalburgi | Instrumentation | Cables | LE21M354-I-WS-PR-CA-5517 | LE21M354-I-WS-PR-CA-5517-C | Gemscab | Sent to BU Operations | 40 |  |  | mrawoof@gemscab.com |  | 11.06.24 | 19.06.24 | 19.06.24 | [8 empty] | 25.06.24 | 25.06.24 | 25.06.24 | T2 | [7 empty] | 25.06.24 | 12.07.24 | 10.09.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | Vibration Monitoring System | LE21M354-I-WS-WT-VMS-5521 | LE21M354-I-WS-WT-VMS-5521-A | Preipolar | Pre-order technically rejected | PR Closed |  | Sivanesh G | sivanesh@preipolar.com | 01.01.22 | 16.09.23 | 16.11.23 | [23 empty] | mehernani@lntecc.com-24.05.2024-11:32:02
Kalburgi | Instrumentation | Vibration Monitoring System | LE21M354-I-WS-WT-VMS-5521 | LE21M354-I-WS-WT-VMS-5521-B | Centum | Sent to BU Operations | 233 |  | Akhil suresh | akhil@centumcontrols.com | 01.01.22 | 16.09.23 | 29.11.23 | 15.12.23 | [8 empty] | 15.12.23 | 15.12.23 | 15.12.23 | T1 | [7 empty] | 15.12.23 | 01.01.24 | 01.03.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | Vibration Monitoring System | LE21M354-I-WS-WT-VMS-5521 | LE21M354-I-WS-WT-VMS-5521-C | Forbes marshall | Sent to BU Operations | 233 |  | Pallavi Gajbhiye | pgajbhiye@forbesmarshall.com | 01.01.22 | 16.09.23 | 29.11.23 | 15.12.23 | [8 empty] | 15.12.23 | 15.12.23 | 15.12.23 | T2 | [7 empty] | 15.12.23 | 01.01.24 | 01.03.24 | mehernani@lntecc.com-11.07.2024-12:45:51
Kalburgi | Instrumentation | Water meter | LEE00354-I-WS-PR-WT-5523 | LEE00354-I-WS-PR-WT-5523-A | Venus | Approved by Client | PR Closed |  | A S JAYARAMA | gm_venusmeters@yahoo.com |  | 20.01.24 | 20.01.24 | 31.01.24 | [8 empty] | 16.02.24 | 16.02.24 | 18.02.24 | T1 | 15.05.24 | Venus | 14.03.24 | 15.03.24 | 15.03.24 | 15.03.24 | 13.05.24 | 16.02.24 | 04.03.24 | 03.05.24 | mehernani@lntecc.com-01.07.2024-16:42:19
Kalburgi | Instrumentation | Ultrasonic Level Transmitter | LEE200354-I-WS-PR-LT-5116 | LEE200354-I-WS-PR-LT-5116-A | Eximp | Sent to BU Operations | PR Closed |  | Jayakrishnan Pallath | Jayakrishnan.Pallath@eximpinc.com | 03.03.22 | 03.03.22 | 14.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 17.03.22 | 17.03.22 | 20.03.22 | T4 | [7 empty] | 17.03.22 | 03.04.22 | 02.06.22 | mehernani@lntecc.com-01.07.2024-16:15:55
Kalburgi | Instrumentation | Ultrasonic Level Transmitter | LEE200354-I-WS-PR-LT-5116 | LEE200354-I-WS-PR-LT-5116-B | E&H | Sent to BU Operations | PR Closed |  | Harinarayan | hari.narayan@endress.com | 03.03.22 | 03.03.22 | 09.03.22 | 18.03.22 | [8 empty] | 18.03.22 | 18.03.22 | 20.03.22 | T2 | [7 empty] | 28.03.22 | 14.04.22 | 13.06.22 | mehernani@lntecc.com-01.07.2024-16:15:55
Kalburgi | Instrumentation | Ultrasonic Level Transmitter | LEE200354-I-WS-PR-LT-5116 | LEE200354-I-WS-PR-LT-5116-C | ABB | Sent to BU Operations | PR Closed |  | Krishna kishore ABB | krishna.kishore@in.abb.com | 03.03.22 | 03.03.22 | 08.03.22 | 16.03.22 | [8 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T3 | [7 empty] | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-01.07.2024-16:15:55
Kalburgi | Instrumentation | Ultrasonic Level Transmitter | LEE200354-I-WS-PR-LT-5116 | LEE200354-I-WS-PR-LT-5116-D | Siemens | Post-order technically cleared | 683 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 03.03.22 | 03.03.22 | 16.03.22 | 16.03.22 | 16.03.22 | [7 empty] | 16.03.22 | 16.03.22 | 20.03.22 | T1 | 14.09.22 | Siemens | 20.09.22 | 21.09.22 | 21.09.22 | 21.09.22 |  | 16.03.22 | 02.04.22 | 01.06.22 | mehernani@lntecc.com-11.07.2024-12:52:46
Kalburgi | Electrical | Switchyard equipments | LE200354-E-WS-CW-PR-4129 | LE200354-E-WS-CW-PR-4129-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | 30.10.23 | 01.11.23 | 06.11.23 | [21 empty] | usman.mohideen@lntecc.com-03.06.2024-15:37:09
Kalburgi | Electrical | Switchyard equipments | LE200354-E-WS-CW-PR-4129 | LE200354-E-WS-CW-PR-4129-B | Govind Electricals | Regret offer | PR Closed |  |  |  |  | 10.05.24 | 03.05.24 | 08.05.24 | [22 empty] | usman.mohideen@lntecc.com-03.06.2024-15:37:09
Kalburgi | Electrical | Transformer | LE200354-E-WS-CW-PR-4131 | LE200354-E-WS-CW-PR-4131-A | Voltech | Pre-order comments issued | 272 |  |  |  |  | 21.10.23 | 30.10.23 | 01.11.23 | 06.11.23 | [10 empty] | T1 | [7 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | Transformer | LE200354-E-WS-CW-PR-4131 | LE200354-E-WS-CW-PR-4131-B | Transcon | Pre-order comments issued | 45 |  |  |  |  | 29.04.24 | 03.05.24 | 08.05.24 | 15.06.24 | 20.06.24 | [17 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | Transformer | LE200354-E-WS-CW-PR-4131 | LE200354-E-WS-CW-PR-4131-C | Telawne | Pre-order comments issued | 265 |  |  |  |  | 21.10.23 | 31.10.23 | 01.11.23 | 06.11.23 | 13.11.23 | [17 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | Transformer | LE200354-E-WS-CW-PR-4131 | LE200354-E-WS-CW-PR-4131-D | Uttam Bharath | Pre-order comments issued | 274 |  |  |  |  | 21.10.23 | 26.10.23 | 04.11.23 | [11 empty] | T1 | [7 empty] | 26.07.24 | 12.08.24 | 11.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT Switchgear | LE200354-E-WS-CW-PR-4133 | LE200354-E-WS-CW-PR-4133-A | Universal | Regret offer | PR Closed |  |  |  |  | 20.04.24 | 28.04.24 | 30.04.24 | [8 empty] | 04.05.24 | 06.05.24 | [12 empty] | usman.mohideen@lntecc.com-01.07.2024-15:36:57
Kalburgi | Electrical | HT Switchgear | LE200354-E-WS-CW-PR-4133 | LE200354-E-WS-CW-PR-4133-B | Lotus | Sent to BU Operations | 45 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | 20.06.24 | t1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT Switchgear | LE200354-E-WS-CW-PR-4133 | LE200354-E-WS-CW-PR-4133-C | Sun Shine | Sent to BU Operations | 39 |  |  |  |  | 23.04.24 | 17.05.24 | 18.05.24 | 29.05.24 | 01.06.24 | [6 empty] | 01.06.24 | 01.06.24 | 26.06.24 | t1 | [7 empty] | 26.06.24 | 13.07.24 | 11.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT Soft Starters | LE200354-E-WS-CW-PR-4134 | LE200354-E-WS-CW-PR-4134-A | Lecon | Sent to BU Operations | PR Closed |  |  |  |  | 02.03.24 | 18.03.24 | 20.03.24 | 22.04.24 | 25.04.24 | [6 empty] | 23.04.24 | 24.04.24 | 21.05.24 | T1 | [7 empty] | 21.05.24 | 07.06.24 | 06.08.24 | usman.mohideen@lntecc.com-01.07.2024-15:36:57
Kalburgi | Electrical | HT Soft Starters | LE200354-E-WS-CW-PR-4134 | LE200354-E-WS-CW-PR-4134-B | Jaya Shree | Post-order technically cleared | 18 |  |  |  |  | 23.02.24 | 27.03.24 | 01.04.24 | 02.04.24 | 03.04.24 | [6 empty] | 07.05.24 | 10.05.24 | 21.05.24 | T1 | 18.06.24 | Jaya Shree | 20.06.24 | 25.06.24 | 17.07.24 | 17.07.24 |  | 21.05.24 | 07.06.24 | 06.08.24 | usman.mohideen@lntecc.com-17.07.2024-15:53:09
Kalburgi | Electrical | HT Capacitors | LE200354-E-WS-CW-PR-4135 | LE200354-E-WS-CW-PR-4135-A | Madhav Capacitors | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 31.03.24 | 10.04.24 | 23.04.24 | 24.04.24 | [6 empty] | 26.04.24 | 27.04.24 | 27.04.24 | T2 | [7 empty] | 27.04.24 | 14.05.24 | 13.07.24 | usman.mohideen@lntecc.com-01.07.2024-15:36:57
Kalburgi | Electrical | HT Capacitors | LE200354-E-WS-CW-PR-4135 | LE200354-E-WS-CW-PR-4135-B | Lecon | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 27.02.24 | 28.02.24 | 08.03.24 | 20.03.24 | [6 empty] | 22.04.24 | 23.04.24 | 23.04.24 | T2 | 27.05.24 | Lecon | 27.05.24 | 04.06.24 |  |  |  | 23.04.24 | 10.05.24 | 09.07.24 | usman.mohideen@lntecc.com-01.07.2024-15:36:57
Kalburgi | Electrical | HT Capacitors | LE200354-E-WS-CW-PR-4135 | LE200354-E-WS-CW-PR-4135-C | Shreem | Regret offer | PR Closed |  |  |  |  | 23.02.24 | 26.02.24 | 19.03.24 | 26.04.24 | 29.04.24 | [6 empty] | 29.04.24 | 02.05.24 | 02.05.24 | T2 | [7 empty] | 02.05.24 | 19.05.24 | 18.07.24 | usman.mohideen@lntecc.com-01.07.2024-15:36:57
Kalburgi | Electrical | LT Switchgear and Auxiliary Panels | LE200354-E-WS-CW-PR-4136 | LE200354-E-WS-CW-PR-4136-A | Lotus | Sent to BU Operations | 57 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | 08.06.24 | T2 | [7 empty] | 08.06.24 | 25.06.24 | 24.08.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | LT Switchgear and Auxiliary Panels | LE200354-E-WS-CW-PR-4136 | LE200354-E-WS-CW-PR-4136-B | Sunshine | Sent to BU Operations | 39 |  |  |  |  | 05.03.24 | 17.05.24 | 18.05.24 | 28.05.24 | 01.06.24 | [6 empty] | 01.06.24 | 01.06.24 | 26.06.24 | T2 | [7 empty] | 26.06.24 | 13.07.24 | 11.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | LT Switchgear and Auxiliary Panels | LE200354-E-WS-CW-PR-4136 | LE200354-E-WS-CW-PR-4136-C | SRCS | Sent to BU Operations | 45 |  |  |  |  | 05.03.24 | 28.05.24 | 08.06.24 | [8 empty] | 08.06.24 | 08.06.24 | 20.06.24 | t1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | Battery, Battery Charger and DCDB | LE200354-E-WS-CW-PR-4137 | LE200354-E-WS-CW-PR-4137-A | Liveline | Sent to BU Operations | 23 |  |  |  |  | 23.02.24 | 01.05.24 | 17.05.24 | 10.06.24 | 13.06.24 | [6 empty] | 14.06.24 | 14.06.24 | 12.07.24 | t2 | [7 empty] | 24.07.24 | 10.08.24 | 09.10.24 | usman.mohideen@lntecc.com-17.07.2024-15:53:09
Kalburgi | Electrical | Battery, Battery Charger and DCDB | LE200354-E-WS-CW-PR-4137 | LE200354-E-WS-CW-PR-4137-B | Voltech | Sent to BU Operations | 23 |  |  |  |  | 23.02.24 | 24.02.24 | 15.04.24 | 20.04.24 | 25.04.24 | 22.05.24 | 13.06.24 |  |  |  |  | 07.05.24 | 15.05.24 | 12.07.24 | t2 | [7 empty] | 24.07.24 | 10.08.24 | 09.10.24 | usman.mohideen@lntecc.com-17.07.2024-15:53:09
Kalburgi | Electrical | NGR | LE200354-E-WS-CW-PR-4138 | LE200354-E-WS-CW-PR-4138-A | RSI switchgear | Sent to BU Operations | 47 |  |  |  |  | 17.05.24 | 06.06.24 | 08.06.24 | 17.06.24 | 18.06.24 | [6 empty] | 18.06.24 | 18.06.24 | 18.06.24 | t1 | [7 empty] | 18.06.24 | 05.07.24 | 03.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | NGR | LE200354-E-WS-CW-PR-4138 | LE200354-E-WS-CW-PR-4138-B | National Resistors | Sent to BU Operations | 47 |  |  |  |  | 17.05.24 | 04.06.24 | 08.06.24 | 17.06.24 | 18.06.24 | [6 empty] | 08.06.24 | 08.06.24 | 18.06.24 | t1 | [7 empty] | 18.06.24 | 05.07.24 | 03.09.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT and LT Power and Control Cables | LE200354-E-WS-CW-PR-4139 | LE200354-E-WS-CW-PR-4139-A | Gemscab | Sent to BU Operations | 25 |  |  |  |  | 02.03.24 | 11.03.24 | 30.04.24 | 04.05.24 | 07.05.24 | [6 empty] | 10.05.24 | 13.05.24 | 10.07.24 | t1 | [7 empty] | 22.07.24 | 08.08.24 | 07.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT and LT Power and Control Cables | LE200354-E-WS-CW-PR-4139 | LE200354-E-WS-CW-PR-4139-B | Axelon | Sent to BU Operations | 25 |  |  |  |  | 02.03.24 | 02.05.24 | 07.05.24 | 08.05.24 | [7 empty] | 08.05.24 | 09.05.24 | 10.07.24 | t1 | [7 empty] | 22.07.24 | 08.08.24 | 07.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT and LT Power and Control Cables | LE200354-E-WS-CW-PR-4139 | LE200354-E-WS-CW-PR-4139-C | Vishal | Sent to BU Operations | 25 |  |  |  |  | 30.04.24 | 02.05.24 | 07.05.24 | 08.05.24 | [7 empty] | 08.05.24 | 09.05.24 | 10.07.24 | t1 | [7 empty] | 22.07.24 | 08.08.24 | 07.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT and LT Power and Control Cables | LE200354-E-WS-CW-PR-4139 | LE200354-E-WS-CW-PR-4139-D | Havells | Regret offer | PR Closed |  |  |  |  | 30.04.24 | [24 empty] | ananthakrishnan.krishnan@lntecc.com-23.05.2024-11:04:05
Kalburgi | Electrical | HT and LT Power and Control Cables | LE200354-E-WS-CW-PR-4139 | LE200354-E-WS-CW-PR-4139-E | KEI | Sent to BU Operations | 25 |  |  |  |  | 17.05.24 | 20.06.24 | 25.06.24 | 08.07.24 | [7 empty] | 08.07.24 | 08.07.24 | 10.07.24 | t1 | [7 empty] | 22.07.24 | 08.08.24 | 07.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | Cable Trays and Supports | LE200354-E-WS-CW-PR-4140 | LE200354-E-WS-CW-PR-4140-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T3 | [7 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-01.07.2024-15:52:16
Kalburgi | Electrical | Cable Trays and Supports | LE200354-E-WS-CW-PR-4140 | LE200354-E-WS-CW-PR-4140-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT CABLE TERMINATION KITS & LT CABLE LUGS AND GLANDS | LE200354-E-WS-CW-PR-4141 | LE200354-E-WS-CW-PR-4141-A | Monaj Trading | Awaiting pre-offer from vendor | 86 |  |  |  |  | 10.05.24 | [21 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | HT CABLE TERMINATION KITS & LT CABLE LUGS AND GLANDS | LE200354-E-WS-CW-PR-4141 | LE200354-E-WS-CW-PR-4141-B | Govind Electricals | Awaiting pre-offer from vendor | 86 |  |  |  |  | 10.05.24 | [21 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | LPBS | LE200354-E-WS-CW-PR-4142 | LE200354-E-WS-CW-PR-4142-A | Lotus | Sent to BU Operations | 57 |  |  |  |  | 26.10.23 | 06.11.23 | 14.11.23 | 23.12.23 | 10.01.24 | 09.03.24 | [5 empty] | 04.05.24 | 04.05.24 | 08.06.24 | T2 | [7 empty] | 08.06.24 | 25.06.24 | 24.08.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | LPBS | LE200354-E-WS-CW-PR-4142 | LE200354-E-WS-CW-PR-4142-B | Sunshine | Sent to BU Operations | 45 |  |  |  |  | 05.03.24 | 17.05.24 | 18.05.24 | 28.05.24 | 01.06.24 | [6 empty] | 01.06.24 | 01.06.24 | 20.06.24 | T2 | [7 empty] | 26.06.24 | 13.07.24 | 11.09.24 | usman.mohideen@lntecc.com-17.07.2024-15:53:09
Kalburgi | Electrical | LPBS | LE200354-E-WS-CW-PR-4142 | LE200354-E-WS-CW-PR-4142-C | SRCS | Sent to BU Operations | 45 |  |  |  |  | 05.03.24 | 28.05.24 | 08.06.24 | [8 empty] | 08.06.24 | 08.06.24 | 20.06.24 | T2 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | usman.mohideen@lntecc.com-17.07.2024-15:53:09
Kalburgi | Electrical | Earthing and Its Accessories | LE200354-E-WS-CW-PR-4143 | LE200354-E-WS-CW-PR-4143-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [13 empty] | T3 | [7 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-01.07.2024-15:52:16
Kalburgi | Electrical | Earthing and Its Accessories | LE200354-E-WS-CW-PR-4143 | LE200354-E-WS-CW-PR-4143-B | Govind Electricals | Pre-order technically cleared | 59 |  |  |  |  | 10.05.24 | 27.05.24 | 06.06.24 | [8 empty] | 06.06.24 | 06.06.24 |  | T3 | [7 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:01
Kalburgi | Electrical | Lighting System | LE200354-E-WS-CW-PR-4144 | LE200354-E-WS-CW-PR-4144-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [21 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-01.07.2024-15:52:16
Kalburgi | Electrical | Lighting System | LE200354-E-WS-CW-PR-4144 | LE200354-E-WS-CW-PR-4144-B | Govind Electricals | Pre-order technically cleared | 65 |  |  |  |  | 10.05.24 | 27.05.24 | 31.05.24 | [8 empty] | 31.05.24 | 31.05.24 | [9 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:02
Kalburgi | Electrical | Electrical Safety Items | LE200354-E-WS-CW-PR-4145 | LE200354-E-WS-CW-PR-4145-A | Monaj Trading | Regret offer | PR Closed |  |  |  |  | 10.05.24 | [21 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-01.07.2024-15:52:16
Kalburgi | Electrical | Electrical Safety Items | LE200354-E-WS-CW-PR-4145 | LE200354-E-WS-CW-PR-4145-B | Govind Electricals | Pre-order technically cleared | 65 |  |  |  |  | 10.05.24 | 27.05.24 | 31.05.24 | [8 empty] | 31.05.24 | 31.05.24 | [9 empty] | 29.07.24 | 15.08.24 | 14.10.24 | usman.mohideen@lntecc.com-17.07.2024-13:54:02
Kendrapada 2 - Aul & Rajkanika | Process | Clariflocculator mechanism | LE21M277-P-WS-WT-PR-2102 | LE21M277-P-WS-WT-PR-2102-A | Sritech | Pre-order technically rejected | PR Closed |  |  |  | 31.12.21 | 14.07.22 | 09.02.24 | 15.02.24 | 19.03.24 | [7 empty] | 15.02.24 | 21.02.24 | [12 empty] | SNEHA-S@lntecc.com-17.05.2024-10:34:53
Kendrapada 2 - Aul & Rajkanika | Process | Clariflocculator mechanism | LE21M277-P-WS-WT-PR-2102 | LE21M277-P-WS-WT-PR-2102-B | Shivpad | Sent to BU Operations | 61 |  | M. Ragavendar | ragavendar@shivpad.com | 31.12.21 | 06.02.24 | 14.02.24 | 13.03.24 | 18.03.24 | 21.03.24 | 26.03.24 | 29.03.24 | 05.04.24 | 16.04.24 |  |  | 29.04.24 | 03.06.24 | 04.06.24 | T2 | [7 empty] | 04.06.24 | 21.06.24 | 20.08.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Clariflocculator mechanism | LE21M277-P-WS-WT-PR-2102 | LE21M277-P-WS-WT-PR-2102-C | Triveni | Sent to BU Operations | 61 |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 31.12.21 | 06.02.24 | 27.02.24 | 13.03.24 | 23.04.24 | 16.05.24 | [6 empty] | 15.05.24 | 31.05.24 | 04.06.24 | T3 | [7 empty] | 04.06.24 | 21.06.24 | 20.08.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Clariflocculator mechanism | LE21M277-P-WS-WT-PR-2102 | LE21M277-P-WS-WT-PR-2102-D | Filsep | Sent to BU Operations | 61 |  |  | filsepengineers@gmail.com | 31.12.21 | 06.02.24 | 07.05.24 | 10.05.24 | 14.05.24 | 17.05.24 | 27.05.24 | [5 empty] | 27.05.24 | 27.05.24 | 04.06.24 | T1 | [7 empty] | 04.06.24 | 21.06.24 | 20.08.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Air Blower | LE21M277-P-WS-WT-PR-2103 | LE21M277-P-WS-WT-PR-2103-A | Kay Blowers | Awaiting post-offer from vendor | 12 |  | Manish | project@kayblowers.com | 14.07.22 | 06.02.24 | 12.02.24 | 17.02.24 | 16.04.24 | 09.05.24 | 20.05.24 | 24.05.24 |  |  |  |  | 24.05.24 | 24.05.24 | 19.06.24 | T3 | 23.07.24 | Kay Blowers | [5 empty] | 19.06.24 | 06.07.24 | 04.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:31:39
Kendrapada 2 - Aul & Rajkanika | Process | Air Blower | LE21M277-P-WS-WT-PR-2103 | LE21M277-P-WS-WT-PR-2103-B | SWAM | Sent to BU Operations | PR Closed |  | Shailesh Srivastava | shailesh@swamatics.com | 14.07.22 | 06.02.24 | 12.02.24 | 17.02.24 | 12.03.24 | 13.03.24 | 22.03.24 | 25.03.24 |  |  |  |  | 29.04.24 | 29.04.24 | 19.06.24 | T2 | [7 empty] | 19.06.24 | 06.07.24 | 04.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Air Blower | LE21M277-P-WS-WT-PR-2103 | LE21M277-P-WS-WT-PR-2103-C | Everest | Sent to BU Operations | PR Closed |  |  | Saif.Ali@irco.com | 14.07.22 | 06.02.24 | 19.04.24 | 29.04.24 | 27.05.24 | 28.05.24 | 04.06.24 | [5 empty] | 20.06.24 | 20.06.24 | 19.06.24 | T1 | [7 empty] | 19.06.24 | 06.07.24 | 04.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Agitator | LE21M277-P-WS-WT-PR-2104 | LE21M277-P-WS-WT-PR-2104-A | Sritech | Pre-order technically rejected | PR Closed |  |  |  | 25.08.22 | 06.02.24 | 13.02.24 | 13.03.24 | 18.03.24 | 25.03.24 | [20 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:05
Kendrapada 2 - Aul & Rajkanika | Process | Agitator | LE21M277-P-WS-WT-PR-2104 | LE21M277-P-WS-WT-PR-2104-B | Shivpad | Sent to BU Operations | PR Closed |  | M. Ragavendar | ragavendar@shivpad.com | 25.08.22 | 06.02.24 | 22.03.24 | 25.03.24 | 05.04.24 | [7 empty] | 18.04.24 | 18.04.24 | 21.06.24 | T1 | [7 empty] | 21.06.24 | 08.07.24 | 06.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Agitator | LE21M277-P-WS-WT-PR-2104 | LE21M277-P-WS-WT-PR-2104-C | Triveni | Pre-order technically rejected | PR Closed |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 25.08.22 | 06.02.24 | 03.04.24 | 09.04.24 | 15.04.24 | 25.04.24 | 17.05.24 | 23.05.24 | [18 empty] | SNEHA-S@lntecc.com-11.06.2024-11:23:10
Kendrapada 2 - Aul & Rajkanika | Process | Agitator | LE21M277-P-WS-WT-PR-2104 | LE21M277-P-WS-WT-PR-2104-D | Verito | Awaiting post-offer from vendor | 12 |  |  | verito.offers@veritoengineering.com | 25.08.22 | 30.05.24 | 01.06.24 | 05.06.24 | 08.06.24 | 11.06.24 | 15.06.24 | [5 empty] | 20.06.24 | 20.06.24 | 21.06.24 | T2 | 23.07.24 | Verito | [5 empty] | 21.06.24 | 08.07.24 | 06.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:31:39
Kendrapada 2 - Aul & Rajkanika | Process | WTP Sluice gates | LE21M277-P-WS-WT-PR-2105 | LE21M277-P-WS-WT-PR-2105-A | JASH | Sent to BU Operations | 88 |  | Prateek Verma | lpgsouth2@jashindia.com | 01.09.22 | 06.02.24 | 27.02.24 | 15.03.24 | 30.03.24 | 01.04.24 | [6 empty] | 08.05.24 | 08.05.24 | 08.05.24 | T2 | [7 empty] | 08.05.24 | 25.05.24 | 24.07.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | WTP Sluice gates | LE21M277-P-WS-WT-PR-2105 | LE21M277-P-WS-WT-PR-2105-B | ORIENTAL | Sent to BU Operations | 12 |  |  |  | 01.09.22 | 06.02.24 | 26.03.24 | 29.03.24 | 30.03.24 | 30.03.24 | 02.04.24 | 10.05.24 |  |  |  |  | 17.04.24 | 20.04.24 | 08.05.24 | T1 | 23.07.24 | ORIENTAL | [5 empty] | 08.05.24 | 25.05.24 | 24.07.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Chlorination system | LE21M277-P-WS-WT-PR-2106 | LE21M277-P-WS-WT-PR-2106-A | Zion | Sent to BU Operations | 17 |  | Deepak Santaram | deepak@ziontech.in | 29.07.22 | 06.02.24 | 25.03.24 | 06.04.24 | 19.04.24 | 24.04.24 | [6 empty] | 29.04.24 | 29.04.24 | 18.07.24 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Chlorination system | LE21M277-P-WS-WT-PR-2106 | LE21M277-P-WS-WT-PR-2106-B | Toshcon | Regret offer | PR Closed |  |  |  | 29.07.22 | 06.02.24 | [24 empty] | SNEHA-S@lntecc.com-18.06.2024-10:46:54
Kendrapada 2 - Aul & Rajkanika | Process | Chlorination system | LE21M277-P-WS-WT-PR-2106 | LE21M277-P-WS-WT-PR-2106-C | ME INFRA | Sent to BU Operations | 17 |  |  |  | 29.07.22 | 03.06.24 | 15.06.24 | 25.06.24 | 28.06.24 | 01.07.24 | [6 empty] | 04.07.24 | 11.07.24 | 18.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Sludge thickener mechanism | LE21M277-P-WS-WT-PR-2107 | LE21M277-P-WS-WT-PR-2107-A | Sritech | Pre-order technically rejected | PR Closed |  | P Mohan | mohan@sritechindia.com | 05.01.22 | 06.02.24 | 13.02.24 | 16.03.24 | 18.03.24 | 19.03.24 | [20 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:05
Kendrapada 2 - Aul & Rajkanika | Process | Sludge thickener mechanism | LE21M277-P-WS-WT-PR-2107 | LE21M277-P-WS-WT-PR-2107-B | Shivpad | Sent to BU Operations | 61 |  | M. Ragavendar | ragavendar@shivpad.com | 05.01.22 | 06.02.24 | 15.02.24 | 16.03.24 | 17.03.24 | 19.03.24 | 16.04.24 | 17.04.24 |  |  |  |  | 26.04.24 | 29.04.24 | 04.06.24 | T2 | [7 empty] | 04.06.24 | 21.06.24 | 20.08.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Sludge thickener mechanism | LE21M277-P-WS-WT-PR-2107 | LE21M277-P-WS-WT-PR-2107-C | Triveni | Sent to BU Operations | 61 |  | Neeraj Agarwal | neeraj.aggarwal@projects.trivenigroup.com | 05.01.22 | 06.02.24 | 27.02.24 | 16.03.24 | 08.04.24 | 17.04.24 | 20.04.24 | 23.04.24 |  |  |  |  | 23.04.24 | 23.04.24 | 04.06.24 | T3 | [7 empty] | 04.06.24 | 21.06.24 | 20.08.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Sludge thickener mechanism | LE21M277-P-WS-WT-PR-2107 | LE21M277-P-WS-WT-PR-2107-D | Filsep | Sent to BU Operations | 61 |  |  | filsepengineers@gmail.com | 05.01.22 | 07.02.24 | 07.05.24 | 10.05.24 | 14.05.24 | 17.05.24 | 27.05.24 | [5 empty] | 03.06.24 | 04.06.24 | 04.06.24 | T1 | [7 empty] | 04.06.24 | 21.06.24 | 20.08.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Filter media | LE21M277-P-WS-WT-PR-2108 | LE21M277-P-WS-WT-PR-2108-A | Dalton | Sent to BU Operations | 20 |  |  | daltonminerals@gmail.com | 24.01.22 | 25.03.24 | 29.03.24 | 03.04.24 | 19.04.24 | [7 empty] | 08.05.24 | 08.05.24 | 15.07.24 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Filter media | LE21M277-P-WS-WT-PR-2108 | LE21M277-P-WS-WT-PR-2108-B | Global Adsorbents | Sent to BU Operations | 20 |  |  |  | 24.01.22 | 25.03.24 | 29.03.24 | 30.05.24 | 11.06.24 | 15.06.24 | [6 empty] | 18.06.24 | 18.06.24 | 15.07.24 | T1 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Centrifuge | LE21M277-P-WS-WT-PR-2109 | LE21M277-P-WS-WT-PR-2109-A | Humbolt | Sent to BU Operations | 90 |  |  |  | 24.01.22 | 19.02.24 | 04.03.24 | 15.03.24 | 25.03.24 | 03.04.24 | [6 empty] | 03.04.24 | 06.05.24 | 06.05.24 | T2 | [7 empty] | 06.05.24 | 23.05.24 | 22.07.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Centrifuge | LE21M277-P-WS-WT-PR-2109 | LE21M277-P-WS-WT-PR-2109-B | Hiller | Sent to BU Operations | 90 |  | Mitali Ojha | enquiry@hillerindia.com | 24.01.22 | 19.02.24 | 03.04.24 | 05.04.24 | 06.04.24 | 10.04.24 | 22.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 06.05.24 | T1 | [7 empty] | 06.05.24 | 23.05.24 | 22.07.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | screw pump | LE21M277-P-WS-WT-PR-2110 | LE21M277-P-WS-WT-PR-2110-A | Tap Engineering | Pre-order technically rejected | PR Closed |  |  |  | 12.01.22 | 25.08.22 | 12.03.24 | 16.03.24 | 10.06.24 | [7 empty] | 18.06.24 | 20.06.24 | [12 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:05
Kendrapada 2 - Aul & Rajkanika | Process | screw pump | LE21M277-P-WS-WT-PR-2110 | LE21M277-P-WS-WT-PR-2110-B | Flosys | Sent to BU Operations | 25 |  |  |  | 12.01.22 | 25.08.22 | 06.07.24 | 08.07.24 | [8 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T1 | [10 empty] | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Backwash Reservoir pump | LE21M277-P-WS-WT-PR-2111 | LE21M277-P-WS-WT-PR-2111-A | KBL | Sent to BU Operations | PR Closed |  | Mohan Kumar | Mohan.Kumar@kbl.co.in | 04.01.22 | 07.02.24 | 01.04.24 | 02.04.24 | 06.04.24 | 29.04.24 | 06.05.24 | 28.05.24 |  |  |  |  | 20.06.24 | 21.06.24 | 28.06.24 | T2 | [7 empty] | 28.06.24 | 15.07.24 | 13.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Backwash Reservoir pump | LE21M277-P-WS-WT-PR-2111 | LE21M277-P-WS-WT-PR-2111-B | WPIL | Regret offer | PR Closed |  | Chandramohan | r.chandramohan@wpil.co.in | 04.01.22 | 07.02.24 | [24 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:05
Kendrapada 2 - Aul & Rajkanika | Process | Backwash Reservoir pump | LE21M277-P-WS-WT-PR-2111 | LE21M277-P-WS-WT-PR-2111-C | Wilo | Awaiting post-offer from vendor | 12 |  | Manikandan | manikkandan.pr@wilo.com | 04.01.22 | 07.02.24 | 22.04.24 | 06.05.24 | [8 empty] | 07.06.24 | 07.06.24 | 28.06.24 | T1 | 23.07.24 | Wilo | [5 empty] | 28.06.24 | 15.07.24 | 13.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:31:39
Kendrapada 2 - Aul & Rajkanika | Process | Submersible pump | LE21M277-P-WS-WT-PR-2112 | LE21M277-P-WS-WT-PR-2112-A | MBH Pumps | Sent to BU Operations | 24 |  | Naresh Koul | northindustrial@mbhpumps.com | 24.01.22 | 15.02.24 | 20.03.24 | 26.03.24 | 05.05.24 | 20.05.24 | [6 empty] | 23.05.24 | 23.05.24 | 11.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Submersible pump | LE21M277-P-WS-WT-PR-2112 | LE21M277-P-WS-WT-PR-2112-B | Aqua | Sent to BU Operations | 24 |  | S.T.Sambandam | chennai@aquapumps.com | 25.08.22 | 25.03.24 | 06.05.24 | 06.05.24 | 27.05.24 | 28.05.24 | [6 empty] | 11.07.24 | 11.07.24 | 11.07.24 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Electrical hoist | LE21M277-P-WS-WT-PR-2113 | LE21M277-P-WS-WT-PR-2113-A | JAPS | Sent to BU Operations | 116 |  |  |  | 30.08.22 | 07.02.24 | 26.02.24 | 07.03.24 | 15.03.24 | 18.03.24 | [6 empty] | 18.03.24 | 18.03.24 | 10.04.24 | T1 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Electrical hoist | LE21M277-P-WS-WT-PR-2113 | LE21M277-P-WS-WT-PR-2113-B | Bradys | Regret offer | PR Closed |  | SRINIVASAN | srinivasan@bradys.in | 30.08.22 | 07.02.24 | [21 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SNEHA-S@lntecc.com-18.07.2024-16:58:35
Kendrapada 2 - Aul & Rajkanika | Process | Electrical hoist | LE21M277-P-WS-WT-PR-2113 | LE21M277-P-WS-WT-PR-2113-C | Indef | Sent to BU Operations | 13 |  |  |  | 30.08.22 | 07.02.24 | 15.03.24 | 20.03.24 | 01.04.24 | 02.04.24 | 15.06.24 | 15.06.24 | 11.07.24 | 15.07.24 |  |  | 18.07.24 | 18.07.24 | 22.07.24 | T2 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Manual chain pulley block | LE21M277-P-WS-WT-PR-2114 | LE21M277-P-WS-WT-PR-2114-A | JAPS | Sent to BU Operations | 116 |  |  |  | 30.08.22 | 07.02.24 | 26.02.24 | 07.03.24 | 15.03.24 | 18.03.24 | [6 empty] | 18.03.24 | 18.03.24 | 10.04.24 | T1 | [7 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Manual chain pulley block | LE21M277-P-WS-WT-PR-2114 | LE21M277-P-WS-WT-PR-2114-B | Bradys | Regret offer | PR Closed |  | SRINIVASAN | srinivasan@bradys.in | 30.08.22 | 07.02.24 | [21 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SNEHA-S@lntecc.com-02.07.2024-19:15:59
Kendrapada 2 - Aul & Rajkanika | Process | Manual chain pulley block | LE21M277-P-WS-WT-PR-2114 | LE21M277-P-WS-WT-PR-2114-C | Indef | Pre-order comments issued | 20 |  |  |  | 30.08.22 | 07.02.24 | 15.03.24 | 20.03.24 | 01.04.24 | 02.04.24 | 15.06.24 | 15.06.24 | 11.07.24 | 15.07.24 | [13 empty] | 15.08.24 | 01.09.24 | 31.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Dosing pump | LE21M277-P-WS-WT-PR-2115 | LE21M277-P-WS-WT-PR-2115-A | Positive metering | Awaiting post-offer from vendor | 12 |  | Jyoti Goikane/ Swati | offers1@positivemetering.com | 31.01.22 | 25.03.24 | 05.04.24 | 22.04.24 | 06.05.24 | [7 empty] | 04.05.24 | 06.05.24 | 24.05.24 | T2 | 23.07.24 | Positive metering | [5 empty] | 24.05.24 | 10.06.24 | 09.08.24 | SNEHA-S@lntecc.com-23.07.2024-17:31:39
Kendrapada 2 - Aul & Rajkanika | Process | Dosing pump | LE21M277-P-WS-WT-PR-2115 | LE21M277-P-WS-WT-PR-2115-B | S R Metering | Sent to BU Operations | PR Closed |  | Sunil | sr1@srmetering.com | 31.01.22 | 25.03.24 | 06.05.24 | 08.05.24 | 09.05.24 | [7 empty] | 10.05.24 | 14.05.24 | 24.05.24 | T1 | [7 empty] | 24.05.24 | 10.06.24 | 09.08.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | DWPE tanks | LE21M277-P-WS-WT-PR-2116 | LE21M277-P-WS-WT-PR-2116-A | FFP | Sent to BU Operations | 103 |  | Yogesh/Ganesh | fibrein@gmail.com | 22.07.22 | 25.03.24 | 12.04.24 | 22.04.24 | 23.04.24 | [7 empty] | 22.04.24 | 23.04.24 | 23.04.24 | T1 | [7 empty] | 23.04.24 | 10.05.24 | 09.07.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | DWPE tank Agitators | LE21M277-P-WS-WT-PR-2117 | LE21M277-P-WS-WT-PR-2117-A | FFP | Sent to BU Operations | 103 |  | Ganesh | fibrein@gmail.com | 29.07.22 | 25.03.24 | 12.04.24 | 22.04.24 | 23.04.24 | [7 empty] | 22.04.24 | 23.04.24 | 23.04.24 | T1 | [7 empty] | 23.04.24 | 10.05.24 | 09.07.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Sampling pump | LE21M277-P-WS-WT-PR-2118 | LE21M277-P-WS-WT-PR-2118-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 24.01.22 | 22.07.22 | [24 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:06
Kendrapada 2 - Aul & Rajkanika | Process | Submersible mixer | LE21M277-P-WS-WT-PR-2119 | LE21M277-P-WS-WT-PR-2119-A | World water tech | Sent to BU Operations | 44 |  | Dawood Basha | wwtechennai@gmail.com | 31.01.22 | 25.03.24 | 05.04.24 | 10.04.24 | 17.04.24 | 20.04.24 | 23.04.24 | 03.05.24 |  |  |  |  | 18.05.24 | 18.05.24 | 21.06.24 | T1 | [7 empty] | 21.06.24 | 08.07.24 | 06.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Submersible mixer | LE21M277-P-WS-WT-PR-2119 | LE21M277-P-WS-WT-PR-2119-B | FFP | Sent to BU Operations | 44 |  | Ganesh | fibrein@gmail.com | 22.07.22 | 25.03.24 | 19.04.24 | 23.04.24 | 17.05.24 | 20.05.24 | 27.05.24 | [5 empty] | 20.06.24 | 21.06.24 | 21.06.24 | T2 | [7 empty] | 21.06.24 | 08.07.24 | 06.09.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Dewatering pump -Process | LE21M277-P-WS-WT-PR-2120 | LE21M277-P-WS-WT-PR-2120-A | Aqua | Sent to BU Operations | 24 |  | S.T.Sambandam | chennai@aquapumps.com | 31.01.22 | 25.03.24 | 06.05.24 | 06.05.24 | 27.05.24 | 28.05.24 | 01.07.24 | [5 empty] | 11.07.24 | 11.07.24 | 11.07.24 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Dewatering pump -Process | LE21M277-P-WS-WT-PR-2120 | LE21M277-P-WS-WT-PR-2120-B | MBH | Sent to BU Operations | 24 |  |  |  | 31.01.22 | 25.03.24 | 24.05.24 | 24.05.24 | [8 empty] | 24.05.24 | 27.05.24 | 11.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Process | Dissolving tray | LE21M277-P-WS-WT-PR-2121 | LE21M277-P-WS-WT-PR-2121-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 16.07.22 | 16.07.22 | [24 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:06
Kendrapada 2 - Aul & Rajkanika | Process | Hand driven Trolley | LE21M277-P-WS-WT-PR-2122 | LE21M277-P-WS-WT-PR-2122-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 24.01.22 | 16.07.22 | [24 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:06
Kendrapada 2 - Aul & Rajkanika | Process | Platform weighing machine | LE21M277-P-WS-WT-PR-2123 | LE21M277-P-WS-WT-PR-2123-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 16.07.22 | 16.07.22 | [24 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:06
Kendrapada 2 - Aul & Rajkanika | Process | Exhaust fan | LE21M277-P-WS-WT-PR-2124 | LE21M277-P-WS-WT-PR-2124-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 16.07.22 | 16.07.22 | [24 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:06
Kendrapada 2 - Aul & Rajkanika | Process | lab equipment | LE21M277-P-WS-WT-PR-2125 | LE21M277-P-WS-WT-PR-2125-A | SITE PROCUREMENT | Regret offer | PR Closed | Site procurement |  |  | 16.07.22 | 16.07.22 | [24 empty] | SNEHA-S@lntecc.com-02.07.2024-18:51:06
Kendrapada 2 - Aul & Rajkanika | Process | Service water pumps | LE21M277-P-WS-WT-PR-2127 | LE21M277-P-WS-WT-PR-2127-A | KSB | Sent to BU Operations | 24 |  |  |  | 29.07.22 | 07.06.24 | 07.06.24 | 13.06.24 | 03.07.24 | 06.07.24 | [6 empty] | 11.07.24 | 11.07.24 | 11.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | SNEHA-S@lntecc.com-23.07.2024-17:30:40
Kendrapada 2 - Aul & Rajkanika | Mechanical | Air Cushion Valves | LE21M277-M-WS-PR-AC-1114 | LE21M277-M-WS-PR-AC-1114-A | avkindia | Regret offer | PR Closed | Regret |  | subhash@avkindia.com |  | 02.04.24 | 29.06.24 | 29.06.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-17:37:59
Kendrapada 2 - Aul & Rajkanika | Mechanical | Air Cushion Valves | LE21M277-M-WS-PR-AC-1114 | LE21M277-M-WS-PR-AC-1114-B | vag group | Regret offer | PR Closed | Regret |  | s.deepkanti@vag-group.com |  | 02.04.24 | 08.04.24 | 17.05.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-18:04:01
Kendrapada 2 - Aul & Rajkanika | Mechanical | Air Cushion Valves | LE21M277-M-WS-PR-AC-1114 | LE21M277-M-WS-PR-AC-1114-C | rd multiples | Regret offer | PR Closed | Regret |  | mumbai@rdmultiples.com |  | 02.04.24 | 31.05.24 | 29.06.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-18:04:01
Kendrapada 2 - Aul & Rajkanika | Mechanical | Air Cushion Valves | LE21M277-M-WS-PR-AC-1114 | LE21M277-M-WS-PR-AC-1114-D | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 02.04.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-18:04:01
Kendrapada 2 - Aul & Rajkanika | Mechanical | Air Cushion Valves | LE21M277-M-WS-PR-AC-1114 | LE21M277-M-WS-PR-AC-1114-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 02.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:01:50
Kendrapada 2 - Aul & Rajkanika | Mechanical | EOT Crane | LE21M277-M-WS-PR-CR-1112 | LE21M277-M-WS-PR-CR-1112-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | dhanaraj.s@lntecc.com-28.05.2024-09:30:04
Kendrapada 2 - Aul & Rajkanika | Mechanical | EOT Crane | LE21M277-M-WS-PR-CR-1112 | LE21M277-M-WS-PR-CR-1112-B |  | Enquiry yet to float | NA | [26 empty] | 14.08.24 | 31.08.24 | 30.10.24 | aknandy@lntecc.com-10.07.2024-09:57:11
Kendrapada 2 - Aul & Rajkanika | Mechanical | HSC Pump | LE21M277-M-WS-PR-DC-1102 | LE21M277-M-WS-PR-DC-1102-A | NA | Regret offer | PR Closed | Convert from HSC TO VT pump |  |  |  | 21.05.24 | 21.05.24 | [23 empty] | aknandy@lntecc.com-11.07.2024-17:03:50
Kendrapada 2 - Aul & Rajkanika | Mechanical | Dismantling Zones | LE21M277-M-WS-PR-DJ-1107 | LE21M277-M-WS-PR-DJ-1107-A | avkindia | Regret offer | PR Closed | Regret |  | subhash@avkindia.com |  | 02.04.24 | 29.06.24 | 29.06.24 | [22 empty] | aknandy@lntecc.com-11.07.2024-17:37:59
Kendrapada 2 - Aul & Rajkanika | Mechanical | Dismantling Zones | LE21M277-M-WS-PR-DJ-1107 | LE21M277-M-WS-PR-DJ-1107-B | vag group | Regret offer | PR Closed | Regret |  | s.deepkanti@vag-group.com |  | 02.04.24 | 08.04.24 | [23 empty] | aknandy@lntecc.com-11.07.2024-18:04:01
Kendrapada 2 - Aul & Rajkanika | Mechanical | Dismantling Zones | LE21M277-M-WS-PR-DJ-1107 | LE21M277-M-WS-PR-DJ-1107-C | rd multiples | Pre-order comments issued | 36 |  |  | mumbai@rdmultiples.com |  | 02.04.24 | 31.05.24 | 29.06.24 | [22 empty] | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | Dismantling Zones | LE21M277-M-WS-PR-DJ-1107 | LE21M277-M-WS-PR-DJ-1107-D | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 02.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:04:01
Kendrapada 2 - Aul & Rajkanika | Mechanical | Dismantling Zones | LE21M277-M-WS-PR-DJ-1107 | LE21M277-M-WS-PR-DJ-1107-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 02.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:01:50
Kendrapada 2 - Aul & Rajkanika | Mechanical | Dewatering Pump - Mech | LE21M277-M-WS-PR-DW-1103 | LE21M277-M-WS-PR-DW-1103-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | dhanaraj.s@lntecc.com-28.05.2024-09:30:04
Kendrapada 2 - Aul & Rajkanika | Mechanical | Expansion Joints | LE21M277-M-WS-PR-EB-1108 | LE21M277-M-WS-PR-EB-1108-A | avkindia | Regret offer | PR Closed | Regret |  | subhash@avkindia.com |  | 02.04.24 | 29.06.24 | 29.06.24 | [22 empty] | aknandy@lntecc.com-11.07.2024-17:37:59
Kendrapada 2 - Aul & Rajkanika | Mechanical | Expansion Joints | LE21M277-M-WS-PR-EB-1108 | LE21M277-M-WS-PR-EB-1108-B | vag group | Regret offer | PR Closed | Regret |  | s.deepkanti@vag-group.com |  | 02.04.24 | 08.04.24 | [23 empty] | aknandy@lntecc.com-11.07.2024-18:04:01
Kendrapada 2 - Aul & Rajkanika | Mechanical | Expansion Joints | LE21M277-M-WS-PR-EB-1108 | LE21M277-M-WS-PR-EB-1108-C | rd multiples | Regret offer | PR Closed | Regret |  | mumbai@rdmultiples.com |  | 02.04.24 | 31.05.24 | 29.06.24 | [22 empty] | aknandy@lntecc.com-11.07.2024-18:04:01
Kendrapada 2 - Aul & Rajkanika | Mechanical | Expansion Joints | LE21M277-M-WS-PR-EB-1108 | LE21M277-M-WS-PR-EB-1108-D | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 02.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:04:01
Kendrapada 2 - Aul & Rajkanika | Mechanical | Expansion Joints | LE21M277-M-WS-PR-EB-1108 | LE21M277-M-WS-PR-EB-1108-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 02.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:01:50
Kendrapada 2 - Aul & Rajkanika | Mechanical | Ventilation (Supply & Exhaust fan) | LE21M277-M-WS-PR-EX-1110 | LE21M277-M-WS-PR-EX-1110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | dhanaraj.s@lntecc.com-28.05.2024-09:30:04
Kendrapada 2 - Aul & Rajkanika | Mechanical | OHT Valves | LE21M277-M-WS-PR-OV-1109 | LE21M277-M-WS-PR-OV-1109-A | avkindia | Pre-order technically cleared | 25 |  |  | subhash@avkindia.com |  | 02.04.24 | 29.06.24 | 29.06.24 | [8 empty] | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:47:58
Kendrapada 2 - Aul & Rajkanika | Mechanical | OHT Valves | LE21M277-M-WS-PR-OV-1109 | LE21M277-M-WS-PR-OV-1109-B | vag group | Pre-order technically cleared | 25 |  |  | s.deepkanti@vag-group.com |  | 02.04.24 | 08.04.24 | 17.05.24 | [8 empty] | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:47:58
Kendrapada 2 - Aul & Rajkanika | Mechanical | OHT Valves | LE21M277-M-WS-PR-OV-1109 | LE21M277-M-WS-PR-OV-1109-C | rd multiples | Pre-order comments issued | 36 |  |  | mumbai@rdmultiples.com |  | 02.04.24 | 31.05.24 | 29.06.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | OHT Valves | LE21M277-M-WS-PR-OV-1109 | LE21M277-M-WS-PR-OV-1109-D | ivc valves | Pre-order technically cleared | 25 |  |  | sales.odisha@ivc-valves.com |  | 02.04.24 | 09.05.24 | 23.05.24 | 31.05.24 | [7 empty] | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:47:58
Kendrapada 2 - Aul & Rajkanika | Mechanical | OHT Valves | LE21M277-M-WS-PR-OV-1109 | LE21M277-M-WS-PR-OV-1109-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 02.04.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-18:01:50
Kendrapada 2 - Aul & Rajkanika | Mechanical | PH valves | LE21M277-M-WS-PR-PV-1106 | LE21M277-M-WS-PR-PV-1106-A | avkindia | Pre-order technically cleared | 25 |  |  | subhash@avkindia.com |  | 02.04.24 | 29.06.24 | 29.06.24 | [8 empty] | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:47:58
Kendrapada 2 - Aul & Rajkanika | Mechanical | PH valves | LE21M277-M-WS-PR-PV-1106 | LE21M277-M-WS-PR-PV-1106-B | vag group | Pre-order technically cleared | 25 |  |  | s.deepkanti@vag-group.com |  | 02.04.24 | 08.04.24 | 17.05.24 | [8 empty] | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:47:58
Kendrapada 2 - Aul & Rajkanika | Mechanical | PH valves | LE21M277-M-WS-PR-PV-1106 | LE21M277-M-WS-PR-PV-1106-C | rd multiples | Pre-order comments issued | 36 |  |  | mumbai@rdmultiples.com |  | 02.04.24 | 31.05.24 | 29.06.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | PH valves | LE21M277-M-WS-PR-PV-1106 | LE21M277-M-WS-PR-PV-1106-D | ivc valves | Pre-order technically cleared | 25 |  |  | sales.odisha@ivc-valves.com |  | 02.04.24 | 09.05.24 | 23.05.24 | 31.05.24 | [7 empty] | 10.07.24 | 10.07.24 | 10.07.24 | T3 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:49:03
Kendrapada 2 - Aul & Rajkanika | Mechanical | PH valves | LE21M277-M-WS-PR-PV-1106 | LE21M277-M-WS-PR-PV-1106-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 02.04.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-18:01:50
Kendrapada 2 - Aul & Rajkanika | Mechanical | Sluice Gate | LE21M277-M-WS-PR-SG-1111 | LE21M277-M-WS-PR-SG-1111-A | Fluid control | Sent to BU Operations | 20 |  |  | sales@fluidcontrol.in |  | 18.03.24 | 17.04.24 | 22.05.24 | 30.05.24 | [7 empty] | 10.07.24 | 15.07.24 | 15.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | Sluice Gate | LE21M277-M-WS-PR-SG-1111 | LE21M277-M-WS-PR-SG-1111-B | orientalcastings | Sent to BU Operations | 20 |  |  | orientalcastings@gmail.com |  | 18.03.24 | 25.03.24 | 04.04.24 | 07.04.24 | 22.05.24 | 31.05.24 | [5 empty] | 10.07.24 | 15.07.24 | 15.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | Sluice Gate | LE21M277-M-WS-PR-SG-1111 | LE21M277-M-WS-PR-SG-1111-C | jashindia | Sent to BU Operations | 20 |  |  | abhijeet@jashindia.com |  | 18.03.24 | 15.07.24 | 15.07.24 | [8 empty] | 15.07.24 | 15.07.24 | 15.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | Pipeline Valves | LE21M277-M-WS-PR-VL-1104 | LE21M277-M-WS-PR-VL-1104-A | avkindia | Pre-order technically cleared | 25 |  |  | subhash@avkindia.com |  | 02.04.24 | 29.06.24 | 29.06.24 | [8 empty] | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:49:54
Kendrapada 2 - Aul & Rajkanika | Mechanical | Pipeline Valves | LE21M277-M-WS-PR-VL-1104 | LE21M277-M-WS-PR-VL-1104-B | vag group | Pre-order technically cleared | 25 |  |  | s.deepkanti@vag-group.com |  | 02.04.24 | 08.04.24 | 17.05.24 | [8 empty] | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:49:54
Kendrapada 2 - Aul & Rajkanika | Mechanical | Pipeline Valves | LE21M277-M-WS-PR-VL-1104 | LE21M277-M-WS-PR-VL-1104-C | rd multiples | Pre-order comments issued | 36 |  |  | mumbai@rdmultiples.com |  | 02.04.24 | 31.05.24 | 29.06.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | Pipeline Valves | LE21M277-M-WS-PR-VL-1104 | LE21M277-M-WS-PR-VL-1104-D | ivc valves | Pre-order technically cleared | 25 |  |  | sales.odisha@ivc-valves.com |  | 02.04.24 | 09.05.24 | 23.05.24 | 31.05.24 | [7 empty] | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:50:30
Kendrapada 2 - Aul & Rajkanika | Mechanical | Pipeline Valves | LE21M277-M-WS-PR-VL-1104 | LE21M277-M-WS-PR-VL-1104-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 02.04.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-18:01:50
Kendrapada 2 - Aul & Rajkanika | Mechanical | VT Pump | LE21M277-M-WS-PR-VT-1101 | LE21M277-M-WS-PR-VT-1101-A | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in | 04.08.21 | 20.02.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-18:04:02
Kendrapada 2 - Aul & Rajkanika | Mechanical | VT Pump | LE21M277-M-WS-PR-VT-1101 | LE21M277-M-WS-PR-VT-1101-B | WILO | Pre-order technically cleared | 25 |  |  | manikkandan.pr@wilo.com | 04.08.21 | 20.02.24 | 03.04.24 | 18.04.24 | 07.06.24 | [7 empty] | 10.07.24 | 10.07.24 | [9 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | VT Pump | LE21M277-M-WS-PR-VT-1101 | LE21M277-M-WS-PR-VT-1101-C | WPIL | Pre-order technically cleared | 55 |  |  | cmktg@wpil.co.in | 04.08.21 | 20.02.24 | 19.03.24 | 04.04.24 | 14.05.24 | 14.05.24 | 20.05.24 | 22.05.24 | 24.05.24 | 10.06.24 |  |  | 10.06.24 | 24.05.24 | [9 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-15:45:55
Kendrapada 2 - Aul & Rajkanika | Mechanical | Zero Velocity Valves | LE21M277-M-WS-PR-ZV-1113 | LE21M277-M-WS-PR-ZV-1113-A | avkindia | Regret offer | PR Closed | Regret |  | subhash@avkindia.com |  | 02.04.24 | 29.06.24 | 29.06.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | aknandy@lntecc.com-11.07.2024-17:37:59
Kendrapada 2 - Aul & Rajkanika | Mechanical | Zero Velocity Valves | LE21M277-M-WS-PR-ZV-1113 | LE21M277-M-WS-PR-ZV-1113-B | vag group | Regret offer | PR Closed | Regret |  | s.deepkanti@vag-group.com |  | 02.04.24 | 08.04.24 | [20 empty] | 31.08.24 | 17.09.24 | 16.11.24 | aknandy@lntecc.com-11.07.2024-18:04:02
Kendrapada 2 - Aul & Rajkanika | Mechanical | Zero Velocity Valves | LE21M277-M-WS-PR-ZV-1113 | LE21M277-M-WS-PR-ZV-1113-C | rd multiples | Regret offer | PR Closed | Regret |  | mumbai@rdmultiples.com |  | 02.04.24 | 31.05.24 | 29.06.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | aknandy@lntecc.com-11.07.2024-18:04:02
Kendrapada 2 - Aul & Rajkanika | Mechanical | Zero Velocity Valves | LE21M277-M-WS-PR-ZV-1113 | LE21M277-M-WS-PR-ZV-1113-D | ivc valves | Regret offer | PR Closed | Regret |  | sales.odisha@ivc-valves.com |  | 02.04.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | aknandy@lntecc.com-11.07.2024-18:04:02
Kendrapada 2 - Aul & Rajkanika | Mechanical | Zero Velocity Valves | LE21M277-M-WS-PR-ZV-1113 | LE21M277-M-WS-PR-ZV-1113-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 02.04.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | aknandy@lntecc.com-11.07.2024-18:01:50
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE21M277-I-WS-WT-PR-5101 | LE21M277-I-WS-WT-PR-5101-A | H Guru | Sent to BU Operations | 73 |  |  | info@hgurusouth.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE21M277-I-WS-WT-PR-5101 | LE21M277-I-WS-WT-PR-5101-B | General Gauges | Sent to BU Operations | 73 |  |  | gicchennai@general-gauges.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Pressure Switch | LE21M277-I-WS-WT-PR-5102 | LE21M277-I-WS-WT-PR-5102-A | H Guru | Sent to BU Operations | 73 |  |  | info@hgurusouth.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Pressure Switch | LE21M277-I-WS-WT-PR-5102 | LE21M277-I-WS-WT-PR-5102-B | General Gauges | Sent to BU Operations | 73 |  |  | gicchennai@general-gauges.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Pressure transmitter | LE21M277-I-WS-WT-PR-5103 | LE21M277-I-WS-WT-PR-5103-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Pressure transmitter | LE21M277-I-WS-WT-PR-5103 | LE21M277-I-WS-WT-PR-5103-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Pressure transmitter | LE21M277-I-WS-WT-PR-5103 | LE21M277-I-WS-WT-PR-5103-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Float & Board Level gauge | LE21M277-I-WS-WT-PR-5104 | LE21M277-I-WS-WT-PR-5104-A | SBEM | Sent to BU Operations | 30 |  |  | rajesh.p@sbem.co.in |  | 06.04.24 | 20.04.24 | 20.04.24 | 30.05.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T1 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Float & Board Level gauge | LE21M277-I-WS-WT-PR-5104 | LE21M277-I-WS-WT-PR-5104-B | Pune Techtrol | Sent to BU Operations | 30 |  |  | mktg2@punetechtrol.com |  | 06.04.24 | 20.04.24 | 14.05.24 | 30.05.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T2 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | level switch - Conductivity type | LE21M277-I-WS-WT-PR-5105 | LE21M277-I-WS-WT-PR-5105-A | SBEM | Sent to BU Operations | 30 |  |  | rajesh.p@sbem.co.in |  | 06.04.24 | 20.04.24 | 20.04.24 | 30.05.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T1 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | level switch - Conductivity type | LE21M277-I-WS-WT-PR-5105 | LE21M277-I-WS-WT-PR-5105-B | Pune Techtrol | Sent to BU Operations | 30 |  |  | mktg2@punetechtrol.com |  | 06.04.24 | 20.04.24 | 14.05.24 | 30.05.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T2 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Ultrasonic level Transmitter | LE21M277-I-WS-WT-PR-5106 | LE21M277-I-WS-WT-PR-5106-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Ultrasonic level Transmitter | LE21M277-I-WS-WT-PR-5106 | LE21M277-I-WS-WT-PR-5106-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Ultrasonic level Transmitter | LE21M277-I-WS-WT-PR-5106 | LE21M277-I-WS-WT-PR-5106-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Radar Level Transmitter | LE21M277-I-WS-WT-PR-5107 | LE21M277-I-WS-WT-PR-5107-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Radar Level Transmitter | LE21M277-I-WS-WT-PR-5107 | LE21M277-I-WS-WT-PR-5107-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Radar Level Transmitter | LE21M277-I-WS-WT-PR-5107 | LE21M277-I-WS-WT-PR-5107-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Loss of head transmitter | LE21M277-I-WS-WT-PR-5108 | LE21M277-I-WS-WT-PR-5108-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Loss of head transmitter | LE21M277-I-WS-WT-PR-5108 | LE21M277-I-WS-WT-PR-5108-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Loss of head transmitter | LE21M277-I-WS-WT-PR-5108 | LE21M277-I-WS-WT-PR-5108-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Rate for flow transmitter | LE21M277-I-WS-WT-PR-5109 | LE21M277-I-WS-WT-PR-5109-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Rate for flow transmitter | LE21M277-I-WS-WT-PR-5109 | LE21M277-I-WS-WT-PR-5109-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Rate for flow transmitter | LE21M277-I-WS-WT-PR-5109 | LE21M277-I-WS-WT-PR-5109-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Bypass Rotameter | LE21M277-I-WS-WT-PR-5110 | LE21M277-I-WS-WT-PR-5110-A | Scientific device | Pre-order comments issued | 13 |  |  | info@scientificdevices.org |  | 09.07.24 | 17.07.24 | 22.07.24 | [19 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:24:52
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Bypass Rotameter | LE21M277-I-WS-WT-PR-5110 | LE21M277-I-WS-WT-PR-5110-B | Eureka | Pre-order comments issued | 13 |  |  | chennaioffice@eurekaflow.com |  | 09.07.24 | 17.07.24 | 22.07.24 | [19 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:24:52
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Electromagnectic flow meter | LE21M277-I-WS-WT-PR-5111 | LE21M277-I-WS-WT-PR-5111-A | E&H | Sent to BU Operations | PR Closed |  |  | ramkumar.m@endress.com |  | 15.03.24 | 26.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T2 | [7 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:27:09
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Electromagnectic flow meter | LE21M277-I-WS-WT-PR-5111 | LE21M277-I-WS-WT-PR-5111-B | Krohne marshall | Sent to BU Operations | PR Closed |  |  | dilibanr@forbesmarshall.com |  | 15.03.24 | 25.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T3 | [7 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:27:09
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Electromagnectic flow meter | LE21M277-I-WS-WT-PR-5111 | LE21M277-I-WS-WT-PR-5111-C | Siemens | Awaiting post-offer from vendor | 13 |  |  | keerthi.guruswamy.ext@siemens.com |  | 15.03.24 | 24.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T1 | 22.07.24 | Siemens | [5 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:27:09
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M277-I-WS-WT-PR-5112 | LE21M277-I-WS-WT-PR-5112-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M277-I-WS-WT-PR-5112 | LE21M277-I-WS-WT-PR-5112-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M277-I-WS-WT-PR-5112 | LE21M277-I-WS-WT-PR-5112-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 29.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Battery Operated Flow meter | LE21M277-I-WS-WT-PR-5113 | LE21M277-I-WS-WT-PR-5113-A | ABB | Pre-order comments issued | 13 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 01.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 15.07.24 | 22.07.24 | [15 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:24:52
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Battery Operated Flow meter | LE21M277-I-WS-WT-PR-5113 | LE21M277-I-WS-WT-PR-5113-B | siemens | Pre-order comments issued | 13 |  |  | keerthi.guruswamy.ext@siemens.com |  | 06.04.24 | 26.04.24 | 30.05.24 | 07.06.24 | 15.06.24 | 15.07.24 | 22.07.24 | [15 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-22.07.2024-09:24:52
Kendrapada 2 - Aul & Rajkanika | Instrumentation | pH Meter | LE21M277-I-WS-WT-PR-5114 | LE21M277-I-WS-WT-PR-5114-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 01.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:01
Kendrapada 2 - Aul & Rajkanika | Instrumentation | pH Meter | LE21M277-I-WS-WT-PR-5114 | LE21M277-I-WS-WT-PR-5114-B | E&H | Sent to BU Operations | 17 |  |  | ramkumar.m@endress.com |  | 06.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T1 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:01
Kendrapada 2 - Aul & Rajkanika | Instrumentation | pH Meter | LE21M277-I-WS-WT-PR-5114 | LE21M277-I-WS-WT-PR-5114-C | ABB | Sent to BU Operations | 17 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T2 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:38:19
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Turbidity meter | LE21M277-I-WS-WT-PR-5115 | LE21M277-I-WS-WT-PR-5115-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:01
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Turbidity meter | LE21M277-I-WS-WT-PR-5115 | LE21M277-I-WS-WT-PR-5115-C | ABB | Sent to BU Operations | 17 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T2 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:38:19
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Residual Chlorine Analyzer | LE21M277-I-WS-WT-PR-5116 | LE21M277-I-WS-WT-PR-5116-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:01
Kendrapada 2 - Aul & Rajkanika | Instrumentation | Residual Chlorine Analyzer | LE21M277-I-WS-WT-PR-5116 | LE21M277-I-WS-WT-PR-5116-B | E&H | Sent to BU Operations | 17 |  |  | ramkumar.m@endress.com |  | 06.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T1 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:01
Kendrapada 2 - Aul & Rajkanika | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M277-I-WS-WT-PR-5117 | LE21M277-I-WS-WT-PR-5117-A | Schneider | Awaiting pre-offer from vendor | 30 |  |  | rushyendhar.repalli@se.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M277-I-WS-WT-PR-5117 | LE21M277-I-WS-WT-PR-5117-B | Honeywell | Awaiting pre-offer from vendor | 30 |  |  | Srinivasan.Venkateswaran@Honeywell.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M277-I-WS-WT-PR-5117 | LE21M277-I-WS-WT-PR-5117-C | Siemens | Awaiting pre-offer from vendor | 30 |  |  | jeyanth.j@siemens.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-12:39:33
Kendrapada 2 - Aul & Rajkanika | Instrumentation | instrumentation Control & signal Cables | LE21M277-I-WS-WT-PR-5118 | LE21M277-I-WS-WT-PR-5118-A | Delton | Sent to BU Operations | 24 |  |  | jus@deltoncables.com |  | 03.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-12.07.2024-10:02:16
Kendrapada 2 - Aul & Rajkanika | Instrumentation | instrumentation Control & signal Cables | LE21M277-I-WS-WT-PR-5118 | LE21M277-I-WS-WT-PR-5118-B | Cords | Sent to BU Operations | 24 |  |  | tendering@cordscable.com |  | 03.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-12.07.2024-10:02:16
Kendrapada 2 - Aul & Rajkanika | Instrumentation | instrumentation Control & signal Cables | LE21M277-I-WS-WT-PR-5118 | LE21M277-I-WS-WT-PR-5118-C | Thermocables | Sent to BU Operations | 24 |  |  | chennai@thermopads.com |  | 03.04.24 | 03.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.07.24 | 16.08.24 | 15.10.24 | SURENDHAR@lntecc.com-12.07.2024-10:02:17
Kendrapada 2 - Aul & Rajkanika | Instrumentation | UPS | LE21M277-I-WS-WT-PR-5119 | LE21M277-I-WS-WT-PR-5119-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.09.24 | 17.10.24 | 16.12.24 | SURENDHAR@lntecc.com-02.07.2024-11:00:16
Kendrapada 2 - Aul & Rajkanika | Electrical | Transformer | LE21M277-E-WS-WT-PR-4103 | LE21M277-E-WS-WT-PR-4103-A | CGL | Regret offer | PR Closed | No response |  | Ramesh.Ram@cgglobal.com | 18.7.23 | 17.2.24 | [21 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:45:38
Kendrapada 2 - Aul & Rajkanika | Electrical | Transformer | LE21M277-E-WS-WT-PR-4103 | LE21M277-E-WS-WT-PR-4103-B | Kirloskar | Regret offer | PR Closed | No Response |  | aditya.ksr@kirloskarelectric.com | 18.7.23 | 17.2.24 | 13.04.24 | 22.04.24 | [19 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-16.07.2024-14:16:34
Kendrapada 2 - Aul & Rajkanika | Electrical | Transformer | LE21M277-E-WS-WT-PR-4103 | LE21M277-E-WS-WT-PR-4103-C | Voltamp | Regret offer | PR Closed | As per telecon ,vendor has informed that they are not interested to quote if the ratings below 250 kVA |  | sasik_vtlchn@voltamptransformers.com | 18.7.23 | 17.2.24 | 27.2.24 | 29.2.24 | [19 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-16.07.2024-14:16:34
Kendrapada 2 - Aul & Rajkanika | Electrical | Transformer | LE21M277-E-WS-WT-PR-4103 | LE21M277-E-WS-WT-PR-4103-D | VOLTECH | Sent to BU Operations | 19 |  |  | adalarasan.r@voltechgroup.com |  | 11.06.24 | 18.06.24 | 21.06.24 | 12.7.24 | 15.7.24 | [6 empty] | 12.7.24 | 15.7.24 | 16.7.24 | T1 | [7 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | Transformer | LE21M277-E-WS-WT-PR-4103 | LE21M277-E-WS-WT-PR-4103-E | Toshiba | Regret offer | PR Closed | Regret Communication Via Mail,not having suitable designs matching with our specifications requirement. 24.6.24 |  |  |  | 14.6.24 | [10 empty] | 21.06.24 | 18.06.24 | [9 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-16.07.2024-14:17:33
Kendrapada 2 - Aul & Rajkanika | Electrical | Transformer | LE21M277-E-WS-WT-PR-4103 | LE21M277-E-WS-WT-PR-4103-F | TBEA | Sent to BU Operations | 19 |  |  |  |  | 2.7.24 | 9.7.24 | 11.7.24 | 12.7.24 | 15.7.24 | [6 empty] | 12.7.24 | 15.7.24 | 16.7.24 | T1 | [7 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | Transformer | LE21M277-E-WS-WT-PR-4103 | LE21M277-E-WS-WT-PR-4103-G | Power Star | Sent to BU Operations | 19 |  |  |  |  | 13.6.24 | 4.7.24 | 5.7.24 | 12.7.24 | 12.7.24 | 15.7.24 | [5 empty] | 12.7.24 | 15.7.24 | 16.7.24 | T1 | [7 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | Transformer | LE21M277-E-WS-WT-PR-4103 | LE21M277-E-WS-WT-PR-4103-H | PETE | Regret offer | PR Closed | Regret Communication Via Mail,not having suitable designs matching with our specifications requirement. 10.7.24 |  |  |  | 9.7.24 | [24 empty] | karthik.ajithkumar@lntecc.com-16.07.2024-14:17:33
Kendrapada 2 - Aul & Rajkanika | Electrical | HT Panel | LE21M277-E-WS-WT-PR-4104 | LE21M277-E-WS-WT-PR-4104-A | Symatic South Siemens | Pre-order technically cleared | 33 | Symatic System integrater |  | symaticindia@gmail.com | 4.12.21 | 2.3.24 | 3.4.24 | 26.04.24 | 6.6.24 | 2.7.24 | [6 empty] | 6.6.24 | 2.7.24 | [9 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | HT Panel | LE21M277-E-WS-WT-PR-4104 | LE21M277-E-WS-WT-PR-4104-B | ABB | Regret offer | PR Closed | ABB is not manufacturing outdoor panels |  | rajkumar.sv@in.abb.com | 4.12.21 | 2.3.24 | [21 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:45:38
Kendrapada 2 - Aul & Rajkanika | Electrical | HT Panel | LE21M277-E-WS-WT-PR-4104 | LE21M277-E-WS-WT-PR-4104-C | Universal | Pre-order technically cleared | 27 |  |  | deepak@upe.co.in | 4.12.21 | 20.04.24 | 2.6.24 | 2.7.24 | 7.7.24 | 8.7.24 | [6 empty] | 7.7.24 | 8.7.24 | [9 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | HT Panel | LE21M277-E-WS-WT-PR-4104 | LE21M277-E-WS-WT-PR-4104-D | EAP | Awaiting pre-offer from vendor | 102 |  |  | sales@eapindia.com | 4.12.21 | 24.04.24 | [21 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | HT Panel | LE21M277-E-WS-WT-PR-4104 | LE21M277-E-WS-WT-PR-4104-E | HTS | Pre-order technically cleared | 34 |  |  | marketing@htswitchgears.com | 4.12.21 | 20.4.24 | 25.4.24 | 30.4.24 | 3.5.24 | 3.5.24 | 8.5.24 | 1.7.24 |  |  |  |  | 1.7.24 | 1.7.24 | [9 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | HT Panel | LE21M277-E-WS-WT-PR-4104 | LE21M277-E-WS-WT-PR-4104-F | Popular | Pre-order technically cleared | 17 |  |  |  | 4.12.21 | 9.7.24 | 12.7.24 | 18.7.24 | [8 empty] | 17.7.24 | 18.7.24 | [12 empty] | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | DG Set | LE21M277-E-WS-WT-PR-4106 | LE21M277-E-WS-WT-PR-4106-A | Jackson | Sent to BU Operations | 18 |  |  | mahenoor.tabassum@jakson.com | 18.7.23 | 28.2.24 | 6.3.24 | 19.3.24 | 29.3.24 | 11.04.24 | 21.5.24 | 28.06.24 |  |  |  |  | 28.06.24 | 21.06.24 | 17.7.24 | T1 | [7 empty] | 18.7.24 | 04.08.24 | 03.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | DG Set | LE21M277-E-WS-WT-PR-4106 | LE21M277-E-WS-WT-PR-4106-B | IEC | Sent to BU Operations | 18 |  |  | niraj.sharma@iecgensets.com | 18.7.23 | 29.2.24 | 29.3.24 | 24.04.24 | 30.5.24 | 29.06.24 | [6 empty] | 29.06.24 | 30.05.24 | 17.7.24 | T1 | [7 empty] | 18.7.24 | 04.08.24 | 03.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | DG Set | LE21M277-E-WS-WT-PR-4106 | LE21M277-E-WS-WT-PR-4106-C | Gainwell | Sent to BU Operations | 18 |  |  | aftab.ali@gainwellindia.com | 18.7.23 | 7.3.24 | 8.3.24 | 20.3.24 | 4.4.24 | 11.4.24 | 30.4.24 | 17.5.24 | 24.5.24 | 29.5.24 | 4.7.24 | 11.7.24 | 4.7.24 | 11.7.24 | 17.7.24 | T1 | [7 empty] | 18.7.24 | 04.08.24 | 03.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | LT panels | LE21M277-E-WS-WT-PR-4107 | LE21M277-E-WS-WT-PR-4107-A | ABB | Pre-order comments issued | 97 |  |  | proposal@kontact.in | 27.7.21 | 23.2.24 | 8.3.24 | 25.3.24 | 6.4.24 | 29.04.24 | [17 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | LT panels | LE21M277-E-WS-WT-PR-4107 | LE21M277-E-WS-WT-PR-4107-B | Schneider | Pre-order comments issued | 72 |  |  | s.sandhya@se.com | 27.7.21 | 23.2.24 | 22.3.24 | 3.4.24 | 18.4.24 | 26.04.24 | 9.5.24 | 24.5.24 | [15 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | LT panels | LE21M277-E-WS-WT-PR-4107 | LE21M277-E-WS-WT-PR-4107-C | Siemens | Regret offer | PR Closed | No response |  | murugaraj.s@siemens.com | 27.7.21 | 27.2.24 | [21 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-08.07.2024-09:20:07
Kendrapada 2 - Aul & Rajkanika | Electrical | LT panels | LE21M277-E-WS-WT-PR-4107 | LE21M277-E-WS-WT-PR-4107-D | SRCS | Pre-order comments issued | 29 |  |  | ashok@ragavendracontrol.com | 27.7.21 | 08.04.24 | 15.05.24 | 14.6.24 | 6.7.24 | 6.7.24 | [17 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | LT panels | LE21M277-E-WS-WT-PR-4107 | LE21M277-E-WS-WT-PR-4107-E | UPE | Pre-order comments issued | 76 |  |  | deepak@upe.co.in | 27.7.21 | 18.4.24 | 26.4.24 | 20.5.24 | [19 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | LT panels | LE21M277-E-WS-WT-PR-4107 | LE21M277-E-WS-WT-PR-4107-F | EAP | Pre-order technically cleared | 25 |  |  | sales@eapindia.com | 27.7.21 | 18.4.24 | 2.5.24 | 17.5.24 | 22.5.24 | 01.07.24 | 1.7.24 | 10.7.24 |  |  |  |  | 01.07.24 | 01.07.24 | [9 empty] | 28.7.24 | 14.08.24 | 13.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | Power and Control Cable | LE21M277-E-WS-WT-PR-4110 | LE21M277-E-WS-WT-PR-4110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:45:38
Kendrapada 2 - Aul & Rajkanika | Electrical | Cable Tray | LE21M277-E-WS-WT-PR-4111 | LE21M277-E-WS-WT-PR-4111-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  |  | 15.5.24 | 15.5.24 | 15.5.24 | [8 empty] | 15.5.24 | 15.5.24 | 15.5.24 | T1 | [7 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:11:55
Kendrapada 2 - Aul & Rajkanika | Electrical | Lugs & Glands | LE21M277-E-WS-WT-PR-4112 | LE21M277-E-WS-WT-PR-4112-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  |  | 15.5.24 | 15.5.24 | 15.5.24 | [8 empty] | 15.5.24 | 15.5.24 | 15.5.24 | T1 | [7 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:11:55
Kendrapada 2 - Aul & Rajkanika | Electrical | LPBS | LE21M277-E-WS-WT-PR-4113 | LE21M277-E-WS-WT-PR-4113-A | Universal | Awaiting pre-offer from vendor | 81 |  |  | deepak@upe.co.in |  | 15.5.24 | [21 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | LPBS | LE21M277-E-WS-WT-PR-4113 | LE21M277-E-WS-WT-PR-4113-B | SRCS | Pre-order pending with EDRC | 59 |  |  | ashok@ragavendracontrol.com |  | 20.5.24 | 6.6.24 | [20 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | Earthing & Lightning Material | LE21M277-E-WS-WT-PR-4114 | LE21M277-E-WS-WT-PR-4114-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:45:38
Kendrapada 2 - Aul & Rajkanika | Electrical | Lighting Fixtures | LE21M277-E-WS-WT-PR-4115 | LE21M277-E-WS-WT-PR-4115-A | Bajaj | Pre-order pending with EDRC | 41 | Pre-order evaluation not required |  | sudhakar.k@bajajelectricals.com |  | 14.6.24 | 24.6.24 | [20 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | Lighting Fixtures | LE21M277-E-WS-WT-PR-4115 | LE21M277-E-WS-WT-PR-4115-B | WIPRO | Pre-order pending with EDRC | 20 | Pre-order evaluation not required |  | vipul.kumar35@wipro.com |  | 14.6.24 | 15.7.24 | [20 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | Lighting Fixtures | LE21M277-E-WS-WT-PR-4115 | LE21M277-E-WS-WT-PR-4115-C | Philips | Pre-order pending with EDRC | 19 | Pre-order evaluation not required |  | kaustuv.chanda@signify.com |  | 14.6.24 | 16.7.24 | [20 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:59
Kendrapada 2 - Aul & Rajkanika | Electrical | Lighting Materials & accessories | LE21M277-E-WS-WT-PR-4115A | LE21M277-E-WS-WT-PR-4115A-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 3.5.24 | 3.5.24 | 3.5.24 | [8 empty] | 3.5.24 | 3.5.24 | 3.5.24 | T1 | [7 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:11:55
Kendrapada 2 - Aul & Rajkanika | Electrical | LDB | LE21M277-E-WS-WT-PR-4115B | LE21M277-E-WS-WT-PR-4115B-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 3.5.24 | 3.5.24 | 3.5.24 | [8 empty] | 3.5.24 | 3.5.24 | 3.5.24 | T1 | [7 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:11:55
Kendrapada 2 - Aul & Rajkanika | Electrical | Safety Accessories | LE21M277-E-WS-WT-PR-4116 | LE21M277-E-WS-WT-PR-4116-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 10.3.23 | 10.3.23 | 10.3.23 | [8 empty] | 10.3.23 | 10.3.23 | 10.3.23 | T1 | [7 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:11:55
Kendrapada 2 - Aul & Rajkanika | Electrical | HT Termination Kit | LE21M277-E-WS-WT-PR-4118 | LE21M277-E-WS-WT-PR-4118-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 12.12.23 | 12.12.23 | 12.12.23 | [8 empty] | 12.12.23 | 12.12.23 | 12.12.23 | T1 | [7 empty] | 29.7.24 | 15.08.24 | 14.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:11:55
Khordha - 3 schemes | Process | Clariflocculator mechanism | LE21M278-P-WS-WT-PR-2402 | LE21M278-P-WS-WT-PR-2402-A | SHIVPAD | Sent to BU Operations | PR Closed |  | 90032 43278 | rajesh@shivpad.com | 14.02.24 | 14.02.24 | 27.02.24 | 07.03.24 | 18.03.24 | 22.03.24 | 28.03.24 | 01.04.24 | 07.04.24 | 16.04.24 | 23.04.24 | 23.04.24 | 16.04.24 | 23.04.24 | 29.06.24 | T2 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | dhitosh.sahoo@lntecc.com-22.07.2024-14:44:23
Khordha - 3 schemes | Process | Clariflocculator mechanism | LE21M278-P-WS-WT-PR-2402 | LE21M278-P-WS-WT-PR-2402-B | SRITECH | Awaiting post-offer from vendor | 13 |  | 94221 11017 | mohan@sritechindia.com | 14.02.24 | 14.02.24 | 26.02.24 | 07.03.24 | 13.03.24 | 20.03.24 | 25.03.24 | 01.04.24 | 05.04.24 | 15.05.24 |  |  | 17.05.24 | 17.05.24 | 29.06.24 | T4 | 22.07.24 | SRITECH | [5 empty] | 29.06.24 | 16.07.24 | 14.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Clariflocculator mechanism | LE21M278-P-WS-WT-PR-2402 | LE21M278-P-WS-WT-PR-2402-C | TRIVENI | Sent to BU Operations | PR Closed |  |  | neeraj.aggarwal@projects.trivenigroup.com hariom.sharma1@projects.trivenigroup.com |  | 08.02.24 | 28.03.24 | 04.04.24 | 26.04.24 | 15.05.24 | [6 empty] | 01.06.24 | 03.06.24 | 29.06.24 | T3 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | dhitosh.sahoo@lntecc.com-22.07.2024-14:44:23
Khordha - 3 schemes | Process | Clariflocculator mechanism | LE21M278-P-WS-WT-PR-2402 | LE21M278-P-WS-WT-PR-2402-D | Filsep Engineers | Sent to BU Operations | PR Closed |  |  | filsepengineers@gmail.com |  | 18.05.24 | 07.06.24 | 11.06.24 | 27.06.24 | [7 empty] | 28.06.24 | 28.06.24 | 29.06.24 | T1 | [7 empty] | 29.06.24 | 16.07.24 | 14.09.24 | dhitosh.sahoo@lntecc.com-22.07.2024-14:44:23
Khordha - 3 schemes | Process | Air Blower | LE21M278-P-WS-WT-PR-2403 | LE21M278-P-WS-WT-PR-2403-A | KAY | Sent to BU Operations | 41 |  | 95993 50900 | manish@kayblowers.com | 16.02.24 | 16.02.24 | 24.02.24 | 07.03.24 | 28.03.24 | 30.03.24 | 31.05.24 | 03.06.24 | 19.06.24 |  |  |  | 21.06.24 | 21.06.24 | 24.06.24 | T2 | [7 empty] | 24.06.24 | 11.07.24 | 09.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Air Blower | LE21M278-P-WS-WT-PR-2403 | LE21M278-P-WS-WT-PR-2403-B | SWAM | Sent to BU Operations | 41 |  | 8130744229 | shailesh@swamatics.com | 16.02.24 | 16.02.24 | 17.02.24 | 20.02.24 | 21.03.24 | 27.03.24 | 10.04.24 | 19.04.24 | 22.04.24 | 23.04.24 | 03.05.24 | 17.05.24 | 17.05.24 | 29.05.24 | 24.06.24 | T3 | [7 empty] | 24.06.24 | 11.07.24 | 09.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Air Blower | LE21M278-P-WS-WT-PR-2403 | LE21M278-P-WS-WT-PR-2403-C | Everest | Sent to BU Operations | 41 |  | 95828 22232 | Armoghan.Anwar@irco.com anurag.arora@irco.com | 16.02.24 | 16.02.24 | 20.03.24 | 27.03.24 | 02.05.24 | 17.05.24 | 30.05.24 | 03.06.24 |  |  |  |  | 03.06.24 | 05.06.24 | 24.06.24 | T1 | [7 empty] | 24.06.24 | 11.07.24 | 09.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Agitator | LE21M278-P-WS-WT-PR-2404 | LE21M278-P-WS-WT-PR-2404-A | FFP | Sent to BU Operations | 75 |  | 8104982550 | fibrein@gmail.com | 09.02.24 | 09.02.24 | 20.03.24 | 20.03.24 | 25.03.24 | 30.03.24 | 17.04.24 | 22.04.24 | 16.05.24 | 18.05.24 |  |  | 18.05.24 | 18.05.24 | 21.05.24 | T3 | [7 empty] | 21.05.24 | 07.06.24 | 06.08.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Agitator | LE21M278-P-WS-WT-PR-2404 | LE21M278-P-WS-WT-PR-2404-B | SRITECH | Sent to BU Operations | 75 |  | 94221 11017 | mohan@sritechindia.com | 09.02.24 | 09.02.24 | 11.03.24 | 15.03.24 | 25.03.24 | 30.03.24 | 02.04.24 | 06.04.24 | 12.04.24 |  |  |  | 12.04.24 | 12.04.24 | 21.05.24 | T2 | [7 empty] | 21.05.24 | 07.06.24 | 06.08.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Agitator | LE21M278-P-WS-WT-PR-2404 | LE21M278-P-WS-WT-PR-2404-C | SHIVPAD | Sent to BU Operations | 75 |  | 90032 43278 | rajesh@shivpad.com | 09.02.24 | 09.02.24 | 25.03.24 | 30.03.24 | 06.04.24 | 10.04.24 | [6 empty] | 10.04.24 | 10.04.24 | 21.05.24 | T1 | [7 empty] | 21.05.24 | 07.06.24 | 06.08.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | WTP Sluice gates | LE21M278-P-WS-WT-PR-2405 | LE21M278-P-WS-WT-PR-2405-A | JASH | Sent to BU Operations | 31 |  |  | lpgsouth@jashindia.com | 06.03.24 | 06.03.24 | 27.03.24 | 02.04.24 | 04.04.24 | 04.04.24 | 16.04.24 | 17.04.24 | 08.05.24 | 08.05.24 | 09.05.24 | 16.05.24 | 24.05.24 | 24.05.24 | 04.07.24 | T2 | [7 empty] | 04.07.24 | 21.07.24 | 19.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | WTP Sluice gates | LE21M278-P-WS-WT-PR-2405 | LE21M278-P-WS-WT-PR-2405-B | ORIENTAL | Sent to BU Operations | 31 |  |  | orientalcastings@gmail.com | 06.03.24 | 06.03.24 | 30.05.24 | 06.06.24 | 10.06.24 | 11.06.24 | 13.06.24 | 15.06.24 |  |  |  |  | 03.07.24 | 04.07.24 | 04.07.24 | T1 | [7 empty] | 04.07.24 | 21.07.24 | 19.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | WTP Sluice gates | LE21M278-P-WS-WT-PR-2405 | LE21M278-P-WS-WT-PR-2405-C | Fluid control | Sent to BU Operations | 31 |  |  | sales@fluidcontrol.in anjan@fluidcontrol.in |  | 01.04.24 | 22.04.24 | 27.04.24 | 01.05.24 | 08.05.24 | 24.05.24 | 06.06.24 | 10.06.24 |  |  |  | 10.06.24 | 10.06.24 | 04.07.24 | T3 | [7 empty] | 04.07.24 | 21.07.24 | 19.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Chlorination system | LE21M278-P-WS-WT-PR-2406 | LE21M278-P-WS-WT-PR-2406-A | Zion tech | Pre-order technically cleared | 55 |  |  | deepak@ziontech.in zion.tech2108@gmail.com | 13.03.24 | 13.03.24 | 29.03.24 | 04.04.24 | 10.04.24 | 24.04.24 | 27.05.24 | 01.06.24 | 10.06.24 |  |  |  | 03.06.24 | 10.06.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Chlorination system | LE21M278-P-WS-WT-PR-2406 | LE21M278-P-WS-WT-PR-2406-B | Toshcon | Pre-order pending with EDRC | 11 | Only data sheet shared, P&ID to be shared by vendor |  | metering2@toshcon.com | 13.03.24 | 13.03.24 | 24.07.24 | [20 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Chlorination system | LE21M278-P-WS-WT-PR-2406 | LE21M278-P-WS-WT-PR-2406-C | ME Infra | Pre-order pending with EDRC | 6 |  |  | amisra@meinfra.net sales@meinfra.net |  | 04.07.24 | 29.07.24 | [20 empty] | 30.08.24 |  |  | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:53
Khordha - 3 schemes | Process | Chlorine Tonner | LE21M278-P-WS-WT-PR-2407 | LE21M278-P-WS-WT-PR-2407-A | Zion tech | Pre-order technically cleared | 55 |  |  |  |  | 13.03.24 | 29.03.24 | 04.04.24 | 10.04.24 | 24.04.24 | 27.05.24 | 01.06.24 | 10.06.24 |  |  |  | 03.06.24 | 10.06.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Chlorine Tonner | LE21M278-P-WS-WT-PR-2407 | LE21M278-P-WS-WT-PR-2407-B | Tuschon | Pre-order pending with EDRC | 11 |  |  |  |  | 13.03.24 | 24.07.24 | [20 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Chlorine Tonner | LE21M278-P-WS-WT-PR-2407 | LE21M278-P-WS-WT-PR-2407-C | ME Infra | Pre-order pending with EDRC | 6 |  |  | amisra@meinfra.net sales@meinfra.net |  | 04.07.24 | 29.07.24 | [20 empty] | 30.08.24 |  |  | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:53
Khordha - 3 schemes | Process | Filter media | LE21M278-P-WS-WT-PR-2408 | LE21M278-P-WS-WT-PR-2408-A | Dalton mineral | Sent to BU Operations | 11 |  |  | daltonminerals@gmail.com |  | 17.06.24 | 20.06.24 | 25.06.24 | 10.07.24 | 12.07.24 | 23.07.24 | [5 empty] | 23.07.24 | 23.07.24 | 24.07.24 | T2 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Filter media | LE21M278-P-WS-WT-PR-2408 | LE21M278-P-WS-WT-PR-2408-B | Global adsorbents | Sent to BU Operations | 11 |  |  | sayoni@globaladsorbents.com |  | 17.06.24 | 21.06.24 | 27.06.24 | 29.06.24 | 04.07.24 | 10.07.24 | [5 empty] | 12.07.24 | 12.07.24 | 24.07.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Backwash pump | LE21M278-P-WS-WT-PR-2409 | LE21M278-P-WS-WT-PR-2409-A | WILO | Pre-order comments issued | 6 |  | 86800 68301 | manikkandan.pr@wilo.com | 16.02.24 | 16.02.24 | 24.02.24 | 28.02.24 | 28.03.24 | 01.04.24 | 12.04.24 | 22.04.24 | 29.07.24 | 29.07.24 | [13 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-11:20:35
Khordha - 3 schemes | Process | Backwash pump | LE21M278-P-WS-WT-PR-2409 | LE21M278-P-WS-WT-PR-2409-B | XYLEM | Regret offer | PR Closed | Vendor not responding sent mail to SCM on 05-07-2024, no response |  | sivakumar.natarajan@xylem.com Ajit.Magar@xylem.com | 16.02.24 | 16.02.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-26.07.2024-16:11:15
Khordha - 3 schemes | Process | Backwash pump | LE21M278-P-WS-WT-PR-2409 | LE21M278-P-WS-WT-PR-2409-C | WPIL | Regret offer | PR Closed | Vendor not responding sent mail to SCM on 05-07-2024, no response |  | cmktg@wpil.co.in r.chandramohan@wpil.co.in | 16.02.24 | 16.02.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-26.07.2024-16:11:15
Khordha - 3 schemes | Process | Backwash pump | LE21M278-P-WS-WT-PR-2409 | LE21M278-P-WS-WT-PR-2409-D | KBL | Regret offer | PR Closed | Vendor not responding sent mail to SCM on 05-07-2024, no response |  | Mohan.Kumar@kbl.co.in |  | 29.04.24 | 03.06.24 | 07.06.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-26.07.2024-16:11:15
Khordha - 3 schemes | Process | Submersible pump | LE21M278-P-WS-WT-PR-2410 | LE21M278-P-WS-WT-PR-2410-A | MBH | Pre-order technically cleared | 52 |  |  | northindustrial@mbhpumps.com | 06.03.24 | 06.03.24 | 10.04.24 | 26.04.24 | 07.05.24 | 21.05.24 | 10.06.24 | [5 empty] | 13.06.24 | 13.06.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Submersible pump | LE21M278-P-WS-WT-PR-2410 | LE21M278-P-WS-WT-PR-2410-B | AQUA | Pre-order comments issued | 51 | Vendor not responding sent mail to SCM on 05-07-2024, no response |  |  | 06.03.24 | 06.03.24 | 11.03.24 | 12.03.24 | 06.04.24 | 14.06.24 | 14.06.24 | [16 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Submersible pump | LE21M278-P-WS-WT-PR-2410 | LE21M278-P-WS-WT-PR-2410-C | Jasco | Pre-order pending with EDRC | 6 |  |  | hyd@jascopump.com tirthpatel@jascopump.com |  | 05.07.24 | 15.07.24 | 17.07.24 | 29.07.24 | [18 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:08:42
Khordha - 3 schemes | Process | Electrical hoist | LE21M278-P-WS-WT-PR-2411 | LE21M278-P-WS-WT-PR-2411-A | JAPS | Sent to BU Operations | 48 |  |  | tech.japsproject@gmail.com | 18.03.24 | 18.03.24 | 20.03.24 | 29.03.24 | 04.04.24 | 04.04.24 | 10.04.24 | 12.04.24 | 15.04.24 | 25.04.24 | 26.04.24 | 02.05.24 | 06.05.24 | 06.05.24 | 17.06.24 | T1 | [7 empty] | 17.06.24 | 04.07.24 | 02.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Electrical hoist | LE21M278-P-WS-WT-PR-2411 | LE21M278-P-WS-WT-PR-2411-B | INDEF | Sent to BU Operations | 48 |  |  | mrs@indef.com | 18.03.24 | 18.03.24 | 22.04.24 | 26.04.24 | 16.05.24 | 24.05.24 | 01.06.24 | 05.06.24 |  |  |  |  | 05.06.24 | 05.06.24 | 17.06.24 | T2 | [7 empty] | 17.06.24 | 04.07.24 | 02.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Manual chain pulley block | LE21M278-P-WS-WT-PR-2412 | LE21M278-P-WS-WT-PR-2412-A | Indef | Sent to BU Operations | 72 |  |  | mrs@indef.com |  | 03.04.24 | 22.04.24 | 26.04.24 | 03.05.24 | 03.05.24 | 16.05.24 | 21.05.24 | 22.05.24 |  |  |  | 22.05.24 | 22.05.24 | 24.05.24 | T2 | [7 empty] | 24.05.24 | 10.06.24 | 09.08.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Manual chain pulley block | LE21M278-P-WS-WT-PR-2412 | LE21M278-P-WS-WT-PR-2412-B | Japs | Sent to BU Operations | 72 |  |  | sales.japs@gmail.com |  | 03.04.24 | 04.04.24 | 09.04.24 | 10.04.24 | 20.04.24 | 20.04.24 | 25.04.24 | 26.04.24 | 26.04.24 |  |  | 26.04.24 | 26.04.24 | 24.05.24 | T1 | [7 empty] | 24.05.24 | 10.06.24 | 09.08.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Dosing pump | LE21M278-P-WS-WT-PR-2413 | LE21M278-P-WS-WT-PR-2413-A | Positive metering | Sent to BU Operations | 37 |  |  | ravindraj@positivemetering.com bdv2@positivemetering.com | 14.03.24 | 14.03.24 | 25.03.24 | 30.03.24 | 21.04.24 | 23.04.24 | 30.04.24 | 04.05.24 | 29.05.24 | 01.06.24 | 13.06.24 | 15.06.24 | 17.06.24 | 18.06.24 | 28.06.24 | T2 | [7 empty] | 28.06.24 | 15.07.24 | 13.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Dosing pump | LE21M278-P-WS-WT-PR-2413 | LE21M278-P-WS-WT-PR-2413-B | S R Metering | Sent to BU Operations | 37 |  |  | sr1@srmetering.com | 14.03.24 | 14.03.24 | 10.04.24 | 20.04.24 | 03.05.24 | 04.05.24 | 27.05.24 | 30.05.24 | 03.06.24 |  |  |  | 03.06.24 | 03.06.24 | 28.06.24 | T1 | [7 empty] | 28.06.24 | 15.07.24 | 13.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Sampling pump | LE21M278-P-WS-WT-PR-2414 | LE21M278-P-WS-WT-PR-2414-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site procurement | [28 empty] | dhitosh.sahoo@lntecc.com-15.05.2024-08:04:39
Khordha - 3 schemes | Process | Submersible mixer | LE21M278-P-WS-WT-PR-2415 | LE21M278-P-WS-WT-PR-2415-A | FFP | Sent to BU Operations | 72 |  | 8104982550 | fibrein@gmail.com |  | 18.03.24 | 25.03.24 | 01.04.24 | 17.04.24 | 24.04.24 | 16.05.24 | 18.05.24 |  |  |  |  | 21.05.24 | 21.05.24 | 24.05.24 | T2 | [7 empty] | 24.05.24 | 10.06.24 | 09.08.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Submersible mixer | LE21M278-P-WS-WT-PR-2415 | LE21M278-P-WS-WT-PR-2415-B | SULZER | Sent to BU Operations | 72 |  |  | wwtechennai@gmail.com |  | 18.03.24 | 25.03.24 | 01.04.24 | 07.05.24 | 18.05.24 | 21.05.24 | [5 empty] | 24.05.24 | 24.05.24 | 24.05.24 | T1 | [7 empty] | 24.05.24 | 10.06.24 | 09.08.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Dewatering pump | LE21M278-P-WS-WT-PR-2416 | LE21M278-P-WS-WT-PR-2416-A | MBH | Pre-order technically cleared | 47 |  |  | northindustrial@mbhpumps.com sales3@mbhpumps.com | 06.03.24 | 06.03.24 | 12.04.24 | 23.04.24 | 14.06.24 | 15.06.24 | [6 empty] | 18.06.24 | 18.06.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Dewatering pump | LE21M278-P-WS-WT-PR-2416 | LE21M278-P-WS-WT-PR-2416-B | AQUA | Regret offer | PR Closed | Vendor not responding sent mail to SCM on 05-07-2024, no response |  |  | 06.03.24 | 06.03.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:03
Khordha - 3 schemes | Process | Dewatering pump | LE21M278-P-WS-WT-PR-2416 | LE21M278-P-WS-WT-PR-2416-C | Jasco | Pre-order pending with EDRC | 6 |  |  | tirthpatel@jascopump.com hyd@jascopump.com |  | 05.07.24 | 15.07.24 | 17.07.24 | 29.07.24 | [18 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:08:42
Khordha - 3 schemes | Process | Dissolving tray | LE21M278-P-WS-WT-PR-2417 | LE21M278-P-WS-WT-PR-2417-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site procurement | [28 empty] | dhitosh.sahoo@lntecc.com-15.05.2024-08:04:39
Khordha - 3 schemes | Process | Trolley | LE21M278-P-WS-WT-PR-2418 | LE21M278-P-WS-WT-PR-2418-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site procurement | [28 empty] | dhitosh.sahoo@lntecc.com-15.05.2024-08:04:39
Khordha - 3 schemes | Process | Platform weighing machine | LE21M278-P-WS-WT-PR-2419 | LE21M278-P-WS-WT-PR-2419-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site procurement | [28 empty] | dhitosh.sahoo@lntecc.com-15.05.2024-08:04:39
Khordha - 3 schemes | Process | Exhaust fan | LE21M278-P-WS-WT-PR-2420 | LE21M278-P-WS-WT-PR-2420-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site procurement | [28 empty] | dhitosh.sahoo@lntecc.com-15.05.2024-08:04:39
Khordha - 3 schemes | Process | Lab Equipments | LE21M278-P-WS-WT-PR-2421 | LE21M278-P-WS-WT-PR-2421-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site procurement | [28 empty] | dhitosh.sahoo@lntecc.com-15.05.2024-08:04:39
Khordha - 3 schemes | Process | Sludge thickener | LE21M278-P-WS-WT-PR-2422 | LE21M278-P-WS-WT-PR-2422-A | SRITECH | Sent to BU Operations | 34 |  | 94221 11017 | mohan@sritechindia.com | 06.03.24 | 06.03.24 | 13.03.24 | 18.03.24 | 21.03.24 | 29.03.24 | 11.04.24 | 17.04.24 |  |  |  |  | 17.05.24 | 17.05.24 | 01.07.24 | T4 | [7 empty] | 01.07.24 | 18.07.24 | 16.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Process | Sludge thickener | LE21M278-P-WS-WT-PR-2422 | LE21M278-P-WS-WT-PR-2422-B | SHIVPAD | Sent to BU Operations | 34 |  | 90032 43278 | rajesh@shivpad.com | 06.03.24 | 06.03.24 | 11.03.24 | 14.03.24 | 27.03.24 | 30.03.24 | 06.04.24 | 17.04.24 |  |  |  |  | 24.05.24 | 24.05.24 | 01.07.24 | T2 | [7 empty] | 01.07.24 | 18.07.24 | 16.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Process | Sludge thickener | LE21M278-P-WS-WT-PR-2422 | LE21M278-P-WS-WT-PR-2422-C | TRIVENI | Sent to BU Operations | 34 |  |  | neeraj.aggarwal@projects.trivenigroup.com | 06.03.24 | 06.03.24 | 01.04.24 | 08.04.24 | 30.04.24 | 15.05.24 | 10.06.24 | [5 empty] | 10.06.24 | 10.06.24 | 01.07.24 | T3 | [7 empty] | 01.07.24 | 18.07.24 | 16.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Process | Sludge thickener | LE21M278-P-WS-WT-PR-2422 | LE21M278-P-WS-WT-PR-2422-D | Filsep Engineers | Sent to BU Operations | 34 |  |  | filsepengineers@gmail.com |  | 18.05.24 | 18.06.24 | 20.06.24 | 27.06.24 | [7 empty] | 28.06.24 | 28.06.24 | 01.07.24 | T1 | [7 empty] | 01.07.24 | 18.07.24 | 16.09.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Process | DWPE tank agitator | LE21M278-P-WS-WT-PR-2423 | LE21M278-P-WS-WT-PR-2423-A | FFP | Pre-order pending with EDRC | 6 |  | 8104982550 | fibrein@gmail.com |  | 02.04.24 | 17.04.24 | 23.04.24 | 29.07.24 | [18 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:08:43
Khordha - 3 schemes | Process | Centrifuge | LE21M278-P-WS-WT-PR-2424 | LE21M278-P-WS-WT-PR-2424-A | HILLERS DECANTER P LTD | Sent to BU Operations | 109 |  | 98300 73768 | enquiry@hillerindia.com | 06.03.24 | 06.03.24 | 11.03.24 | 13.03.24 | 14.03.24 | 15.03.24 | 20.03.24 | 30.03.24 | 05.04.24 | 10.04.24 | 10.04.24 |  | 16.04.24 | 16.04.24 | 17.04.24 | T1 | [7 empty] | 17.04.24 | 04.05.24 | 03.07.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Process | Centrifuge | LE21M278-P-WS-WT-PR-2424 | LE21M278-P-WS-WT-PR-2424-B | MCNALLY SAYAJI ENGINEERING LTD | Sent to BU Operations | 109 |  | 98303 80032 | tapan.datta@msel.co.in | 06.03.24 | 06.03.24 | 20.03.24 | 27.03.24 | 30.03.24 | 30.03.24 | 03.04.24 | 10.04.24 | 15.04.24 |  |  |  | 16.04.24 | 16.04.24 | 17.04.24 | T2 | [7 empty] | 17.04.24 | 04.05.24 | 03.07.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Process | Centrifuge | LE21M278-P-WS-WT-PR-2424 | LE21M278-P-WS-WT-PR-2424-C | Alfa laval | Regret offer | PR Closed |  |  |  |  | 01.04.24 | [21 empty] | 17.04.24 | 04.05.24 | 03.07.24 | dhitosh.sahoo@lntecc.com-02.07.2024-10:16:39
Khordha - 3 schemes | Process | Screw pumps | LE21M278-P-WS-WT-PR-2425 | LE21M278-P-WS-WT-PR-2425-A | FLOSYS | Pre-order comments issued | 48 | Vendor not responding |  | chennaibr@flosys.in | 06.03.24 | 06.03.24 | 08.04.24 | 19.04.24 | 31.05.24 | 06.06.24 | 17.06.24 | 17.06.24 | [15 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Process | Screw pumps | LE21M278-P-WS-WT-PR-2425 | LE21M278-P-WS-WT-PR-2425-B | CIRCOR | Pre-order technically cleared | 30 |  |  | Kavinkumar.Jaganathan@circor.com gowtham@tapengineering.com | 06.03.24 | 06.03.24 | 29.03.24 | 04.04.24 | 26.04.24 | 01.05.24 | 22.05.24 | 28.05.24 | 25.06.24 | 25.06.24 | 05.07.24 |  | 05.07.24 | 05.07.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Process | Screw pumps | LE21M278-P-WS-WT-PR-2425 | LE21M278-P-WS-WT-PR-2425-C | ROTO PUMPS | Regret offer | PR Closed |  |  | brd1@rotopumps.com chn3@rotopumps.com | 06.03.24 | 06.03.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-10.07.2024-11:44:51
Khordha - 3 schemes | Process | Screw pumps | LE21M278-P-WS-WT-PR-2425 | LE21M278-P-WS-WT-PR-2425-D | Positive Metering | Pre-order technically rejected | PR Closed |  | vendor not providing all the document, power consumption is very high so electrical rejected it. | bdv2@positivemetering.com |  | 02.05.24 | 28.05.24 | 28.05.24 | 15.07.24 | [18 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-20.07.2024-17:43:42
Khordha - 3 schemes | Process | PACL Unloading cum Transfer pump | LE21M278-P-WS-WT-PR-2426 | LE21M278-P-WS-WT-PR-2426-A | S J Industries | Pre-order comments issued | 6 |  | 9840350439 | sales@analapumps.co.in |  | 10.07.24 | 15.07.24 | 22.07.24 | 25.07.24 | 29.07.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-12:05:27
Khordha - 3 schemes | Process | Service water pump | LE21M278-P-WS-WT-PR-2427 | LE21M278-P-WS-WT-PR-2427-A | KSB | Awaiting pre-offer from vendor | 25 |  |  | Dhananjay.Bidnur@ksb.com |  | 10.07.24 | [21 empty] | 31.07.24 | 17.08.24 | 16.10.24 | dhitosh.sahoo@lntecc.com-29.07.2024-10:05:04
Khordha - 3 schemes | Mechanical | HSC Pump -CWPH & IBPS | LE21M278-M-WS-CW-PR-1503 | LE21M278-M-WS-CW-PR-1503-A | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 30.03.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | HSC Pump -CWPH & IBPS | LE21M278-M-WS-CW-PR-1503 | LE21M278-M-WS-CW-PR-1503-B | wilo | Pre-order comments issued | 25 |  |  | karticraja.s@wilo.com |  | 30.03.24 | 09.05.24 | 23.05.24 |  | 10.07.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:23:30
Khordha - 3 schemes | Mechanical | HSC Pump -CWPH & IBPS | LE21M278-M-WS-CW-PR-1503 | LE21M278-M-WS-CW-PR-1503-C | wpil | Pre-order comments issued | 25 |  |  | r.chandramohan@wpil.co.in |  | 30.03.24 | 24.04.24 | 15.05.24 | 15.05.24 | 10.07.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:23:30
Khordha - 3 schemes | Mechanical | SLV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1504 | LE21M278-M-WS-CW-PR-1504-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | SLV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1504 | LE21M278-M-WS-CW-PR-1504-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 01.04.24 | 04.04.24 | 05.05.24 | 08.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | SLV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1504 | LE21M278-M-WS-CW-PR-1504-C | rd multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 01.04.24 | 14.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | SLV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1504 | LE21M278-M-WS-CW-PR-1504-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | 12.04.24 | 17.05.24 | 31.05.24 | 29.06.24 | [6 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | SLV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1504 | LE21M278-M-WS-CW-PR-1504-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1505 | LE21M278-M-WS-CW-PR-1505-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1505 | LE21M278-M-WS-CW-PR-1505-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 01.04.24 | 04.04.24 | 05.05.24 | 08.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1505 | LE21M278-M-WS-CW-PR-1505-C | rd multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 01.04.24 | 14.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1505 | LE21M278-M-WS-CW-PR-1505-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | 12.04.24 | 17.05.24 | 31.05.24 | 29.06.24 | [6 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1505 | LE21M278-M-WS-CW-PR-1505-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | DJ -CWPH & IBPS | LE21M278-M-WS-CW-PR-1506 | LE21M278-M-WS-CW-PR-1506-A | avkindia | Regret offer | PR Closed |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [19 empty] | aknandy@lntecc.com-09.07.2024-20:15:03
Khordha - 3 schemes | Mechanical | DJ -CWPH & IBPS | LE21M278-M-WS-CW-PR-1506 | LE21M278-M-WS-CW-PR-1506-B | vag group | Regret offer | PR Closed |  |  | s.deepkanti@vag-group.com |  | 01.04.24 | 04.04.24 | 05.05.24 | 08.05.24 | 27.05.24 | 12.06.24 | [19 empty] | aknandy@lntecc.com-09.07.2024-20:12:08
Khordha - 3 schemes | Mechanical | DJ -CWPH & IBPS | LE21M278-M-WS-CW-PR-1506 | LE21M278-M-WS-CW-PR-1506-C | rd multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 01.04.24 | 14.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | DJ -CWPH & IBPS | LE21M278-M-WS-CW-PR-1506 | LE21M278-M-WS-CW-PR-1506-D | ivc valves | Regret offer | PR Closed |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-23.05.2024-12:10:31
Khordha - 3 schemes | Mechanical | DJ -CWPH & IBPS | LE21M278-M-WS-CW-PR-1506 | LE21M278-M-WS-CW-PR-1506-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1507 | LE21M278-M-WS-CW-PR-1507-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1507 | LE21M278-M-WS-CW-PR-1507-B | vag group | Pre-order technically rejected | PR Closed |  |  | s.deepkanti@vag-group.com |  | 01.04.24 | 04.04.24 | 05.05.24 | 08.05.24 | 27.05.24 | 12.06.24 | 29.06.24 | [18 empty] | aknandy@lntecc.com-10.07.2024-09:39:20
Khordha - 3 schemes | Mechanical | AV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1507 | LE21M278-M-WS-CW-PR-1507-C | rd multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 01.04.24 | 14.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1507 | LE21M278-M-WS-CW-PR-1507-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | 12.04.24 | 17.05.24 | 31.05.24 | 29.06.24 | [6 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1507 | LE21M278-M-WS-CW-PR-1507-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | EOT Crane -CWPH & IBPS | LE21M278-M-WS-CW-PR-1509 | LE21M278-M-WS-CW-PR-1509-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | dhanaraj.s@lntecc.com-15.05.2024-09:58:34
Khordha - 3 schemes | Mechanical | BFV -CWPH & IBPS | LE21M278-M-WS-CW-PR-1510 | LE21M278-M-WS-CW-PR-1510-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | Electric Hoist -CWPH & IBPS | LE21M278-M-WS-CW-PR-1511 | LE21M278-M-WS-CW-PR-1511-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | dhanaraj.s@lntecc.com-15.05.2024-09:58:34
Khordha - 3 schemes | Mechanical | Submersible Pump -CWPH & IBPS | LE21M278-M-WS-CW-PR-1512 | LE21M278-M-WS-CW-PR-1512-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | dhanaraj.s@lntecc.com-15.05.2024-09:58:34
Khordha - 3 schemes | Mechanical | Isolation Valve -Pipeline | LE21M278-M-WS-CW-PR-1513 | LE21M278-M-WS-CW-PR-1513-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -Pipeline | LE21M278-M-WS-CW-PR-1514 | LE21M278-M-WS-CW-PR-1514-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | PRV -Pipeline | LE21M278-M-WS-CW-PR-1515 | LE21M278-M-WS-CW-PR-1515-A | avkindia | Regret offer | PR Closed |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | [21 empty] | aknandy@lntecc.com-21.05.2024-17:46:26
Khordha - 3 schemes | Mechanical | FCV -Pipeline | LE21M278-M-WS-CW-PR-1516 | LE21M278-M-WS-CW-PR-1516-A | avkindia | Regret offer | PR Closed |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | [21 empty] | aknandy@lntecc.com-23.05.2024-12:10:31
Khordha - 3 schemes | Mechanical | Sluice Gate -CWPH & IBPS | LE21M278-M-WS-CW-PR-1517 | LE21M278-M-WS-CW-PR-1517-A | Fluid Control | Sent to BU Operations | 20 |  |  | sales@fluidcontrol.in | 18.01.23 | 28.02.24 | 29.02.24 | 13.03.24 | 15.03.24 | 29.03.24 | 06.04.24 | [5 empty] | 17.05.24 | 06.04.24 | 15.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-18.07.2024-14:08:10
Khordha - 3 schemes | Mechanical | Sluice Gate -CWPH & IBPS | LE21M278-M-WS-CW-PR-1517 | LE21M278-M-WS-CW-PR-1517-B | JashIndia | Sent to BU Operations | 20 |  |  | abhijeet@jashindia.com | 18.01.23 | 28.02.24 | 05.04.24 | 30.04.24 | 02.05.24 | 22.05.24 | [6 empty] | 15.07.24 | 15.07.24 | 15.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-18.07.2024-14:09:32
Khordha - 3 schemes | Mechanical | Sluice Gate -Intake | LE21M278-M-WS-CW-PR-1517 | LE21M278-M-WS-CW-PR-1517-C | Orientalcastings | Sent to BU Operations | 20 |  |  | orientalcastings@gmail.com | 18.01.23 | 28.02.24 | 05.04.24 | 30.04.24 | 20.06.24 | 15.07.24 | [6 empty] | 12.07.24 | 12.07.24 | 15.07.24 | T1 | [10 empty] | deepak.sabnani@lntecc.com-18.07.2024-14:09:32
Khordha - 3 schemes | Mechanical | ACV -Surge Protection Device | LE21M278-M-WS-CW-PR-1518 | LE21M278-M-WS-CW-PR-1518-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | aknandy@lntecc.com-23.05.2024-12:10:31
Khordha - 3 schemes | Mechanical | ZVV -Surge Protection Device | LE21M278-M-WS-CW-PR-1519 | LE21M278-M-WS-CW-PR-1519-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | aknandy@lntecc.com-23.05.2024-12:10:31
Khordha - 3 schemes | Mechanical | Surge Vessel -Surge Protection Device | LE21M278-M-WS-CW-PR-1520 | LE21M278-M-WS-CW-PR-1520-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | dhanaraj.s@lntecc.com-15.05.2024-09:58:34
Khordha - 3 schemes | Mechanical | Exhaust fan -Mech | LE21M278-M-WS-CW-PR-1521 | LE21M278-M-WS-CW-PR-1521-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | dhanaraj.s@lntecc.com-15.05.2024-09:58:34
Khordha - 3 schemes | Mechanical | VT Pump -Intake | LE21M278-M-WS-RW-PR-1501A | LE21M278-M-WS-RW-PR-1501A-A | KBL | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in | 18.01.23 | 19.02.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:14:14
Khordha - 3 schemes | Mechanical | VT Pump -Intake | LE21M278-M-WS-RW-PR-1501A | LE21M278-M-WS-RW-PR-1501A-B | WILO | Pre-order technically cleared | 75 |  |  | karticraja.s@wilo.com | 18.01.23 | 19.02.24 | 24.02.24 | 11.03.24 | 20.05.24 | 21.05.24 | [6 empty] | 21.05.24 | 20.05.24 | [12 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | VT Pump -Intake | LE21M278-M-WS-RW-PR-1501A | LE21M278-M-WS-RW-PR-1501A-C | WPIL | Pre-order comments issued | 24 |  |  | cmktg@wpil.co.in | 18.01.23 | 19.02.24 | 27.05.24 | 11.07.24 | [22 empty] | aknandy@lntecc.com-11.07.2024-21:01:43
Khordha - 3 schemes | Mechanical | Sluice Gate -Intake | LE21M278-M-WS-RW-PR-1502A | LE21M278-M-WS-RW-PR-1502A-A | Fluid Control | Sent to BU Operations | 20 |  |  | sales@fluidcontrol.in | 18.01.23 | 28.02.24 | 29.02.24 | 13.03.24 | 15.03.24 | 29.03.24 | 06.04.24 | [5 empty] | 17.05.24 | 06.04.24 | 15.07.24 | T1 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-14:03:06
Khordha - 3 schemes | Mechanical | Sluice Gate -Intake | LE21M278-M-WS-RW-PR-1502A | LE21M278-M-WS-RW-PR-1502A-B | JashIndia | Sent to BU Operations | 20 |  |  | abhijeet@jashindia.com | 18.01.23 | 28.02.24 | 05.04.24 | 30.04.24 | 02.05.24 | 22.05.24 | [6 empty] | 15.07.24 | 15.07.24 | 15.07.24 | T1 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | deepak.sabnani@lntecc.com-18.07.2024-14:03:06
Khordha - 3 schemes | Mechanical | Sluice Gate -Intake | LE21M278-M-WS-RW-PR-1502A | LE21M278-M-WS-RW-PR-1502A-C | Orientalcastings | Sent to BU Operations | 20 |  |  | orientalcastings@gmail.com | 18.01.23 | 28.02.24 | 05.04.24 | 30.04.24 | 20.06.24 | 15.07.24 | [6 empty] | 12.07.24 | 12.07.24 | 15.07.24 | T1 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | rallabandi.bharadwaj@lntecc.com-15.07.2024-18:49:08
Khordha - 3 schemes | Mechanical | SLV -Intake | LE21M278-M-WS-RW-PR-1504 | LE21M278-M-WS-RW-PR-1504-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | SLV -Intake | LE21M278-M-WS-RW-PR-1504 | LE21M278-M-WS-RW-PR-1504-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 01.04.24 | 04.04.24 | 05.05.24 | 08.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | SLV -Intake | LE21M278-M-WS-RW-PR-1504 | LE21M278-M-WS-RW-PR-1504-C | rd multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 01.04.24 | 14.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | SLV -Intake | LE21M278-M-WS-RW-PR-1504 | LE21M278-M-WS-RW-PR-1504-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | 12.04.24 | 17.05.24 | 31.05.24 | 29.06.24 | [6 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | SLV -Intake | LE21M278-M-WS-RW-PR-1504 | LE21M278-M-WS-RW-PR-1504-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -Intake | LE21M278-M-WS-RW-PR-1505 | LE21M278-M-WS-RW-PR-1505-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -Intake | LE21M278-M-WS-RW-PR-1505 | LE21M278-M-WS-RW-PR-1505-B | vag group | Sent to BU Operations | 36 |  |  | s.deepkanti@vag-group.com |  | 01.04.24 | 04.04.24 | 05.05.24 | 08.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -Intake | LE21M278-M-WS-RW-PR-1505 | LE21M278-M-WS-RW-PR-1505-C | rd multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 01.04.24 | 14.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -Intake | LE21M278-M-WS-RW-PR-1505 | LE21M278-M-WS-RW-PR-1505-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | 12.04.24 | 17.05.24 | 31.05.24 | 29.06.24 | [6 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | NRV -Intake | LE21M278-M-WS-RW-PR-1505 | LE21M278-M-WS-RW-PR-1505-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | DJ -Intake | LE21M278-M-WS-RW-PR-1506 | LE21M278-M-WS-RW-PR-1506-A | avkindia | Regret offer | PR Closed |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [19 empty] | aknandy@lntecc.com-09.07.2024-20:15:03
Khordha - 3 schemes | Mechanical | DJ -Intake | LE21M278-M-WS-RW-PR-1506 | LE21M278-M-WS-RW-PR-1506-B | vag group | Regret offer | PR Closed |  |  | s.deepkanti@vag-group.com |  | 01.04.24 | 04.04.24 | 05.05.24 | 08.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | [12 empty] | aknandy@lntecc.com-09.07.2024-20:12:08
Khordha - 3 schemes | Mechanical | DJ -Intake | LE21M278-M-WS-RW-PR-1506 | LE21M278-M-WS-RW-PR-1506-C | rd multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 01.04.24 | 14.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | DJ -Intake | LE21M278-M-WS-RW-PR-1506 | LE21M278-M-WS-RW-PR-1506-D | ivc valves | Regret offer | PR Closed |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-21.05.2024-17:53:32
Khordha - 3 schemes | Mechanical | DJ -Intake | LE21M278-M-WS-RW-PR-1506 | LE21M278-M-WS-RW-PR-1506-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -Intake | LE21M278-M-WS-RW-PR-1507 | LE21M278-M-WS-RW-PR-1507-A | avkindia | Sent to BU Operations | 36 |  |  | subhash@avkindia.com |  | 01.04.24 | 08.04.24 | 02.05.24 | 04.05.24 | 27.05.24 | 12.06.24 | [5 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -Intake | LE21M278-M-WS-RW-PR-1507 | LE21M278-M-WS-RW-PR-1507-B | vag group | Pre-order technically rejected | PR Closed |  |  | s.deepkanti@vag-group.com |  | 01.04.24 | 04.04.24 | 05.05.24 | 08.05.24 | 27.05.24 | 12.06.24 | 29.06.24 | [15 empty] | 12.07.24 | 29.07.24 | 27.09.24 | aknandy@lntecc.com-10.07.2024-09:39:20
Khordha - 3 schemes | Mechanical | AV -Intake | LE21M278-M-WS-RW-PR-1507 | LE21M278-M-WS-RW-PR-1507-C | rd multiples | Pre-order comments issued | 26 |  |  | mumbai@rdmultiples.com |  | 01.04.24 | 14.06.24 | 09.07.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -Intake | LE21M278-M-WS-RW-PR-1507 | LE21M278-M-WS-RW-PR-1507-D | ivc valves | Sent to BU Operations | 36 |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | 12.04.24 | 17.05.24 | 31.05.24 | 29.06.24 | [6 empty] | 29.06.24 | 29.06.24 | 29.06.24 | T2 |  |  |  |  | 29.06.24 |  |  | 29.06.24 | 16.07.24 | 14.09.24 | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | AV -Intake | LE21M278-M-WS-RW-PR-1507 | LE21M278-M-WS-RW-PR-1507-E | kbl | Regret offer | PR Closed | Not responded |  | Nilu.Deb@kbl.co.in |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-11.07.2024-19:15:04
Khordha - 3 schemes | Mechanical | EB -Intake | LE21M278-M-WS-RW-PR-1508 | LE21M278-M-WS-RW-PR-1508-A | ivc valves | Regret offer | PR Closed |  |  | sales.odisha@ivc-valves.com |  | 01.04.24 | [24 empty] | aknandy@lntecc.com-23.05.2024-12:10:31
Khordha - 3 schemes | Mechanical | EOT Crane -Intake | LE21M278-M-WS-RW-PR-1509 | LE21M278-M-WS-RW-PR-1509-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | aknandy@lntecc.com-23.05.2024-12:10:31
Khordha - 3 schemes | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE21M278-I-WS-WT-PR-5101 | LE21M278-I-WS-WT-PR-5101-A | H Guru | Sent to BU Operations | 73 |  |  | info@hgurusouth.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE21M278-I-WS-WT-PR-5101 | LE21M278-I-WS-WT-PR-5101-B | General Gauges | Sent to BU Operations | 73 |  |  | gicchennai@general-gauges.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Pressure Switch | LE21M278-I-WS-WT-PR-5102 | LE21M278-I-WS-WT-PR-5102-A | H Guru | Sent to BU Operations | 73 |  |  | info@hgurusouth.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Pressure Switch | LE21M278-I-WS-WT-PR-5102 | LE21M278-I-WS-WT-PR-5102-B | General Gauges | Sent to BU Operations | 73 |  |  | gicchennai@general-gauges.com |  | 03.04.24 | 04.04.24 | 12.04.24 | 16.04.24 | [7 empty] | 16.04.24 | 16.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Pressure transmitter | LE21M278-I-WS-WT-PR-5103 | LE21M278-I-WS-WT-PR-5103-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Pressure transmitter | LE21M278-I-WS-WT-PR-5103 | LE21M278-I-WS-WT-PR-5103-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Pressure transmitter | LE21M278-I-WS-WT-PR-5103 | LE21M278-I-WS-WT-PR-5103-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Float & Board Level gauge | LE21M278-I-WS-WT-PR-5104 | LE21M278-I-WS-WT-PR-5104-A | SBEM | Sent to BU Operations | 30 |  |  | rajesh.p@sbem.co.in |  | 06.04.24 | 14.05.24 | 14.05.24 | 30.05.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:01:06
Khordha - 3 schemes | Instrumentation | Float & Board Level gauge | LE21M278-I-WS-WT-PR-5104 | LE21M278-I-WS-WT-PR-5104-B | Pune Techtrol | Sent to BU Operations | 30 |  |  | mktg2@punetechtrol.com |  | 06.04.24 | 20.04.24 | 14.05.24 | 30.05.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:01:06
Khordha - 3 schemes | Instrumentation | level switch - Conductivity type | LE21M278-I-WS-WT-PR-5105 | LE21M278-I-WS-WT-PR-5105-A | SBEM | Sent to BU Operations | 30 |  |  | rajesh.p@sbem.co.in |  | 06.04.24 | 20.04.24 | 20.04.24 | 30.05.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:01:06
Khordha - 3 schemes | Instrumentation | level switch - Conductivity type | LE21M278-I-WS-WT-PR-5105 | LE21M278-I-WS-WT-PR-5105-B | Pune Techtrol | Sent to BU Operations | 30 |  |  | mktg2@punetechtrol.com |  | 06.04.24 | 20.04.24 | 14.05.24 | 30.05.24 | [7 empty] | 01.06.24 | 01.06.24 | 05.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:01:06
Khordha - 3 schemes | Instrumentation | Ultrasonic level Transmitter | LE21M278-I-WS-WT-PR-5106 | LE21M278-I-WS-WT-PR-5106-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Ultrasonic level Transmitter | LE21M278-I-WS-WT-PR-5106 | LE21M278-I-WS-WT-PR-5106-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Ultrasonic level Transmitter | LE21M278-I-WS-WT-PR-5106 | LE21M278-I-WS-WT-PR-5106-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Radar Level Transmitter | LE21M278-I-WS-WT-PR-5107 | LE21M278-I-WS-WT-PR-5107-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Radar Level Transmitter | LE21M278-I-WS-WT-PR-5107 | LE21M278-I-WS-WT-PR-5107-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Radar Level Transmitter | LE21M278-I-WS-WT-PR-5107 | LE21M278-I-WS-WT-PR-5107-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Loss of head transmitter | LE21M278-I-WS-WT-PR-5108 | LE21M278-I-WS-WT-PR-5108-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Loss of head transmitter | LE21M278-I-WS-WT-PR-5108 | LE21M278-I-WS-WT-PR-5108-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Loss of head transmitter | LE21M278-I-WS-WT-PR-5108 | LE21M278-I-WS-WT-PR-5108-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Rate for flow transmitter | LE21M278-I-WS-WT-PR-5109 | LE21M278-I-WS-WT-PR-5109-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Rate for flow transmitter | LE21M278-I-WS-WT-PR-5109 | LE21M278-I-WS-WT-PR-5109-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Rate for flow transmitter | LE21M278-I-WS-WT-PR-5109 | LE21M278-I-WS-WT-PR-5109-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Bypass Rotameter | LE21M278-I-WS-WT-PR-5110 | LE21M278-I-WS-WT-PR-5110-A | Scientific device | Pre-order comments issued | 13 |  |  | info@scientificdevices.org |  | 09.07.24 | 17.07.24 | 22.07.24 | [19 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:27:07
Khordha - 3 schemes | Instrumentation | Bypass Rotameter | LE21M278-I-WS-WT-PR-5110 | LE21M278-I-WS-WT-PR-5110-B | Eureka | Pre-order comments issued | 13 |  |  | chennaioffice@eurekaflow.com |  | 09.07.24 | 17.07.24 | 22.07.24 | [19 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:27:07
Khordha - 3 schemes | Instrumentation | Electromagnectic flow meter | LE21M278-I-WS-WT-PR-5111 | LE21M278-I-WS-WT-PR-5111-A | E&H | Sent to BU Operations | PR Closed |  |  | ramkumar.m@endress.com |  | 15.03.24 | 26.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T2 | [7 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:30:12
Khordha - 3 schemes | Instrumentation | Electromagnectic flow meter | LE21M278-I-WS-WT-PR-5111 | LE21M278-I-WS-WT-PR-5111-B | Krohne marshall | Sent to BU Operations | PR Closed |  |  | dilibanr@forbesmarshall.com |  | 15.03.24 | 25.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T3 | [7 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:30:12
Khordha - 3 schemes | Instrumentation | Electromagnectic flow meter | LE21M278-I-WS-WT-PR-5111 | LE21M278-I-WS-WT-PR-5111-C | Siemens | Awaiting post-offer from vendor | 13 |  |  | keerthi.guruswamy.ext@siemens.com |  | 15.03.24 | 24.04.24 | 03.05.24 | 28.05.24 | [7 empty] | 28.05.24 | 28.05.24 | 01.06.24 | T1 | 22.07.24 | Siemens | [5 empty] | 01.06.24 | 18.06.24 | 17.08.24 | SURENDHAR@lntecc.com-22.07.2024-15:30:12
Khordha - 3 schemes | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M278-I-WS-WT-PR-5112 | LE21M278-I-WS-WT-PR-5112-A | ABB | Sent to BU Operations | 73 |  |  | sai.ram@in.abb.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 16.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T3 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M278-I-WS-WT-PR-5112 | LE21M278-I-WS-WT-PR-5112-B | E&H | Sent to BU Operations | 73 |  |  | ramkumar.m@endress.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 11.04.24 | 20.04.24 | 26.04.24 | [5 empty] | 26.04.24 | 26.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Ultrasonic type Open channel flow transmitter | LE21M278-I-WS-WT-PR-5112 | LE21M278-I-WS-WT-PR-5112-C | Siemens | Sent to BU Operations | 73 |  |  | keerthi.guruswamy.ext@siemens.com |  | 19.03.24 | 25.03.24 | 11.04.24 | 17.04.24 | 20.04.24 | 24.04.24 | [5 empty] | 24.04.24 | 24.04.24 | 23.05.24 | T1 | [7 empty] | 23.05.24 | 09.06.24 | 08.08.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Instrumentation | Battery Operated Flow meter | LE21M278-I-WS-WT-PR-5113 | LE21M278-I-WS-WT-PR-5113-A | ABB | Pre-order comments issued | 13 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 01.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 15.07.24 | 22.07.24 | [15 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:27:07
Khordha - 3 schemes | Instrumentation | Battery Operated Flow meter | LE21M278-I-WS-WT-PR-5113 | LE21M278-I-WS-WT-PR-5113-B | siemens | Pre-order comments issued | 13 |  |  | keerthi.guruswamy.ext@siemens.com |  | 06.04.24 | 26.04.24 | 30.05.24 | 07.06.24 | 15.06.24 | 15.07.24 | 22.07.24 | [15 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-22.07.2024-09:27:07
Khordha - 3 schemes | Instrumentation | pH Meter | LE21M278-I-WS-WT-PR-5114 | LE21M278-I-WS-WT-PR-5114-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:21:25
Khordha - 3 schemes | Instrumentation | pH Meter | LE21M278-I-WS-WT-PR-5114 | LE21M278-I-WS-WT-PR-5114-B | E&H | Sent to BU Operations | 17 |  |  | ramkumar.m@endress.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:21:25
Khordha - 3 schemes | Instrumentation | pH Meter | LE21M278-I-WS-WT-PR-5114 | LE21M278-I-WS-WT-PR-5114-C | ABB | Sent to BU Operations | 17 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:21:25
Khordha - 3 schemes | Instrumentation | Turbidity meter | LE21M278-I-WS-WT-PR-5115 | LE21M278-I-WS-WT-PR-5115-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 02.05.24 | 24.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:21:25
Khordha - 3 schemes | Instrumentation | Turbidity meter | LE21M278-I-WS-WT-PR-5115 | LE21M278-I-WS-WT-PR-5115-C | ABB | Sent to BU Operations | 17 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:21:25
Khordha - 3 schemes | Instrumentation | Residual Chlorine Analyzer | LE21M278-I-WS-WT-PR-5116 | LE21M278-I-WS-WT-PR-5116-A | HACH | Sent to BU Operations | 17 |  |  | mohanraj.elumalai@hach.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T3 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:21:25
Khordha - 3 schemes | Instrumentation | Turbidity meter | LE21M278-I-WS-WT-PR-5115 | LE21M278-I-WS-WT-PR-5116-B | E&H | Sent to BU Operations | 17 |  |  | ramkumar.m@endress.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:21:25
Khordha - 3 schemes | Instrumentation | Residual Chlorine Analyzer | LE21M278-I-WS-WT-PR-5116 | LE21M278-I-WS-WT-PR-5116-C | ABB | Sent to BU Operations | 17 |  |  | sai.ram@in.abb.com |  | 06.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 10.07.24 | [5 empty] | 15.07.24 | 16.07.24 | 18.07.24 | T2 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-18.07.2024-14:21:25
Khordha - 3 schemes | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M278-I-WS-WT-PR-5117 | LE21M278-I-WS-WT-PR-5117-A | Schneider | Awaiting pre-offer from vendor | 30 |  |  | rushyendhar.repalli@se.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-11:56:23
Khordha - 3 schemes | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M278-I-WS-WT-PR-5117 | LE21M278-I-WS-WT-PR-5117-B | Honeywell | Awaiting pre-offer from vendor | 30 |  |  | Srinivasan.Venkateswaran@Honeywell.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-11:56:23
Khordha - 3 schemes | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE21M278-I-WS-WT-PR-5117 | LE21M278-I-WS-WT-PR-5117-C | Siemens | Awaiting pre-offer from vendor | 30 |  |  | jeyanth.j@siemens.com |  | 05.07.24 | [21 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-09.07.2024-12:01:06
Khordha - 3 schemes | Instrumentation | instrumentation Control & signal Cables | LE21M278-I-WS-WT-PR-5118 | LE21M278-I-WS-WT-PR-5118-A | Delton | Sent to BU Operations | 24 |  |  | jus@deltoncables.com |  | 03.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-15.07.2024-10:03:01
Khordha - 3 schemes | Instrumentation | instrumentation Control & signal Cables | LE21M278-I-WS-WT-PR-5118 | LE21M278-I-WS-WT-PR-5118-B | Cords | Sent to BU Operations | 24 |  |  | tendering@cordscable.com |  | 03.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-15.07.2024-10:03:01
Khordha - 3 schemes | Instrumentation | instrumentation Control & signal Cables | LE21M278-I-WS-WT-PR-5118 | LE21M278-I-WS-WT-PR-5118-C | Thermocables | Sent to BU Operations | 24 |  |  | chennai@thermopads.com |  | 03.04.24 | 02.05.24 | 30.05.24 | 07.06.24 | 15.06.24 | 05.07.24 | [5 empty] | 05.07.24 | 05.07.24 | 11.07.24 | T1 | [7 empty] | 30.08.24 | 16.09.24 | 15.11.24 | SURENDHAR@lntecc.com-15.07.2024-10:03:01
Khordha - 3 schemes | Instrumentation | UPS | LE21M278-I-WS-WT-PR-5119 | LE21M278-I-WS-WT-PR-5119-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.09.24 | 17.10.24 | 16.12.24 | SURENDHAR@lntecc.com-02.07.2024-14:25:52
Khordha - 3 schemes | Electrical | Transformer | LE21M278-E-WS-WT-PR-4103 | LE21M278-E-WS-WT-PR-4103-A | CGL | Regret offer | PR Closed | No Response |  | Ramesh.Ram@cgglobal.com | 30.11.23 | 17.2.24 | [21 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:43:13
Khordha - 3 schemes | Electrical | Transformer | LE21M278-E-WS-WT-PR-4103 | LE21M278-E-WS-WT-PR-4103-B | Kirloskar | Regret offer | PR Closed | No response |  | aditya.ksr@kirloskarelectric.com | 30.11.23 | 17.2.24 | 13.04.24 | 22.04.24 | [19 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-10.07.2024-12:03:58
Khordha - 3 schemes | Electrical | Transformer | LE21M278-E-WS-WT-PR-4103 | LE21M278-E-WS-WT-PR-4103-C | Voltamp | Regret offer | PR Closed | As per telecon ,vendor has informed that they are not interested to quote if the ratings below 250 kVA |  | sasik_vtlchn@voltamptransformers.com | 30.11.23 | 17.2.24 | 27.2.24 | 29.2.24 | [19 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-16.07.2024-14:15:37
Khordha - 3 schemes | Electrical | Transformer | LE21M278-E-WS-WT-PR-4103 | LE21M278-E-WS-WT-PR-4103-D | VOLTECH | Sent to BU Operations | 19 |  |  | adalarasan.r@voltechgroup.com |  | 11.06.24 | 18.06.24 | 21.06.24 | 11.7.24 | 15.7.24 | [6 empty] | 11.7.24 | 15.7.24 | 16.7.24 | T1 | [7 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | Transformer | LE21M278-E-WS-WT-PR-4103 | LE21M278-E-WS-WT-PR-4103-E | Toshiba | Regret offer | PR Closed | Regret Communication Via Mail,not having suitable designs matching with our specifications requirement. 24.6.24 |  | marketing@toshiba-ttdi.com |  | 14.6.24 | [21 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-16.07.2024-14:15:37
Khordha - 3 schemes | Electrical | Transformer | LE21M278-E-WS-WT-PR-4103 | LE21M278-E-WS-WT-PR-4103-F | Power Star | Sent to BU Operations | 19 |  |  | sailaja@powerstarelectric.net |  | 14.6.24 | 4.7.24 | 5.7.24 | 12.7.24 | 12.7.24 | 15.7.24 | [5 empty] | 12.7.24 | 15.7.24 | 16.7.24 | T1 | [7 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | Transformer | LE21M278-E-WS-WT-PR-4103 | LE21M278-E-WS-WT-PR-4103-G | TBEA | Sent to BU Operations | 19 |  |  |  |  | 2.7.24 | 12.7.24 | 12.7.24 | 15.7.24 | [7 empty] | 12.7.24 | 15.7.24 | 16.7.24 | T1 | [7 empty] | 15.7.24 | 01.08.24 | 30.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | Transformer | LE21M278-E-WS-WT-PR-4103 | LE21M278-E-WS-WT-PR-4103-H | PETE | Regret offer | PR Closed | Regret Communication Via Mail,not having suitable designs matching with our specifications requirement.10.7.24 |  | rajesh.b@hammondpowersolutions.com |  | 9.7.24 | [24 empty] | karthik.ajithkumar@lntecc.com-16.07.2024-14:15:37
Khordha - 3 schemes | Electrical | HT Panel | LE21M278-E-WS-WT-PR-4104 | LE21M278-E-WS-WT-PR-4104-A | Symatic south Siemens | Pre-order technically cleared | 33 | Symatic System integrater |  | symaticindia@gmail.com | 7.12.23 | 2.3.24 | 3.4.24 | 26.04.24 | 6.6.24 | 2.7.24 | [6 empty] | 6.6.24 | 2.7.24 | [9 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | HT Panel | LE21M278-E-WS-WT-PR-4104 | LE21M278-E-WS-WT-PR-4104-B | ABB | Regret offer | PR Closed | Since ABB is not manufacturing outdoor panel |  | rajkumar.sv@in.abb.com | 7.12.23 | 2.3.24 | [21 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:43:13
Khordha - 3 schemes | Electrical | HT Panel | LE21M278-E-WS-WT-PR-4104 | LE21M278-E-WS-WT-PR-4104-C | Universal | Pre-order technically cleared | 27 |  |  | deepak@upe.co.in | 7.12.23 | 20.04.24 | 2.6.24 | 2.7.24 | 7.7.24 | 8.7.24 | [6 empty] | 7.7.24 | 8.7.24 | [9 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | HT Panel | LE21M278-E-WS-WT-PR-4104 | LE21M278-E-WS-WT-PR-4104-D | EAP | Regret offer | PR Closed | sent mailfor type test report on 24.5.24 No response |  | sales@eapindia.com | 7.12.23 | 24.04.24 | [21 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-18.07.2024-16:54:12
Khordha - 3 schemes | Electrical | HT Panel | LE21M278-E-WS-WT-PR-4104 | LE21M278-E-WS-WT-PR-4104-E | HTS | Pre-order technically cleared | 34 |  |  | marketing@htswitchgears.com | 7.12.23 | 20.4.24 | 25.4.24 | 30.4.24 | 3.5.24 | 3.5.24 | 8.5.24 | 1.7.24 |  |  |  |  | 1.7.24 | 1.7.24 | [9 empty] | 14.7.24 | 31.07.24 | 29.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | HT Panel | LE21M278-E-WS-WT-PR-4104 | LE21M278-E-WS-WT-PR-4104-H | Popular | Pre-order technically cleared | 17 |  |  | lkrishnamoorthi@popularswitchgears.co.in |  | 9.7.24 | 12.7.24 | 18.7.24 | [8 empty] | 17.7.24 | 18.7.24 | [12 empty] | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | DG Set | LE21M278-E-WS-WT-PR-4106 | LE21M278-E-WS-WT-PR-4106-A | Jackson | Sent to BU Operations | 18 | Followed up on 9.5.24 Reminder mail send on 18.5.24 |  | mahenoor.tabassum@jakson.com | 30.11.23 | 28.2.24 | 6.3.24 | 19.3.24 | 29.3.24 | 11.04.24 | 21.5.24 | 28.06.24 |  |  |  |  | 28.06.24 | 21.06.24 | 17.7.24 | T1 | [7 empty] | 13.7.24 | 30.07.24 | 28.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | DG Set | LE21M278-E-WS-WT-PR-4106 | LE21M278-E-WS-WT-PR-4106-B | IEC | Sent to BU Operations | 18 |  |  | niraj.sharma@iecgensets.com | 30.11.23 | 29.2.24 | 29.3.24 | 24.04.24 | 30.5.24 | 29.06.24 | [6 empty] | 29.06.24 | 30.05.24 | 17.7.24 | T1 | [7 empty] | 13.7.24 | 30.07.24 | 28.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | DG Set | LE21M278-E-WS-WT-PR-4106 | LE21M278-E-WS-WT-PR-4106-C | Gainwell | Sent to BU Operations | 18 |  |  | aftab.ali@gainwellindia.com | 30.11.23 | 7.3.24 | 8.3.24 | 20.3.24 | 4.4.24 | 11.4.24 | 30.4.24 | 17.5.24 | 21.5.24 | 29.5.24 | 4.7.24 | 11.7.24 | 4.7.24 | 11.7.24 | 17.7.24 | T1 | [7 empty] | 13.7.24 | 30.07.24 | 28.09.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | LT panels | LE21M278-E-WS-WT-PR-4107 | LE21M278-E-WS-WT-PR-4107-A | Kontact ABB | Regret offer | PR Closed | No response |  | proposal@kontact.in | 7.12.23 | 23.2.24 | 08.03.24 | 25.3.24 | 6.4.24 | 29.04.24 | [17 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | LT panels | LE21M278-E-WS-WT-PR-4107 | LE21M278-E-WS-WT-PR-4107-B | Schneider | Regret offer | PR Closed | No response |  | s.sandhya@se.com | 7.12.23 | 23.2.24 | 22.3.24 | 3.4.24 | 18.4.24 | 26.04.24 | 9.5.24 | 24.5.24 | [15 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | LT panels | LE21M278-E-WS-WT-PR-4107 | LE21M278-E-WS-WT-PR-4107-C | Siemens | Regret offer | PR Closed | No response |  | murugaraj.s@siemens.com | 7.12.23 | 27.2.24 | [21 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-06.07.2024-16:13:14
Khordha - 3 schemes | Electrical | LT panels | LE21M278-E-WS-WT-PR-4107 | LE21M278-E-WS-WT-PR-4107-D | SRCS | Pre-order pending with EDRC | 26 |  |  | ashok@ragavendracontrol.com | 7.12.23 | 8.4.24 | 15.5.24 | 14.6.24 | 6.7.24 | 6.7.24 | 9.7.24 | [16 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | LT panels | LE21M278-E-WS-WT-PR-4107 | LE21M278-E-WS-WT-PR-4107-E | UPE | Pre-order pending with EDRC | 19 |  |  | deepak@upe.co.in | 7.12.23 | 18.04.24 | 26.4.24 | 31.5.24 | 16.7.24 | [18 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | LT panels | LE21M278-E-WS-WT-PR-4107 | LE21M278-E-WS-WT-PR-4107-F | EAP | Pre-order technically cleared | 25 |  |  | sales@eapindia.com | 7.12.23 | 18.04.24 | 2.5.24 | 17.5.24 | 22.5.24 | 01.07.24 | 1.7.24 | 10.7.24 |  |  |  |  | 01.07.24 | 01.07.24 | [9 empty] | 20.7.24 | 06.08.24 | 05.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | Power and Control Cable | LE21M278-E-WS-WT-PR-4110 | LE21M278-E-WS-WT-PR-4110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:43:13
Khordha - 3 schemes | Electrical | Cable Tray | LE21M278-E-WS-WT-PR-4111 | LE21M278-E-WS-WT-PR-4111-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:43:13
Khordha - 3 schemes | Electrical | Lugs & Glands | LE21M278-E-WS-WT-PR-4112 | LE21M278-E-WS-WT-PR-4112-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:43:13
Khordha - 3 schemes | Electrical | HT Termination Kit | LE21M278-E-WS-WT-PR-4112A | LE21M278-E-WS-WT-PR-4112A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-03.07.2024-17:43:13
Khordha - 3 schemes | Electrical | LPBS | LE21M278-E-WS-WT-PR-4113 | LE21M278-E-WS-WT-PR-4113-A | Universal | Awaiting pre-offer from vendor | 81 |  |  | deepak@upe.co.in |  | 15.5.24 | [21 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | LPBS | LE21M278-E-WS-WT-PR-4113 | LE21M278-E-WS-WT-PR-4113-B | SRCS | Pre-order pending with EDRC | 59 |  |  | ashok@ragavendracontrol.com |  | 20.5.24 | 6.6.24 | [20 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | Earthing & Lightning Material | LE21M278-E-WS-WT-PR-4114 | LE21M278-E-WS-WT-PR-4114-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 15.5.24 | 15.5.24 | 15.5.24 | [8 empty] | 15.5.24 | 15.5.24 | 15.5.24 | T1 | [7 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:05:52
Khordha - 3 schemes | Electrical | Lighting Fixtures | LE21M278-E-WS-WT-PR-4115 | LE21M278-E-WS-WT-PR-4115-A | Bajaj | Pre-order pending with EDRC | 41 | Pre-order evaluation not required |  | sudhakar.k@bajajelectricals.com |  | 14.6.24 | 24.6.24 | [9 empty] | 3.5.24 | 3.5.24 | 3.5.24 | T1 | [7 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | Lighting Fixtures | LE21M278-E-WS-WT-PR-4115 | LE21M278-E-WS-WT-PR-4115-B | WIPRO | Pre-order pending with EDRC | 22 | Pre-order evaluation not required |  | vipul.kumar35@wipro.com |  | 14.6.24 | 13.7.24 | [20 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | Lighting Fixtures | LE21M278-E-WS-WT-PR-4115 | LE21M278-E-WS-WT-PR-4115-C | Philips | Pre-order pending with EDRC | 20 | Pre-order evaluation not required |  | kaustuv.chanda@signify.com |  | 14.6.24 | 15.7.24 | [20 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-08:44:08
Khordha - 3 schemes | Electrical | Lighting Materials & accessories | LE21M278-E-WS-WT-PR-4115A | LE21M278-E-WS-WT-PR-4115A-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 3.5.24 | 3.5.24 | 3.5.24 | [8 empty] | 3.5.24 | 3.5.24 | 3.5.24 | T1 | [7 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:05:52
Khordha - 3 schemes | Electrical | LDB | LE21M278-E-WS-WT-PR-4115B | LE21M278-E-WS-WT-PR-4115B-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 3.5.24 | 3.5.24 | 3.5.24 | [8 empty] | 3.5.24 | 3.5.24 | 3.5.24 | T1 | [7 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:05:52
Khordha - 3 schemes | Electrical | Safety Accessories | LE21M278-E-WS-WT-PR-4116 | LE21M278-E-WS-WT-PR-4116-A | Vendor Name yet to provide | Enquiry yet to float | NA | Pre-order evaluation not required |  |  |  | 11.10.21 | 11.10.21 | 11.10.21 | [8 empty] | 11.10.21 | 11.10.21 | 11.10.21 | T1 | [7 empty] | 25.7.24 | 11.08.24 | 10.10.24 | karthik.ajithkumar@lntecc.com-22.07.2024-15:05:52
MADIKHEDA | Process | clariflocculator mechanism | LE20M185-P-WS-WT-PR-2302 | LE20M185-P-WS-WT-PR-2302-A | SHIVPAD | Approved by Client | PR Closed |  |  |  | 26.05.21 | 26.05.21 | 07.01.22 | 13.01.22 | [8 empty] | 25.02.22 | 28.02.22 | 21.04.22 | T1 | 24.04.22 | SHIVPAD | 28.04.22 | 06.05.22 | 08.08.22 | 18.08.22 | 29.09.22 |  |  | 23.06.22 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | clariflocculator mechanism | LE20M185-P-WS-WT-PR-2302 | LE20M185-P-WS-WT-PR-2302-B | Triveni | Sent to BU Operations | PR Closed |  |  |  | 26.05.21 | 26.05.21 | 15.01.22 | 21.01.22 | [8 empty] | 05.03.22 | 07.03.22 | 21.03.22 | T2 | [6 empty] | 06.04.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:29:12
MADIKHEDA | Process | clariflocculator mechanism | LE20M185-P-WS-WT-PR-2302 | LE20M185-P-WS-WT-PR-2302-C | HWE | Sent to BU Operations | PR Closed |  |  |  | 26.05.21 | 26.05.21 | 10.03.22 | 17.03.22 | [8 empty] | 21.03.22 | 23.03.22 | 30.03.22 | T3 | [6 empty] | 16.04.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:29:12
MADIKHEDA | Process | Air Blower | LE20M185-P-WS-WT-PR-2303 | LE20M185-P-WS-WT-PR-2303-A | Kay | Sent to BU Operations | PR Closed |  |  |  | 29.05.21 | 29.05.21 | 25.03.22 | 16.04.22 | [8 empty] | 23.06.22 | 30.06.22 | 01.07.22 | T2 | [6 empty] | 30.07.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-12:35:21
MADIKHEDA | Process | Air Blower | LE20M185-P-WS-WT-PR-2303 | LE20M185-P-WS-WT-PR-2303-B | Everest | Approved by Client | PR Closed |  |  |  | 29.05.21 | 29.05.21 | 21.04.22 | 25.04.22 | [8 empty] | 11.06.22 | 13.06.22 | 29.07.22 | T1 | 18.08.22 | Everest | 22.08.22 | 24.08.22 | 03.01.23 | 07.01.23 | 25.08.23 |  |  | 17.10.22 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Air Blower | LE20M185-P-WS-WT-PR-2303 | LE20M185-P-WS-WT-PR-2303-C | KPT Industries | Sent to BU Operations | PR Closed |  |  |  | 29.05.21 | 29.05.21 | 30.03.22 | 16.04.22 | [8 empty] | 11.05.22 | 12.05.22 | 14.05.22 | T3 | [6 empty] | 16.05.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-12:35:21
MADIKHEDA | Process | Agitator | LE20M185-P-WS-WT-PR-2304 | LE20M185-P-WS-WT-PR-2304-A | SHIVPAD | Approved by Client | PR Closed |  |  |  | 11.06.21 | 11.06.21 | 12.01.22 | 29.01.22 | [8 empty] | 25.02.22 | 01.03.22 | 19.03.22 | T1 | 24.03.22 | SHIVPAD | 04.04.22 | 06.05.22 | 20.06.22 | 21.06.22 | 21.06.22 |  |  | 23.05.22 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Agitator | LE20M185-P-WS-WT-PR-2304 | LE20M185-P-WS-WT-PR-2304-B | Triveni | Sent to BU Operations | PR Closed |  |  |  | 11.06.21 | 11.06.21 | 15.01.22 | 31.01.22 | [8 empty] | 05.03.22 | 07.03.22 | 21.03.22 | T2 | [6 empty] | 06.04.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-12:34:07
MADIKHEDA | Process | Agitator | LE20M185-P-WS-WT-PR-2304 | LE20M185-P-WS-WT-PR-2304-C | HWE | Sent to BU Operations | PR Closed |  |  |  | 11.06.21 | 11.06.21 | 10.03.22 | 17.03.22 | [8 empty] | 11.04.22 | 15.04.22 | 15.04.22 | T3 | [6 empty] | 16.04.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-12:34:07
MADIKHEDA | Process | Sluice gates | LE20M185-P-WS-WT-PR-2305 | LE20M185-P-WS-WT-PR-2305-A | Jash | Approved by Client | PR Closed |  |  |  | 02.08.21 | 02.08.21 | 19.01.22 | 28.01.22 | [8 empty] | 03.03.22 | 05.03.22 | 23.03.22 | T1 | 09.04.22 | Jash | 16.04.22 | 24.04.22 | 22.07.22 | 22.07.22 | 02.08.22 |  |  | 08.06.22 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Sluice gates | LE20M185-P-WS-WT-PR-2305 | LE20M185-P-WS-WT-PR-2305-B | Oriental | Sent to BU Operations | PR Closed |  |  |  | 02.08.21 | 02.08.21 | 07.02.22 | 24.02.22 | [8 empty] | 15.03.22 | 21.03.22 | 25.03.22 | T3 | [6 empty] | 26.03.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:36:18
MADIKHEDA | Process | Sluice gates | LE20M185-P-WS-WT-PR-2305 | LE20M185-P-WS-WT-PR-2305-C | HWE | Sent to BU Operations | PR Closed |  |  |  | 02.08.21 | 02.08.21 | 10.03.22 | 16.03.22 | [8 empty] | 22.03.22 | 24.03.22 | 27.03.22 | T2 | [6 empty] | 15.04.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:36:18
MADIKHEDA | Process | Chlorination system | LE20M185-P-WS-WT-PR-2306 | LE20M185-P-WS-WT-PR-2306-A | Zion | Approved by Client | PR Closed |  |  |  | 19.08.21 | 19.08.21 | 18.01.22 | 10.02.22 | [8 empty] | 20.06.22 | 22.06.22 | 15.08.22 | T1 | 20.08.22 | Zion | 29.08.22 | 02.09.22 | 02.12.22 | 17.12.22 | 30.12.22 |  |  | 19.10.22 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Chlorination system | LE20M185-P-WS-WT-PR-2306 | LE20M185-P-WS-WT-PR-2306-B | ME Infra | Sent to BU Operations | PR Closed |  |  |  | 19.08.21 | 19.08.21 | 05.02.22 | 22.02.22 | [8 empty] | 22.06.22 | 22.06.22 | 01.07.22 | T3 | [6 empty] | 22.07.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:31:24
MADIKHEDA | Process | Chlorination system | LE20M185-P-WS-WT-PR-2306 | LE20M185-P-WS-WT-PR-2306-C | IEC | Sent to BU Operations | PR Closed |  |  |  | 19.08.21 | 19.08.21 | 10.02.22 | 02.05.22 | [8 empty] | 27.05.22 | 29.05.22 | 29.05.22 | T4 | [6 empty] | 01.06.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:31:24
MADIKHEDA | Process | Chlorination system | LE20M185-P-WS-WT-PR-2306 | LE20M185-P-WS-WT-PR-2306-D | Toshcon | Sent to BU Operations | PR Closed |  |  |  | 19.08.21 | 19.08.21 | 14.02.22 | 03.05.22 | [8 empty] | 25.05.22 | 25.05.22 | 30.05.22 | T2 | [6 empty] | 02.06.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:31:24
MADIKHEDA | Process | Air compressor | LE20M185-P-WS-WT-PR-2307 | LE20M185-P-WS-WT-PR-2307-A | Indo Air | Sent to BU Operations | 419 |  |  |  | 29.06.21 | 29.06.21 | 22.09.22 | 01.10.22 | [8 empty] | 19.12.22 | 26.12.22 | 09.06.23 | T3 | [6 empty] | 12.06.23 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-15:15:40
MADIKHEDA | Process | Air compressor | LE20M185-P-WS-WT-PR-2307 | LE20M185-P-WS-WT-PR-2307-B | Atlas Copco | Sent to BU Operations | 422 |  |  |  | 29.06.21 | 29.06.21 | 26.09.22 | 01.10.22 | [8 empty] | 27.10.22 | 01.12.22 | 09.06.23 | T2 | [6 empty] | 09.06.23 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-15:15:40
MADIKHEDA | Process | Air compressor | LE20M185-P-WS-WT-PR-2307 | LE20M185-P-WS-WT-PR-2307-C | ELGi | Pre-order comments issued | 47 |  |  |  |  | 29.06.21 | 15.06.24 | 18.06.24 | [11 empty] | T1 | [10 empty] | rajesh.g1@lntecc.com-03.07.2024-15:15:40
MADIKHEDA | Process | Filter media | LE20M185-P-WS-WT-PR-2308 | LE20M185-P-WS-WT-PR-2308-A | Dalton | Approved by Client | PR Closed |  |  |  | 24.06.21 | 24.06.21 | 23.09.22 | 28.09.22 | [8 empty] | 05.11.22 | 15.11.22 | 13.01.23 | T1 | 21.02.23 | Dalton | 15.03.23 | 24.03.23 | 25.03.23 | 28.03.23 | 11.04.23 |  |  | 22.04.23 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Filter media | LE20M185-P-WS-WT-PR-2308 | LE20M185-P-WS-WT-PR-2308-B | Maa kalyaneshwari | Sent to BU Operations | PR Closed |  |  |  | 24.06.21 | 24.06.21 | 07.10.22 | 14.10.22 | [8 empty] | 26.10.22 | 04.11.22 | 21.11.22 | T3 | [6 empty] | 04.12.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:38:25
MADIKHEDA | Process | Filter media | LE20M185-P-WS-WT-PR-2308 | LE20M185-P-WS-WT-PR-2308-C | Bharat Mineral | Sent to BU Operations | PR Closed |  |  |  | 24.06.21 | 24.06.21 | 29.11.22 | 17.12.22 | [8 empty] | 13.02.23 | 17.02.23 | 11.03.23 | T2 | [6 empty] | 19.03.23 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:38:25
MADIKHEDA | Process | Backwash Reservoir pump | LE20M185-P-WS-WT-PR-2309 | LE20M185-P-WS-WT-PR-2309-A | KBL | Sent to BU Operations | PR Closed |  |  |  | 05.06.21 | 05.06.21 | 19.03.22 | 19.04.22 | [8 empty] | 26.04.22 | 27.04.22 | 11.05.22 | T3 | [6 empty] | 19.05.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:27:29
MADIKHEDA | Process | Backwash Reservoir pump | LE20M185-P-WS-WT-PR-2309 | LE20M185-P-WS-WT-PR-2309-B | WILO | Approved by Client | PR Closed |  |  |  | 05.06.21 | 05.06.21 | 06.04.22 | 25.04.22 | [8 empty] | 25.07.22 | 30.07.22 | 01.11.22 | T1 | 14.12.22 | WILO | 11.01.23 | 04.02.23 | 16.06.23 | 17.06.23 | 23.06.23 |  |  | 12.02.23 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Backwash Reservoir pump | LE20M185-P-WS-WT-PR-2309 | LE20M185-P-WS-WT-PR-2309-C | WPIL | Sent to BU Operations | PR Closed |  |  |  | 05.06.21 | 05.06.21 | 06.04.22 | 19.04.22 | [8 empty] | 01.08.22 | 18.08.22 | 12.09.22 | T2 | [6 empty] | 17.09.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:27:29
MADIKHEDA | Process | Submersible pump | LE20M185-P-WS-WT-PR-2310 | LE20M185-P-WS-WT-PR-2310-A | Aqua | Sent to BU Operations | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 13.10.22 | 19.10.22 | [8 empty] | 04.01.23 | 06.02.23 | 14.02.23 | T2 | [6 empty] | 08.03.23 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:34:29
MADIKHEDA | Process | Submersible pump | LE20M185-P-WS-WT-PR-2310 | LE20M185-P-WS-WT-PR-2310-B | Sulzer | Sent to BU Operations | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 21.10.22 | 04.11.22 | [8 empty] | 11.11.22 | 24.11.22 | 30.11.22 | T3 | [6 empty] | 04.12.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:34:29
MADIKHEDA | Process | Submersible pump | LE20M185-P-WS-WT-PR-2310 | LE20M185-P-WS-WT-PR-2310-C | MBH pumps | Approved by Client | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 25.10.22 | 04.11.22 | [8 empty] | 06.02.23 | 23.02.23 | 28.05.23 | T1 | 21.06.23 | MBH pumps | 22.06.23 | 30.06.23 | 07.08.23 | 09.08.23 | 23.08.23 |  |  | 20.08.23 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Electrical hoist | LE20M185-P-WS-WT-PR-2311 | LE20M185-P-WS-WT-PR-2311-A | JAPS | Approved by Client | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 18.06.22 | 14.07.22 | [8 empty] | 01.08.22 | 06.08.22 | 26.08.22 | T1 | 12.09.22 | JAPS | 29.10.22 | 25.11.22 | 26.12.22 | 11.01.23 | 27.01.23 |  |  | 11.11.22 | rajesh.g1@lntecc.com-03.07.2024-15:15:41
MADIKHEDA | Process | Electrical hoist | LE20M185-P-WS-WT-PR-2311 | LE20M185-P-WS-WT-PR-2311-B | REVA | Sent to BU Operations | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 05.07.22 | 14.07.22 | [8 empty] | 02.08.22 | 17.08.22 | 03.09.22 | T2 | [6 empty] | 16.09.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Manual chain pulley block | LE20M185-P-WS-WT-PR-2312 | LE20M185-P-WS-WT-PR-2312-A | JAPS | Approved by Client | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 18.06.22 | 14.07.22 | [8 empty] | 01.08.22 | 06.08.22 | 07.09.22 | T1 | 13.09.22 | JAPS | 29.10.22 | 25.11.22 | 26.12.22 | 11.01.23 | 27.01.23 |  |  | 12.11.22 | rajesh.g1@lntecc.com-03.07.2024-15:15:41
MADIKHEDA | Process | Manual chain pulley block | LE20M185-P-WS-WT-PR-2312 | LE20M185-P-WS-WT-PR-2312-B | REVA | Sent to BU Operations | PR Closed |  |  |  | 23.07.21 | 23.07.21 | 05.07.22 | 14.07.22 | [8 empty] | 02.08.22 | 17.08.22 | 19.08.22 | T2 | [6 empty] | 16.09.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Dosing pump | LE20M185-P-WS-WT-PR-2313 | LE20M185-P-WS-WT-PR-2313-A | Positive Metering | Sent to BU Operations | PR Closed |  |  |  | 11.06.21 | 11.06.21 | 22.09.22 | 27.09.22 | [8 empty] | 17.11.22 | 01.12.22 | 14.12.22 | T2 | [6 empty] | 31.12.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Dosing pump | LE20M185-P-WS-WT-PR-2313 | LE20M185-P-WS-WT-PR-2313-B | SR Metering | Approved by Client | PR Closed |  |  |  | 11.06.21 | 11.06.21 | 22.09.22 | 28.09.22 | [8 empty] | 18.12.22 | 26.12.22 | 27.12.22 | T1 | 31.12.22 | SR Metering | 21.06.21 | 09.03.22 | 28.04.23 | 02.06.23 | 12.06.23 |  |  | 01.03.23 | rajesh.g1@lntecc.com-03.07.2024-15:15:41
MADIKHEDA | Process | Sampling pump | LE20M185-P-WS-WT-PR-2314 | LE20M185-P-WS-WT-PR-2314-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 25.05.21 | 25.05.21 | 28.05.21 | [19 empty] | 24.06.21 |  |  |  | rajesh.g1@lntecc.com-10.06.2024-09:45:11
MADIKHEDA | Process | Submersible mixer | LE20M185-P-WS-WT-PR-2315 | LE20M185-P-WS-WT-PR-2315-A | ATE Sulzer | Approved by Client | PR Closed |  |  |  | 29.05.21 | 29.05.21 | 12.10.22 | 19.10.22 | [8 empty] | 07.12.22 | 17.12.22 | 01.01.23 | T1 | 10.01.23 | ATE Sulzer | 22.02.23 | 23.02.23 | 05.05.23 | 02.06.23 | 19.06.23 |  |  | 11.03.23 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Submersible mixer | LE20M185-P-WS-WT-PR-2315 | LE20M185-P-WS-WT-PR-2315-B | FFP | Sent to BU Operations | PR Closed |  |  |  | 29.05.21 | 29.05.21 | 20.01.23 | 27.01.23 | [8 empty] | 25.02.23 | 25.02.23 | 25.02.23 | T2 | [6 empty] | 26.02.23 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:34:29
MADIKHEDA | Process | Dewatering pump | LE20M185-P-WS-WT-PR-2316 | LE20M185-P-WS-WT-PR-2316-A | Aqua | Sent to BU Operations | PR Closed |  |  |  | 11.06.21 | 11.06.21 | 13.10.22 | 19.10.22 | [8 empty] | 04.01.23 | 06.02.23 | 02.03.23 | T2 | [6 empty] | 08.03.23 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Dewatering pump | LE20M185-P-WS-WT-PR-2316 | LE20M185-P-WS-WT-PR-2316-B | Sulzer | Sent to BU Operations | PR Closed |  |  |  | 11.06.21 | 11.06.21 | 21.10.22 | 04.11.22 | [8 empty] | 21.11.22 | 02.12.22 | 02.12.22 | T3 | [6 empty] | 04.12.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Dewatering pump | LE20M185-P-WS-WT-PR-2316 | LE20M185-P-WS-WT-PR-2316-C | MBH pumps | Approved by Client | PR Closed |  |  |  | 11.06.21 | 11.06.21 | 25.10.22 | 04.11.22 | [8 empty] | 06.02.23 | 23.02.23 | 07.06.23 | T1 | 21.06.23 | MBH pumps | 22.06.23 | 30.06.23 | 07.08.23 | 09.08.23 | 24.08.23 |  |  | 20.08.23 | rajesh.g1@lntecc.com-03.07.2024-15:15:41
MADIKHEDA | Process | trolley | LE20M185-P-WS-WT-PR-2317 | LE20M185-P-WS-WT-PR-2317-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 29.05.21 | 29.05.21 | [24 empty] | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | platform weighing machine | LE20M185-P-WS-WT-PR-2318 | LE20M185-P-WS-WT-PR-2318-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 29.05.21 | 29.05.21 | [24 empty] | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | SDB Media | LE20M185-P-WS-WT-PR-2319 | LE20M185-P-WS-WT-PR-2319-A | Dalton | Approved by Client | PR Closed |  |  |  | 24.06.21 | 24.06.21 | 23.09.22 | 28.09.22 | [8 empty] | 05.11.22 | 15.11.22 | 15.02.23 | T1 | 02.03.23 | Dalton | 15.03.23 | 24.03.23 | 25.03.23 | 28.03.23 | 11.04.23 |  |  | 01.05.23 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | SDB Media | LE20M185-P-WS-WT-PR-2319 | LE20M185-P-WS-WT-PR-2319-B | Maa kalyaneshwari | Sent to BU Operations | PR Closed |  |  |  | 24.06.21 | 24.06.21 | 07.10.22 | 14.10.22 | [8 empty] | 26.10.22 | 04.11.22 | 15.11.22 | T3 | [6 empty] | 04.12.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:38:25
MADIKHEDA | Process | SDB Media | LE20M185-P-WS-WT-PR-2319 | LE20M185-P-WS-WT-PR-2319-C | Bharat Mineral | Sent to BU Operations | PR Closed |  |  |  | 24.06.21 | 24.06.21 | 29.11.22 | 17.12.22 | [8 empty] | 13.02.23 | 17.02.23 | 14.03.23 | T2 | [6 empty] | 19.03.23 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:38:25
MADIKHEDA | Process | lab equipment | LE20M185-P-WS-WT-PR-2320 | LE20M185-P-WS-WT-PR-2320-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 05.06.21 | 05.06.21 | [24 empty] | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Nozzles | LE20M185-P-WS-WT-PR-2321 | LE20M185-P-WS-WT-PR-2321-A | VP Engineers | Approved by Client | PR Closed |  |  |  | 29.06.21 | 29.06.21 | 23.02.22 | 24.02.22 | [8 empty] | 25.02.22 | 28.02.22 | 04.03.22 | T1 | 04.03.22 | VP Engineers | 09.03.22 | 14.03.22 | 26.03.22 | 02.04.22 | 12.04.22 |  |  | 03.05.22 | rajesh.g1@lntecc.com-03.07.2024-15:15:41
MADIKHEDA | Process | Nozzles | LE20M185-P-WS-WT-PR-2321 | LE20M185-P-WS-WT-PR-2321-B | Guddi | Sent to BU Operations | PR Closed |  |  |  | 29.06.21 | 29.06.21 | 24.02.22 | 25.02.22 | [8 empty] | 02.03.22 | 03.03.22 | 04.03.22 | T2 | [6 empty] | 02.04.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Exhaust fan | LE20M185-P-WS-WT-PR-2322 | LE20M185-P-WS-WT-PR-2322-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 02.08.21 | 02.08.21 | [24 empty] | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Service water pump | LE20M185-P-WS-WT-PR-2323 | LE20M185-P-WS-WT-PR-2323-A | Vendor Name yet to provide | Regret offer | PR Closed | Site Procurement |  |  | 23.07.21 | 23.07.21 | [24 empty] | rajesh.g1@lntecc.com-03.07.2024-15:15:41
MADIKHEDA | Process | Chlorine tonner | LE20M185-P-WS-WT-PR-2324 | LE20M185-P-WS-WT-PR-2324-A | Zion | Approved by Client | PR Closed |  |  |  | 07.08.21 | 07.08.21 | 18.01.22 | 10.02.22 | [8 empty] | 20.06.22 | 22.06.22 | 08.07.22 | T1 | 21.08.22 | Zion | 29.08.22 | 02.09.22 | 02.12.22 | 17.12.22 | 30.12.22 |  |  | 20.10.22 | rajesh.g1@lntecc.com-03.07.2024-14:53:20
MADIKHEDA | Process | Chlorine tonner | LE20M185-P-WS-WT-PR-2324 | LE20M185-P-WS-WT-PR-2324-B | ME Infra | Sent to BU Operations | PR Closed |  |  |  | 07.08.21 | 07.08.21 | 05.02.22 | 22.02.22 | [8 empty] | 22.06.22 | 22.06.22 | 27.06.22 | T3 | [6 empty] | 22.07.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:31:24
MADIKHEDA | Process | Chlorine tonner | LE20M185-P-WS-WT-PR-2324 | LE20M185-P-WS-WT-PR-2324-C | IEC | Sent to BU Operations | PR Closed |  |  |  | 07.08.21 | 07.08.21 | 10.02.22 | 02.05.22 | [8 empty] | 27.05.22 | 30.05.22 | 30.05.22 | T4 | [6 empty] | 01.06.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:31:24
MADIKHEDA | Process | Chlorine tonner | LE20M185-P-WS-WT-PR-2324 | LE20M185-P-WS-WT-PR-2324-D | Toshcon | Sent to BU Operations | PR Closed |  |  |  | 07.08.21 | 07.08.21 | 14.02.22 | 03.05.22 | [8 empty] | 14.05.22 | 29.05.22 | 29.05.22 | T2 | [6 empty] | 02.06.22 |  |  |  | rajesh.g1@lntecc.com-03.07.2024-14:31:24
MADIKHEDA | Process | Rechlorination system | LE20M185-P-WS-WT-PR-2325 | LE20M185-P-WS-WT-PR-2325-A | Vendor Name yet to provide | Enquiry yet to float | NA | BU to float enquiry |  |  | 07.08.21 | 07.08.21 | [24 empty] | rajesh.g1@lntecc.com-03.07.2024-15:15:41
MADIKHEDA | Mechanical | ACV, ZVV | LE20M185-M-002 | LE20M185-M-002-A | Sigmaflow | Post-order technically cleared | 52 | Enquiry floated to sigmaflow/Flownix/Jash |  |  | 27.03.22 | 27.03.24 | 17.04.24 | 21.04.24 | 26.04.24 | [7 empty] | 06.05.24 | 06.05.24 | 06.05.24 | T1 | 27.05.24 | Sigmaflow | 29.05.24 | 30.05.24 | 31.05.24 | 13.06.24 |  | 06.05.24 | 23.05.24 | 26.07.24 | gopal.samarth@lntecc.com-10.07.2024-16:56:54
MADIKHEDA | Mechanical | ACV, ZVV | LE20M185-M-002 | LE20M185-M-002-B | JASH | Sent to BU Operations | PR Closed | Enquiry floated to sigmaflow/Flownix/Jash |  |  | 27.03.22 | 27.03.24 | 14.04.24 | 18.04.24 | [8 empty] | 18.04.24 | 18.04.24 | 18.04.24 | T1 | [7 empty] | 18.04.24 | 05.05.24 |  | gopal.samarth@lntecc.com-10.07.2024-16:56:54
MADIKHEDA | Mechanical | VT pumps | LE20M185-M-003 | LE20M185-M-003-A | WPIL | Approved by Client | PR Closed |  |  |  | 27.03.22 | 27.03.22 | 10.07.22 | 03.08.22 | [8 empty] | 03.09.22 | 23.09.22 | 27.09.22 | T1 | 01.10.22 | WPIL | 16.06.23 | 25.06.23 | 27.07.23 | 31.07.23 | 06.08.23 | 27.09.22 | 14.10.22 | 30.11.22 | gopal.samarth@lntecc.com-03.07.2024-13:36:18
MADIKHEDA | Mechanical | HSC pumps | LE20M185-M-004 | LE20M185-M-004-A | Wilo | Approved by Client | PR Closed |  |  |  | 27.03.22 | 27.03.22 | 21.07.22 | 31.07.22 | [8 empty] | 18.08.22 | 22.08.22 | 27.09.22 | T1 | 16.11.22 | Wilo | 11.07.23 | 01.08.23 | 05.08.23 | 05.08.23 | 06.08.23 | 27.09.22 | 14.10.22 | 15.01.23 | gopal.samarth@lntecc.com-10.07.2024-16:56:54
MADIKHEDA | Mechanical | Ventilation fans | LE20M185-M-005 | LE20M185-M-005-A | Almonard | Approved by Client | PR Closed |  |  |  |  | 11.12.23 | 14.12.23 | 15.12.23 | 16.12.23 | 18.12.23 | 19.12.23 | [5 empty] | 18.12.23 | 19.12.23 | 20.12.23 | T1 | 05.01.24 | Almonard | 11.01.24 | 12.01.24 | 13.01.24 | 15.01.24 | 30.01.24 | 01.12.23 | 05.03.24 |  | gopal.samarth@lntecc.com-10.07.2024-17:11:32
MADIKHEDA | Mechanical | EOT-crane | LE20M185-M-006 | LE20M185-M-006-A | JAPS | Approved by Client | PR Closed |  |  |  |  | 02.10.23 | 17.10.23 | 18.10.23 | 19.10.23 | 20.10.23 | 23.10.23 | [5 empty] | 28.10.23 | 29.10.23 | 02.10.23 | T1 | 30.10.23 | JAPS | 30.10.23 | 31.10.23 | 01.11.23 | 02.11.23 | 28.11.23 | 02.10.23 | 02.11.23 |  | gopal.samarth@lntecc.com-10.07.2024-17:40:31
MADIKHEDA | Mechanical | Sluice valves | LE20M185-M-007 | LE20M185-M-007-A | AVK | Approved by Client | PR Closed |  |  |  |  | 02.10.23 | 17.10.23 | 18.10.23 | 19.10.23 | 20.10.23 | 23.10.23 | [5 empty] | 28.10.23 | 29.10.23 | 02.10.23 | T1 | 30.10.23 | AVK | 30.10.23 | 31.10.23 | 01.11.23 | 02.11.23 | 28.11.23 | 02.10.23 | 29.12.23 |  | gopal.samarth@lntecc.com-10.07.2024-17:40:31
MADIKHEDA | Mechanical | Butterfly valves | LE20M185-M-008 | LE20M185-M-008-A | AVK | Approved by Client | PR Closed |  |  |  |  | 02.10.23 | 17.10.23 | 18.10.23 | 19.10.23 | 20.10.23 | 23.10.23 | [5 empty] | 28.10.23 | 29.10.23 | 02.10.23 | T1 | 30.10.23 | AVK | 30.10.23 | 31.10.23 | 01.11.23 | 02.11.23 | 28.11.23 | 02.10.23 | 29.12.23 |  | gopal.samarth@lntecc.com-10.07.2024-17:40:31
MADIKHEDA | Mechanical | AIR valves | LE20M185-M-010 | LE20M185-M-010-A | AVK | Approved by Client | PR Closed |  |  |  |  | 02.10.23 | 17.10.23 | 18.10.23 | 19.10.23 | 20.10.23 | 23.10.23 | [5 empty] | 28.10.23 | 29.10.23 | 02.10.23 | T1 | 30.10.23 | AVK | 30.10.23 | 31.10.23 | 01.11.23 | 02.11.23 | 28.11.23 | 02.10.23 | 29.12.23 |  | gopal.samarth@lntecc.com-10.07.2024-17:40:31
MADIKHEDA | Mechanical | Dismantling joints | LE20M185-M-011 | LE20M185-M-011-A | Precise engineers | Approved by Client | PR Closed |  |  |  |  | 02.10.23 | 17.10.23 | 18.10.23 | 19.10.23 | 20.10.23 | 23.10.23 | [5 empty] | 28.10.23 | 29.10.23 | 02.10.23 | T1 | 30.10.23 | Precise engineers | 30.10.23 | 31.10.23 | 01.11.23 | 02.11.23 | 28.11.23 | 02.10.23 | 29.12.23 |  | gopal.samarth@lntecc.com-10.07.2024-17:40:31
MADIKHEDA | Mechanical | Sluice gate | LE20M185-M-013 | LE20M185-M-013-A | HWE | Approved by Client | PR Closed |  |  |  |  | 02.10.23 | 17.10.23 | 18.10.23 | 19.10.23 | 20.10.23 | 23.10.23 | [5 empty] | 28.10.23 | 29.10.23 | 02.10.23 | T1 | 30.10.23 | HWE | 30.10.23 | 31.10.23 | 01.11.23 | 02.11.23 | 28.11.23 | 02.10.23 | 29.12.23 |  | gopal.samarth@lntecc.com-10.07.2024-17:40:31
MADIKHEDA | Instrumentation | Purchase requisition for Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M185-I-001 | LE20M185-I-001-A | HGuru | Sent to BU Operations | 460 |  |  |  | 2.04.23 | 13.11.22 | 02.01.23 | 23.01.23 | [8 empty] | 02.04.23 | 16.04.23 | 16.04.23 | T1 | [6 empty] | 02.05.23 |  |  |  | sooryaprakash.t@lntecc.com-10.07.2024-14:44:59
MADIKHEDA | Instrumentation | Purchase requisition for Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M185-I-001 | LE20M185-I-001-B | SIAS | Sent to BU Operations | 460 |  |  |  | 2.04.23 | 09.10.22 | 02.01.23 | 14.01.23 | [8 empty] | 02.04.23 | 20.04.23 | 20.04.23 | T3 | [6 empty] | 02.05.23 |  |  |  | sooryaprakash.t@lntecc.com-10.07.2024-14:44:59
MADIKHEDA | Instrumentation | Purchase requisition for Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M185-I-001 | LE20M185-I-001-C | WIKA | Sent to BU Operations | 460 |  |  |  | 2.04.23 | 20.11.22 | 02.01.23 | 17.03.23 | [8 empty] | 02.04.23 | 16.04.23 | 16.04.23 | T2 | [6 empty] | 02.05.23 |  |  |  | sooryaprakash.t@lntecc.com-10.07.2024-14:44:59
MADIKHEDA | Instrumentation | Purchase requisition for Pressure Switch | LE20M185-I-002 | LE20M185-I-002-A | SUN | Sent to BU Operations | 489 |  |  |  | 2.04.23 | 13.12.22 | 02.01.23 | 01.04.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Pressure Switch | LE20M185-I-002 | LE20M185-I-002-B | SIAS | Sent to BU Operations | 489 |  |  |  | 2.04.23 | 11.11.22 | 02.01.23 | 24.02.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Pressure Switch | LE20M185-I-002 | LE20M185-I-002-C | WIKA | Sent to BU Operations | 489 |  |  |  | 2.04.23 | 09.11.22 | 02.01.23 | 23.01.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Pressure transmitter | LE20M185-I-003 | LE20M185-I-003-A | ABB | Sent to BU Operations | PR Closed |  |  |  | 2.04.23 | 24.12.22 | 31.01.23 | 28.03.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Pressure transmitter | LE20M185-I-003 | LE20M185-I-003-B | E&H | Approved by Client | PR Closed |  |  |  | 2.04.23 | 03.12.22 | 31.01.23 | 22.02.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 |  | 19.04.23 | E&H | 03.05.23 | 16.05.23 | 19.05.23 | 26.02.23 | 23.03.23 |  |  | 18.06.23 | sooryaprakash.t@lntecc.com-17.02.2024-12:20:17
MADIKHEDA | Instrumentation | Purchase requisition for Pressure transmitter | LE20M185-I-003 | LE20M185-I-003-C | Honeywell | Sent to BU Operations | PR Closed |  |  |  | 2.04.23 | 11.12.22 | 31.01.23 | 04.03.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Float & Board Level gauge | LE20M185-I-004 | LE20M185-I-004-A | Pune Techtrol | Approved by Client | PR Closed |  |  |  | 2.06.23 | 08.11.22 | 02.02.23 | 21.05.23 | [8 empty] | 02.06.23 | 02.06.23 | 02.06.23 | T1 | 29.09.23 | Pune Techtrol | 16.10.23 | 16.10.23 | 16.10.23 | 16.10.23 | 16.10.23 |  |  | 28.11.23 | sooryaprakash.t@lntecc.com-10.07.2024-14:46:47
MADIKHEDA | Instrumentation | Purchase requisition for Float & Board Level gauge | LE20M185-I-004 | LE20M185-I-004-B | SAPCON | Sent to BU Operations | PR Closed |  |  |  | 2.06.23 | 02.06.23 | 14.09.23 | 10.10.23 | [8 empty] | 14.10.23 | 07.11.23 | 13.11.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:46:47
MADIKHEDA | Instrumentation | Purchase requisition for Float & Board Level gauge | LE20M185-I-004 | LE20M185-I-004-C | SBEM | Sent to BU Operations | PR Closed |  |  |  | 2.06.23 | 19.12.22 | 02.02.23 | 07.03.23 | [8 empty] | 02.06.23 | 02.06.23 | 02.06.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:46:47
MADIKHEDA | Instrumentation | Purchase requisition for level switch - Conductivity type | LE20M185-I-005 | LE20M185-I-005-A | Pune Techtrol | Approved by Client | PR Closed |  |  |  | 2.06.23 | 25.11.22 | 02.02.23 | 16.02.23 | [8 empty] | 02.06.23 | 02.06.23 | 02.06.23 | T1 | 13.10.23 | Pune Techtrol | 16.10.23 | 16.10.23 | 16.10.23 | 16.10.23 | 16.10.23 |  |  | 12.12.23 | sooryaprakash.t@lntecc.com-10.07.2024-14:46:47
MADIKHEDA | Instrumentation | Purchase requisition for level switch - Conductivity type | LE20M185-I-005 | LE20M185-I-005-B | SAPCON | Sent to BU Operations | PR Closed |  |  |  | 2.06.23 | 02.06.23 | 14.09.23 | 23.09.23 | [8 empty] | 14.10.23 | 10.11.23 | 13.11.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:46:47
MADIKHEDA | Instrumentation | Purchase requisition for level switch - Conductivity type | LE20M185-I-005 | LE20M185-I-005-C | SBEM | Sent to BU Operations | PR Closed |  |  |  | 2.06.23 | 25.12.22 | 02.02.23 | 23.02.23 | [8 empty] | 02.06.23 | 02.06.23 | 02.06.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:46:47
MADIKHEDA | Instrumentation | Purchase requisition for Ultrasonic level Transmitter | LE20M185-I-006 | LE20M185-I-006-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 2.03.23 | 09.01.23 | 01.02.23 | 17.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:42:33
MADIKHEDA | Instrumentation | Purchase requisition for Ultrasonic level Transmitter | LE20M185-I-006 | LE20M185-I-006-B | Electronet | Approved by Client | PR Closed |  |  |  | 2.03.23 | 31.01.23 | 01.02.23 | 13.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | T1 | 03.08.23 | Electronet | 12.09.23 | 15.09.23 | 15.09.23 | 16.09.23 | 16.09.23 |  |  | 02.10.23 | sooryaprakash.t@lntecc.com-10.07.2024-14:42:33
MADIKHEDA | Instrumentation | Purchase requisition for Radar Level Transmitter | LE20M185-I-007 | LE20M185-I-007-A | siemens | Sent to BU Operations | PR Closed |  |  |  | 3.03.23 | 25.01.23 | 07.02.23 | 11.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Radar Level Transmitter | LE20M185-I-007 | LE20M185-I-007-B | Electronet | Approved by Client | PR Closed |  |  |  | 3.03.23 | 10.11.22 | 02.01.23 | 21.01.23 | [8 empty] | 23.01.23 | 23.01.23 | 23.01.23 |  | 14.05.23 | Electronet | 12.09.23 | 15.09.23 | 15.09.23 | 16.09.23 | 16.09.23 |  |  | 13.07.23 | sooryaprakash.t@lntecc.com-17.02.2024-12:20:17
MADIKHEDA | Instrumentation | Purchase requisition for Radar Level Transmitter | LE20M185-I-007 | LE20M185-I-007-C | Forbes marshall | Sent to BU Operations | PR Closed |  |  |  | 3.03.23 | 04.02.23 | 07.02.23 | 10.02.23 | [8 empty] | 03.03.23 | 03.03.23 | 03.03.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M185-I-017 | LE20M185-I-007-D | Honeywell | Sent to BU Operations | 311 |  |  |  | 24.04.23 | 24.04.23 | 09.07.23 | 14.09.23 | [8 empty] | 28.09.23 | 28.09.23 | 28.09.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Loss of head transmitter | LE20M185-I-008 | LE20M185-I-008-A | ABB | Sent to BU Operations | 489 |  |  |  | 2.04.23 | 19.01.23 | 31.01.23 | 13.03.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Loss of head transmitter | LE20M185-I-008 | LE20M185-I-008-B | E&H | Sent to BU Operations | 489 |  |  |  | 2.04.23 | 16.12.22 | 31.01.23 | 01.03.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Loss of head transmitter | LE20M185-I-008 | LE20M185-I-008-C | Honeywell | Sent to BU Operations | 489 |  |  |  | 2.04.23 | 14.01.23 | 31.01.23 | 25.03.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Rate for flow transmitter | LE20M185-I-009 | LE20M185-I-009-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 2.03.23 | 11.01.23 | 01.02.23 | 09.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:42:33
MADIKHEDA | Instrumentation | Purchase requisition for Rate for flow transmitter | LE20M185-I-009 | LE20M185-I-009-B | Electronet | Approved by Client | PR Closed |  |  |  | 2.03.23 | 30.01.23 | 01.02.23 | 18.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | T1 | 05.05.23 | Electronet | 12.09.23 | 12.09.23 | 12.09.23 | 16.09.23 | 16.09.23 |  |  | 04.07.23 | sooryaprakash.t@lntecc.com-10.07.2024-14:42:33
MADIKHEDA | Instrumentation | Purchase requisition for Bypass Rotameter | LE20M185-I-010 | LE20M185-I-010-A | Eureka | Sent to BU Operations | 369 |  |  |  | 13.02.23 | 13.02.23 | 02.06.23 | 29.06.23 | [8 empty] | 02.07.23 | 13.07.23 | 01.08.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Bypass Rotameter | LE20M185-I-010 | LE20M185-I-010-B | Scientific devices | Sent to BU Operations | 469 |  |  |  | 13.02.23 | 13.02.23 | 22.02.23 | 28.02.23 | [8 empty] | 24.03.23 | 30.03.23 | 23.04.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Electromagnectic flow meter | LE20M185-I-011 | LE20M185-I-011-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 29.12.22 | 29.12.22 | 02.02.23 | 04.02.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:47:19
MADIKHEDA | Instrumentation | Purchase requisition for Electromagnectic flow meter | LE20M185-I-011 | LE20M185-I-011-B | Khrone | Approved by Client | PR Closed |  |  |  | 29.12.22 | 29.12.22 | 02.02.23 | 08.03.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T1 | 21.07.23 | Khrone | 03.11.23 | 03.11.23 | 03.11.23 | 04.11.23 | 04.11.23 |  |  | 19.09.23 | sooryaprakash.t@lntecc.com-10.07.2024-14:47:19
MADIKHEDA | Instrumentation | Purchase requisition for Electromagnectic flow meter | LE20M185-I-011 | LE20M185-I-011-C | siemens | Sent to BU Operations | PR Closed |  |  |  | 29.12.22 | 29.12.22 | 02.02.23 | 24.02.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:47:19
MADIKHEDA | Instrumentation | Purchase requisition for Ultrasonic type Open channel flow transmitter | LE20M185-I-012 | LE20M185-I-012-A | E&H | Sent to BU Operations | PR Closed |  |  |  | 2.03.23 | 24.01.23 | 01.02.23 | 24.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:42:33
MADIKHEDA | Instrumentation | Purchase requisition for Ultrasonic type Open channel flow transmitter | LE20M185-I-012 | LE20M185-I-012-B | Electronet | Approved by Client | PR Closed |  |  |  | 2.03.23 | 05.01.23 | 01.02.23 | 11.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | T1 | 28.08.23 | Electronet | 12.09.23 | 14.09.23 | 14.09.23 | 16.09.23 | 16.09.23 |  |  | 27.10.23 | sooryaprakash.t@lntecc.com-10.07.2024-14:42:33
MADIKHEDA | Instrumentation | Purchase requisition for VTC Flow meter | LE20M185-I-013 | LE20M185-I-013-A | Zenner | Enquiry yet to float | NA |  |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:49:48
MADIKHEDA | Instrumentation | Purchase requisition for VTC Flow meter | LE20M185-I-013 | LE20M185-I-013-B | Kranthi water meter | Enquiry yet to float | NA |  |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:49:48
MADIKHEDA | Instrumentation | Purchase requisition for pH Meter | LE20M185-I-014 | LE20M185-I-014-A | Emerson | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 26.09.23 | [8 empty] | 25.10.23 | 03.11.23 | 24.11.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for pH Meter | LE20M185-I-014 | LE20M185-I-014-B | HACH | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 13.10.23 | [8 empty] | 25.10.23 | 29.10.23 | 24.11.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for pH Meter | LE20M185-I-014 | LE20M185-I-014-C | ABB | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 28.09.23 | [8 empty] | 25.10.23 | 23.11.23 | 24.11.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for pH Meter | LE20M185-I-014 | LE20M185-I-014-D | E&H | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 06.10.23 | [8 empty] | 25.10.23 | 01.11.23 | 24.11.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Turbidity meter | LE20M185-I-015 | LE20M185-I-015-A | Emerson | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 13.10.23 | [8 empty] | 25.10.23 | 09.11.23 | 24.11.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Turbidity meter | LE20M185-I-015 | LE20M185-I-015-B | HACH | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 26.09.23 | [8 empty] | 25.10.23 | 01.11.23 | 24.11.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Turbidity meter | LE20M185-I-015 | LE20M185-I-015-C | ABB | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 07.10.23 | [8 empty] | 25.10.23 | 17.11.23 | 24.11.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Turbidity meter | LE20M185-I-015 | LE20M185-I-015-D | E&H | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 26.09.23 | [8 empty] | 25.10.23 | 08.11.23 | 24.11.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Residual Chlorine Analyzer | LE20M185-I-016 | LE20M185-I-016-A | Emerson | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 12.10.23 | [8 empty] | 25.10.23 | 10.11.23 | 24.11.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Residual Chlorine Analyzer | LE20M185-I-016 | LE20M185-I-016-B | HACH | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 16.10.23 | [8 empty] | 25.10.23 | 08.11.23 | 24.11.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Residual Chlorine Analyzer | LE20M185-I-016 | LE20M185-I-016-C | ABB | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 24.10.23 | [8 empty] | 25.10.23 | 18.11.23 | 24.11.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for Residual Chlorine Analyzer | LE20M185-I-016 | LE20M185-I-016-D | E&H | Sent to BU Operations | 254 |  |  |  | 10.07.23 | 10.07.23 | 25.09.23 | 05.10.23 | [8 empty] | 25.10.23 | 19.11.23 | 24.11.23 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M185-I-017 | LE20M185-I-017-A | Siemens | Sent to BU Operations | 281 |  |  |  | 24.04.23 | 24.04.23 | 09.07.23 | 14.09.23 | [8 empty] | 28.09.23 | 18.10.23 | 28.10.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M185-I-017 | LE20M185-I-017-B | Schneider | Sent to BU Operations | 311 |  |  |  | 24.04.23 | 24.04.23 | 09.07.23 | 14.09.23 | [8 empty] | 28.09.23 | 28.09.23 | 28.09.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M185-I-017 | LE20M185-I-017-C | Mitsubishi | Sent to BU Operations | 311 |  |  |  | 24.04.23 | 24.04.23 | 09.07.23 | 14.09.23 | [8 empty] | 28.09.23 | 28.09.23 | 28.09.23 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M185-I-017 | LE20M185-I-017-E | Autosys Rockwell | Sent to BU Operations | 222 |  |  |  | 24.04.23 | 24.04.23 | 26.12.23 | 14.08.23 | [8 empty] | 28.09.23 | 28.09.23 | 28.09.23 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for ICP, PLC panel, RTU & SCADA Accessories | LE20M185-I-017 | LE20M185-I-017-F | Sai applied Tech | Sent to BU Operations | 161 | conditional clearance |  |  | 24.04.23 | 24.04.23 | 27.12.23 | 22.01.24 | [8 empty] | 26.01.24 | 18.02.24 | 25.02.24 | T5 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:51:56
MADIKHEDA | Instrumentation | Purchase requisition for instrumentation Control & signal Cables | LE20M185-I-018 | LE20M185-I-018-A | Axelon | Sent to BU Operations | PR Closed |  |  |  | 9.01.23 | 09.12.22 | 21.12.22 | 26.12.22 | [8 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:47:53
MADIKHEDA | Instrumentation | Purchase requisition for instrumentation Control & signal Cables | LE20M185-I-018 | LE20M185-I-018-B | Cords | Approved by Client | PR Closed |  |  |  | 9.01.23 | 09.01.23 | 28.12.23 | 14.01.24 | [8 empty] | 27.01.24 | 27.01.24 | 26.02.24 | T1 | 21.03.24 | Cords | 27.03.24 | 08.04.24 | 20.04.24 | 01.05.22 | 23.03.23 |  |  | 20.05.24 | sooryaprakash.t@lntecc.com-10.07.2024-14:47:53
MADIKHEDA | Instrumentation | Purchase requisition for instrumentation Control & signal Cables | LE20M185-I-018 | LE20M185-I-018-C | Delton | Sent to BU Operations | PR Closed |  |  |  | 9.01.23 | 09.01.23 | 28.12.23 | 06.01.24 | [8 empty] | 27.01.24 | 14.02.24 | 26.02.24 | T3 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:47:53
MADIKHEDA | Instrumentation | Purchase requisition for instrumentation Control & signal Cables | LE20M185-I-018 | LE20M185-I-018-D | Thermo | Sent to BU Operations | PR Closed |  |  |  | 9.01.23 | 12.12.22 | 21.12.22 | 05.01.23 | [8 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T4 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:47:53
MADIKHEDA | Instrumentation | Purchase requisition for UPS | LE20M185-I-019 | LE20M185-I-019-A | Vertiv | Enquiry yet to float | NA |  |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:49:48
MADIKHEDA | Instrumentation | Purchase requisition for UPS | LE20M185-I-019 | LE20M185-I-019-B | Hirel | Enquiry yet to float | NA |  |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:49:48
MADIKHEDA | Instrumentation | Purchase requisition for EPABX System | LE20M185-I-020 | LE20M185-I-020-A | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:49:48
MADIKHEDA | Instrumentation | Purchase requisition for EPABX System | LE20M185-I-020 | LE20M185-I-020-B | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:49:48
MADIKHEDA | Instrumentation | Purchase requisition for EPABX System | LE20M185-I-020 | LE20M185-I-020-C | Vendor Name yet to provide | Enquiry yet to float | NA |  |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:49:48
MADIKHEDA | Electrical | Transformer | LE20M185-E-001 | LE20M185-E-001-A | Uttam Bharat | Pre-order technically cleared | 363 |  |  |  | 18.08.21 | 18.08.21 | 26.12.22 | 13.02.23 | [8 empty] | 07.06.23 | 07.08.23
MADIKHEDA | Electrical | Transformer | LE20M185-E-001 | LE20M185-E-001-B | Vardhaman | Post-order technically cleared | 199 |  |  |  | 18.08.21 | 18.08.21 | 31.12.22 | 14.02.23 | [8 empty] | 05.06.23 | 06.08.23 | 01.11.23 |  | 18.11.23 | Vardhaman | 25.11.23 | 18.12.23 | 19.12.23 | 05.01.24 | 18.01.24 |  |  | 17.01.24
MADIKHEDA | Electrical | Transformer | LE20M185-E-001 | LE20M185-E-001-C | VMC | Pre-order technically cleared | 365 |  |  |  | 18.08.21 | 18.08.21 | 30.12.22 | 11.02.23 | [8 empty] | 08.06.23 | 05.08.23
MADIKHEDA | Electrical | Transformer | LE20M185-E-001 | LE20M185-E-001-D | TBEA | Pre-order technically cleared | 363 |  |  |  | 18.08.21 | 18.08.21 | 28.12.22 | 13.02.23 | [8 empty] | 07.06.23 | 07.08.23
MADIKHEDA | Electrical | LT Panel | LE20M185-E-002 | LE20M185-E-002-A | SRCS | Post-order technically cleared | 268 |  |  |  | 18.08.21 | 18.08.21 | 09.02.23 | 16.03.23 | [8 empty] | 10.07.23 | 17.07.23 | 17.08.23 |  | 28.08.23 | SRCS | 13.09.23 | 05.10.23 | 09.11.23 | 10.11.23 |  |  |  | 27.10.23
MADIKHEDA | Electrical | LT Panel | LE20M185-E-002 | LE20M185-E-002-B | BCH | Pre-order technically cleared | 383 |  |  |  | 18.08.21 | 18.08.21 | 06.02.23 | 15.03.23 | [8 empty] | 09.07.23 | 18.07.23
MADIKHEDA | Electrical | LT Panel | LE20M185-E-002 | LE20M185-E-002-C | HTS | Pre-order technically cleared | 386 |  |  |  | 18.08.21 | 18.08.21 | 06.02.23 | 15.03.23 | [8 empty] | 08.07.23 | 15.07.23
MADIKHEDA | Electrical | LT Panel | LE20M185-E-002 | LE20M185-E-002-D | UNIVERSAL | Pre-order technically cleared | 354 |  |  |  | 18.08.21 | 18.08.21 | 11.02.23 | 16.03.23 | [8 empty] | 11.07.23 | 16.08.23
MADIKHEDA | Electrical | HT Panel | LE20M185-E-003 | LE20M185-E-003-A | HTS | Pre-order technically cleared | 363 |  |  |  | 15.09.22 | 15.09.22 | 27.02.23 | 17.03.23 | [8 empty] | 25.07.23 | 07.08.23
MADIKHEDA | Electrical | HT Panel | LE20M185-E-003 | LE20M185-E-003-B | POPULAR | Pre-order technically cleared | 367 |  |  |  | 15.09.22 | 15.09.22 | 20.02.23 | 18.03.23 | [8 empty] | 24.07.23 | 03.08.23
MADIKHEDA | Electrical | HT Panel | LE20M185-E-003 | LE20M185-E-003-C | UPE | Post-order technically cleared | 254 |  |  |  | 15.09.22 | 15.09.22 | 18.02.23 | 17.03.23 | [8 empty] | 27.07.23 | 02.08.23 | 22.08.23 |  | 28.08.23 | UPE | 14.09.23 | 09.10.23 | 23.11.23 | 24.11.23 |  |  |  | 27.10.23
MADIKHEDA | Electrical | HT soft starter | LE20M185-E-004 | LE20M185-E-004-A | JAYSHREE | Post-order technically cleared | 242 |  |  |  | 15.09.22 | 15.09.22 | 27.06.23 | 06.07.23 | [8 empty] | 20.08.23 | 28.08.23 | 16.09.23 |  | 03.11.23 | JAYSHREE | 22.11.23 | 24.11.23 | 30.11.23 | 06.12.23 |  |  |  | 02.01.24
MADIKHEDA | Electrical | HT soft starter | LE20M185-E-004 | LE20M185-E-004-B | LECON | Pre-order technically cleared | 343 |  |  |  | 15.09.22 | 15.09.22 | 25.06.23 | 05.07.23 | [8 empty] | 21.08.23 | 27.08.23
MADIKHEDA | Electrical | HT VFD | LE20M185-E-005 | LE20M185-E-005-A | ABB | Pre-order technically cleared | 294 |  |  |  | 15.09.22 | 15.09.22 | 09.09.23 | 28.09.23 | [8 empty] | 10.10.23 | 15.10.23
MADIKHEDA | Electrical | HT VFD | LE20M185-E-005 | LE20M185-E-005-B | HITACHI | Pre-order technically cleared | 300 |  |  |  | 15.09.22 | 15.09.22 | 10.09.23 | 25.09.23 | [8 empty] | 06.10.23 | 09.10.23
MADIKHEDA | Electrical | HT VFD | LE20M185-E-005 | LE20M185-E-005-C | TMEIC | Pre-order technically cleared | 307 |  |  |  | 15.09.22 | 15.09.22 | 15.09.23 | 21.09.23 | [8 empty] | 28.09.23 | 02.10.23
MADIKHEDA | Electrical | Lighting Fixtures | LE20M185-E-006 | LE20M185-E-006-A | Vendor Name yet to provide | Sent to BU Operations | 647 | Pre-order offer evaluation is not required |  |  | 27.09.22 | 27.09.22 | 30.09.22 | 18.10.22 | [8 empty] | 20.10.22 | 22.10.22 | 26.10.22 | [7 empty] | 27.10.22
MADIKHEDA | Electrical | LPBS & LDB | LE20M185-E-007 | LE20M185-E-007-A | Vendor Name yet to provide | Sent to BU Operations | 1052 | Pre-order offer evaluation is not required |  |  | 18.08.21 | 18.08.21 | 30.08.21 | 12.09.21 | [8 empty] | 15.09.21 | 16.09.21 | 16.09.21 | [7 empty] | 17.09.21
MADIKHEDA | Electrical | AAAC Conductor | LE20M185-E-008 | LE20M185-E-008-A | Vendor Name yet to provide | Sent to BU Operations | 1172 | Pre-order offer evaluation is not required |  |  | 20.04.21 | 20.04.21 | 08.05.21 | 14.05.21 | [8 empty] | 15.05.21 | 16.05.21 | 18.05.21 | [7 empty] | 20.05.21
MADIKHEDA | Electrical | Control & Relay Panel | LE20M185-E-009 | LE20M185-E-009-A | Vendor Name yet to provide | Sent to BU Operations | 1172 | Pre-order offer evaluation is not required |  |  | 20.04.21 | 20.04.21 | 03.05.21 | 03.05.21 | [8 empty] | 06.05.21 | 10.05.21 | 12.05.21 | [7 empty] | 20.05.21
MADIKHEDA | Electrical | CT & PT | LE20M185-E-010 | LE20M185-E-010-A | Vendor Name yet to provide | Sent to BU Operations | 1172 | Pre-order offer evaluation is not required |  |  | 20.04.21 | 20.04.21 | 13.05.21 | 14.05.21 | [8 empty] | 18.05.21 | 18.05.21 | 18.05.21 | [7 empty] | 20.05.21
MADIKHEDA | Electrical | Swicthyard Structures | LE20M185-E-011 | LE20M185-E-011-A | Vendor Name yet to provide | Sent to BU Operations | 1172 | Pre-order offer evaluation is not required |  |  | 20.04.21 | 20.04.21 | 22.04.21 | 16.05.21 | [8 empty] | 19.05.21 | 19.05.21 | 19.05.21 | [7 empty] | 20.05.21
MADIKHEDA | Electrical | HT/ LT Power & Control Cables | LE20M185-E-012 | LE20M185-E-012-A | Vendor Name yet to provide | Sent to BU Operations | 1448 | Pre-order offer evaluation is not required |  |  | 18.07.20 | 18.07.20 | 09.08.20 | 15.08.20 | [8 empty] | 15.08.20 | 15.08.20 | 16.08.20 | [7 empty] | 17.08.20
MADIKHEDA | Electrical | Cable Trays & Its accessories | LE20M185-E-013 | LE20M185-E-013-A | Vendor Name yet to provide | Sent to BU Operations | 647 | Pre-order offer evaluation is not required |  |  | 27.09.22 | 27.09.22 | 02.10.22 | 26.10.22 | [8 empty] | 26.10.22 | 26.10.22 | 26.10.22 | [7 empty] | 27.10.22
MADIKHEDA | Electrical | Earthing & Lightning Materials | LE20M185-E-014 | LE20M185-E-014-A | Vendor Name yet to provide | Sent to BU Operations | 647 | Pre-order offer evaluation is not required |  |  | 27.09.22 | 27.09.22 | 13.10.22 | 24.10.22 | [8 empty] | 26.10.22 | 26.10.22 | 26.10.22 | [7 empty] | 27.10.22
MADIKHEDA | Electrical | Galns & Lugs | LE20M185-E-015 | LE20M185-E-015-A | Vendor Name yet to provide | Sent to BU Operations | 541 | Pre-order offer evaluation is not required |  |  | 11.01.23 | 11.01.23 | 24.01.23 | 09.02.23 | [8 empty] | 09.02.23 | 09.02.23 | 09.02.23 | [7 empty] | 10.02.23
MADIKHEDA | Electrical | Safety Accessories | LE20M185-E-016 | LE20M185-E-016-A | Vendor Name yet to provide | Sent to BU Operations | 647 | Pre-order offer evaluation is not required |  |  | 27.09.22 | 27.09.22 | 26.10.22 | 26.10.22 | [8 empty] | 26.10.22 | 26.10.22 | 26.10.22 | [7 empty] | 27.10.22
Mandya | Process | Clariflocculator mechanism | LE22M954-P-WS-WT-PR-2002 | LE22M954-P-WS-WT-PR-2002-A | Sritech | Pre-order technically cleared | 62 | Awaiting for other vendor clearance | 9422111017 | mohan@sritechindia.com | 16.02.24 | 16.02.24 | 19.02.24 | 04.03.24 | 09.03.24 | 23.04.24 | 24.04.24 | 06.05.24 | 07.05.24 | 09.05.24 | 03.06.24 |  | 03.06.24 | 03.06.24 |  | T3 | [7 empty] | 20.08.24 | 06.09.24 | 05.11.24 | premkumar.nagarajan@lntecc.com-26.07.2024-10:24:07
Mandya | Process | Clariflocculator mechanism | LE22M954-P-WS-WT-PR-2002 | LE22M954-P-WS-WT-PR-2002-B | Shivpad | Pre-order technically cleared | 65 | Awaiting for other vendor clearance | 9003243278 | ragavendar@shivpad.com | 16.02.24 | 16.02.24 | 17.02.24 | 01.03.24 | 15.03.24 | 24.04.24 | 25.04.24 | 06.05.24 | 14.05.24 | 29.05.24 | 31.05.24 |  | 31.05.24 | 31.05.24 |  | T1 | [7 empty] | 20.08.24 | 06.09.24 | 05.11.24 | premkumar.nagarajan@lntecc.com-26.07.2024-10:22:48
Mandya | Process | Clariflocculator mechanism | LE22M954-P-WS-WT-PR-2002 | LE22M954-P-WS-WT-PR-2002-C | Triveni | Pre-order technically cleared | 54 | Pending with Electrical | 9841731882 | h.sathyanarayanan@projects.trivenigroup.com | 16.02.24 | 16.02.24 | 26.02.24 | 11.03.24 | 04.04.24 | 24.04.24 | 13.05.24 | 23.05.24 | 04.06.24 |  |  |  | 11.06.24 | 11.06.24 |  | T2 | [7 empty] | 20.08.24 | 06.09.24 | 05.11.24 | premkumar.nagarajan@lntecc.com-26.07.2024-10:23:20
Mandya | Process | Air Blower | LE22M954-P-WS-WT-PR-2003 | LE22M954-P-WS-WT-PR-2003-A | SWAM PNEUMATICS | Pre-order comments issued | 18 |  | Shailesh Srivastava 8130744229 | shailesh@swamatics.com |  | 27.05.24 | 28.05.24 | 03.06.24 | 01.07.24 | 01.07.24 | 17.07.24 | [16 empty] | 31.10.24 | 17.11.24 | 16.01.25 | premkumar.nagarajan@lntecc.com-23.07.2024-10:57:15
Mandya | Process | Air Blower | LE22M954-P-WS-WT-PR-2003 | LE22M954-P-WS-WT-PR-2003-B | Kay Blower | Pre-order comments issued | 12 |  | Manish - 8572899449 | manish@kayblowers.com;sgarg@kayblowers.com;chennai@kayblowers.com |  | 27.05.24 | 29.05.24 | 12.06.24 | 13.06.24 | 20.06.24 | 15.07.24 | 23.07.24 | [15 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-23.07.2024-10:57:15
Mandya | Process | Air Blower | LE22M954-P-WS-WT-PR-2003 | LE22M954-P-WS-WT-PR-2003-C | Everest Blower | Awaiting pre-offer from vendor | 69 |  | Saif Ali - 9582600965 | saif.ali@irco.com |  | 27.05.24 | [21 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-23.07.2024-10:57:15
Mandya | Process | Agitator | LE22M954-P-WS-WT-PR-2004 | LE22M954-P-WS-WT-PR-2004-A | Shivpad | Pre-order technically cleared | 17 |  | 9003243278 | ragavendar@shivpad.com | 22.02.24 | 22.02.24 | 25.03.24 | 27.04.24 | 28.05.24 | 07.06.24 | 12.06.24 | 24.06.24 | 24.06.24 | 09.07.24 | 09.07.24 | 18.07.24 | 18.07.24 | 09.07.24 |  | T1 | [7 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-26.07.2024-10:22:48
Mandya | Process | Agitator | LE22M954-P-WS-WT-PR-2004 | LE22M954-P-WS-WT-PR-2004-B | Sritech | Pre-order technically cleared | 9 |  | 9422111017 | mohan@sritechindia.com | 22.02.24 | 22.02.24 | 20.04.24 | 29.04.24 | 08.05.24 | 24.05.24 | 14.06.24 | 24.06.24 | 25.06.24 | 09.07.24 | 22.07.24 |  | 22.07.24 | 26.07.24 |  | T3 | [7 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-26.07.2024-10:24:07
Mandya | Process | Agitator | LE22M954-P-WS-WT-PR-2004 | LE22M954-P-WS-WT-PR-2004-C | Triveni | Pre-order technically cleared | 9 |  | 9841731882 | h.sathyanarayanan@projects.trivenigroup.com | 22.02.24 | 22.02.24 | 23.04.24 | 30.04.24 | 13.05.24 | 24.05.24 | 04.07.24 | 09.07.24 | 23.07.24 |  |  |  | 22.07.24 | 26.07.24 |  | T2 | [7 empty] | 30.09.24 | 17.10.24 | 16.12.24 | premkumar.nagarajan@lntecc.com-26.07.2024-10:23:20
Mandya | Process | WTP Sluice gates | LE22M954-P-WS-WT-PR-2005 | LE22M954-P-WS-WT-PR-2005-A | AVK Valves | Pre-order pending with EDRC | 10 | Electrical Pending | 9176966455 | subhash@avkindia.com | 08.02.24 | 08.02.24 | 20.02.24 | 01.04.24 | 24.04.24 | 06.05.24 | 25.07.24 | [16 empty] | 31.10.24 | 17.11.24 | 16.01.25 | premkumar.nagarajan@lntecc.com-25.07.2024-10:43:17
Mandya | Process | WTP Sluice gates | LE22M954-P-WS-WT-PR-2005 | LE22M954-P-WS-WT-PR-2005-B | Jash | Pre-order comments issued | 132 |  | Prateek Verma 72900 40722 | lpgsouth2@jashindia.com | 08.02.24 | 08.02.24 | 21.02.24 | 25.03.24 | [19 empty] | 31.10.24 | 17.11.24 | 16.01.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:57:23
Mandya | Process | WTP Sluice gates | LE22M954-P-WS-WT-PR-2005 | LE22M954-P-WS-WT-PR-2005-C | Oriental | Awaiting pre-offer from vendor | 11 |  | Sanjay 9810205011 | orientalcastings@gmail.com | 08.02.24 | 24.07.24 | 21.02.24 | 25.03.24 | [20 empty] | 17.11.24 | 16.01.25 | premkumar.nagarajan@lntecc.com-24.07.2024-10:41:12
Mandya | Process | Chlorination system | LE22M954-P-WS-WT-PR-2006 | LE22M954-P-WS-WT-PR-2006-A | SUPREME TECHNOLOGY | Awaiting pre-offer from vendor | 69 |  | Saurabh Tripathi 09323641733 | st@supremetechnology.co.in; |  | 27.05.24 | [21 empty] | 30.12.24 | 16.01.25 | 17.03.25 | premkumar.nagarajan@lntecc.com-01.07.2024-12:52:15
Mandya | Process | Chlorination system | LE22M954-P-WS-WT-PR-2006 | LE22M954-P-WS-WT-PR-2006-B | IEC Fabchem | Pre-order comments issued | 33 |  | Shagul Ameed 7550013258 | marketing@iecfabchem.in; |  | 27.05.24 | 21.06.24 | 02.07.24 | 21.06.24 | 02.07.24 | [17 empty] | 30.12.24 | 16.01.25 | 17.03.25 | premkumar.nagarajan@lntecc.com-15.07.2024-14:11:05
Mandya | Process | Chlorination system | LE22M954-P-WS-WT-PR-2006 | LE22M954-P-WS-WT-PR-2006-C | Zion Technologies | Pre-order pending with EDRC | 17 | Electrical Pending | Deepak Santram 8094570996 / 9828977765 | zion.tech2108@gmail.com |  | 27.05.24 | 28.05.24 | 11.06.24 | 12.06.24 | 02.07.24 | 05.07.24 | 17.07.24 | 18.07.24 | [14 empty] | 30.12.24 | 16.01.25 | 17.03.25 | premkumar.nagarajan@lntecc.com-25.07.2024-10:34:53
Mandya | Process | Chlorine Tonner | LE22M954-P-WS-WT-PR-2007 | LE22M954-P-WS-WT-PR-2007-A | SUPREME TECHNOLOGY | Awaiting pre-offer from vendor | 69 |  | Saurabh Tripathi 09323641733 | st@supremetechnology.co.in; |  | 27.05.24 | [21 empty] | 30.12.24 | 16.01.25 | 17.03.25 | premkumar.nagarajan@lntecc.com-01.07.2024-12:52:15
Mandya | Process | Chlorine Tonner | LE22M954-P-WS-WT-PR-2007 | LE22M954-P-WS-WT-PR-2007-B | IEC Fabchem | Pre-order comments issued | 33 |  | Shagul Ameed 7550013258 | marketing@iecfabchem.in; |  | 27.05.24 | 21.06.24 | 02.07.24 | 21.06.24 | 02.07.24 | [17 empty] | 30.12.24 | 16.01.25 | 17.03.25 | premkumar.nagarajan@lntecc.com-15.07.2024-14:11:05
Mandya | Process | Chlorine Tonner | LE22M954-P-WS-WT-PR-2007 | LE22M954-P-WS-WT-PR-2007-C | Zion Technologies | Pre-order pending with EDRC | 17 | Electrical Pending | Deepak Santram 8094570996 / 9828977765 | zion.tech2108@gmail.com |  | 27.05.24 | 28.05.24 | 11.06.24 | 12.06.24 | 02.07.24 | 05.07.24 | 17.07.24 | 18.07.24 | [14 empty] | 30.12.24 | 16.01.25 | 17.03.25 | premkumar.nagarajan@lntecc.com-25.07.2024-10:34:53
Mandya | Process | Filter media | LE22M954-P-WS-WT-PR-2008 | LE22M954-P-WS-WT-PR-2008-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.11.24 | 17.12.24 | 15.02.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:57:23
Mandya | Process | Backwash pump | LE22M954-P-WS-WT-PR-2009 | LE22M954-P-WS-WT-PR-2009-A | KBL Kirloskar Brothers Limited | Awaiting pre-offer from vendor | 9 |  | Azharuddin Tamboli 8669664820 | Azharuddin.Tamboli@kbl.co.in |  | 26.07.24 | [21 empty] | 20.12.24 | 06.01.25 | 07.03.25 | premkumar.nagarajan@lntecc.com-26.07.2024-12:39:32
Mandya | Process | Backwash pump | LE22M954-P-WS-WT-PR-2009 | LE22M954-P-WS-WT-PR-2009-B | WPIL | Awaiting pre-offer from vendor | 9 |  | Praveen Deshmukh 07290027621 | cmktg@wpil.co.in;design.gzb01@wpil.co.in; d.saha@wpil.co.in; |  | 26.07.24 | [21 empty] | 20.12.24 | 06.01.25 | 07.03.25 | premkumar.nagarajan@lntecc.com-26.07.2024-12:39:32
Mandya | Process | Backwash pump | LE22M954-P-WS-WT-PR-2009 | LE22M954-P-WS-WT-PR-2009-C | KSB | Awaiting pre-offer from vendor | 9 |  | Dhananjay- 9960866738 | dhananjay.bidnur@ksb.com; Uday.Joshi@ksb.com |  | 26.07.24 | [21 empty] | 20.12.24 | 06.01.25 | 07.03.25 | premkumar.nagarajan@lntecc.com-26.07.2024-12:39:32
Mandya | Process | Submersible pump | LE22M954-P-WS-WT-PR-2010 | LE22M954-P-WS-WT-PR-2010-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 20.11.24 | 07.12.24 | 05.02.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:52:40
Mandya | Process | Electrical hoist | LE22M954-P-WS-WT-PR-2011 | LE22M954-P-WS-WT-PR-2011-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.11.24 | 17.12.24 | 15.02.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:53:59
Mandya | Process | Manual chain pulley block | LE22M954-P-WS-WT-PR-2012 | LE22M954-P-WS-WT-PR-2012-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.11.24 | 17.12.24 | 15.02.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:53:59
Mandya | Process | Dosing pump | LE22M954-P-WS-WT-PR-2013 | LE22M954-P-WS-WT-PR-2013-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.10.24 | 17.11.24 | 16.01.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:53:59
Mandya | Process | Sampling pump | LE22M954-P-WS-WT-PR-2014 | LE22M954-P-WS-WT-PR-2014-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com-13.05.2024-18:31:15
Mandya | Process | Submersible mixer | LE22M954-P-WS-WT-PR-2015 | LE22M954-P-WS-WT-PR-2015-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.11.24 | 17.12.24 | 15.02.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:55:37
Mandya | Process | Dewatering pump | LE22M954-P-WS-WT-PR-2016 | LE22M954-P-WS-WT-PR-2016-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 20.11.24 | 07.12.24 | 05.02.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:52:40
Mandya | Process | Sludge thickener | LE22M954-P-WS-WT-PR-2017 | LE22M954-P-WS-WT-PR-2017-A | Sritech | Pre-order technically cleared | 62 | Awaiting for other vendor clearance | 9422111017 | mohan@sritechindia.com | 16.02.24 | 16.02.24 | 19.02.24 | 16.03.24 | 17.03.24 | 25.04.24 | 28.04.24 | 06.05.24 | 07.05.24 | 24.05.24 | 03.06.24 |  | 03.06.24 | 03.06.24 |  | T3 | [7 empty] | 30.11.24 | 17.12.24 | 15.02.25 | premkumar.nagarajan@lntecc.com-26.07.2024-10:24:07
Mandya | Process | Sludge thickener | LE22M954-P-WS-WT-PR-2017 | LE22M954-P-WS-WT-PR-2017-B | Shivpad | Pre-order technically cleared | 65 | Awaiting for other vendor clearance | 9003243278 | ragavendar@shivpad.com | 16.02.24 | 16.02.24 | 17.02.24 | 14.03.24 | 25.03.24 | 26.04.24 | 26.04.24 | 06.05.24 | 06.05.24 | 07.05.24 | 31.05.24 |  | 31.05.24 | 31.05.24 |  | T1 | [7 empty] | 30.11.24 | 17.12.24 | 15.02.25 | premkumar.nagarajan@lntecc.com-26.07.2024-10:22:48
Mandya | Process | Sludge thickener | LE22M954-P-WS-WT-PR-2017 | LE22M954-P-WS-WT-PR-2017-C | Triveni | Pre-order technically cleared | 53 | Pending with electricals | 9841731882 | h.sathyanarayanan@projects.trivenigroup.com | 16.02.24 | 16.02.24 | 26.02.24 | 16.03.24 | 04.04.24 | 27.04.24 | 30.04.24 | 23.05.24 |  |  |  |  | 12.06.24 | 12.06.24 |  | T2 | [7 empty] | 30.11.24 | 17.12.24 | 15.02.25 | premkumar.nagarajan@lntecc.com-26.07.2024-10:23:20
Mandya | Process | Centrifuge | LE22M954-P-WS-WT-PR-2018 | LE22M954-P-WS-WT-PR-2018-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.01.25 | 17.02.25 | 18.04.25 | premkumar.nagarajan@lntecc.com-01.07.2024-12:51:09
Mandya | Process | Trolley | LE22M954-P-WS-WT-PR-2019 | LE22M954-P-WS-WT-PR-2019-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com-13.05.2024-18:31:15
Mandya | Process | DWPE tank | LE22M954-P-WS-WT-PR-2020 | LE22M954-P-WS-WT-PR-2020-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 24.01.25 | 10.02.25 | 11.04.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:51:45
Mandya | Process | DWPE tank agitator | LE22M954-P-WS-WT-PR-2021 | LE22M954-P-WS-WT-PR-2021-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 24.01.25 | 10.02.25 | 11.04.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:58:29
Mandya | Process | Platform weighing machine | LE22M954-P-WS-WT-PR-2022 | LE22M954-P-WS-WT-PR-2022-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com-13.05.2024-18:31:15
Mandya | Process | Screw pumps | LE22M954-P-WS-WT-PR-2023 | LE22M954-P-WS-WT-PR-2023-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 20.11.24 | 07.12.24 | 05.02.25 | premkumar.nagarajan@lntecc.com-01.07.2024-13:55:37
Mandya | Process | Dissolving tray | LE22M954-P-WS-WT-PR-2024 | LE22M954-P-WS-WT-PR-2024-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.01.25 | 16.02.25 | 17.04.25 | premkumar.nagarajan@lntecc.com-01.07.2024-14:03:51
Mandya | Process | Exhaust fan | LE22M954-P-WS-WT-PR-2025 | LE22M954-P-WS-WT-PR-2025-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com-13.05.2024-18:31:15
Mandya | Process | Lab Equipments | LE22M954-P-WS-WT-PR-2026 | LE22M954-P-WS-WT-PR-2026-A | Vendor Name yet to provide | Enquiry yet to float | NA | Site Procurement | [28 empty] | premkumar.nagarajan@lntecc.com-13.05.2024-18:31:15
Mandya | Process | Air compressor | LE22M954-P-WS-WT-PR-2027 | LE22M954-P-WS-WT-PR-2027-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.11.24 | 17.12.24 | 15.02.25 | premkumar.nagarajan@lntecc.com-01.07.2024-12:49:20
Mandya | Mechanical | HSC pumps | LE22M954-M-WS-CW-PR-1248 | LE22M954-M-WS-CW-PR-1248-A | KBL | Pre-order technically cleared | 82 |  |  |  | 25.01.24 | 25.01.24 | 18.02.24 | 20.02.24 | 14.05.24 | 14.05.24 | [6 empty] | 14.05.24 | 14.05.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | HSC pumps | LE22M954-M-WS-CW-PR-1248 | LE22M954-M-WS-CW-PR-1248-B | WPIL | Pre-order technically cleared | 45 |  |  |  | 24.01.24 | 24.01.24 | 29.02.24 | 04.03.24 | 20.06.24 | [7 empty] | 20.06.24 | 20.06.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | HSC pumps | LE22M954-M-WS-CW-PR-1248 | LE22M954-M-WS-CW-PR-1248-C | WILO | Pre-order technically cleared | 13 |  |  |  | 24.01.24 | 24.01.24 | 12.03.24 | 18.03.24 | 19.03.24 | 21.03.24 | 03.07.24 | 04.07.24 | 18.07.24 | 22.07.24 |  |  | 22.07.24 | 22.07.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | HSC pumps | LE22M954-M-WS-CW-PR-1248 | LE22M954-M-WS-CW-PR-1248-D | XYLEM | Pre-order technically cleared | 25 |  |  | Sivakumar.Natarajan@xylem.com |  | 21.03.24 | 25.04.24 | 09.05.24 | 20.05.24 | 21.05.24 | 05.06.24 | 10.06.24 | 25.06.24 | 10.07.24 |  |  | 10.07.24 | 10.07.24 |  | T1 | [7 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | CWPH -VALVES,EB&DJ | LE22M954-M-WS-CW-PR-1249 | LE22M954-M-WS-CW-PR-1249-A | Durga | Pre-order comments issued | 25 |  |  |  | 18.01.24 | 18.01.24 | 27.01.24 | 05.02.24 | 14.06.24 | 14.06.24 | 10.07.24 | [16 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | CWPH -VALVES,EB&DJ | LE22M954-M-WS-CW-PR-1249 | LE22M954-M-WS-CW-PR-1249-B | Hawle | Pre-order comments issued | 33 | Electrical review is going on |  |  | 18.01.24 | 18.01.24 | 04.03.24 | 12.03.24 | 21.05.24 | 14.06.24 | 02.07.24 | 02.07.24 | [15 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | CWPH -VALVES,EB&DJ | LE22M954-M-WS-CW-PR-1249 | LE22M954-M-WS-CW-PR-1249-C | Sigma Flow | Pre-order technically cleared | 24 |  |  | jagadesh@sigmaflow.in |  | 18.01.24 | 22.02.24 | 03.05.24 | 10.06.24 | 14.06.24 | 03.07.24 | 06.07.24 | 11.07.24 | 11.07.24 |  |  | 11.07.24 | 11.07.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | CWPH -VALVES,EB&DJ | LE22M954-M-WS-CW-PR-1249 | LE22M954-M-WS-CW-PR-1249-D | Magwene | Pre-order technically cleared | 25 |  |  | Ramkumar.T@magwen.de |  | 23.04.24 | 02.05.24 | 03.05.24 | 10.05.24 | 15.05.24 | 14.06.24 | 14.06.24 | 04.07.24 | 06.07.24 | 10.07.24 | 10.07.24 | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Sluice gate - CWPH | LE22M954-M-WS-CW-PR-1252 | LE22M954-M-WS-CW-PR-1252-A | ORIENTAL | Pre-order technically cleared | 20 |  |  |  | 18.01.24 | 18.01.24 | 19.01.24 | 13.02.24 | 29.06.24 | 05.07.24 | 10.07.24 | 10.07.24 |  |  |  |  | 10.07.24 | 10.07.24 | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Sluice gate - CWPH | LE22M954-M-WS-CW-PR-1252 | LE22M954-M-WS-CW-PR-1252-B | JASH | Pre-order technically cleared | 20 |  | lpgsouth2@jashindia.com |  | 18.01.24 | 18.01.24 | 24.04.24 | 25.04.24 | 30.04.24 | 03.05.24 | 04.07.24 | 10.07.24 |  |  |  |  | 10.07.24 | 10.07.24 | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Sluice gate - CWPH | LE22M954-M-WS-CW-PR-1252 | LE22M954-M-WS-CW-PR-1252-C | AVK | Sent to BU Operations | 20 |  | neal@avkindia.com |  | 24.01.24 | 24.01.24 | 12.02.24 | 16.02.24 | 30.04.24 | 02.05.24 | 02.05.24 | 03.05.24 | 05.07.24 | 06.07.24 | 03.07.24 | 06.07.24 | 12.07.24 | 12.07.24 | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Sluice gate - CWPH | LE22M954-M-WS-CW-PR-1252 | LE22M954-M-WS-CW-PR-1252-D | Fluid Control | Sent to BU Operations | 20 |  |  |  |  | 21.06.24 | 24.06.24 | 25.06.24 | 25.06.24 | 01.07.24 | 02.07.24 | 05.07.24 | 08.07.24 | 10.07.24 |  |  | 10.07.24 | 10.07.24 | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | EOT crane - CWPH | LE22M954-M-WS-CW-PR-1254 | LE22M954-M-WS-CW-PR-1254-A | INDEF | Pre-order comments issued | 37 | Pending with Vendor |  |  | 01.03.24 | 01.03.24 | 10.06.24 | 19.06.24 | 20.06.24 | 28.06.24 | [17 empty] | 31.07.24 | 17.08.24 | 16.10.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | EOT crane - CWPH | LE22M954-M-WS-CW-PR-1254 | LE22M954-M-WS-CW-PR-1254-B | JAPS | Pre-order comments issued | 30 |  |  |  | 05.03.24 | 05.03.24 | 05.03.24 | 11.03.24 | 05.07.24 | 05.07.24 | [6 empty] | 11.03.24 | 11.03.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | EOT crane - CWPH | LE22M954-M-WS-CW-PR-1254 | LE22M954-M-WS-CW-PR-1254-C | Reva | Pre-order comments issued | 136 |  |  |  | 05.03.24 | 05.03.24 | 20.03.24 | 21.03.24 | [19 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Exhaust fan -CWPH &Intake | LE22M954-M-WS-CW-PR-1255 | LE22M954-M-WS-CW-PR-1255-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.07.24 | 17.08.24 |  | rallabandi.bharadwaj@lntecc.com-10.07.2024-16:21:47
Mandya | Mechanical | Surge Protection devices | LE22M954-M-WS-CW-PR-1256 | LE22M954-M-WS-CW-PR-1256-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.07.24 | 17.08.24 |  | rallabandi.bharadwaj@lntecc.com-10.07.2024-16:21:47
Mandya | Mechanical | Pipe line valves | LE22M954-M-WS-CW-PR-1257 | LE22M954-M-WS-CW-PR-1257-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-10.07.2024-16:21:47
Mandya | Mechanical | VT Pumps | LE22M954-M-WS-RW-PR-1247 | LE22M954-M-WS-RW-PR-1247-A | KBL | Pre-order technically cleared | 82 |  |  |  | 25.01.24 | 25.01.24 | 18.02.24 | 20.02.24 | 14.05.24 | 14.05.24 | [6 empty] | 14.05.24 | 14.05.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | VT Pumps | LE22M954-M-WS-RW-PR-1247 | LE22M954-M-WS-RW-PR-1247-B | WPIL | Pre-order technically cleared | 45 | Technically In line with Mechanical requirements. Sent to Electrical for clearance. |  |  | 24.01.24 | 24.01.24 | 29.02.24 | 04.03.24 | 20.06.24 | [7 empty] | 20.06.24 | 20.06.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | VT Pumps | LE22M954-M-WS-RW-PR-1247 | LE22M954-M-WS-RW-PR-1247-C | WILO | Pre-order comments issued | 139 |  |  |  | 24.01.24 | 24.01.24 | 12.03.24 | 18.03.24 | [19 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | VT Pumps | LE22M954-M-WS-RW-PR-1247 | LE22M954-M-WS-RW-PR-1247-D | Xylem | Pre-order technically cleared | 25 |  |  |  | 25.01.24 | 17.02.24 | 04.03.24 | 11.03.24 | 22.04.24 | 25.04.24 | 20.05.24 | 20.05.24 | 25.06.24 | 10.07.24 |  |  | 10.07.24 | 10.07.24 |  | T1 | [7 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | INTAKE - VALVES,EB&DJ | LE22M954-M-WS-RW-PR-1250 | LE22M954-M-WS-RW-PR-1250-A | Durga | Pre-order comments issued | 25 |  |  |  | 18.01.24 | 18.01.24 | 27.01.24 | 05.02.24 | 14.06.24 | 14.06.24 | 10.07.24 | [16 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | INTAKE - VALVES,EB&DJ | LE22M954-M-WS-RW-PR-1250 | LE22M954-M-WS-RW-PR-1250-B | Hawle | Pre-order comments issued | 33 | Electrical review is going on |  |  | 18.01.24 | 18.01.24 | 04.03.24 | 12.03.24 | 21.05.24 | 14.06.24 | 02.07.24 | 02.07.24 | [15 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | INTAKE - VALVES,EB&DJ | LE22M954-M-WS-RW-PR-1250 | LE22M954-M-WS-RW-PR-1250-C | Sigma Flow | Pre-order technically cleared | 24 |  |  | jagadesh@sigmaflow.in |  | 18.01.24 | 22.02.24 | 03.05.24 | 10.06.24 | 14.06.24 | 03.07.24 | 06.07.24 |  |  |  |  | 11.07.24 | 11.07.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | INTAKE - VALVES,EB&DJ | LE22M954-M-WS-RW-PR-1250 | LE22M954-M-WS-RW-PR-1250-D | Magwene | Pre-order comments issued | 25 |  |  | Ramkumar.T@magwen.de |  | 23.04.24 | 02.05.24 | 03.05.24 | 10.05.24 | 15.05.24 | 14.06.24 | 14.06.24 | 04.07.24 | 06.07.24 |  |  | 10.07.24 | 10.07.24 | [9 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Sluice gate - Intake | LE22M954-M-WS-RW-PR-1251 | LE22M954-M-WS-RW-PR-1251-A | ORIENTAL | Sent to BU Operations | 20 |  |  |  | 18.01.24 | 18.01.24 | 19.01.24 | 13.02.24 | 13.06.24 | 20.06.24 | [6 empty] | 10.07.24 | 10.07.24 | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Sluice gate - Intake | LE22M954-M-WS-RW-PR-1251 | LE22M954-M-WS-RW-PR-1251-B | JASH | Sent to BU Operations | 20 |  | lpgsouth2@jashindia.com |  | 18.01.24 | 18.01.24 | 24.04.24 | 25.04.24 | 30.04.24 | 03.05.24 | 04.07.24 | 10.07.24 |  |  |  |  | 10.07.24 | 10.07.24 | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Sluice gate - Intake | LE22M954-M-WS-RW-PR-1251 | LE22M954-M-WS-RW-PR-1251-C | AVK | Sent to BU Operations | 20 |  | neal@avkindia.com |  | 24.01.24 | 24.01.24 | 12.02.24 | 16.02.24 | 30.04.24 | 02.05.24 | 02.05.24 | 03.05.24 | 05.07.24 | 06.07.24 | 03.07.24 | 06.07.24 | 12.07.24 | 12.07.24 | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | Sluice gate - Intake | LE22M954-M-WS-RW-PR-1251 | LE22M954-M-WS-RW-PR-1251-D | IVC | Regret offer | PR Closed |  |  |  | 24.01.24 | 24.01.24 | [12 empty] | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-15.07.2024-09:36:42
Mandya | Mechanical | Sluice gate - Intake | LE22M954-M-WS-RW-PR-1251 | LE22M954-M-WS-RW-PR-1251-E | Fluid Control | Sent to BU Operations | 20 |  |  |  |  | 21.06.24 | 24.06.24 | 25.06.24 | 25.06.24 | 01.07.24 | 02.07.24 | 05.07.24 | 08.07.24 | 10.07.24 |  |  | 10.07.24 | 10.07.24 | 15.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | EOT crane - Intake | LE22M954-M-WS-RW-PR-1253 | LE22M954-M-WS-RW-PR-1253-A | INDEF | Pre-order comments issued | 37 | Pending with Vendor |  |  | 01.03.24 | 01.03.24 | 10.06.24 | 19.06.24 | 20.06.24 | 28.06.24 | [17 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | EOT crane - Intake | LE22M954-M-WS-RW-PR-1253 | LE22M954-M-WS-RW-PR-1253-B | Japs | Pre-order comments issued | 146 | Cleared from Mechanical Side. Sent to Electrical Team for clearance. |  |  | 05.03.24 | 05.03.24 | 05.03.24 | 11.03.24 | [19 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Mechanical | EOT crane - Intake | LE22M954-M-WS-RW-PR-1253 | LE22M954-M-WS-RW-PR-1253-C | Reva | Pre-order comments issued | 136 |  |  |  | 05.03.24 | 05.03.24 | 20.03.24 | 21.03.24 | [19 empty] | 31.07.24 | 17.08.24 |  | deepak.sabnani@lntecc.com-22.07.2024-09:32:46
Mandya | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M954-I-WS-WT-PR-5101 | LE22M954-I-WS-WT-PR-5101-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Pressure transmitter | LE22M954-I-WS-WT-PR-5102 | LE22M954-I-WS-WT-PR-5102-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Float & Board Level gauge | LE22M954-I-WS-WT-PR-5103 | LE22M954-I-WS-WT-PR-5103-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | level switch - Conductivity type | LE22M954-I-WS-WT-PR-5104 | LE22M954-I-WS-WT-PR-5104-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Ultrasonic level Transmitter | LE22M954-I-WS-WT-PR-5105 | LE22M954-I-WS-WT-PR-5105-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Radar Level Transmitter | LE22M954-I-WS-WT-PR-5106 | LE22M954-I-WS-WT-PR-5106-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Rate for flow transmitter | LE22M954-I-WS-WT-PR-5108 | LE22M954-I-WS-WT-PR-5108-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Bypass Rotameter | LE22M954-I-WS-WT-PR-5109 | LE22M954-I-WS-WT-PR-5109-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Electromagnectic flow meter | LE22M954-I-WS-WT-PR-5110 | LE22M954-I-WS-WT-PR-5110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Ultrasonic type Open channel flow transmitter | LE22M954-I-WS-WT-PR-5111 | LE22M954-I-WS-WT-PR-5111-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | battery operated Flow meter | LE22M954-I-WS-WT-PR-5112 | LE22M954-I-WS-WT-PR-5112-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | pH Meter | LE22M954-I-WS-WT-PR-5113 | LE22M954-I-WS-WT-PR-5113-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Turbidity meter | LE22M954-I-WS-WT-PR-5114 | LE22M954-I-WS-WT-PR-5114-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Residual Chlorine Analyzer | LE22M954-I-WS-WT-PR-5115 | LE22M954-I-WS-WT-PR-5115-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:31
Mandya | Instrumentation | Conductivity Analyzer | LE22M954-I-WS-WT-PR-5116 | LE22M954-I-WS-WT-PR-5116-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:32
Mandya | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M954-I-WS-WT-PR-5117 | LE22M954-I-WS-WT-PR-5117-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:32
Mandya | Instrumentation | instrumentation Control & signal Cables | LE22M954-I-WS-WT-PR-5118 | LE22M954-I-WS-WT-PR-5118-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:32
Mandya | Instrumentation | UPS | LE22M954-I-WS-WT-PR-5119 | LE22M954-I-WS-WT-PR-5119-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.12.24 | 02.01.25 | 03.03.25 | sooryaprakash.t@lntecc.com-04.07.2024-10:10:32
Mandya | Electrical | Lugs & Glands | LE22M954-E-WS-WT-PR-4003 | LE22M954-E-WS-WT-PR-4003-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | Transformer | LE22M954-E-WS-WT-PR-4004 | LE22M954-E-WS-WT-PR-4004-A | Kirloskar | Pre-order comments issued | 118 |  |  | aditya.ksr@kirloskarelectric.com | 26.10.22 | 29.2.24 | 25.03.24 | 08.04.24 | [19 empty] | 30.09.24 | 17.10.24 | 16.12.24 | duppalapudi.raviteja@lntecc.com-06.07.2024-10:07:17
Mandya | Electrical | Transformer | LE22M954-E-WS-WT-PR-4004 | LE22M954-E-WS-WT-PR-4004-B | Universal | Awaiting pre-offer from vendor | 130 | Only commercial offer recieved Reminder mail sent on 27-03 -24 Technical offer yet to recieve |  | abhishek@upt.in | 26.10.22 | 29.2.24 | 27.03.24 | [20 empty] | 30.09.24 | 17.10.24 | 16.12.24 | duppalapudi.raviteja@lntecc.com-06.07.2024-10:07:17
Mandya | Electrical | Transformer | LE22M954-E-WS-WT-PR-4004 | LE22M954-E-WS-WT-PR-4004-C | Voltamp | Awaiting pre-offer from vendor | 157 |  |  | sasik_vtlchn@voltamptransformers.com | 26.10.22 | 29.2.24 | [21 empty] | 30.09.24 | 17.10.24 | 16.12.24 | duppalapudi.raviteja@lntecc.com-06.07.2024-10:07:17
Mandya | Electrical | Transformer | LE22M954-E-WS-WT-PR-4004 | LE22M954-E-WS-WT-PR-4004-D | Power Star | Pre-order pending with EDRC | 37 |  |  | sailaja@powerstarelectric.net | 26.10.22 | 13.6.24 | 28.06.24 | [20 empty] | 30.09.24 | 17.10.24 | 16.12.24 | duppalapudi.raviteja@lntecc.com-06.07.2024-10:07:17
Mandya | Electrical | Transformer | LE22M954-E-WS-WT-PR-4004 | LE22M954-E-WS-WT-PR-4004-E | Toshiba | Regret offer | PR Closed |  |  | marketing@toshiba-ttdi.com |  | 14.6.24 | [21 empty] | 30.09.24 | 17.10.24 | 16.12.24 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Panel | LE22M954-E-WS-WT-PR-4005 | LE22M954-E-WS-WT-PR-4005-A | SCHNIEDER | Pre-order pending with EDRC | 131 |  |  | sunshinecontrols96@gmail.com | 20.10.23 | 02.03.24 | 07.03.24 | 21.03.24 | 26.03.24 | [18 empty] | 30.09.24 | 17.10.24 | 16.12.24 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Panel | LE22M954-E-WS-WT-PR-4005 | LE22M954-E-WS-WT-PR-4005-B | ABB | Regret offer | PR Closed | Not manufacturing outdoor panels |  |  |  | 02.03.24 | [21 empty] | 31.12.24 | 17.01.25 | 18.03.25 | duppalapudi.raviteja@lntecc.com-01.07.2024-12:02:26
Mandya | Electrical | HT Panel | LE22M954-E-WS-WT-PR-4005 | LE22M954-E-WS-WT-PR-4005-C | SIEMENS | Pre-order pending with EDRC | 132 |  |  | Vinay.a@siemens.com |  | 02.03.24 | 25.03.24 | [20 empty] | 31.12.24 | 17.01.25 | 18.03.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Panel | LE22M954-E-WS-WT-PR-4005 | LE22M954-E-WS-WT-PR-4005-D | LOTUS POWER GEAR | Pre-order pending with EDRC | 88 |  |  | vinaykumar_s@lotuspowergear.co.in | 20.10.23 | 02.03.24 | 09.03.24 | 16.03.24 | 08.05.24 | [18 empty] | 31.12.24 | 17.01.25 | 18.03.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | LT panels | LE22M954-E-WS-WT-PR-4007 | LE22M954-E-WS-WT-PR-4007-A | LOTUS POWER GEAR | Pre-order pending with EDRC | 89 |  |  | vinaykumar_s@lotuspowergear.co.in |  | 24.04.24 | 07.05.24 | [20 empty] | 31.12.24 | 17.01.25 | 18.03.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Termination Kit | LE22M954-E-WS-WT-PR-4008 | LE22M954-E-WS-WT-PR-4008-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Fixed Capacitor | LE22M954-E-WS-WT-PR-4009 | LE22M954-E-WS-WT-PR-4009-A | ABB | Pre-order pending with EDRC | 72 |  |  | karthik.kaki@hitachienergy.com |  | 28.03.24 | 09.04.24 | 10.05.24 | 24.5.24 | [18 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Fixed Capacitor | LE22M954-E-WS-WT-PR-4009 | LE22M954-E-WS-WT-PR-4009-B | Madhav Capacitors | Pre-order pending with EDRC | 82 |  |  | vaibhav@madhavcapacitors.co.in |  | 02.04.24 | 05.04.24 | 10.05.24 | 14.05.24 | [18 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Fixed Capacitor | LE22M954-E-WS-WT-PR-4009 | LE22M954-E-WS-WT-PR-4009-C | Universal Power Equipments | Awaiting pre-offer from vendor | 124 |  |  | deepak@upe.co.in |  | 02.04.24 | [21 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Fixed Capacitor | LE22M954-E-WS-WT-PR-4009 | LE22M954-E-WS-WT-PR-4009-D | TDK | Awaiting pre-offer from vendor | 123 |  |  | rupesh@conquerent .in |  | 03.04.24 | [21 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | Power and Control Cable | LE22M954-E-WS-WT-PR-4010 | LE22M954-E-WS-WT-PR-4010-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | Earthing & Lightning Material | LE22M954-E-WS-WT-PR-4011 | LE22M954-E-WS-WT-PR-4011-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | Safety Accessories | LE22M954-E-WS-WT-PR-4012 | LE22M954-E-WS-WT-PR-4012-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | Cable Tray | LE22M954-E-WS-WT-PR-4013 | LE22M954-E-WS-WT-PR-4013-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | LPBS | LE22M954-E-WS-WT-PR-4014 | LE22M954-E-WS-WT-PR-4014-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | CTPT Unit | LE22M954-E-WS-WT-PR-4015A | LE22M954-E-WS-WT-PR-4015A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | Poles & conductors | LE22M954-E-WS-WT-PR-4015B | LE22M954-E-WS-WT-PR-4015B-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | Lighting Fixtures | LE22M954-E-WS-WT-PR-4016 | LE22M954-E-WS-WT-PR-4016-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | Lighting Materials & accessories | LE22M954-E-WS-WT-PR-4016A | LE22M954-E-WS-WT-PR-4016A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | LDB | LE22M954-E-WS-WT-PR-4016B | LE22M954-E-WS-WT-PR-4016B-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 16.10.24 | 02.11.24 | 01.01.25 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT Soft Starter | LE22M954-E-WS-WT-PR-4017 | LE22M954-E-WS-WT-PR-4017-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.09.24 | 17.10.24 | 16.12.24 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Mandya | Electrical | HT VFD | LE22M954-E-WS-WT-PR-4018 | LE22M954-E-WS-WT-PR-4018-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 30.09.24 | 17.10.24 | 16.12.24 | duppalapudi.raviteja@lntecc.com-03.07.2024-17:28:57
Nabrangpur (4 schemes) | Process | Clariflocculator mechanism | LE23M357-P-WS-WT-PR-2402 | LE23M357-P-WS-WT-PR-2402-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Air Blower | LE23M357-P-WS-WT-PR-2403 | LE23M357-P-WS-WT-PR-2403-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Agitator | LE23M357-P-WS-WT-PR-2404 | LE23M357-P-WS-WT-PR-2404-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | WTP Sluice gates | LE23M357-P-WS-WT-PR-2405 | LE23M357-P-WS-WT-PR-2405-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Chlorination system | LE23M357-P-WS-WT-PR-2406 | LE23M357-P-WS-WT-PR-2406-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Chlorine Tonner | LE23M357-P-WS-WT-PR-2407 | LE23M357-P-WS-WT-PR-2407-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Filter media | LE23M357-P-WS-WT-PR-2408 | LE23M357-P-WS-WT-PR-2408-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Backwash pump | LE23M357-P-WS-WT-PR-2409 | LE23M357-P-WS-WT-PR-2409-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Submersible pump | LE23M357-P-WS-WT-PR-2410 | LE23M357-P-WS-WT-PR-2410-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Electrical hoist | LE23M357-P-WS-WT-PR-2411 | LE23M357-P-WS-WT-PR-2411-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Manual chain pulley block | LE23M357-P-WS-WT-PR-2412 | LE23M357-P-WS-WT-PR-2412-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Dosing pump | LE23M357-P-WS-WT-PR-2413 | LE23M357-P-WS-WT-PR-2413-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Sampling pump | LE23M357-P-WS-WT-PR-2414 | LE23M357-P-WS-WT-PR-2414-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Submersible mixer | LE23M357-P-WS-WT-PR-2415 | LE23M357-P-WS-WT-PR-2415-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Dewatering pump | LE23M357-P-WS-WT-PR-2416 | LE23M357-P-WS-WT-PR-2416-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Dissolving tray | LE23M357-P-WS-WT-PR-2417 | LE23M357-P-WS-WT-PR-2417-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Trolley | LE23M357-P-WS-WT-PR-2418 | LE23M357-P-WS-WT-PR-2418-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Platform weighing machine | LE23M357-P-WS-WT-PR-2419 | LE23M357-P-WS-WT-PR-2419-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Exhaust fan | LE23M357-P-WS-WT-PR-2420 | LE23M357-P-WS-WT-PR-2420-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Lab Equipments | LE23M357-P-WS-WT-PR-2421 | LE23M357-P-WS-WT-PR-2421-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Sludge thickener | LE23M357-P-WS-WT-PR-2422 | LE23M357-P-WS-WT-PR-2422-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | DWPE tank agitator | LE23M357-P-WS-WT-PR-2423 | LE23M357-P-WS-WT-PR-2423-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Centrifuge | LE23M357-P-WS-WT-PR-2424 | LE23M357-P-WS-WT-PR-2424-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Screw pumps | LE23M357-P-WS-WT-PR-2425 | LE23M357-P-WS-WT-PR-2425-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | PACL Unloading cum Transfer pump | LE23M357-P-WS-WT-PR-2426 | LE23M357-P-WS-WT-PR-2426-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Process | Service water pump | LE23M357-P-WS-WT-PR-2427 | LE23M357-P-WS-WT-PR-2427-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | HSC Pump - CWPH & IBPS | LE23M357-M-WS-CW-PR-1503 | LE23M357-M-WS-CW-PR-1503-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | SLV - CWPH & IBPS | LE23M357-M-WS-CW-PR-1504 | LE23M357-M-WS-CW-PR-1504-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | NRV - CWPH & IBPS | LE23M357-M-WS-CW-PR-1505 | LE23M357-M-WS-CW-PR-1505-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | DJ - CWPH & IBPS | LE23M357-M-WS-CW-PR-1506 | LE23M357-M-WS-CW-PR-1506-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | AV - CWPH & IBPS | LE23M357-M-WS-CW-PR-1507 | LE23M357-M-WS-CW-PR-1507-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | EOT Crane - CWPH & IBPS | LE23M357-M-WS-CW-PR-1509 | LE23M357-M-WS-CW-PR-1509-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | BFV - CWPH & IBPS | LE23M357-M-WS-CW-PR-1510 | LE23M357-M-WS-CW-PR-1510-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | Electric Hoist - CWPH & IBPS | LE23M357-M-WS-CW-PR-1511 | LE23M357-M-WS-CW-PR-1511-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | Submersible Pump - CWPH & IBPS | LE23M357-M-WS-CW-PR-1512 | LE23M357-M-WS-CW-PR-1512-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | Isolation Valve - Pipeline | LE23M357-M-WS-CW-PR-1513 | LE23M357-M-WS-CW-PR-1513-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | AV - Pipeline | LE23M357-M-WS-CW-PR-1514 | LE23M357-M-WS-CW-PR-1514-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | PRV - Pipeline | LE23M357-M-WS-CW-PR-1515 | LE23M357-M-WS-CW-PR-1515-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | FCV - Pipeline | LE23M357-M-WS-CW-PR-1516 | LE23M357-M-WS-CW-PR-1516-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | Sluice Gate - CWPH & IBPS | LE23M357-M-WS-CW-PR-1517 | LE23M357-M-WS-CW-PR-1517-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | ACV - Surge Protection Device | LE23M357-M-WS-CW-PR-1518 | LE23M357-M-WS-CW-PR-1518-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | ZVV - Surge Protection Device | LE23M357-M-WS-CW-PR-1519 | LE23M357-M-WS-CW-PR-1519-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | Surge Vessel - Surge Protection Device | LE23M357-M-WS-CW-PR-1520 | LE23M357-M-WS-CW-PR-1520-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | Exhaust fan - Mech | LE23M357-M-WS-CW-PR-1521 | LE23M357-M-WS-CW-PR-1521-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | VT Pump - Intake | LE23M357-M-WS-RW-PR-1501A | LE23M357-M-WS-RW-PR-1501A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | Sluice Gate - Intake | LE23M357-M-WS-RW-PR-1502A | LE23M357-M-WS-RW-PR-1502A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | SLV - Intake | LE23M357-M-WS-RW-PR-1504 | LE23M357-M-WS-RW-PR-1504-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | NRV - Intake | LE23M357-M-WS-RW-PR-1505 | LE23M357-M-WS-RW-PR-1505-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | DJ - Intake | LE23M357-M-WS-RW-PR-1506 | LE23M357-M-WS-RW-PR-1506-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | AV - Intake | LE23M357-M-WS-RW-PR-1507 | LE23M357-M-WS-RW-PR-1507-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | EB - Intake | LE23M357-M-WS-RW-PR-1508 | LE23M357-M-WS-RW-PR-1508-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Mechanical | EOT Crane - Intake | LE23M357-M-WS-RW-PR-1509 | LE23M357-M-WS-RW-PR-1509-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M357-I-WS-WT-PR-5101 | LE22M357-I-WS-WT-PR-5101-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Pressure transmitter | LE22M357-I-WS-WT-PR-5102 | LE22M357-I-WS-WT-PR-5102-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Float & Board Level gauge | LE22M357-I-WS-WT-PR-5103 | LE22M357-I-WS-WT-PR-5103-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | level switch - Conductivity type | LE22M357-I-WS-WT-PR-5104 | LE22M357-I-WS-WT-PR-5104-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Ultrasonic level Transmitter | LE22M357-I-WS-WT-PR-5105 | LE22M357-I-WS-WT-PR-5105-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Radar Level Transmitter | LE22M357-I-WS-WT-PR-5106 | LE22M357-I-WS-WT-PR-5106-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Rate for flow transmitter | LE22M357-I-WS-WT-PR-5108 | LE22M357-I-WS-WT-PR-5108-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Bypass Rotameter | LE22M357-I-WS-WT-PR-5109 | LE22M357-I-WS-WT-PR-5109-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Electromagnectic flow meter | LE22M357-I-WS-WT-PR-5110 | LE22M357-I-WS-WT-PR-5110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Ultrasonic type Open channel flow transmitter | LE22M357-I-WS-WT-PR-5111 | LE22M357-I-WS-WT-PR-5111-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | battery operated Flow meter | LE22M357-I-WS-WT-PR-5112 | LE22M357-I-WS-WT-PR-5112-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | pH Meter | LE22M357-I-WS-WT-PR-5113 | LE22M357-I-WS-WT-PR-5113-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Turbidity meter | LE22M357-I-WS-WT-PR-5114 | LE22M357-I-WS-WT-PR-5114-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Residual Chlorine Analyzer | LE22M357-I-WS-WT-PR-5115 | LE22M357-I-WS-WT-PR-5115-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | Conductivity Analyzer | LE22M357-I-WS-WT-PR-5116 | LE22M357-I-WS-WT-PR-5116-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M357-I-WS-WT-PR-5117 | LE22M357-I-WS-WT-PR-5117-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | instrumentation Control & signal Cables | LE22M357-I-WS-WT-PR-5118 | LE22M357-I-WS-WT-PR-5118-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Instrumentation | UPS | LE22M357-I-WS-WT-PR-5119 | LE22M357-I-WS-WT-PR-5119-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | sooryaprakash.t@lntecc.com
Nabrangpur (4 schemes) | Electrical | CTPT Unit | LE23M357-E-WS-WT-PR-4101 | LE23M357-E-WS-WT-PR-4101-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Poles & conductors | LE23M357-E-WS-WT-PR-4101A | LE23M357-E-WS-WT-PR-4101A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Transformer | LE23M357-E-WS-WT-PR-4103 | LE23M357-E-WS-WT-PR-4103-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | HT Panel | LE23M357-E-WS-WT-PR-4104 | LE23M357-E-WS-WT-PR-4104-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | HT Soft Starter | LE23M357-E-WS-WT-PR-4105 | LE23M357-E-WS-WT-PR-4105-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | HT Fixed Capacitor | LE23M357-E-WS-WT-PR-4106 | LE23M357-E-WS-WT-PR-4106-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | LT panels | LE23M357-E-WS-WT-PR-4107 | LE23M357-E-WS-WT-PR-4107-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | DCDB | LE23M357-E-WS-WT-PR-4109 | LE23M357-E-WS-WT-PR-4109-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Power and Control Cable | LE23M357-E-WS-WT-PR-4110 | LE23M357-E-WS-WT-PR-4110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Cable Tray | LE23M357-E-WS-WT-PR-4111 | LE23M357-E-WS-WT-PR-4111-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Lugs & Glands | LE23M357-E-WS-WT-PR-4112 | LE23M357-E-WS-WT-PR-4112-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | HT Termination Kit | LE23M357-E-WS-WT-PR-4112A | LE23M357-E-WS-WT-PR-4112A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | LPBS | LE23M357-E-WS-WT-PR-4113 | LE23M357-E-WS-WT-PR-4113-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Earthing & Lightning Material | LE23M357-E-WS-WT-PR-4114 | LE23M357-E-WS-WT-PR-4114-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Lighting Fixtures | LE23M357-E-WS-WT-PR-4115 | LE23M357-E-WS-WT-PR-4115-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Lighting Materials & accessories | LE23M357-E-WS-WT-PR-4115A | LE23M357-E-WS-WT-PR-4115A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | LDB | LE23M357-E-WS-WT-PR-4115B | LE23M357-E-WS-WT-PR-4115B-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | Safety Accessories | LE23M357-E-WS-WT-PR-4116 | LE23M357-E-WS-WT-PR-4116-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
Nabrangpur (4 schemes) | Electrical | DG Set | LE23M357-E-WS-WT-PR-4118 | LE23M357-E-WS-WT-PR-4118-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthik.ajithkumar@lntecc.com
NC 42 | Mechanical | EOT Crane | LE22M232-M-WS-DC-1001 | LE22M232-M-WS-DC-1001-A | JAPS | Pre-order technically cleared | 75 |  | Rashmin Patel 09825098913 | japspro@yahoo.co.in, tech.japsproject@gmail.com |  | 19.10.22 | 02.11.22 | 03.01.23 | 04.04.24 | 23.04.24 | 25.04.24 | 26.04.24 | 16.05.24 | 21.05.24 |  |  | 21.05.24 | 21.05.24 |  | T1 | [7 empty] | 21.05.24 | 07.06.24 | 06.08.24 | svcn@lntecc.com-26.07.2024-17:12:46
NC 42 | Mechanical | EOT Crane | LE22M232-M-WS-DC-1001 | LE22M232-M-WS-DC-1001-B | REVA | Pre-order technically cleared | 48 |  | Amita Shah 9899484744 | mkt@revacranes.com, crm@revacranes.com,south@revacranes.com |  | 02.11.22 | 07.11.22 | 03.01.23 | 23.04.24 | 26.04.24 | 06.06.24 | 12.06.24 | 13.06.24 | 17.06.24 |  |  | 17.06.24 | 17.06.24 | 17.06.24 | T2 | [7 empty] | 17.06.24 | 04.07.24 | 02.09.24 | svcn@lntecc.com-26.07.2024-17:12:46
NC 42 | Mechanical | Pump houseValves | LE22M232-M-WS-DC-1002 | LE22M232-M-WS-DC-1002-A | R&D | Post-order technically cleared | 142 |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 05.03.24 | 05.03.24 | 05.03.24 | [8 empty] | 06.03.24 | 06.03.24 | 07.03.24 | T1 | 08.03.24 | R&D | 15.03.24 | 15.03.24 | 15.03.24 | 15.03.24 |  | 06.03.24 | 23.03.24 | 07.05.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | Pipe line valves | LE22M232-M-WS-DC-1003 | LE22M232-M-WS-DC-1003-A | R&D | Post-order technically cleared | 142 |  | Bhupesh Deshmukh | bhupesh@rdmultiples.com |  | 05.03.24 | 05.03.24 | 05.03.24 | [8 empty] | 06.03.24 | 06.03.24 | 07.03.24 | T1 | 08.03.24 | R&D | 15.03.24 | 15.03.24 | 15.03.24 | 15.03.24 |  | 06.03.24 | 23.03.24 | 07.05.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | VT pumps | LE22M232-M-WS-DC-1004 | LE22M232-M-WS-DC-1004-A | Xylem | Approved by Client | PR Closed |  | Vishal Patil | <Vishal.Patil@xylem.com |  | 05.03.24 | 05.03.24 | 05.03.24 | [8 empty] | 06.03.24 | 06.03.24 | 07.03.24 | T1 | 08.03.24 | Xylem | 15.03.24 | 15.03.24 | 15.03.24 | 15.03.24 | 19.03.24 | 06.03.24 | 23.03.24 | 07.05.24 | svcn@lntecc.com-02.07.2024-10:30:53
NC 42 | Mechanical | Stop lock gate | LE22M232-M-WS-DC-1005 | LE22M232-M-WS-DC-1005-A | JASH | Pre-order technically rejected | PR Closed |  | Rupanshu Geete | iipgmarketing@jashindia.com; abhishekkumar@jashindia.com <abhishekkumar@jashindia.com> |  | 13.04.23 | 01.10.23 | 02.10.23 | 08.10.23 | 05.07.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | bnk@lntecc.com-12.07.2024-15:17:20
NC 42 | Mechanical | Stop lock gate | LE22M232-M-WS-DC-1005 | LE22M232-M-WS-DC-1005-B | Triveni | Pre-order comments issued | 30 |  | Gaurav Dhiman | navajyoti.roy@projects.trivenigroup.com>; gauravdhiman@projects.trivenigroup.com> |  | 13.04.23 | 21.03.24 | 21.03.24 | 05.07.24 | 05.07.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | Trash rack | LE22M232-M-WS-DC-1006 | LE22M232-M-WS-DC-1006-A | Triveni | Approved by Client | PR Closed |  | Gaurav Dhiman | navajyoti.roy@projects.trivenigroup.com>; gauravdhiman@projects.trivenigroup.com> |  | 26.09.23 | 27.09.23 | 27.09.23 | [8 empty] | 05.10.23 | 05.10.23 | 05.10.23 | T1 | 31.01.24 | Triveni | 01.02.24 | 20.03.24 | 20.03.24 | 20.03.24 | 28.03.24 | 05.10.23 | 22.10.23 | 21.12.23 | svcn@lntecc.com-02.07.2024-10:30:53
NC 42 | Mechanical | Wire mesh | LE22M232-M-WS-DC-1007 | LE22M232-M-WS-DC-1007-A | JASH | Regret offer | PR Closed |  | Rupanshu Geete | iipgmarketing@jashindia.com; abhishekkumar@jashindia.com <abhishekkumar@jashindia.com> |  | 13.04.23 | 01.10.23 | 02.10.23 | 08.10.23 | 05.07.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-17:21:54
NC 42 | Mechanical | Wire mesh | LE22M232-M-WS-DC-1007 | LE22M232-M-WS-DC-1007-B | Triveni | Pre-order technically cleared | 17 |  | Gaurav Dhiman | navajyoti.roy@projects.trivenigroup.com>; gauravdhiman@projects.trivenigroup.com> |  | 13.04.23 | 21.03.24 | 21.03.24 | 05.07.24 | 05.07.24 | 16.07.24 | 18.07.24 |  |  |  |  | 16.07.24 | 16.07.24 | 17.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | Exhaust fans | LE22M232-M-WS-DC-1008 | LE22M232-M-WS-DC-1008-A | BU | Awaiting pre-offer from vendor | 45 |  |  | ROHITH-SS@Lntecc.com |  | 20.06.24 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | Dewatering pumps | LE22M232-M-WS-DC-1009 | LE22M232-M-WS-DC-1009-A | AQUA | Pre-order technically cleared | 12 |  | S.T.Sambandam 8144003131 | chennai@aquapumps.com | 10.04.24 | 10.04.24 | 22.04.24 | 30.05.24 | 12.06.24 | 24.06.24 | 28.06.24 | 12.07.24 | 18.07.24 | 20.07.24 | 22.07.24 | 23.07.24 | 22.07.24 | 22.07.24 | 23.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-23.07.2024-17:56:53
NC 42 | Mechanical | Sluice Gates | LE22M232-M-WS-DC-1010 | LE22M232-M-WS-DC-1010-A | Jash | Pre-order comments issued | 23 |  | manogya@jashindia.com | manogya@jashindia.com | 21.05.24 | 21.05.24 | 29.05.24 | 17.06.24 | 20.06.24 | 02.07.24 | 04.07.24 | 12.07.24 | [15 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | Sluice Gates | LE22M232-M-WS-DC-1010 | LE22M232-M-WS-DC-1010-B | Oreintal | Pre-order technically cleared | 9 |  | Sanjay Mahensaria | orientalcastings@gmail.com | 21.05.24 | 21.05.24 | 02.07.24 | 09.07.24 | 09.07.24 | 26.07.24 | [6 empty] | 26.07.24 | 26.07.24 | 26.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:12:56
NC 42 | Mechanical | Expansion bellow | LE22M232-M-WS-DC-1011 | LE22M232-M-WS-DC-1011-A | Ratnaflex | Pre-order technically cleared | 45 |  | Anurag Patel 9512041253 | sales02@ratnaflex.com |  | 05.11.22 | 11.11.22 | 30.12.22 | 10.04.24 | 20.04.24 | 20.05.24 | 23.05.24 |  |  |  |  | 20.06.24 | 20.06.24 | 20.06.24 | T1 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | Expansion bellow | LE22M232-M-WS-DC-1011 | LE22M232-M-WS-DC-1011-B | Precise | Pre-order technically cleared | 45 |  | S. J. Mehta 93777 73186 | sjm@vedantagroup.net |  | 05.11.22 | 11.11.22 | 30.12.22 | 10.04.24 | 20.04.24 | 20.05.24 | 23.05.24 | 11.06.24 | 13.06.24 |  |  | 20.06.24 | 20.06.24 | 20.06.24 | T2 | [7 empty] | 20.06.24 | 07.07.24 | 05.09.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | ACV | LE22M232-M-WS-DC-1012 | LE22M232-M-WS-DC-1012-A | AVK | Regret offer | PR Closed | Vendor Suggesting for a new Product with enhanced features which is not in line with NIT. | Subhash 9176966455 | subhash@avkindia.com | 03.05.24 | 03.05.24 | 30.05.24 | 06.06.24 | 10.06.24 | 12.06.24 | [17 empty] | 12.06.24 | 29.06.24 | 28.08.24 | svcn@lntecc.com-02.07.2024-10:31:40
NC 42 | Mechanical | ACV | LE22M232-M-WS-DC-1012 | LE22M232-M-WS-DC-1012-B | JASH | Regret offer | PR Closed | Sluice Valve , a part of ACV is not manufactured by Jash. They are going with Sub Vendor who is deviating in MOC of sluice Valve. NIT requirement is DI, Vendor proposing CI | Ashwini Sharma 7869910427 | ashwini@jashindia.com; neeraj@jashindia.com | 23.05.24 | 23.05.24 | 28.05.24 | 30.05.24 | 10.06.24 | 12.06.24 | 18.06.24 | 24.06.24 | [15 empty] | 24.06.24 | 11.07.24 | 09.09.24 | svcn@lntecc.com-02.07.2024-10:31:40
NC 42 | Mechanical | ACV | LE22M232-M-WS-DC-1012 | LE22M232-M-WS-DC-1012-C | Sigmaflow | Pre-order technically cleared | 50 |  | J.Jagadesh 9073342195 | jagadesh@sigmaflow.in | 03.05.24 | 03.05.24 | 06.05.24 | 23.05.24 | 12.06.24 | 14.06.24 | [6 empty] | 14.06.24 | 10.06.24 | 15.06.24 | T1 | [7 empty] | 10.06.24 | 27.06.24 | 26.08.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Mechanical | Pipe line valves (Air Valves) | LE22M232-M-WS-DC-1013 | LE22M232-M-WS-DC-1013-A | sigmaflow | Pre-order technically cleared | 24 |  | J.Jagadesh 9073342195 | jagadesh@sigmaflow.in |  | 03.05.24 | 26.06.24 | 11.07.24 | [8 empty] | 11.07.24 | 11.07.24 | 11.07.24 | [8 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-26.07.2024-17:12:47
NC 42 | Instrumentation | Instrumentation Control & signal Cables | LE22M232-I-WS-PR-CA-5508 | LE22M232-I-WS-PR-CA-5508-A | Avocab | Pre-order comments issued | 92 |  |  |  |  | 27.07.21 | 16.04.24 | 04.05.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Instrumentation Control & signal Cables | LE22M232-I-WS-PR-CA-5508 | LE22M232-I-WS-PR-CA-5508-B | Gemscab | Sent to BU Operations | 92 |  |  |  |  | 27.07.21 | 16.04.24 | 04.05.24 | [8 empty] | 04.05.24 | 04.05.24 | 04.05.24 | T1 | [7 empty] | 04.05.24 | 21.05.24 | 20.07.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Instrumentation Control & signal Cables | LE22M232-I-WS-PR-CA-5508 | LE22M232-I-WS-PR-CA-5508-C | Special Cables | Pre-order comments issued | 68 |  |  |  |  | 27.07.21 | 28.05.24 | 28.05.24 | [19 empty] | 31.07.24 | 17.08.24 | 16.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Float & Board Level gauge | LE22M232-I-WS-PR-LI-5503 | LE22M232-I-WS-PR-LI-5503-A | Scientific Devices | Sent to BU Operations | 246 |  |  |  |  | 27.07.21 | 31.10.23 | 20.11.23 | 28.11.23 | [7 empty] | 02.12.23 | 02.12.23 | 02.12.23 | T1 | [7 empty] | 02.12.23 | 19.12.23 | 17.02.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Float & Board Level gauge | LE22M232-I-WS-PR-LI-5503 | LE22M232-I-WS-PR-LI-5503-B | Pune Techtrol | Sent to BU Operations | 102 |  |  |  |  | 27.07.21 | 09.11.23 | 20.11.23 | 24.04.24 | [7 empty] | 24.04.24 | 24.04.24 | 24.04.24 | T2 | [7 empty] | 24.04.24 | 11.05.24 | 10.07.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Level switch - Conductivity type type | LE22M232-I-WS-PR-LS-5504 | LE22M232-I-WS-PR-LS-5504-A |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 | 17.08.24 | 16.10.24 | gopika.nath@lntecc.com-10.07.2024-15:28:42
NC 42 | Instrumentation | Ultrasonic level transmitter | LE22M232-I-WS-PR-LT-5505 | LE22M232-I-WS-PR-LT-5505-A | Siemens | Sent to BU Operations | 424 |  |  |  |  | 27.07.21 | 05.05.23 | 07.06.23 | [8 empty] | 07.06.23 | 07.06.23 | 07.06.23 | T1 | [7 empty] | 07.06.23 | 24.06.23 | 23.08.23 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Ultrasonic level transmitter | LE22M232-I-WS-PR-LT-5505 | LE22M232-I-WS-PR-LT-5505-B | E&H | Sent to BU Operations | 424 |  |  |  |  | 27.07.21 | 18.05.23 | 07.06.23 | [8 empty] | 07.06.23 | 07.06.23 | 07.06.23 | T2 | [7 empty] | 07.06.23 | 24.06.23 | 23.08.23 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Ultrasonic level transmitter | LE22M232-I-WS-PR-LT-5505 | LE22M232-I-WS-PR-LT-5505-C | ABB | Sent to BU Operations | 424 |  |  |  |  | 27.07.21 | 18.05.23 | 07.06.23 | [8 empty] | 07.06.23 | 07.06.23 | 07.06.23 | T3 | [7 empty] | 07.06.23 | 24.06.23 | 23.08.23 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M232-I-WS-PR-PG-5501 | LE22M232-I-WS-PR-PG-5501-A | Forbes Marshall | Sent to BU Operations | 241 |  |  |  |  | 27.07.21 | 07.12.23 | 07.12.23 | [8 empty] | 07.12.23 | 07.12.23 | 07.12.23 | T1 | [7 empty] | 07.12.23 | 24.12.23 | 22.02.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M232-I-WS-PR-PG-5501 | LE22M232-I-WS-PR-PG-5501-B | GIC | Sent to BU Operations | 206 |  |  |  |  | 27.07.21 | 07.12.23 | 07.12.23 | [8 empty] | 11.01.24 | 11.01.24 | 11.01.24 | T2 | [7 empty] | 11.01.24 | 28.01.24 | 28.03.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M232-I-WS-PR-PG-5501 | LE22M232-I-WS-PR-PG-5501-C | H Guru | Sent to BU Operations | 206 |  |  |  |  | 27.07.21 | 07.12.23 | 07.12.23 | [8 empty] | 11.01.24 | 11.01.24 | 11.01.24 | T3 | [7 empty] | 11.01.24 | 28.01.24 | 28.03.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M232-I-WS-PR-PL-5507 | LE22M232-I-WS-PR-PL-5507-A | Mitsubushi | Post-order technically cleared | 78 |  |  |  |  | 27.07.21 | 02.05.23 | 16.10.23 | [8 empty] | 16.10.23 | 16.10.23 | 16.10.23 | T1 | 20.04.24 | Mitsubushi | 28.04.24 | 18.05.24 | 18.05.24 | 18.05.24 |  | 16.10.23 | 02.11.23 | 01.01.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M232-I-WS-PR-PL-5507 | LE22M232-I-WS-PR-PL-5507-B | SATPL | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 06.05.23 | 25.10.23 | [8 empty] | 25.10.23 | 25.10.23 | 25.10.23 | T2 | [7 empty] | 25.10.23 | 11.11.23 | 10.01.24 | gopika.nath@lntecc.com-01.07.2024-15:12:35
NC 42 | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M232-I-WS-PR-PL-5507 | LE22M232-I-WS-PR-PL-5507-C | SIAS | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 04.05.23 | 16.10.23 | [8 empty] | 16.10.23 | 16.10.23 | 16.10.23 | T3 | [7 empty] | 16.10.23 | 02.11.23 | 01.01.24 | gopika.nath@lntecc.com-01.07.2024-15:12:35
NC 42 | Instrumentation | Pressure transmitter | LE22M232-I-WS-PR-PT-5502 | LE22M232-I-WS-PR-PT-5502-A | Siemens | Sent to BU Operations | 424 |  |  |  |  | 27.07.21 | 05.05.23 | 07.06.23 | [8 empty] | 07.06.23 | 07.06.23 | 07.06.23 | T1 | [7 empty] | 07.06.23 | 24.06.23 | 23.08.23 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Pressure transmitter | LE22M232-I-WS-PR-PT-5502 | LE22M232-I-WS-PR-PT-5502-B | E&H | Sent to BU Operations | 424 |  |  |  |  | 27.07.21 | 18.05.23 | 07.06.23 | [8 empty] | 07.06.23 | 07.06.23 | 07.06.23 | T2 | [7 empty] | 07.06.23 | 24.06.23 | 23.08.23 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Pressure transmitter | LE22M232-I-WS-PR-PT-5502 | LE22M232-I-WS-PR-PT-5502-C | ABB | Sent to BU Operations | 424 |  |  |  |  | 27.07.21 | 18.05.23 | 07.06.23 | [8 empty] | 07.06.23 | 07.06.23 | 07.06.23 | T3 | [7 empty] | 07.06.23 | 24.06.23 | 23.08.23 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Ultrasonic type flow transmitter | LE22M232-I-WS-PR-UF-5506 | LE22M232-I-WS-PR-UF-5506-A | SBEM | Sent to BU Operations | 120 |  |  |  |  | 27.07.21 | 12.03.24 | 06.04.24 | [8 empty] | 06.04.24 | 06.04.24 | 06.04.24 | T1 | [7 empty] | 06.04.24 | 23.04.24 | 22.06.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | Ultrasonic type flow transmitter | LE22M232-I-WS-PR-UF-5506 | LE22M232-I-WS-PR-UF-5506-B | Siemens | Pre-order technically cleared | 64 |  |  |  |  | 27.07.21 | 28.05.24 | 29.05.24 | 30.05.24 | 01.06.24 | [6 empty] | 01.06.24 | 01.06.24 | [9 empty] | 31.07.24 | 17.08.24 | 16.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Instrumentation | UPS | LE22M232-I-WS-PR-UP-5509 | LE22M232-I-WS-PR-UP-5509-A |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 | 17.08.24 | 16.10.24 | gopika.nath@lntecc.com-10.07.2024-15:28:42
NC 42 | Electrical | POWER & DISTRIBUTION TRANSFORMERS | LE22M232-E-WS-WT-PR-4101 | LE22M232-E-WS-WT-PR-4101-A | Hammond Power Solutions | Post-order technically cleared | 68 |  |  | rajesh.b@hammondpowersolutions.com |  | 14.12.22 | 07.01.23 | 11.01.23 | 19.01.23 | 21.01.23 | [6 empty] | 20.01.23 | 21.01.23 | 07.11.23 | T2 | 07.11.23 | Hammond Power Solutions | 20.12.23 | 22.12.23 | 12.03.24 | 28.05.24 |  | 21.01.23 | 07.02.23 | 08.04.23 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | MV VARIABLE FREQUENCY DRIVE | LE22M232-E-WS-WT-PR-4103 | LE22M232-E-WS-WT-PR-4103-A | TMEIC | Pre-order technically cleared | 83 |  | +91 9952935915 | Sreekarthick.Rangaswamy@tmeic.in |  | 30.06.23 | 06.07.23 | 19.07.23 | 12.04.24 | 02.05.24 | 03.05.24 | 10.05.24 |  |  |  |  | 02.05.24 | 13.05.24 |  | T1 | [7 empty] | 13.05.24 | 30.05.24 | 29.07.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | MV VARIABLE FREQUENCY DRIVE | LE22M232-E-WS-WT-PR-4103 | LE22M232-E-WS-WT-PR-4103-B | Hitachi | Pre-order technically cleared | 69 |  | +91 8980003832 | patel_hardik@hitachi-hirel.com |  | 30.06.23 | 06.07.23 | 06.04.24 | 16.04.24 | 02.05.24 | 10.05.24 | 13.05.24 |  |  |  |  | 16.05.24 | 27.05.24 |  | T1 | [7 empty] | 27.05.24 | 13.06.24 | 12.08.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | MV VARIABLE FREQUENCY DRIVE | LE22M232-E-WS-WT-PR-4103 | LE22M232-E-WS-WT-PR-4103-C | Schneider | Pre-order comments issued | 80 |  | +91 8976901682 | Anoop.Satheesh@se.com |  | 30.06.23 | 03.07.23 | 05.04.24 | 10.05.24 | 15.05.24 | [6 empty] | 16.05.24 | 16.05.24 |  | T1 | [7 empty] | 16.05.24 | 02.06.24 | 01.08.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | HT SWITCHGEAR | LE22M232-E-WS-WT-PR-4104 | LE22M232-E-WS-WT-PR-4104-A | HTS SWITCHGEARS | Sent to BU Operations | 151 |  | +91 7720010571 | abdul.patel@htswitchgears.com |  | 09.08.23 | 13.10.23 | 26.10.23 | 27.10.23 | 08.11.23 | [6 empty] | 10.11.23 | 28.02.24 | 06.03.24 | T1 | [7 empty] | 28.02.24 | 16.03.24 | 15.05.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | HT SWITCHGEAR | LE22M232-E-WS-WT-PR-4104 | LE22M232-E-WS-WT-PR-4104-B | POPULAR SWITCHGEAR | Sent to BU Operations | 151 |  | +91 9875142981 | barodaestimation@popularswitchgears.com |  | 09.08.23 | 18.10.23 | 04.01.24 | 21.02.24 | 06.03.24 | [6 empty] | 06.03.24 | 06.03.24 | 06.03.24 | T1 | [7 empty] | 06.03.24 | 23.03.24 | 22.05.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | HT Soft starter | LE22M232-E-WS-WT-PR-4105 | LE22M232-E-WS-WT-PR-4105-A | Jayashree Electron | Pre-order comments issued | 87 |  | +91 9422362586 | je_soft@jayashree.in |  | 29.04.24 | 08.05.24 | 09.05.24 | [11 empty] | T2 | [7 empty] | 19.07.24 | 05.08.24 | 04.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | HT Soft starter | LE22M232-E-WS-WT-PR-4105 | LE22M232-E-WS-WT-PR-4105-B | Innovative technomics | Pre-order comments issued | 76 |  | +91 9423578196 | sales.itpl@itechnomics.com |  | 29.04.24 | 10.05.24 | 20.05.24 | [11 empty] | T2 | [7 empty] | 20.07.24 | 06.08.24 | 05.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | BATTERY | LE22M232-E-WS-WT-PR-4106 | LE22M232-E-WS-WT-PR-4106-A |  | Enquiry yet to float | NA | [26 empty] | 11.09.24 | 28.09.24 | 27.11.24 | muthukumar.r@lntecc.com-10.07.2024-15:24:15
NC 42 | Electrical | LT Switchgear & APFC | LE22M232-E-WS-WT-PR-4107 | LE22M232-E-WS-WT-PR-4107-A | Sia Engineering Projects | Post-order comments issued | 41 |  | +91 7861880849 | shaishav.chandel@siasales.in |  | 09.08.23 | 21.08.23 | 31.08.23 | 02.11.23 | 07.11.23 | 08.11.23 | 10.11.23 |  |  |  |  | 28.03.24 | 28.03.24 | 04.05.24 | T1 | 04.05.24 | Sia Engineering Projects | 20.06.24 | 24.06.24 |  |  |  | 04.05.24 | 21.05.24 | 03.07.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | LT Switchgear & APFC | LE22M232-E-WS-WT-PR-4107 | LE22M232-E-WS-WT-PR-4107-B | HTS SWITCHGEARS | Regret offer | PR Closed |  | +91 7720010571 | abdul.patel@htswitchgears.com |  | 09.08.23 | 13.10.23 | 31.10.23 | 04.11.23 | 07.11.23 | 10.01.24 | 02.03.24 |  |  |  |  | 28.03.24 | 30.03.24 | 06.04.24 | T1 | [7 empty] | 06.04.24 | 23.04.24 | 22.06.24 | muthukumar.r@lntecc.com-01.07.2024-18:09:02
NC 42 | Electrical | LT Switchgear & APFC | LE22M232-E-WS-WT-PR-4107 | LE22M232-E-WS-WT-PR-4107-C | POPULAR SWITCHGEARS | Regret offer | PR Closed |  | +91 9316755702 | barodamktg@popularswitchgears.com |  | 09.08.23 | 13.10.23 | 06.11.23 | 28.12.23 | 08.01.24 | 21.02.24 | 06.03.24 |  |  |  |  | 13.03.24 | 13.03.24 | 13.03.24 | T1 | [7 empty] | 13.03.24 | 30.03.24 | 29.05.24 | muthukumar.r@lntecc.com-01.07.2024-18:09:02
NC 42 | Electrical | HT CAPACITOR | LE22M232-E-WS-WT-PR-4108 | LE22M232-E-WS-WT-PR-4108-A | Shreem Electrical | Awaiting pre-offer from vendor | 59 |  |  | htapfc@shreemelectric.com |  | 06.06.24 | [21 empty] | 29.07.24 | 15.08.24 | 14.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | HT CAPACITOR | LE22M232-E-WS-WT-PR-4108 | LE22M232-E-WS-WT-PR-4108-B | Madhav capacitor | Pre-order comments issued | 39 |  |  | vaibhav@madhavcapacitors.co.in |  | 06.06.24 | 14.06.24 | 26.06.24 | [19 empty] | 30.07.24 | 16.08.24 | 15.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | 66KV OutDoor Switchyard Equipments & CRP Panel | LE22M232-E-WS-WT-PR-4109 | LE22M232-E-WS-WT-PR-4109-A |  | Enquiry yet to float | NA | Change in primary voltage yet to be confirmed by site. | [25 empty] | 15.09.24 |  |  | muthukumar.r@lntecc.com-10.07.2024-15:12:15
NC 42 | Electrical | HT & LT CABLES | LE22M232-E-WS-WT-PR-4110 | LE22M232-E-WS-WT-PR-4110-A | Purva Vashi | Pre-order technically cleared | 41 |  |  | pvespl@vashiisl.com |  | 04.04.24 | 11.04.24 | 09.05.24 | [8 empty] | 24.06.24 | 24.06.24 | 24.06.24 | T1 | [7 empty] | 24.07.24 | 10.08.24 | 09.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | HT & LT CABLES | LE22M232-E-WS-WT-PR-4110 | LE22M232-E-WS-WT-PR-4110-B | Gemscab | Pre-order technically cleared | 39 | Vendor need clarification on PR. | +91 9147047963 | depankarchowdhury@gemscab.com |  | 10.04.24 | 12.04.24 | 22.05.24 | [8 empty] | 26.06.24 | 26.06.24 | 26.06.24 | T1 | [7 empty] | 26.07.24 | 12.08.24 | 11.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | HT & LT CABLES | LE22M232-E-WS-WT-PR-4110 | LE22M232-E-WS-WT-PR-4110-C | Vishal Cables | Pre-order technically cleared | 83 |  | +91 9892168365 | nimesh@vishalcables.com |  | 04.04.24 | 09.04.24 | 08.05.24 | 09.05.24 | [7 empty] | 13.05.24 | 13.05.24 | 13.05.24 | T1 | [7 empty] | 22.07.24 | 08.08.24 | 07.10.24 | bnk@lntecc.com-20.07.2024-16:50:29
NC 42 | Electrical | Cable tray and its Supports | LE22M232-E-WS-WT-PR-4111 | LE22M232-E-WS-WT-PR-4111-A |  | Enquiry yet to float | NA | Site team procurement | [25 empty] | 19.09.24 |  |  | muthukumar.r@lntecc.com-10.07.2024-15:12:15
NC 42 | Electrical | Cable Termination Kit,Lugs & Glands | LE22M232-E-WS-WT-PR-4112 | LE22M232-E-WS-WT-PR-4112-A |  | Enquiry yet to float | NA | Site team procurement | [25 empty] | 19.09.24 |  |  | muthukumar.r@lntecc.com-10.07.2024-15:12:15
NC 42 | Electrical | Earthing & Lightning Protection System | LE22M232-E-WS-WT-PR-4114 | LE22M232-E-WS-WT-PR-4114-A |  | Enquiry yet to float | NA | Site team procurement | [25 empty] | 19.09.24 |  |  | muthukumar.r@lntecc.com-10.07.2024-15:12:15
NC 42 | Electrical | Lighting Materials | LE22M232-E-WS-WT-PR-4115 | LE22M232-E-WS-WT-PR-4115-A |  | Enquiry yet to float | NA | Site team procurement | [25 empty] | 19.09.24 |  |  | muthukumar.r@lntecc.com-10.07.2024-15:12:15
NC 42 | Electrical | Electrical Safety Items | LE22M232-E-WS-WT-PR-4116 | LE22M232-E-WS-WT-PR-4116-A |  | Enquiry yet to float | NA | Site team procurement | [25 empty] | 19.09.24 |  |  | muthukumar.r@lntecc.com-10.07.2024-15:12:15
Pakur Hiranpur WSP | Mechanical | Butterfly Valves | E22M643-M-WS-BV-PR-1510 | E22M643-M-WS-BV-PR-1510-A | Avk | Pre-order pending with EDRC | 19 | Mechanical points closed, electrical pending. | 91769 66455 | subhash@avkindia.com |  | 27.03.24 | 12.04.24 | 25.04.24 | 16.07.24 | [21 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Butterfly Valves | E22M643-M-WS-BV-PR-1510 | E22M643-M-WS-BV-PR-1510-B | IVC | Pre-order technically cleared | 59 |  | 98905 57289 | sudip.ghosh@ivc-valves.com |  | 27.03.24 | 09.05.24 | 16.05.24 | 22.05.24 | [7 empty] | 06.06.24 | 06.06.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Butterfly Valves | E22M643-M-WS-BV-PR-1510 | E22M643-M-WS-BV-PR-1510-C | R&D | Awaiting pre-offer from vendor | 130 |  | 90040 31331 81694 09954 | bhupesh@rdmultiples.com mumbai@rdmultiples.com |  | 27.03.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Butterfly Valves | E22M643-M-WS-BV-PR-1510 | E22M643-M-WS-BV-PR-1510-D | Sigmaflow | Pre-order technically cleared | 59 |  | 90733 42195 | jagadesh@sigmaflow.in |  | 27.03.24 | 04.05.24 | 16.05.24 | 24.05.24 | [7 empty] | 06.06.24 | 06.06.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | SG EOT Crane and CPB | LE22M643-M-CW-CR-PR-1506 | LE22M643-M-CW-CR-PR-1506-A | Reva | Awaiting pre-offer from vendor | 96 |  | 98994 84751 | south@revacranes.com |  | 30.04.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | SG EOT Crane and CPB | LE22M643-M-CW-CR-PR-1506 | LE22M643-M-CW-CR-PR-1506-B | Indef | Pre-order comments issued | 19 | 1.Offer received for EOT, CPB Pending mech done get crs from elec and send | 81211 74337 | mkm@indef.com |  | 30.04.24 | 13.06.24 | 16.07.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | SG EOT Crane and CPB | LE22M643-M-CW-CR-PR-1506 | LE22M643-M-CW-CR-PR-1506-C | Bradys | Pre-order comments issued | 19 |  | 90030 25481 | saleschennai@bradys.in |  | 30.04.24 | 03.07.24 | 16.07.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Dewatering Pump | LE22M643-M-CW-DP-PR-1509 | LE22M643-M-CW-DP-PR-1509-A | Kishor Pumps | Awaiting pre-offer from vendor | 145 |  | 91766 10938 | P.Dixon@kishorpumps.com |  | 12.03.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Dewatering Pump | LE22M643-M-CW-DP-PR-1509 | LE22M643-M-CW-DP-PR-1509-B | MBH Pumps | Pre-order pending with EDRC | 6 |  | 98254 67472 99200 13772 | Parth@mbhpumps.com |  | 12.03.24 | 28.03.24 | 20.06.24 | 29.06.24 | 26.07.24 | 29.07.24 | [19 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:58
Pakur Hiranpur WSP | Mechanical | Dewatering Pump | LE22M643-M-CW-DP-PR-1509 | LE22M643-M-CW-DP-PR-1509-C | Jasco Pump | Pre-order pending with EDRC | 24 |  | 70690 99037 | info@jascopump.com |  | 12.03.24 | 20.03.24 | 20.06.24 | 11.07.24 | [21 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Pressure Reducing Valves | LE22M643-M-CW-FC-PR-1512 | LE22M643-M-CW-FC-PR-1512-A | AVK | Pre-order comments issued | 19 |  | 91769 66455 | subhash@avkindia.com |  | 01.03.24 | 01.04.24 | 16.04.24 | 16.04.24 | 22.05.24 | 22.05.24 | 16.07.24 |  |  |  |  | 16.04.24 | 16.04.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Pressure Reducing Valves | LE22M643-M-CW-FC-PR-1512 | LE22M643-M-CW-FC-PR-1512-B | Dorot | Pre-order pending with EDRC | 9 |  | 98281 38427 | abhishek.mathur@aquestia.com |  | 01.03.24 | 01.03.24 | 27.03.24 | 28.03.24 | 16.04.24 | 19.04.24 | 16.07.24 | 26.07.24 |  |  |  | 26.04.24 | 26.04.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:58
Pakur Hiranpur WSP | Mechanical | Pressure Reducing Valves | LE22M643-M-CW-FC-PR-1512 | LE22M643-M-CW-FC-PR-1512-C | Hawle | Pre-order comments issued | 19 |  | 99440 74005 | sagaya.prabhu@hawle.in |  | 01.03.24 | 30.04.24 | 16.07.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Pressure Reducing Valves | LE22M643-M-CW-FC-PR-1512 | LE22M643-M-CW-FC-PR-1512-D | Magwen | Regret offer | PR Closed |  | 95739 38553 | naresh.gs@magwen.de |  | 01.03.24 | 20.04.24 | [23 empty] | rachamalla.nithish@lntecc.com-21.05.2024-11:04:13
Pakur Hiranpur WSP | Mechanical | Pressure Reducing Valves | LE22M643-M-CW-FC-PR-1512 | LE22M643-M-CW-FC-PR-1512-E | Sigmaflow | Awaiting pre-offer from vendor | 156 |  | 90733 42195 | jagadesh@sigmaflow.in |  | 01.03.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Sluice Gates | LE22M643-M-CW-SG-PR-1507 | LE22M643-M-CW-SG-PR-1507-A | Jash | Pre-order comments issued | 58 | electrical done | 78699 10452 | robin@jashindia.com |  | 01.03.24 | 18.03.24 | 27.03.24 | 27.03.24 | 06.04.24 | 08.04.24 | 10.05.24 | 31.05.24 | 07.06.24 | [16 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Sluice Gates | LE22M643-M-CW-SG-PR-1507 | LE22M643-M-CW-SG-PR-1507-B | Sigmaflow | Pre-order technically cleared | 33 |  | 90733 42195 | jagadesh@sigmaflow.in |  | 01.03.24 | 01.04.24 | 06.04.24 | 24.06.24 | 01.07.24 | 02.07.24 | [5 empty] | 02.07.24 | 02.07.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Sluice Gates | LE22M643-M-CW-SG-PR-1507 | LE22M643-M-CW-SG-PR-1507-C | Oriental Castings | Pre-order comments issued | 54 |  | 98102 05011 | orientalcastings@gmail.com |  | 01.03.24 | 12.03.24 | 06.04.24 | 01.06.24 | 07.06.24 | 11.06.24 | 11.06.24 | [18 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Zero Velocity Valve and Air Cushion Valve | LE22M643-M-CW-SP-PR-1511 | LE22M643-M-CW-SP-PR-1511-A |  | Enquiry yet to float | NA | [29 empty] | srb@lntecc.com-13.05.2024-15:14:05
Pakur Hiranpur WSP | Mechanical | Zero Velocity Valve and Air Cushion Valve | LE22M643-M-CW-SP-PR-1511 | LE22M643-M-CW-SP-PR-1511-B |  | Enquiry yet to float | NA | [29 empty] | srb@lntecc.com-13.05.2024-15:14:05
Pakur Hiranpur WSP | Mechanical | Zero Velocity Valve and Air Cushion Valve | LE22M643-M-CW-SP-PR-1511 | LE22M643-M-CW-SP-PR-1511-C |  | Enquiry yet to float | NA | [29 empty] | srb@lntecc.com-13.05.2024-15:14:05
Pakur Hiranpur WSP | Mechanical | Exhaust Fans | LE22M643-M-CW-VF-PR-1508 | LE22M643-M-CW-VF-PR-1508-A | Nadi | Pre-order pending with EDRC | 41 |  | 89398 12409 | satheeshkumar.r@nadiairtechnics.com |  | 12.03.24 | 12.03.24 | 18.06.24 | 24.06.24 | [21 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Exhaust Fans | LE22M643-M-CW-VF-PR-1508 | LE22M643-M-CW-VF-PR-1508-B | Almonard | Awaiting pre-offer from vendor | 145 |  | 99625 13700 | purchase.almonard@gmail.com |  | 12.03.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Air Valves | LE22M643-M-WS-AV-PR-1505 | LE22M643-M-WS-AV-PR-1505-A | Avk | Sent to BU Operations | 12 |  | 91769 66455 | subhash@avkindia.com |  | 27.03.24 | 12.04.24 | 25.04.24 | 29.04.24 | 30.04.24 | 30.04.24 | [5 empty] | 30.04.24 | 30.04.24 | 23.07.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Air Valves | LE22M643-M-WS-AV-PR-1505 | LE22M643-M-WS-AV-PR-1505-B | IVC | Sent to BU Operations | 12 |  | 98905 57289 | sudip.ghosh@ivc-valves.com |  | 27.03.24 | 04.05.24 | 09.05.24 | 10.05.24 | 14.05.24 | 21.05.24 | 04.06.24 | 04.06.24 |  |  |  | 06.06.24 | 06.06.24 | 23.07.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Air Valves | LE22M643-M-WS-AV-PR-1505 | LE22M643-M-WS-AV-PR-1505-C | R&D | Awaiting pre-offer from vendor | 130 |  | 90040 31331 81694 09954 | bhupesh@rdmultiples.com mumbai@rdmultiples.com |  | 27.03.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Air Valves | LE22M643-M-WS-AV-PR-1505 | LE22M643-M-WS-AV-PR-1505-D | Sigmaflow | Sent to BU Operations | 12 |  | 90733 42195 | jagadesh@sigmaflow.in |  | 27.03.24 | 11.06.24 | 11.06.24 | 24.06.24 | [7 empty] | 24.06.24 | 24.06.24 | 23.07.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Air Valves | LE22M643-M-WS-AV-PR-1505 | LE22M643-M-WS-AV-PR-1505-E | Hawle | Pre-order comments issued | 27 |  | 99440 74005 | sagaya.prabhu@hawle.in |  | 11.06.24 | 05.07.24 | 08.07.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Butterfly Valves | LE22M643-M-WS-BV-PR-1510 | LE22M643-M-WS-BV-PR-1510-E | Hawle | Pre-order comments issued | 27 |  | 99440 74005 | sagaya.prabhu@hawle.in |  | 11.06.24 | 05.07.24 | 08.07.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Dismantling Joints | LE22M643-M-WS-DJ-PR-1502 | LE22M643-M-WS-DJ-PR-1502-A | Precise Engineers | Pre-order comments issued | 40 |  | 93777 73186 | sjm@vedantagroup.net |  | 12.06.24 | 25.06.24 | 25.06.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Dismantling Joints | LE22M643-M-WS-DJ-PR-1502 | LE22M643-M-WS-DJ-PR-1502-B | Shiva Industries | Awaiting pre-offer from vendor | 53 |  | 97823 57700 | navinebus@yahoo.co.in |  | 12.06.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Dismantling Joints | LE22M643-M-WS-DJ-PR-1502 | LE22M643-M-WS-DJ-PR-1502-C | Bikaner Engineering Works | Awaiting pre-offer from vendor | 53 |  | 97994 95511 | bewfoundries@hotmail.com |  | 12.06.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Expansion Joint | LE22M643-M-WS-DJ-PR-1503 | LE22M643-M-WS-DJ-PR-1503-A | Precise Engineers | Pre-order comments issued | 40 |  | 93777 73186 | sjm@vedantagroup.net |  | 12.06.24 | 25.06.24 | 25.06.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Expansion Joint | LE22M643-M-WS-DJ-PR-1503 | LE22M643-M-WS-DJ-PR-1503-B | Shiva Industries | Awaiting pre-offer from vendor | 53 |  | 97823 57700 | navinebus@yahoo.co.in |  | 12.06.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Expansion Joint | LE22M643-M-WS-DJ-PR-1503 | LE22M643-M-WS-DJ-PR-1503-C | Bikaner Engineering Works | Awaiting pre-offer from vendor | 53 |  | 97994 95511 | bewfoundries@hotmail.com |  | 12.06.24 | [24 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | HSC Pumps | LE22M643-M-WS-HS-PR-1501 | LE22M643-M-WS-HS-PR-1501-A | KBL | Sent to BU Operations | PR Closed |  | 86696 64820 | azharuddin.tamboli@kbl.co.in |  | 01.03.24 | 09.03.24 | 04.04.24 | 16.04.24 | 17.04.24 | 17.04.24 | 22.04.24 | 26.04.24 | 30.04.24 | 02.05.24 |  | 03.05.24 | 03.05.24 | 03.05.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-20.06.2024-10:17:25
Pakur Hiranpur WSP | Mechanical | HSC Pumps | LE22M643-M-WS-HS-PR-1501 | LE22M643-M-WS-HS-PR-1501-B | WILO | Post-order comments issued | 32 |  | 86800 68301 | manikkandan.pr@wilo.com |  | 01.03.24 | 01.04.24 | 03.04.24 | 22.04.24 | 22.04.24 | 03.05.24 | [5 empty] | 03.05.24 | 03.05.24 | 03.05.24 | T1 | 19.06.24 | WILO | 19.06.24 | 03.07.24 | [5 empty] | 18.08.24 | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | HSC Pumps | LE22M643-M-WS-HS-PR-1501 | LE22M643-M-WS-HS-PR-1501-C | WPIL | Sent to BU Operations | PR Closed |  | 91473 32553 94323 15337 | r.chandramohan@wpil.co.in |  | 01.03.24 | 02.04.24 | 04.04.24 | 15.04.24 | 18.04.24 | 02.05.24 | [5 empty] | 03.05.24 | 03.05.24 | 03.05.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-20.06.2024-10:17:25
Pakur Hiranpur WSP | Mechanical | Non Return Valves | LE22M643-M-WS-NRV-PR-1513 | LE22M643-M-WS-NRV-PR-1513-A | Avk | Pre-order comments issued | 37 |  | 91769 66455 | subhash@avkindia.com |  | 27.03.24 | 12.04.24 | 15.05.24 | 16.05.24 | 07.06.24 | 27.06.24 | 28.06.24 | [18 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Non Return Valves | LE22M643-M-WS-NRV-PR-1513 | LE22M643-M-WS-NRV-PR-1513-B | IVC | Pre-order technically cleared | 61 |  | 98905 57289 | sudip.ghosh@ivc-valves.com |  | 27.03.24 | 04.05.24 | 15.05.24 | 22.05.24 | [7 empty] | 04.06.24 | 04.06.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Non Return Valves | LE22M643-M-WS-NRV-PR-1513 | LE22M643-M-WS-NRV-PR-1513-C | R&D | Pre-order comments issued | 61 |  | 90040 31331 81694 09954 | bhupesh@rdmultiples.com mumbai@rdmultiples.com |  | 27.03.24 | 01.06.24 | 04.06.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Non Return Valves | LE22M643-M-WS-NRV-PR-1513 | LE22M643-M-WS-NRV-PR-1513-D | Hawle | Pre-order comments issued | 27 |  | 99440 74005 | sagaya.prabhu@hawle.in |  | 11.06.24 | 05.07.24 | 08.07.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Non Return Valves | LE22M643-M-WS-NRV-PR-1513 | LE22M643-M-WS-NRV-PR-1513-E | Sigma Flow | Pre-order technically cleared | 43 |  | 90733 42195 | jagadesh@sigmaflow.in |  | 27.03.24 | 16.05.24 | 21.06.24 | 22.06.24 | [7 empty] | 22.06.24 | 22.06.24 | [12 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Sluice Valves | LE22M643-M-WS-SV-PR-1504 | LE22M643-M-WS-SV-PR-1504-A | Avk | Sent to BU Operations | 18 |  | 91769 66455 | subhash@avkindia.com |  | 27.03.24 | 12.04.24 | 17.05.24 | 07.06.24 | 18.06.24 | 19.06.24 | 28.06.24 |  |  |  |  | 16.07.24 | 16.07.24 | 17.07.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Sluice Valves | LE22M643-M-WS-SV-PR-1504 | LE22M643-M-WS-SV-PR-1504-B | IVC | Sent to BU Operations | 18 |  | 98905 57289 | sudip.ghosh@ivc-valves.com |  | 27.03.24 | 04.05.24 | 16.05.24 | 22.05.24 | [7 empty] | 06.06.24 | 06.06.24 | 17.07.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Sluice Valves | LE22M643-M-WS-SV-PR-1504 | LE22M643-M-WS-SV-PR-1504-C | R&D | Pre-order comments issued | 79 |  | 90040 31331 81694 09954 | bhupesh@rdmultiples.com mumbai@rdmultiples.com |  | 27.03.24 | 24.04.24 | 17.05.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:41
Pakur Hiranpur WSP | Mechanical | Sluice Valves | LE22M643-M-WS-SV-PR-1504 | LE22M643-M-WS-SV-PR-1504-D | Hawle | Pre-order comments issued | 25 |  | 99440 74005 | sagaya.prabhu@hawle.in |  | 11.06.24 | 05.07.24 | 10.07.24 | [22 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:42
Pakur Hiranpur WSP | Mechanical | Sluice Valves | LE22M643-M-WS-SV-PR-1504 | LE22M643-M-WS-SV-PR-1504-E | Sigma Flow | Sent to BU Operations | 18 |  | 90733 42195 | jagadesh@sigmaflow.in |  | 27.03.24 | 13.05.24 | 16.05.24 | 24.06.24 | 28.06.24 | 02.07.24 | [5 empty] | 02.07.24 | 02.07.24 | 17.07.24 | T1 | [10 empty] | rachamalla.nithish@lntecc.com-29.07.2024-10:38:42
Parallel carrier system to RGLC | Mechanical | VT pumps | LE20M034-M-WS-DC-1201 | LE20M034-M-WS-DC-1201-A | WILO | Approved by Client | PR Closed |  | 86800 68301 | manikkandan.pr@wilo.com | 19.10.22 | 19.10.22 | 07.02.23 | 09.03.23 | [8 empty] | 21.03.23 | 21.03.23 | 21.03.23 | T1 | 29.08.23 | WILO | 29.11.23 | 25.12.23 | 24.03.24 | 23.03.24 | 27.03.24 | 21.03.23 | 07.04.23 | 06.06.23 | svcn@lntecc.com-03.07.2024-15:04:53
Parallel carrier system to RGLC | Mechanical | Pipe line valves | LE20M034-M-WS-DC-1202 | LE20M034-M-WS-DC-1202-A | IVC | Post-order technically cleared | 101 |  | Sudip ghosh | sudip.ghosh@ivc-valves.com | 25.10.22 | 25.10.22 | 07.11.22 | 21.02.23 | [8 empty] | 10.03.23 | 10.03.23 | 10.03.23 | T1 | 25.03.23 | IVC | 13.07.23 | 17.07.23 | 25.04.24 | 25.04.24 |  | 10.03.23 | 27.03.23 | 24.05.23 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Pump house valves | LE20M034-M-WS-DC-1203 | LE20M034-M-WS-DC-1203-A | IVC | Approved by Client | PR Closed |  | Sudip ghosh | sudip.ghosh@ivc-valves.com | 19.10.22 | 19.10.22 | 07.11.22 | 21.02.23 | [8 empty] | 10.03.23 | 10.03.23 | 10.03.23 | T1 | 25.03.23 | IVC | 13.07.23 | 17.07.23 | 25.04.24 | 25.04.24 | 15.03.24 | 10.03.23 | 27.03.23 | 24.05.23 | svcn@lntecc.com-03.07.2024-15:04:53
Parallel carrier system to RGLC | Mechanical | Dismantling joints | LE20M034-M-WS-DC-1204 | LE20M034-M-WS-DC-1204-A | Precise | Post-order technically cleared | 114 |  | Shailendra Mehta 93777 73186 | sjm@vedantagroup.net | 20.10.22 | 20.10.22 | 01.12.23 | 02.12.23 | [8 empty] | 19.01.24 | 19.01.24 | 19.01.24 | T1 | 19.01.24 | Precise | 12.04.24 | 12.04.24 | 12.04.24 | 12.04.24 |  | 19.01.24 | 05.02.24 | 19.03.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Expansion bellows | LE20M034-M-WS-DC-1205 | LE20M034-M-WS-DC-1205-A | Precise | Post-order technically cleared | 114 |  | Shailendra Mehta 93777 73186 | sjm@vedantagroup.net | 20.10.22 | 20.10.22 | 01.12.23 | 02.12.23 | [8 empty] | 19.01.24 | 19.01.24 | 19.01.24 | T1 | 19.01.24 | Precise | 12.04.24 | 12.04.24 | 12.04.24 | 12.04.24 |  | 19.01.24 | 05.02.24 | 19.03.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | EOT cranes | LE20M034-M-WS-DC-1206 | LE20M034-M-WS-DC-1206-A | JAPS | Sent to BU Operations | 144 |  | Gaurang Shah 99789 00589 | Jsales.japs@gmail.com | 20.10.22 | 20.10.22 | 06.02.24 | 06.02.24 | 07.02.24 | 09.02.24 | 09.02.24 | 12.02.24 | 26.02.24 | 11.03.24 | 13.03.24 | 13.03.24 | 13.03.24 | 13.03.24 | 13.03.24 | T1 | [7 empty] | 13.03.24 | 30.03.24 | 29.05.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | EOT cranes | LE20M034-M-WS-DC-1206 | LE20M034-M-WS-DC-1206-B | REVA | Sent to BU Operations | 146 |  | Amita Singh 99789 00589 | mkt@revacranes.com | 15.10.22 | 15.10.22 | 06.02.24 | 06.02.24 | 08.02.24 | 08.02.24 | 21.02.24 | 26.02.24 | 06.03.24 | 11.03.24 |  |  | 11.03.24 | 11.03.24 | 11.03.24 | T2 | [7 empty] | 11.03.24 | 28.03.24 | 27.05.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | EOT cranes | LE20M034-M-WS-DC-1206 | LE20M034-M-WS-DC-1206-C | ACME | Regret offer | PR Closed |  |  | Proposal ( Acme Air )' <proposal@airequipments.com>:jagathees@airequipments.com; vishwesh.p@airequipments.com | 15.10.22 | 15.10.22 | [21 empty] | 15.10.22 | 01.11.22 | 31.12.22 | svcn@lntecc.com-02.07.2024-10:39:51
Parallel carrier system to RGLC | Mechanical | Dewatering Pumps | LE20M034-M-WS-DC-1207 | LE20M034-M-WS-DC-1207-A | KSB | Pre-order comments issued | 29 |  | Uday Joshi | Uday.Joshi@ksb.com, Ashwin.Sridhar@ksb.com | 11.10.22 | 19.06.24 | 19.06.24 | 06.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Dewatering Pumps | LE20M034-M-WS-DC-1207 | LE20M034-M-WS-DC-1207-B | MBH Pumps | Pre-order comments issued | 29 |  | Chaitany Patel | westindustrial@mbhpumps.com |  | 19.06.24 | 19.06.24 | 06.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Dewatering Pumps | LE20M034-M-WS-DC-1207 | LE20M034-M-WS-DC-1207-C | Aqua | Pre-order comments issued | 29 |  | ST sambandam | chennai@aquapumps.com | Mechanical | 19.06.24 | 27.06.24 | 06.07.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Sluice gates | LE20M034-M-WS-DC-1208 | LE20M034-M-WS-DC-1208-A | JASH | Pre-order technically cleared | 142 |  | 78699 10452 | robin@jashindia.com | 11.10.22 | 11.10.22 | 06.02.24 | 28.02.24 | 11.03.24 | [7 empty] | 15.03.24 | 15.03.24 | [9 empty] | 15.03.24 | 01.04.24 | 31.05.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Sluice gates | LE20M034-M-WS-DC-1208 | LE20M034-M-WS-DC-1208-B | Oriental | Pre-order technically cleared | 142 |  | Subash 91769 66455 | subhash@avkindia.com | 11.10.22 | 11.10.22 | 14.11.23 | 28.02.24 | [8 empty] | 15.03.24 | 15.03.24 | [9 empty] | 15.03.24 | 01.04.24 | 31.05.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | DPCV | LE20M034-M-WS-DC-1209 | LE20M034-M-WS-DC-1209-A | IVC | Post-order technically cleared | 237 |  | Sudip ghosh | sudip.ghosh@ivc-valves.com | 19.10.22 | 19.10.23 | 26.10.23 | 27.11.23 | [8 empty] | 11.12.23 | 11.12.23 | 30.11.23 | T1 | 30.11.23 | IVC | 11.12.23 | 11.12.23 | 11.12.23 | 11.12.23 |  | 11.12.23 | 28.12.23 | 29.01.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Surge equipments | LE20M034-M-WS-DC-1210 | LE20M034-M-WS-DC-1210-A |  | Enquiry yet to float | NA | Surge Design under IISC Approval considering optimization of BOQ |  |  | 27.05.24 | [22 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-02.07.2024-10:39:24
Parallel carrier system to RGLC | Mechanical | Bypass valves | LE20M034-M-WS-DC-1211 | LE20M034-M-WS-DC-1211-A | IVC | Pre-order technically cleared | 54 |  | Sudip ghosh | sudip.ghosh@ivc-valves.com | 27.05.24 | 27.05.24 | 27.05.24 | 29.05.24 | 11.06.24 | 11.06.24 | [6 empty] | 11.06.24 | 11.06.24 | 11.06.24 | T1 | [7 empty] | 11.06.24 | 28.06.24 | 27.08.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Exhaust fans | LE20M034-M-WS-DC-1212 | LE20M034-M-WS-DC-1212-A |  | Enquiry yet to float | NA |  |  |  | 17.10.22 | [22 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-02.07.2024-10:39:24
Parallel carrier system to RGLC | Mechanical | Trash Rack | LE20M034-M-WS-DC-1213 | LE20M034-M-WS-DC-1213-A | Triveni | Pre-order technically cleared | 48 |  | Gaurav Dhiman 9953317091 | gauravdhiman@projects.trivenigroup.com | 27.05.24 | 27.05.24 | 27.05.24 | 28.05.24 | 31.05.24 | 11.06.24 | 14.06.24 | 17.06.24 |  |  |  |  | 14.06.24 | 17.06.24 | 17.06.24 | T1 | [7 empty] | 14.06.24 | 01.07.24 | 30.08.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Mechanical | Trash Rack | LE20M034-M-WS-DC-1213 | LE20M034-M-WS-DC-1213-B | Jash | Pre-order technically cleared | 55 |  | Rupanshu Geete 9826644554 | iipgmarketing@jashindia.com <iipgmarketing@jashindia.com> | 27.05.24 | 27.05.24 | 29.05.24 | 10.06.24 | [8 empty] | 10.06.24 | 10.06.24 | 10.06.24 | T1 | [7 empty] | 10.06.24 | 27.06.24 | 26.08.24 | svcn@lntecc.com-12.07.2024-15:47:52
Parallel carrier system to RGLC | Instrumentation | Cables | LE22M448-I-WS-PR-CA-5507 | LE22M448-I-WS-PR-CA-5507-A | PVESPL | Regret offer | PR Closed |  | Purva | pvespl@vashiisl.com | 04.03.23 | 20.02.24 | 26.02.24 | 20.05.24 | 29.05.24 | 05.06.24 | [20 empty] | mehernani@lntecc.com-08.07.2024-17:28:57
Parallel carrier system to RGLC | Instrumentation | Cables | LE22M448-I-WS-PR-CA-5507 | LE22M448-I-WS-PR-CA-5507-B | Gemscab | Pre-order technically cleared | 38 |  | MOHAMED RAWOOF | www.gemscab.com | 04.03.23 | 20.02.24 | 14.05.24 | 14.05.24 | 05.06.24 | [7 empty] | 27.06.24 | 27.06.24 | 27.06.24 | [8 empty] | 27.06.24 | 14.07.24 | 12.09.24 | mehernani@lntecc.com-11.07.2024-13:58:54
Parallel carrier system to RGLC | Instrumentation | Cables | LE22M448-I-WS-PR-CA-5507 | LE22M448-I-WS-PR-CA-5507-C | Cords | Pre-order technically cleared | 48 |  | Honey Panwar | hp@cordscable.com |  | 20.02.24 | 21.05.24 | 28.05.24 | 05.06.24 | [7 empty] | 17.06.24 | 17.06.24 | 17.06.24 | [8 empty] | 17.06.24 | 04.07.24 | 02.09.24 | mehernani@lntecc.com-11.07.2024-13:58:54
Parallel carrier system to RGLC | Instrumentation | Solar power operated datalogger | LE22M448-I-WS-PR-DL-5510 | LE22M448-I-WS-PR-DL-5510-A | ABB | Awaiting pre-offer from vendor | 27 |  | Sairam | sai.ram@in.abb.com |  | 08.07.24 | [21 empty] | 18.07.24 | 04.08.24 | 03.10.24 | mehernani@lntecc.com-08.07.2024-17:27:21
Parallel carrier system to RGLC | Instrumentation | Solar power operated datalogger | LE22M448-I-WS-PR-DL-5511 | LE22M448-I-WS-PR-DL-5510-B | SIAS | Awaiting pre-offer from vendor | 27 |  | Ramachandran | ramachandran@sias.co.in |  | 08.07.24 | [21 empty] | 18.07.24 | 04.08.24 | 03.10.24 | mehernani@lntecc.com-08.07.2024-17:27:21
Parallel carrier system to RGLC | Instrumentation | Solar power operated datalogger | LE22M448-I-WS-PR-DL-5512 | LE22M448-I-WS-PR-DL-5510-C | GSV Microtech | Awaiting pre-offer from vendor | 27 |  | Manikandan | sales@gsv-microtech.com |  | 08.07.24 | [21 empty] | 18.07.24 | 04.08.24 | 03.10.24 | mehernani@lntecc.com-08.07.2024-17:27:21
Parallel carrier system to RGLC | Instrumentation | Electromagnetic Flowmeter | LE22M448-I-WS-PR-FM-5505 | LE22M448-I-WS-PR-FM-5505-A | Khrone | Pre-order technically cleared | 155 |  | Diliban | dilibanr@forbesmarshall.com | 09.02.23 | 04.07.23 | 14.07.23 | 05.02.24 | 12.02.24 | 20.02.24 | 26.02.24 | [5 empty] | 02.03.24 | 02.03.24 | 02.03.24 | [8 empty] | 02.03.24 | 19.03.24 | 18.05.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | Electromagnetic Flowmeter | LE22M448-I-WS-PR-FM-5505 | LE22M448-I-WS-PR-FM-5505-B | Siemens | Pre-order technically cleared | 155 |  | GURUSWAMY, KEERTHI | keerthi.guruswamy.ext@siemens.com | 09.02.23 | 04.07.23 | 12.07.23 | 05.01.24 | 21.02.24 | [7 empty] | 02.03.24 | 02.03.24 | 02.03.24 | [8 empty] | 02.03.24 | 19.03.24 | 18.05.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | Electromagnetic Flowmeter | LE22M448-I-WS-PR-FM-5505 | LE22M448-I-WS-PR-FM-5505-C | ABB | Pre-order technically cleared | 101 |  | Sai ram | sai.ram@in.abb.com | 09.02.23 | 05.02.24 | 21.02.24 | 02.03.24 | 18.04.24 | [7 empty] | 25.04.24 | 25.04.24 | 25.04.24 | [8 empty] | 25.04.24 | 12.05.24 | 11.07.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | Electromagnetic Flowmeter | LE22M448-I-WS-PR-FM-5505 | LE22M448-I-WS-PR-FM-5505-D | SBEM | Pre-order technically cleared | 118 |  | Rajesh | rajesh.p@sbem.co.in | 09.02.23 | 05.02.24 | 21.03.24 | 27.03.24 | 01.04.24 | 03.04.24 | 03.04.24 | [5 empty] | 08.04.24 | 08.04.24 | 08.04.24 | [8 empty] | 08.04.24 | 25.04.24 | 24.06.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | Electromagnetic Flowmeter | LE22M448-I-WS-PR-FM-5505 | LE22M448-I-WS-PR-FM-5505-E | E&H | Pre-order technically cleared | 155 |  | Ramkumar | ramkumar.m@endress.com | 09.02.23 | 04.07.23 | 05.02.24 | 13.02.24 | 21.02.24 | [7 empty] | 02.03.24 | 02.03.24 | 02.03.24 | [8 empty] | 02.03.24 | 19.03.24 | 18.05.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | Level Indicator | LE22M448-I-WS-PR-LI-5503 | LE22M448-I-WS-PR-LI-5503-A | SBEM | Pre-order comments issued | 78 |  | Rajesh | rajesh.p@sbem.co.in | 09.02.23 | 20.02.24 | 02.03.24 | 18.05.24 | [19 empty] | 12.07.24 | 29.07.24 | 27.09.24 | mehernani@lntecc.com-08.07.2024-17:28:01
Parallel carrier system to RGLC | Instrumentation | Level Indicator | LE22M448-I-WS-PR-LI-5503 | LE22M448-I-WS-PR-LI-5503-B | Pune Techtrol | Pre-order comments issued | 64 |  | Anita Raskar | mktg2@punetechtrol.com |  | 02.03.24 | 29.05.24 | 01.06.24 | [19 empty] | 12.07.24 | 29.07.24 | 27.09.24 | mehernani@lntecc.com-08.07.2024-17:28:01
Parallel carrier system to RGLC | Instrumentation | Ultrasonic Level Transmitter | LE22M448-I-WS-PR-LT-5504 | LE22M448-I-WS-PR-LT-5504-A | ABB | Pre-order technically cleared | 101 |  | Sai Ram | sai.ram@in.abb.com | 09.02.23 | 05.02.24 | 21.02.24 | 02.03.24 | 22.04.24 | [7 empty] | 25.04.24 | 25.04.24 | 25.04.24 | T3 | [7 empty] | 25.04.24 | 12.05.24 | 11.07.24 | mehernani@lntecc.com-11.07.2024-14:01:13
Parallel carrier system to RGLC | Instrumentation | Ultrasonic Level Transmitter | LE22M448-I-WS-PR-LT-5504 | LE22M448-I-WS-PR-LT-5504-B | E&H | Pre-order technically cleared | 166 |  | Ramkumar M | ramkumar.m@endress.com | 09.02.23 | 04.02.24 | 13.02.24 | 13.02.24 | [8 empty] | 20.02.24 | 20.02.24 | 20.02.24 | T2 | [7 empty] | 20.02.24 | 08.03.24 | 07.05.24 | mehernani@lntecc.com-11.07.2024-14:01:13
Parallel carrier system to RGLC | Instrumentation | Ultrasonic Level Transmitter | LE22M448-I-WS-PR-LT-5504 | LE22M448-I-WS-PR-LT-5504-C | Siemens | Pre-order technically cleared | 234 |  | Keerthi .G | keerthi.guruswamy.ext@siemens.com | 09.02.23 | 04.07.23 | 12.07.23 | 12.07.23 | [8 empty] | 14.12.23 | 14.12.23 | 14.12.23 | T1 | [7 empty] | 14.12.23 | 31.12.23 | 29.02.24 | mehernani@lntecc.com-11.07.2024-14:01:13
Parallel carrier system to RGLC | Instrumentation | Pressure Gauge | LE22M448-I-WS-PR-PG-5501 | LE22M448-I-WS-PR-PG-5501-A | Hguru | Pre-order technically cleared | 37 |  | Anand | info@hgurusouth.com | 09.02.23 | 20.02.24 | 20.02.24 | 18.05.24 | 18.05.24 | [7 empty] | 28.06.24 | 28.06.24 | 28.06.24 | [8 empty] | 28.06.24 | 15.07.24 | 13.09.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | PLC | LE22M448-I-WS-PR-PL-5506 | LE22M448-I-WS-PR-PL-5506-A | Coronet | Pre-order comments issued | 59 |  | Laxman | laxman@coronet.in | 04.03.23 | 20.02.24 | 22.03.24 | 25.03.24 | 27.03.24 | 28.03.24 | 30.03.24 | 30.03.24 | 06.04.24 | 02.05.24 | 05.06.24 | 06.06.24 | [11 empty] | 16.07.24 | 02.08.24 | 01.10.24 | mehernani@lntecc.com-18.07.2024-13:55:06
Parallel carrier system to RGLC | Instrumentation | PLC | LE22M448-I-WS-PR-PL-5506 | LE22M448-I-WS-PR-PL-5506-B | Mitsubushi | Pre-order technically cleared | 61 |  | Sudarshan Gupta | Sudarsan.Gupta@asia.meap.com> | 04.03.23 | 20.02.24 | 26.02.24 | 16.03.24 | 05.04.24 | 08.04.24 | 12.04.24 | 29.04.24 | 04.06.24 |  |  |  | 04.06.24 | 04.06.24 | 04.06.24 | [8 empty] | 04.06.24 | 21.06.24 | 20.08.24 | mehernani@lntecc.com-18.07.2024-13:55:06
Parallel carrier system to RGLC | Instrumentation | PLC | LE22M448-I-WS-PR-PL-5506 | LE22M448-I-WS-PR-PL-5506-C | SAI Applied | Pre-order pending with EDRC | 23 |  | Meet Makwana | meet.makwana@saiapplied.com | 04.03.23 | 20.02.24 | 05.04.24 | 08.04.24 | 01.05.24 | 02.05.24 | 17.06.24 | 27.06.24 | 12.07.24 | [14 empty] | 16.07.24 | 02.08.24 | 01.10.24 | mehernani@lntecc.com-18.07.2024-13:55:06
Parallel carrier system to RGLC | Instrumentation | PLC | LE22M448-I-WS-PR-PL-5506 | LE22M448-I-WS-PR-PL-5506-D | SIAS | Pre-order technically cleared | 86 |  | Sudha Nandhini | nandhinik@sias.in; | 04.03.23 | 05.04.24 | 06.04.24 | 08.04.24 | 09.04.24 | 25.04.24 | 26.04.24 | 29.04.24 | 10.05.24 |  |  |  | 10.05.24 | 10.05.24 | 10.05.24 | [8 empty] | 10.05.24 | 27.05.24 | 26.07.24 | mehernani@lntecc.com-18.07.2024-13:55:06
Parallel carrier system to RGLC | Instrumentation | Pressure Transmitter | LE22M448-I-WS-PR-PT-5502 | LE22M448-I-WS-PR-PT-5502-A | ABB | Pre-order technically cleared | 101 |  | Sai Ram | sai.ram@in.abb.com | 09.02.23 | 05.02.24 | 21.02.24 | 02.03.24 | 22.04.24 | [7 empty] | 25.04.24 | 25.04.24 | 25.04.24 | [8 empty] | 25.04.24 | 12.05.24 | 11.07.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | Pressure Transmitter | LE22M448-I-WS-PR-PT-5502 | LE22M448-I-WS-PR-PT-5502-B | E&H | Pre-order technically cleared | 166 |  | Ramkumar M | ramkumar.m@endress.com | 09.02.23 | 04.02.24 | 13.02.24 | 13.02.24 | [8 empty] | 20.02.24 | 20.02.24 | 20.02.24 | [8 empty] | 20.02.24 | 08.03.24 | 07.05.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | Pressure Transmitter | LE22M448-I-WS-PR-PT-5502 | LE22M448-I-WS-PR-PT-5502-C | Siemens | Pre-order technically cleared | 234 |  | Keerthi .G | keerthi.guruswamy.ext@siemens.com | 09.02.23 | 04.07.23 | 12.07.23 | 12.07.23 | [8 empty] | 14.12.23 | 14.12.23 | 14.12.23 | [8 empty] | 14.12.23 | 31.12.23 | 29.02.24 | mehernani@lntecc.com-11.07.2024-13:58:53
Parallel carrier system to RGLC | Instrumentation | UPS | LE22M448-I-WS-PR-UP-5508 | LE22M448-I-WS-PR-UP-5508-A | Hitachi | Pre-order pending with EDRC | 18 |  | S Balakumaran | balakumaran_s@hitachi-hirel.com |  | 08.07.24 | 17.07.24 | [20 empty] | 18.07.24 | 04.08.24 | 03.10.24 | mehernani@lntecc.com-18.07.2024-13:57:19
Parallel carrier system to RGLC | Instrumentation | UPS | LE22M448-I-WS-PR-UP-5508 | LE22M448-I-WS-PR-UP-5508-B | Liveline | Pre-order pending with EDRC | 22 |  | Shilajit Naskar | sales2@livelineindia.com |  | 08.07.24 | 13.07.24 | [20 empty] | 18.07.24 | 04.08.24 | 03.10.24 | mehernani@lntecc.com-18.07.2024-13:57:19
Parallel carrier system to RGLC | Instrumentation | UPS | LE22M448-I-WS-PR-UP-5508 | LE22M448-I-WS-PR-UP-5508-C | Virtue | Awaiting pre-offer from vendor | 27 |  | K Shivakumar | k.shivakumar@vertiv.com |  | 08.07.24 | [21 empty] | 18.07.24 | 04.08.24 | 03.10.24 | mehernani@lntecc.com-18.07.2024-13:57:19
Parallel carrier system to RGLC | Electrical | Transformer | LE22M448-E-WS-WT-PR-4101 | LE22M448-E-WS-WT-PR-4101-A | CGL | Pre-order comments issued | 143 |  |  |  |  | 06.02.24 | 10.03.24 | 14.03.24 | [19 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-12:06:19
Parallel carrier system to RGLC | Electrical | Transformer | LE22M448-E-WS-WT-PR-4101 | LE22M448-E-WS-WT-PR-4101-B | Kirloskar | Pre-order comments issued | 143 |  |  |  |  | 06.02.24 | 05.03.24 | 14.03.24 | [19 empty] | 19.07.24 | 05.08.24 | 04.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-12:06:19
Parallel carrier system to RGLC | Electrical | Transformer | LE22M448-E-WS-WT-PR-4101 | LE22M448-E-WS-WT-PR-4101-C | Uttam Bharat | Sent to BU Operations | 29 |  |  |  |  | 28.02.24 | 03.05.24 | 10.05.24 | 25.05.24 | 29.05.24 | 06.06.24 | 07.06.24 |  |  |  |  | 07.06.24 | 06.07.24 | 07.06.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:16:12
Parallel carrier system to RGLC | Electrical | Transformer | LE22M448-E-WS-WT-PR-4101 | LE22M448-E-WS-WT-PR-4101-D | Voltamp | Sent to BU Operations | 65 |  |  |  |  | 05.02.24 | 10.03.24 | 14.03.24 | 02.04.24 | 12.04.24 | 29.05.24 | 31.05.24 |  |  |  |  | 29.05.24 | 31.05.24 | 29.05.24 | T1 | [7 empty] | 29.05.24 | 15.06.24 | 14.08.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:08:49
Parallel carrier system to RGLC | Electrical | HT Switchgear | LE22M448-E-WS-WT-PR-4103 | LE22M448-E-WS-WT-PR-4103-A | HTS | Pre-order pending with EDRC | 43 |  |  |  |  | 05.02.24 | 28.02.24 | 08.03.24 | 18.03.24 | 10.04.24 | 22.04.24 | 18.05.24 | 22.06.24 | [14 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-12:06:19
Parallel carrier system to RGLC | Electrical | HT Capacitor | LE22M448-E-WS-WT-PR-4104 | LE22M448-E-WS-WT-PR-4104-A |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | HT Capacitor | LE22M448-E-WS-WT-PR-4104 | LE22M448-E-WS-WT-PR-4104-B |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Soft starter | LE22M448-E-WS-WT-PR-4105 | LE22M448-E-WS-WT-PR-4105-A |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Soft starter | LE22M448-E-WS-WT-PR-4105 | LE22M448-E-WS-WT-PR-4105-B |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Battery & Charger | LE22M448-E-WS-WT-PR-4107 | LE22M448-E-WS-WT-PR-4107-A |  | Enquiry yet to float | NA | [26 empty] | 01.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Battery & Charger | LE22M448-E-WS-WT-PR-4107 | LE22M448-E-WS-WT-PR-4107-B |  | Enquiry yet to float | NA | [26 empty] | 01.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | LT Panel | LE22M448-E-WS-WT-PR-4108 | LE22M448-E-WS-WT-PR-4108-A | HTS | Pre-order pending with EDRC | 43 |  |  |  |  | 05.02.24 | 28.02.24 | 08.03.24 | 18.03.24 | 10.04.24 | 22.04.24 | 18.05.24 | 22.06.24 | [14 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:02:30
Parallel carrier system to RGLC | Electrical | LT Panel | LE22M448-E-WS-WT-PR-4108 | LE22M448-E-WS-WT-PR-4108-B | Engineers & Engineers | Pre-order comments issued | 143 |  | 09413333413 | bsharma@eneepl.com |  | 05.02.24 | 11.03.24 | 14.03.24 | [19 empty] | 30.07.24 | 16.08.24 | 15.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:02:30
Parallel carrier system to RGLC | Electrical | LT Panel | LE22M448-E-WS-WT-PR-4108 | LE22M448-E-WS-WT-PR-4108-C | SIA | Pre-order comments issued | 78 |  | +91 9662647403 | loma.patel@siasales.in |  | 26.02.24 | 20.03.24 | 25.03.24 | 05.04.24 | 10.04.24 | 12.04.24 | 18.05.24 | [15 empty] | 31.07.24 | 17.08.24 | 16.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:02:30
Parallel carrier system to RGLC | Electrical | NGR | LE22M448-E-WS-WT-PR-4111 | LE22M448-E-WS-WT-PR-4111-A |  | Enquiry yet to float | NA | [26 empty] | 02.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | NGR | LE22M448-E-WS-WT-PR-4111 | LE22M448-E-WS-WT-PR-4111-B |  | Enquiry yet to float | NA | [26 empty] | 02.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | HT & LT Power and Control Cables | LE22M448-E-WS-WT-PR-4112 | LE22M448-E-WS-WT-PR-4112-A | Gemscab | Sent to BU Operations | 52 |  |  |  |  | 20.02.24 | 28.02.24 | 05.04.24 | 14.05.24 | 13.06.24 | [6 empty] | 13.06.24 | 14.05.24 | 13.06.24 | T1 | [7 empty] | 13.06.24 | 30.06.24 | 29.08.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:08:49
Parallel carrier system to RGLC | Electrical | HT & LT Power and Control Cables | LE22M448-E-WS-WT-PR-4112 | LE22M448-E-WS-WT-PR-4112-B | Cords | Sent to BU Operations | 80 |  |  |  |  | 17.02.24 | 27.02.24 | 02.04.24 | 12.04.24 | 16.05.24 | [6 empty] | 16.05.24 | 12.04.24 | 16.05.24 | T1 | [7 empty] | 16.05.24 | 02.06.24 | 01.08.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:08:49
Parallel carrier system to RGLC | Electrical | Cable Tray & its supports | LE22M448-E-WS-WT-PR-4113 | LE22M448-E-WS-WT-PR-4113-A |  | Enquiry yet to float | NA | [26 empty] | 08.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Cable Tray & its supports | LE22M448-E-WS-WT-PR-4113 | LE22M448-E-WS-WT-PR-4113-B |  | Enquiry yet to float | NA | [26 empty] | 08.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | HT Cable termination, Gland & Lugs | LE22M448-E-WS-WT-PR-4114 | LE22M448-E-WS-WT-PR-4114-A | Monaj Tradings | Sent to BU Operations | 52 |  | +91 9432160680 | monajtrading@gmail.com |  | 05.02.24 | 12.02.24 | 13.06.24 | [8 empty] | 13.06.24 | 12.02.24 | 13.06.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:04:45
Parallel carrier system to RGLC | Electrical | HT Cable termination, Gland & Lugs | LE22M448-E-WS-WT-PR-4114 | LE22M448-E-WS-WT-PR-4114-B |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | LBPS | LE22M448-E-WS-WT-PR-4115 | LE22M448-E-WS-WT-PR-4115-A |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | LBPS | LE22M448-E-WS-WT-PR-4115 | LE22M448-E-WS-WT-PR-4115-B |  | Enquiry yet to float | NA | [26 empty] | 31.07.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Earthing & Lightning | LE22M448-E-WS-WT-PR-4116 | LE22M448-E-WS-WT-PR-4116-A | Monaj Tradings | Sent to BU Operations | 66 |  | +91 9432160680 | monajtrading@gmail.com |  | 05.02.24 | 12.02.24 | 30.05.24 | [8 empty] | 30.05.24 | 12.02.24 | 30.05.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:08:49
Parallel carrier system to RGLC | Electrical | Earthing & Lightning | LE22M448-E-WS-WT-PR-4116 | LE22M448-E-WS-WT-PR-4116-B |  | Enquiry yet to float | NA | [26 empty] | 06.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Lighting Materials | LE22M448-E-WS-WT-PR-4117 | LE22M448-E-WS-WT-PR-4117-A | Monaj Tradings | Sent to BU Operations | 66 |  | +91 9432160680 | monajtrading@gmail.com |  | 05.02.24 | 12.02.24 | 30.05.24 | [8 empty] | 30.05.24 | 12.02.24 | 30.05.24 | T1 | [7 empty] | 18.07.24 | 04.08.24 | 03.10.24 | bhuvaneswari.natarajan@lntecc.com-17.07.2024-14:08:49
Parallel carrier system to RGLC | Electrical | Lighting Materials | LE22M448-E-WS-WT-PR-4117 | LE22M448-E-WS-WT-PR-4117-B |  | Enquiry yet to float | NA | [26 empty] | 06.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | RMU | LE22M448-E-WS-WT-PR-4118 | LE22M448-E-WS-WT-PR-4118-A |  | Enquiry yet to float | NA | [26 empty] | 15.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | RMU | LE22M448-E-WS-WT-PR-4118 | LE22M448-E-WS-WT-PR-4118-B |  | Enquiry yet to float | NA | [26 empty] | 15.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Electrical safety items | LE22M448-E-WS-WT-PR-4119 | LE22M448-E-WS-WT-PR-4119-A |  | Enquiry yet to float | NA | [26 empty] | 16.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Electrical safety items | LE22M448-E-WS-WT-PR-4119 | LE22M448-E-WS-WT-PR-4119-B |  | Enquiry yet to float | NA | [26 empty] | 16.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Switchyard | LE22M448-E-WS-WT-PR-4120 | LE22M448-E-WS-WT-PR-4120-A |  | Enquiry yet to float | NA | [26 empty] | 19.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Parallel carrier system to RGLC | Electrical | Switchyard | LE22M448-E-WS-WT-PR-4120 | LE22M448-E-WS-WT-PR-4120-B |  | Enquiry yet to float | NA | [26 empty] | 19.08.24 |  |  | bhuvaneswari.natarajan@lntecc.com-10.07.2024-16:42:27
Patiala | Process | Reactor clarifier | LE20M034-P-WS-WT-PR-2202 | LE20M034-P-WS-WT-PR-2202-A | Triveni | Post-order technically cleared | 359 |  |  | neeraj.aggarwal@projects.trivenigroup.com | 20.01.21 | 20.01.21 | 05.11.22 | 09.11.22 | [8 empty] | 02.01.23 | 02.01.23 | 04.01.23 | T1 | 19.06.23 | Triveni | 19.06.23 | 26.06.23 | 11.08.23 | 11.08.23 | 11.08.23 |  |  | 18.08.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Reactor clarifier | LE20M034-P-WS-WT-PR-2202 | LE20M034-P-WS-WT-PR-2202-B | Shivpad | Regret offer | PR Closed |  |  |  | 20.01.21 | 20.01.21 | 30.01.22 | 17.02.22 | [22 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Air Blower | LE20M034-P-WS-WT-PR-2203 | LE20M034-P-WS-WT-PR-2203-A | Everest | Post-order technically cleared | 432 |  |  |  | 28.01.21 | 28.01.21 | 14.12.22 | 17.12.22 | [8 empty] | 18.02.23 | 18.02.23 | 18.02.23 | T1 | 25.05.23 | Everest | 25.05.23 | 30.05.23 | 30.05.23 | 30.05.23 | 30.05.23 |  |  | 24.07.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Air Blower | LE20M034-P-WS-WT-PR-2203 | LE20M034-P-WS-WT-PR-2203-B | Kay | Sent to BU Operations | PR Closed |  |  |  | 28.01.21 | 28.01.21 | 14.09.23 | 20.09.23 | [8 empty] | 18.01.23 | 21.01.23 | 18.02.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Air Blower | LE20M034-P-WS-WT-PR-2203 | LE20M034-P-WS-WT-PR-2203-C | Swam | Regret offer | PR Closed |  |  |  | 28.01.21 | 28.01.21 | 14.09.23 | 22.09.23 | [10 empty] | 18.02.23 | [11 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Air Compressor | LE20M034-P-WS-WT-PR-2204 | LE20M034-P-WS-WT-PR-2204-A | Atlas Capco | Post-order technically cleared | 87 |  |  |  | 20.01.21 | 20.01.21 | 11.05.23 | 22.05.23 | [8 empty] | 26.05.23 | 29.05.23 | 29.05.23 | T1 | 04.04.24 | Atlas Capco | 04.04.24 | 06.04.24 | 17.04.24 | 27.04.24 | 09.05.24 |  |  | 03.06.24 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Air Compressor | LE20M034-P-WS-WT-PR-2204 | LE20M034-P-WS-WT-PR-2204-B | Compair | Regret offer | PR Closed |  |  |  | 20.01.21 | 20.01.21 | 10.05.23 | 22.05.23 | [10 empty] | 29.05.23 | [11 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Agitator | LE20M034-P-WS-WT-PR-2205 | LE20M034-P-WS-WT-PR-2205-A | FFP | Post-order technically cleared | 332 |  |  | fibrein@gmail.com | 19.12.20 | 19.12.20 | 16.09.22 | 01.10.22 | [8 empty] | 19.04.23 | 29.04.23 | 29.04.23 | T2 | 03.07.23 | FFP | 03.07.23 | 03.07.23 | 07.07.23 | 05.09.23 | 07.09.23 |  |  | 01.09.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Agitator | LE20M034-P-WS-WT-PR-2205 | LE20M034-P-WS-WT-PR-2205-B | Milton Roy | Sent to BU Operations | PR Closed |  |  |  | 19.12.20 | 19.12.20 | 09.12.22 | 17.12.22 | [8 empty] | 21.02.23 | 21.02.23 | 29.04.23 | T1 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | WTP Sluice gates | LE20M034-P-WS-WT-PR-2206 | LE20M034-P-WS-WT-PR-2206-A | Oriental | Post-order technically cleared | 318 |  |  |  | 07.01.21 | 07.01.21 | 26.08.22 | 01.09.22 | [8 empty] | 21.01.23 | 01.02.23 | 03.06.23 | T1 | 26.06.23 | Oriental | 26.06.23 | 01.07.23 | 15.09.23 | 21.09.23 | 21.09.23 |  |  | 25.08.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | WTP Sluice gates | LE20M034-P-WS-WT-PR-2206 | LE20M034-P-WS-WT-PR-2206-B | Jash | Sent to BU Operations | PR Closed |  |  |  | 07.01.21 | 07.01.21 | 20.10.22 | 08.11.22 | [8 empty] | 02.06.23 | 03.06.23 | 03.06.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | WTP Sluice gates | LE20M034-P-WS-WT-PR-2206 | LE20M034-P-WS-WT-PR-2206-C | IVC | Regret offer | PR Closed |  |  |  | 07.01.21 | 07.01.21 | 20.10.22 | 08.11.22 | [22 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Chlorination system | LE20M034-P-WS-WT-PR-2207 | LE20M034-P-WS-WT-PR-2207-A | Zion | Post-order technically cleared | 464 |  |  |  | 07.01.21 | 07.01.21 | 28.11.22 | 02.12.22 | [8 empty] | 18.01.23 | 22.01.23 | 21.02.23 | T1 | 07.03.23 | Zion | 07.03.23 | 14.03.23 | 20.04.23 | 28.04.23 | 28.04.23 |  |  | 06.05.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Chlorination system | LE20M034-P-WS-WT-PR-2207 | LE20M034-P-WS-WT-PR-2207-B | Toshcon | Sent to BU Operations | PR Closed |  |  |  | 07.01.21 | 07.01.21 | 20.01.23 | 17.02.23 | [8 empty] | 17.02.23 | 21.02.23 | 21.02.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Chlorination system | LE20M034-P-WS-WT-PR-2207 | LE20M034-P-WS-WT-PR-2207-C | IEC | Sent to BU Operations | PR Closed |  |  |  | 07.01.21 | 07.01.21 | 07.02.23 | 17.02.23 | [8 empty] | 21.02.23 | 21.02.23 | 21.02.23 | T3 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Chlorine Tonners | LE20M034-P-WS-WT-PR-2208 | LE20M034-P-WS-WT-PR-2208-A | Zion | Post-order technically cleared | 464 |  |  |  | 24.12.20 | 24.12.20 | 28.11.22 | 02.12.22 | [8 empty] | 18.01.23 | 22.01.23 | 21.02.23 | T1 | 07.03.23 | Zion | 07.03.23 | 14.03.23 | 20.04.23 | 28.04.23 | 28.04.23 |  |  | 06.05.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Chlorine Tonners | LE20M034-P-WS-WT-PR-2208 | LE20M034-P-WS-WT-PR-2208-B | Toshcon | Sent to BU Operations | PR Closed |  |  |  | 24.12.20 | 24.12.20 | 20.01.23 | 17.02.23 | [8 empty] | 17.02.23 | 21.02.23 | 21.02.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Chlorine Tonners | LE20M034-P-WS-WT-PR-2208 | LE20M034-P-WS-WT-PR-2208-C | IEC | Sent to BU Operations | PR Closed |  |  |  | 24.12.20 | 24.12.20 | 07.02.23 | 17.02.23 | [8 empty] | 21.02.23 | 21.02.23 | 21.02.23 | T3 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Sludge thickener | LE20M034-P-WS-WT-PR-2209 | LE20M034-P-WS-WT-PR-2209-A | Triveni | Post-order technically cleared | 409 |  |  |  | 28.01.21 | 28.01.21 | 25.10.22 | 30.10.22 | [8 empty] | 22.12.22 | 22.12.22 | 22.12.22 | T2 | 10.05.23 | Triveni | 10.05.23 | 17.05.23 | 17.06.23 | 22.06.23 | 22.06.23 |  |  | 09.07.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Sludge thickener | LE20M034-P-WS-WT-PR-2209 | LE20M034-P-WS-WT-PR-2209-B | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 28.01.21 | 28.01.21 | 20.10.22 | 04.11.22 | [8 empty] | 05.12.22 | 07.12.22 | 22.12.22 | T1 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Filter media | LE20M034-P-WS-WT-PR-2210 | LE20M034-P-WS-WT-PR-2210-A | Dalton | Post-order technically cleared | 225 |  |  |  | 19.12.20 | 19.12.20 | 03.08.23 | 10.08.23 | [8 empty] | 23.11.23 | 23.11.23 | 23.11.23 | T1 | 23.12.23 | Dalton | 23.12.23 | 23.12.23 | 23.12.23 | 23.12.23 | 23.12.23 |  |  | 21.02.24 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Filter media | LE20M034-P-WS-WT-PR-2210 | LE20M034-P-WS-WT-PR-2210-B | Global Adsorbents | Regret offer | PR Closed |  |  |  | 19.12.20 | 19.12.20 | 02.08.23 | 10.08.23 | [22 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Nozzles | LE20M034-P-WS-WT-PR-2211 | LE20M034-P-WS-WT-PR-2211-A | Guddi Plastcons | Post-order technically cleared | 345 |  |  |  | 19.12.20 | 19.12.20 | 05.07.22 | 08.07.22 | [8 empty] | 13.07.22 | 02.08.22 | 02.08.22 | T1 | 22.08.23 | Guddi Plastcons | 22.08.23 | 25.08.23 | 25.08.23 | 25.08.23 | 25.08.23 |  |  | 21.10.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Nozzles | LE20M034-P-WS-WT-PR-2211 | LE20M034-P-WS-WT-PR-2211-B | VP Engineers | Sent to BU Operations | PR Closed |  |  |  | 19.12.20 | 19.12.20 | 05.07.22 | 06.07.22 | [8 empty] | 06.07.22 | 06.07.22 | 02.08.22 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Centrifuge | LE20M034-P-WS-WT-PR-2212 | LE20M034-P-WS-WT-PR-2212-A | Humbolt | Post-order technically cleared | 290 |  |  |  | 28.01.21 | 28.01.21 | 08.09.23 | 23.09.23 | [8 empty] | 23.06.23 | 23.06.23 | 23.06.23 | T2 | 18.08.23 | Humbolt | 18.08.23 | 22.08.23 | 04.10.23 | 18.10.23 | 19.10.23 |  |  | 17.10.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Centrifuge | LE20M034-P-WS-WT-PR-2213 | LE20M034-P-WS-WT-PR-2212-B | Alfa laval | Sent to BU Operations | PR Closed |  |  |  | 28.01.21 | 28.01.21 | 15.09.23 | 23.09.23 | [8 empty] | 30.01.23 | 30.01.23 | 23.06.23 | T1 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Centrifuge | LE20M034-P-WS-WT-PR-2214 | LE20M034-P-WS-WT-PR-2212-C | Hiller | Sent to BU Operations | PR Closed |  |  |  | 28.01.21 | 28.01.21 | 26.04.23 | 02.05.23 | [8 empty] | 09.05.23 | 18.05.23 | 23.06.23 | T3 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | screw pump | LE20M034-P-WS-WT-PR-2213 | LE20M034-P-WS-WT-PR-2213-A | Circor | Post-order technically cleared | 239 |  |  |  | 30.12.20 | 30.12.20 | 12.06.23 | 19.06.23 | [8 empty] | 24.07.23 | 24.07.23 | 24.07.23 | T1 | 17.11.23 | Circor | 17.11.23 | 23.11.23 | 09.12.23 | 09.12.23 | 09.12.23 |  |  | 16.01.24 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Backwash Reservoir pump | LE20M034-P-WS-WT-PR-2214 | LE20M034-P-WS-WT-PR-2214-A | Flowmore | Post-order technically cleared | 367 |  |  |  | 20.01.21 | 20.01.21 | 21.01.23 | 25.01.23 | [8 empty] | 14.07.23 | 15.07.23 | 15.07.23 | T1 | 16.06.23 | Flowmore | 16.06.23 | 19.06.23 | 01.08.23 | 01.08.23 | 03.08.23 |  |  | 15.08.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Backwash Reservoir pump | LE20M034-P-WS-WT-PR-2214 | LE20M034-P-WS-WT-PR-2214-B | KBL | Regret offer | PR Closed |  |  |  | 20.01.21 | 20.01.21 | 23.08.22 | 29.08.22 | [22 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Backwash Reservoir pump | LE20M034-P-WS-WT-PR-2214 | LE20M034-P-WS-WT-PR-2214-C | Wilo | Sent to BU Operations | PR Closed |  |  |  | 20.01.21 | 20.01.21 | 28.12.23 | 29.12.23 | [8 empty] | 23.02.23 | 23.02.23 | 15.07.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Submersible pump | LE20M034-P-WS-WT-PR-2215 | LE20M034-P-WS-WT-PR-2215-A | Aqua | Post-order technically cleared | 44 |  |  |  | 24.12.20 | 24.12.20 | 08.02.23 | 17.02.23 | [8 empty] | 23.06.23 | 28.06.23 | 28.06.23 | T1 | 06.04.24 | Aqua | 06.04.24 | 18.04.24 | 09.05.24 | 17.06.24 | 21.06.24 |  |  | 05.06.24 | SNEHA-S@lntecc.com-25.06.2024-12:05:15
Patiala | Process | Electrical hoist | LE20M034-P-WS-WT-PR-2216 | LE20M034-P-WS-WT-PR-2216-A | Indef | Post-order comments issued | 87 |  |  |  | 03.03.21 | 03.03.21 | 17.05.23 | 30.05.23 | [8 empty] | 04.01.23 | 12.01.23 | 12.01.23 | T1 | 04.05.24 | Indef | 04.05.24 | 09.05.24 | 06.07.24 |  |  |  |  | 03.07.24 | SNEHA-S@lntecc.com-11.07.2024-14:29:38
Patiala | Process | Electrical hoist | LE20M034-P-WS-WT-PR-2216 | LE20M034-P-WS-WT-PR-2216-B | Bradys | Sent to BU Operations | PR Closed |  |  |  | 03.03.21 | 03.03.21 | 03.04.23 | 19.04.023 | [8 empty] | 04.01.23 | 12.01.23 | 12.01.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-11.07.2024-14:29:38
Patiala | Process | Crane | LE20M034-P-WS-WT-PR-2217 | LE20M034-P-WS-WT-PR-2217-A | Indef | Post-order technically cleared | 41 |  |  |  | 27.02.21 | 27.02.21 | 30.05.23 | 30.05.23 | [8 empty] | 12.01.23 | 12.01.23 | 12.01.23 | T1 | 04.05.24 | Indef | 04.05.24 | 20.05.24 | 19.06.24 | 20.06.24 | 24.06.24 |  |  | 03.07.24 | SNEHA-S@lntecc.com-11.07.2024-14:32:28
Patiala | Process | Crane | LE20M034-P-WS-WT-PR-2217 | LE20M034-P-WS-WT-PR-2217-B | Bradys | Sent to BU Operations | PR Closed |  |  |  | 27.02.21 | 27.02.21 | 19.04.23 | 19.04.23 | [8 empty] | 12.01.23 | 12.01.23 | 12.01.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-25.06.2024-12:01:46
Patiala | Process | Manual chain pulley block | LE20M034-P-WS-WT-PR-2218 | LE20M034-P-WS-WT-PR-2218-A | Indef | Post-order comments issued | 87 |  |  |  | 27.02.21 | 27.02.21 | 30.05.23 | 30.05.23 | [8 empty] | 12.01.23 | 12.01.23 | 12.01.23 | T1 | 04.05.24 | Indef | 04.05.24 | 09.05.24 | 06.07.24 |  |  |  | Invalid date | Invalid date | SNEHA-S@lntecc.com-11.07.2024-14:32:28
Patiala | Process | Manual chain pulley block | LE20M034-P-WS-WT-PR-2218 | LE20M034-P-WS-WT-PR-2218-B | Bradys | Sent to BU Operations | PR Closed |  |  |  | 27.02.21 | 27.02.21 | 19.04.23 | 19.04.23 | [8 empty] | 12.01.23 | 12.01.23 | 12.01.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Dosing pump | LE20M034-P-WS-WT-PR-2219 | LE20M034-P-WS-WT-PR-2219-A | Positive Metering | Post-order technically cleared | 226 |  |  |  | 27.02.21 | 27.02.21 | 13.04.23 | 18.04.23 | [8 empty] | 18.08.23 | 28.08.23 | 28.08.23 | T1 | 15.12.23 | Positive Metering | 15.12.23 | 18.12.23 | 22.12.23 | 22.12.23 | 22.12.23 |  |  | 13.02.24 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Dosing pump | LE20M034-P-WS-WT-PR-2219 | LE20M034-P-WS-WT-PR-2219-B | Milton Roy | Sent to BU Operations | PR Closed |  |  |  | 27.02.21 | 27.02.21 | 12.04.23 | 28.04.23 | [8 empty] | 09.05.23 | 18.05.23 | 28.08.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Chemical transfer pump | LE20M034-P-WS-WT-PR-2220 | LE20M034-P-WS-WT-PR-2220-A |  | Enquiry yet to float | NA |  |  |  | 20.02.21 | 20.02.21 | [21 empty] | 31.08.24 | 17.09.24 | 16.11.24 | SNEHA-S@lntecc.com-03.07.2024-19:03:09
Patiala | Process | Flocculator paddle pre-flocculate tank | LE20M034-P-WS-WT-PR-2221 | LE20M034-P-WS-WT-PR-2221-A | Triveni | Post-order technically cleared | 157 |  |  |  | 13.02.21 | 13.02.21 | 06.12.22 | 12.12.22 | [8 empty] | 17.02.23 | 17.02.23 | 17.02.23 | T1 | 12.01.24 | Triveni | 12.01.24 | 17.01.24 | 29.02.24 | 29.02.24 | 29.02.24 |  |  | 12.03.24 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Flocculator paddle pre-flocculate tank | LE20M034-P-WS-WT-PR-2222 | LE20M034-P-WS-WT-PR-2221-B | Shivpad | Sent to BU Operations | PR Closed |  |  |  | 13.02.21 | 13.02.21 | 17.09.22 | 01.10.22 | [8 empty] | 20.12.22 | 26.12.22 | 17.02.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | DWPE dosing tanks | LE20M034-P-WS-WT-PR-2222 | LE20M034-P-WS-WT-PR-2222-A | FFP | Post-order technically cleared | -133 |  |  |  | 13.02.21 | 13.02.21 | 19.07.23 | 26.07.23 | [8 empty] | 21.08.23 | 09.10.23 | 09.10.23 | T1 | 12.12.23 | FFP | 12.12.23 | 12.12.24 | 15.12.24 | 15.12.24 | 15.12.24 |  |  | 10.02.24 | SNEHA-S@lntecc.com-30.05.2024-14:30:11
Patiala | Process | Sampling pump | LE20M034-P-WS-WT-PR-2224 | LE20M034-P-WS-WT-PR-2224-A | Site Procurement | Regret offer | PR Closed |  |  |  | 20.02.21 | 20.02.21 | [15 empty] | Site Procurement | [8 empty] | SNEHA-S@lntecc.com-25.06.2024-12:00:24
Patiala | Process | Submersible mixer | LE20M034-P-WS-WT-PR-2225 | LE20M034-P-WS-WT-PR-2225-A | Sulzer | Post-order technically cleared | 304 |  |  |  | 27.02.21 | 27.02.21 | 19.01.23 | 06.02.23 | [8 empty] | 14.02.23 | 17.02.23 | 24.03.23 | T1 | 12.06.23 | Sulzer | 12.06.23 | 21.06.23 | 04.10.23 | 05.10.23 | 05.10.23 |  |  | 11.08.23 | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Submersible mixer | LE20M034-P-WS-WT-PR-2225 | LE20M034-P-WS-WT-PR-2225-B | FFP | Sent to BU Operations | PR Closed |  |  |  | 27.02.21 | 27.02.21 | 20.01.23 | 06.02.23 | [8 empty] | 18.03.23 | 24.03.23 | 24.03.23 | T2 | [10 empty] | SNEHA-S@lntecc.com-20.05.2024-12:24:21
Patiala | Process | Dewatering pump | LE20M034-P-WS-WT-PR-2226 | LE20M034-P-WS-WT-PR-2226-A | Aqua | Post-order technically cleared | 44 |  |  |  | 20.01.21 | 20.01.21 | 08.02.23 | 17.02.23 | [8 empty] | 23.06.23 | 28.06.23 | 28.06.23 | T1 | 06.04.24 | Aqua | 06.04.24 | 18.04.24 | 30.05.24 | 17.06.24 | 21.06.24 |  |  | 05.06.24 | SNEHA-S@lntecc.com-25.06.2024-12:05:15
Patiala | Process | Dissolving tray | LE20M034-P-WS-WT-PR-2227 | LE20M034-P-WS-WT-PR-2227-A | Site Procurement | Regret offer | PR Closed |  |  |  | 30.12.20 | 30.12.20 | [15 empty] | Site Procurement | [8 empty] | SNEHA-S@lntecc.com-25.06.2024-12:00:24
Patiala | Process | Trolley | LE20M034-P-WS-WT-PR-2228 | LE20M034-P-WS-WT-PR-2228-A | Site Procurement | Regret offer | PR Closed |  |  |  | 07.01.21 | 07.01.21 | [15 empty] | Site Procurement | [8 empty] | SNEHA-S@lntecc.com-25.06.2024-12:00:24
Patiala | Process | Platm weighing machine | LE20M034-P-WS-WT-PR-2229 | LE20M034-P-WS-WT-PR-2229-A | Site Procurement | Regret offer | PR Closed |  |  |  | 13.02.21 | 13.02.21 | [15 empty] | Site Procurement | [8 empty] | SNEHA-S@lntecc.com-25.06.2024-12:00:24
Patiala | Process | Exhaust fan | LE20M034-P-WS-WT-PR-2230 | LE20M034-P-WS-WT-PR-2230-A | Site Procurement | Regret offer | PR Closed |  |  |  | 13.02.21 | 13.02.21 | [15 empty] | Site Procurement | [8 empty] | SNEHA-S@lntecc.com-25.06.2024-12:00:24
Patiala | Process | lab equipment | LE20M034-P-WS-WT-PR-2231 | LE20M034-P-WS-WT-PR-2231-A | Site Procurement | Regret offer | PR Closed |  |  |  | 20.02.21 | 20.02.21 | [15 empty] | Site Procurement | [8 empty] | SNEHA-S@lntecc.com-25.06.2024-12:00:24
Patiala | Mechanical | Air vessel | LE20M034-M-WS-PR-AV-1207 | LE20M034-M-WS-PR-AV-1207-A | Flodyne | Pre-order comments issued | 37 | Swarup Dhanawade | 9029 505097 | swarup@flo-dyne.net |  | 19.11.21 | 30.01.24 | 09.02.24 | 16.03.24 | 28.06.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-12:19:16
Patiala | Mechanical | EOT Crane | LE20M034-M-WS-PR-CR-1201 | LE20M034-M-WS-PR-CR-1201-A | Indef | Post-order technically cleared | 104 | Moinuddin | 93219 70456 | Mmkm@indef.com |  | 16.11.21 | 18.01.23 | 18.01.23 | [8 empty] | 25.01.24 | 25.01.24 | 25.01.24 | T1 | 26.02.24 | Indef | 20.04.24 | 20.04.24 | 22.04.24 | 22.04.24 |  |  |  | 26.04.24 | svcn@lntecc.com-18.07.2024-12:19:16
Patiala | Mechanical | EOT Crane | LE20M034-M-WS-PR-CR-1201 | LE20M034-M-WS-PR-CR-1201-B | Bradys | Sent to BU Operations | PR Closed | srinivasan |  | srinivasan@bradys.in |  | 16.11.21 | 25.01.24 | 25.01.24 | [8 empty] | 03.02.24 | 03.02.24 | 03.02.24 | T2 | [10 empty] | svcn@lntecc.com-04.06.2024-11:32:40
Patiala | Mechanical | HSC Pumps | LE20M034-M-WS-PR-HC-1202 | LE20M034-M-WS-PR-HC-1202-A | WILO | Post-order technically cleared | 127 | Manikandan | 86800 68301 | manikkandan.pr@wilo.com |  | 16.11.21 | 16.12.23 | 02.01.24 | [8 empty] | 20.03.24 | 20.03.24 | 20.03.24 | T1 | 20.03.24 | WILO | 30.03.24 | 30.03.24 | 30.03.24 | 30.03.24 |  |  |  | 19.05.24 | svcn@lntecc.com-18.07.2024-12:19:16
Patiala | Mechanical | Sluice gates | LE20M034-M-WS-PR-SG-1207 | LE20M034-M-WS-PR-SG-1207-A | JASH | Post-order comments issued | 130 | Robin | 78699 10452 | robin@jashindia.com |  | 23.01.23 | 13.03.24 | 13.03.24 | [8 empty] | 19.03.24 | 19.03.24 | 19.03.24 | T1 | 20.03.24 | JASH | 22.03.24 | 27.03.24 | [5 empty] | 19.05.24 | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | Sluice gates | LE20M034-M-WS-PR-SG-1207 | LE20M034-M-WS-PR-SG-1207-B | Oriental | Sent to BU Operations | PR Closed | Sanjay Mahensaria | 98102 05011 | orientalcastings@gmail.com |  | 23.01.23 | 13.03.24 | 13.03.24 | [8 empty] | 19.03.24 | 19.03.24 | 19.03.24 | T2 | [10 empty] | svcn@lntecc.com-04.06.2024-11:32:40
Patiala | Mechanical | Exhaust fans | LE20M034-M-WS-PR-VE-1203 | LE20M034-M-WS-PR-VE-1203-A | SV air system | Approved by Client | PR Closed | VINOD RATURI | 9650720655, 8279708634 | svairsystems@gmail.com |  | 03.04.23 | 05.02.24 | 05.02.24 | [8 empty] | 17.02.24 | 17.02.24 | 19.02.24 | T1 | 20.02.24 | SV air system | 29.02.24 | 29.02.24 | 01.03.24 | 01.03.24 | 10.04.24 |  |  | 20.04.24 | bnk@lntecc.com-28.06.2024-15:50:18
Patiala | Mechanical | pump house valves | LE20M034-M-WS-VL-PR-1200 | LE20M034-M-WS-PR-VL-1200-B | IVC | Pre-order technically rejected | PR Closed |  | Sudip ghosh | sudip.ghosh@ivc-valves.com |  | 27.05.24 | 07.06.24 | 05.07.24 | [22 empty] | svcn@lntecc.com-11.07.2024-10:31:10
Patiala | Mechanical | pump house valves | LE20M034-M-WS-VL-PR-1200 | LE20M034-M-WS-PR-VL-1200-C | KBL | Pre-order technically cleared | 30 |  | Karthikeyan R | Karthikeyan.R@kbl.co.in |  | 27.05.24 | 13.06.24 | 05.07.24 | [8 empty] | 05.07.24 | 05.07.24 | 05.07.24 | T1 | [10 empty] | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | OHT Valves | LE20M034-M-WS-PR-VL-1204 | LE20M034-M-WS-PR-VL-1204-A | Sigmaflow | Pre-order technically cleared | 33 | Resilient has been rejected by Client. Discussed with 5 vendors & consolidated comparison shared to BU/SCM. Awaiting for final offers. |  | jagadesh@sigmaflow.in> |  | 18.11.21 | 02.07.24 | 02.07.24 | [8 empty] | 02.07.24 | 02.07.24 | 02.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | OHT Valves | LE20M034-M-WS-PR-VL-1204 | LE20M034-M-WS-PR-VL-1204-B | IVC | Pre-order technically rejected | PR Closed |  | Sudip ghosh | sudip.ghosh@ivc-valves.com |  | 27.05.24 | 07.06.24 | 05.07.24 | [22 empty] | svcn@lntecc.com-11.07.2024-10:31:10
Patiala | Mechanical | OHT Valves | LE20M034-M-WS-PR-VL-1204 | LE20M034-M-WS-PR-VL-1204-C | KBL | Pre-order technically cleared | 30 |  | Karthikeyan R | Karthikeyan.R@kbl.co.in |  | 27.05.24 | 13.06.24 | 05.07.24 | [8 empty] | 05.07.24 | 05.07.24 | 05.07.24 | T1 | [10 empty] | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | Pipeline valves | LE20M034-M-WS-PR-ZV-1205 | LE20M034-M-WS-PR-ZV-1205-A | Sigmaflow | Pre-order technically cleared | 33 | Resilient has been rejected by Client. Discussed with 5 vendors & consolidated comparison shared to BU/SCM. Awaiting for final offers. |  | jagadesh@sigmaflow.in> |  | 18.11.21 | 02.07.24 | 02.07.24 | [8 empty] | 02.07.24 | 02.07.24 | 02.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | Pipeline valves | LE20M034-M-WS-PR-ZV-1205 | LE20M034-M-WS-PR-ZV-1205-B | IVC | Pre-order technically rejected | PR Closed |  | Sudip ghosh | sudip.ghosh@ivc-valves.com |  | 27.05.24 | 07.06.24 | 05.07.24 | [22 empty] | svcn@lntecc.com-11.07.2024-10:31:10
Patiala | Mechanical | Pipeline valves | LE20M034-M-WS-PR-ZV-1205 | LE20M034-M-WS-PR-ZV-1205-C | KBL | Pre-order technically cleared | 30 |  | Karthikeyan R | Karthikeyan.R@kbl.co.in |  | 27.05.24 | 13.06.24 | 05.07.24 | [8 empty] | 05.07.24 | 05.07.24 | 05.07.24 | T1 | [10 empty] | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | Air cushion and zero velocity valves | LE20M034-M-WS-PR-ZV-1206 | LE20M034-M-WS-PR-ZV-1206-A | Sigmaflow | Post-order technically cleared | 127 | Jagadesh |  | jagadesh@sigmaflow.in |  | 19.11.21 | 16.02.24 | 16.03.24 | [8 empty] | 16.03.24 | 16.03.24 | 16.03.24 | T1 | 16.03.24 | Sigmaflow | 30.03.24 | 30.03.24 | 30.03.24 | 30.03.24 |  |  |  | 15.05.24 | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | pump house valves | LE20M034-M-WS-VL-PR-1200 | LE20M034-M-WS-VL-PR-1200-A | Sigmaflow | Pre-order technically cleared | 33 | Resilient has been rejected by Client. Discussed with 5 vendors & consolidated comparison shared to BU/SCM. Awaiting for final offers. |  | jagadesh@sigmaflow.in> |  | 15.11.21 | 02.07.24 | 02.07.24 | [8 empty] | 02.07.24 | 02.07.24 | 02.07.24 | T1 | [7 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | Dismantling joints | LE20M034-M-WS-VL-PR-12009 | LE20M034-M-WS-VL-PR-12009-A | Precise | Sent to BU Operations | PR Closed | Shailendra Mehta |  | sjm@vedantagroup.net |  | 15.11.21 | 07.03.24 | 07.03.24 | [8 empty] | 10.04.24 | 10.04.24 | 10.04.24 | T2 | [10 empty] | svcn@lntecc.com-04.06.2024-10:26:59
Patiala | Mechanical | Dismantling joints | LE20M034-M-WS-VL-PR-12009 | LE20M034-M-WS-VL-PR-12009-B | Sur industries | Approved by Client | PR Closed |  |  | surindustries <info@surind.com>; Sheikh Mohammed Fayazuddin <fayazaseema@gmail.com> |  | 15.11.21 | 07.03.24 | 07.03.24 | [8 empty] | 10.04.24 | 10.04.24 | 10.04.24 | T1 | 02.05.24 | Sur industries | 29.05.24 | 29.05.24 | 29.05.24 | 29.05.24 | 29.05.24 |  |  | 01.07.24 | svcn@lntecc.com-04.06.2024-10:39:45
Patiala | Mechanical | Dewatering Pumps | LE20M034-M-WS-WT-PR-2226 | LE20M034-M-WS-WT-PR-2226-A | AQUA | Pre-order pending with EDRC | 62 | S.T.Sambandam | 81440 03131 | chennai@aquapumps.com |  | 15.11.21 | 03.06.24 | [20 empty] | 31.08.24 | 17.09.24 | 16.11.24 | svcn@lntecc.com-18.07.2024-12:19:17
Patiala | Mechanical | Float valve | LE20M034-M-WS-WT-PR-2236 | LE20M034-M-WS-WT-PR-2236-A | AVK | Sent to BU Operations | PR Closed | Subhash | 91769 66455 | subhash@avkindia.com |  | 11.12.23 | 15.12.23 | 15.12.23 | [8 empty] | 20.12.23 | 20.12.23 | 21.12.23 | T2 | [10 empty] | svcn@lntecc.com-04.06.2024-11:32:40
Patiala | Mechanical | Float valve | LE20M034-M-WS-WT-PR-2236 | LE20M034-M-WS-WT-PR-2236-B | Sigmaflow | Approved by Client | PR Closed | Jagadesh |  | jagadesh@sigmaflow.in |  | 11.12.23 | 12.12.23 | 12.12.23 | [8 empty] | 20.12.23 | 20.12.23 | 20.12.23 | T1 | 20.04.24 | Sigmaflow | 28.04.24 | 29.04.24 | 29.04.24 | 29.04.24 | 30.04.24 |  |  | 19.06.24 | svcn@lntecc.com-04.06.2024-11:32:40
Patiala | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M034-I-WS-WT-PR-5501 | LE20M034-I-WS-WT-PR-5501-A | AN Instruments | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 22.12.22 | 29.12.22 | [8 empty] | 29.12.22 | 29.12.22 | 29.12.22 | T2 | [7 empty] | 29.12.22 | 15.01.23 | 16.03.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M034-I-WS-WT-PR-5501 | LE20M034-I-WS-WT-PR-5501-B | HGuru | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 07.12.23 | 13.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 13.12.23 | T3 | [7 empty] | 13.12.23 | 30.12.23 | 28.02.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M034-I-WS-WT-PR-5501 | LE20M034-I-WS-WT-PR-5501-C | Forbes Marshall | Approved by Client | PR Closed |  |  |  |  | 27.07.21 | 07.12.23 | 07.12.23 | [8 empty] | 07.12.23 | 07.12.23 | 07.12.23 | T1 | 12.12.23 | Forbes Marshall | 21.12.23 | 21.12.23 | 21.12.23 | 21.12.23 | 21.12.23 | 07.12.23 | 24.12.23 | 10.02.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Pressure Switch | LE20M034-I-WS-WT-PR-5502 | LE20M034-I-WS-WT-PR-5502-A | AN Instruments | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 22.12.22 | 29.12.22 | [8 empty] | 29.12.22 | 29.12.22 | 29.12.22 | T3 | [7 empty] | 29.12.22 | 15.01.23 | 16.03.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Pressure Switch | LE20M034-I-WS-WT-PR-5502 | LE20M034-I-WS-WT-PR-5502-B | HGuru | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 12.04.24 | 23.04.24 | [8 empty] | 23.04.24 | 23.04.24 | 23.04.24 | T2 | [7 empty] | 23.04.24 | 10.05.24 | 09.07.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Pressure Switch | LE20M034-I-WS-WT-PR-5502 | LE20M034-I-WS-WT-PR-5502-C | Forbes Marshall | Approved by Client | PR Closed |  |  |  |  | 27.07.21 | 21.12.23 | 02.01.24 | [8 empty] | 02.01.24 | 02.01.24 | 02.01.24 | T1 | 10.01.24 | Forbes Marshall | 17.01.24 | 17.01.24 | 17.01.24 | 17.01.24 | 24.01.24 | 02.01.24 | 19.01.24 | 10.03.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Pressure transmitter | LE20M034-I-WS-WT-PR-5503 | LE20M034-I-WS-WT-PR-5503-A | ABB | Regret offer | PR Closed |  |  |  |  | 27.07.21 | 09.03.23 | 09.03.23 | [22 empty] | gopika.nath@lntecc.com-21.05.2024-12:16:08
Patiala | Instrumentation | Pressure transmitter | LE20M034-I-WS-WT-PR-5503 | LE20M034-I-WS-WT-PR-5503-B | E&H | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 28.04.23 | 08.05.23 | [8 empty] | 08.05.23 | 08.05.23 | 08.05.23 | T2 | [7 empty] | 08.05.23 | 25.05.23 | 24.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Pressure transmitter | LE20M034-I-WS-WT-PR-5503 | LE20M034-I-WS-WT-PR-5503-C | Siemens | Approved by Client | PR Closed |  |  |  |  | 27.07.21 | 28.04.23 | 08.05.23 | [8 empty] | 08.05.23 | 08.05.23 | 08.05.23 | T1 | 12.09.23 | Siemens | 22.09.23 | 12.10.23 | 12.10.23 | 12.10.23 | 12.11.23 | 08.05.23 | 25.05.23 | 24.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Pressure transmitter | LE20M034-I-WS-WT-PR-5503 | LE20M034-I-WS-WT-PR-5503-D | Yokogawa | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 03.05.23 | 08.05.23 | [8 empty] | 08.05.23 | 08.05.23 | 08.05.23 | T3 | [7 empty] | 08.05.23 | 25.05.23 | 24.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Float & Board Level gauge | LE20M034-I-WS-WT-PR-5504 | LE20M034-I-WS-WT-PR-5504-A | Pune Techtrol | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 09.11.23 | 15.11.23 | 22.04.24 | 25.04.24 | [6 empty] | 25.04.24 | 25.04.24 | 25.04.24 | T1 | [7 empty] | 25.04.24 | 12.05.24 | 11.07.24 | gopika.nath@lntecc.com-24.07.2024-12:30:16
Patiala | Instrumentation | Float & Board Level gauge | LE20M034-I-WS-WT-PR-5504 | LE20M034-I-WS-WT-PR-5504-B | Scientific Devices | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 31.10.23 | 20.11.23 | 28.11.23 | 02.12.23 | [6 empty] | 02.12.23 | 02.12.23 | 02.12.23 | T2 | [7 empty] | 02.12.23 | 19.12.23 | 17.02.24 | gopika.nath@lntecc.com-24.07.2024-12:30:16
Patiala | Instrumentation | Float & Board Level gauge | LE20M034-I-WS-WT-PR-5504 | LE20M034-I-WS-WT-PR-5504-C | SBEM | Post-order technically cleared | 11 |  |  |  |  | 27.07.21 | 22.01.24 | 02.05.24 | 04.05.24 | 04.05.24 | [6 empty] | 04.05.24 | 04.05.24 | 04.05.24 | T3 | 17.07.24 | SBEM | 19.07.24 | 20.07.24 | 24.07.24 | 24.07.24 |  | 04.05.24 | 21.05.24 | 20.07.24 | gopika.nath@lntecc.com-24.07.2024-12:30:16
Patiala | Instrumentation | Ultrasonic level transmitter | LE20M034-I-WS-WT-PR-5505 | LE20M034-I-WS-WT-PR-5505-A | E&H | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 28.04.23 | 08.05.23 | [8 empty] | 08.05.23 | 08.05.23 | 08.05.23 | T2 | [7 empty] | 08.05.23 | 25.05.23 | 24.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Ultrasonic level transmitter | LE20M034-I-WS-WT-PR-5505 | LE20M034-I-WS-WT-PR-5505-B | Siemens | Approved by Client | PR Closed |  |  |  |  | 27.07.21 | 28.04.23 | 08.05.23 | [8 empty] | 08.05.23 | 08.05.23 | 08.05.23 | T1 | 12.09.23 | Siemens | 22.09.23 | 12.10.23 | 12.10.23 | 12.10.23 | 12.11.23 | 08.05.23 | 25.05.23 | 24.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Ultrasonic level transmitter | LE20M034-I-WS-WT-PR-5505 | LE20M034-I-WS-WT-PR-5505-C | Yokogawa | Regret offer | PR Closed |  |  |  |  | 27.07.21 | 03.05.23 | 08.05.23 | [9 empty] | 08.05.23 | 08.05.23 | T3 | [7 empty] | 08.05.23 | 25.05.23 | 24.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Level switch - Conductivity type | LE20M034-I-WS-WT-PR-5506 | LE20M034-I-WS-WT-PR-5506-A | SBEM | Post-order technically cleared | 11 |  |  |  |  | 27.07.21 | 22.01.24 | 09.02.24 | [8 empty] | 09.02.24 | 09.02.24 | 09.02.24 | T1 | 17.07.24 | SBEM | 19.07.24 | 20.07.24 | 24.07.24 | 24.07.24 |  | 09.02.24 | 26.02.24 | 26.04.24 | gopika.nath@lntecc.com-24.07.2024-12:30:16
Patiala | Instrumentation | Ultrasonic flow meter (channel) | LE20M034-I-WS-WT-PR-5507 | LE20M034-I-WS-WT-PR-5507-A | E&H | Pre-order technically cleared | 229 |  |  |  |  | 27.07.21 | 09.12.23 | 19.12.23 | [8 empty] | 19.12.23 | 19.12.23 | 19.12.23 | [8 empty] | 19.12.23 | 05.01.24 | 05.03.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Ultrasonic flow meter (channel) | LE20M034-I-WS-WT-PR-5507 | LE20M034-I-WS-WT-PR-5507-B | Siemens | Pre-order technically cleared | 227 |  |  |  |  | 27.07.21 | 20.12.23 | 21.12.23 | [8 empty] | 21.12.23 | 21.12.23 | 21.12.23 | [8 empty] | 21.12.23 | 07.01.24 | 07.03.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Loss of head transmitter | LE20M034-I-WS-WT-PR-5508 | LE20M034-I-WS-WT-PR-5508-A | E&H | Pre-order technically cleared | 229 |  |  |  |  | 27.07.21 | 09.12.23 | 19.12.23 | [8 empty] | 19.12.23 | 19.12.23 | 19.12.23 | [8 empty] | 19.12.23 | 05.01.24 | 05.03.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Loss of head transmitter | LE20M034-I-WS-WT-PR-5508 | LE20M034-I-WS-WT-PR-5508-B | Siemens | Pre-order technically cleared | 227 |  |  |  |  | 27.07.21 | 20.12.23 | 21.12.23 | [8 empty] | 21.12.23 | 21.12.23 | 21.12.23 | [8 empty] | 21.12.23 | 07.01.24 | 07.03.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Rate for flow transmitter | LE20M034-I-WS-WT-PR-5509 | LE20M034-I-WS-WT-PR-5509-A | E&H | Pre-order technically cleared | 229 |  |  |  |  | 27.07.21 | 09.12.23 | 19.12.23 | [8 empty] | 19.12.23 | 19.12.23 | 19.12.23 | [8 empty] | 19.12.23 | 05.01.24 | 05.03.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Rate for flow transmitter | LE20M034-I-WS-WT-PR-5509 | LE20M034-I-WS-WT-PR-5509-B | Siemens | Pre-order technically cleared | 227 |  |  |  |  | 27.07.21 | 20.12.23 | 21.12.23 | [8 empty] | 21.12.23 | 21.12.23 | 21.12.23 | [8 empty] | 21.12.23 | 07.01.24 | 07.03.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Bypass Rotameter | LE20M034-I-WS-WT-PR-5510 | LE20M034-I-WS-WT-PR-5510-A | Eureka | Pre-order technically cleared | 269 |  |  |  |  | 27.07.21 | 31.10.23 | 09.11.23 | [8 empty] | 09.11.23 | 09.11.23 | 09.11.23 | [8 empty] | 09.11.23 | 26.11.23 | 25.01.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Bypass Rotameter | LE20M034-I-WS-WT-PR-5510 | LE20M034-I-WS-WT-PR-5510-B | Scientific Devices | Pre-order technically cleared | 263 |  |  |  |  | 27.07.21 | 10.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 02.12.23 | 31.01.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | pH Meter | LE20M034-I-WS-WT-PR-5511 | LE20M034-I-WS-WT-PR-5511-A | E&H | Approved by Client | PR Closed |  |  |  |  | 27.07.21 | 21.12.23 | 02.01.24 | [8 empty] | 02.01.24 | 02.01.24 | 02.01.24 | T1 | 01.04.23 | E&H | 11.04.24 | 11.04.24 | 17.04.24 | 17.04.24 | 20.04.24 | 02.01.24 | 19.01.24 | 31.05.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | pH Meter | LE20M034-I-WS-WT-PR-5511 | LE20M034-I-WS-WT-PR-5511-B | Khrone | Regret offer | PR Closed |  |  |  |  | 27.07.21 | 02.01.24 | 03.01.24 | [11 empty] | T4 | [10 empty] | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | pH Meter | LE20M034-I-WS-WT-PR-5511 | LE20M034-I-WS-WT-PR-5511-C | ABB | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 11.01.24 | 18.01.24 | [8 empty] | 20.01.24 | 20.01.24 | 20.01.24 | T2 | [7 empty] | 20.01.24 | 06.02.24 | 06.04.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | pH Meter | LE20M034-I-WS-WT-PR-5511 | LE20M034-I-WS-WT-PR-5511-D | Hach | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 13.02.24 | 26.02.24 | [8 empty] | 26.02.24 | 26.02.24 | 26.02.24 | T3 | [7 empty] | 26.02.24 | 14.03.24 | 13.05.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Turbidity meter | LE20M034-I-WS-WT-PR-5512 | LE20M034-I-WS-WT-PR-5512-A | E&H | Approved by Client | PR Closed |  |  |  |  | 27.07.21 | 21.12.23 | 02.01.24 | [8 empty] | 02.01.24 | 02.01.24 | 02.01.24 | T1 | 01.04.23 | E&H | 11.04.24 | 11.04.24 | 17.04.24 | 17.04.24 | 20.04.24 | 02.01.24 | 19.01.24 | 31.05.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Turbidity meter | LE20M034-I-WS-WT-PR-5512 | LE20M034-I-WS-WT-PR-5512-B | Khrone | Regret offer | PR Closed |  |  |  |  | 27.07.21 | 02.01.24 | 04.01.24 | [22 empty] | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Turbidity meter | LE20M034-I-WS-WT-PR-5512 | LE20M034-I-WS-WT-PR-5512-C | ABB | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 11.01.24 | 20.01.24 | [8 empty] | 20.01.24 | 20.01.24 | 20.01.24 | T2 | [7 empty] | 20.01.24 | 06.02.24 | 06.04.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Turbidity meter | LE20M034-I-WS-WT-PR-5512 | LE20M034-I-WS-WT-PR-5512-D | Hach | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 13.02.24 | 26.02.24 | [8 empty] | 26.02.24 | 26.02.24 | 26.02.24 | T3 | [7 empty] | 26.02.24 | 14.03.24 | 13.05.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Residual Chlorine Analyzer | LE20M034-I-WS-WT-PR-5513 | LE20M034-I-WS-WT-PR-5513-A | E&H | Approved by Client | PR Closed |  |  |  |  | 27.07.21 | 21.12.23 | 02.01.24 | [8 empty] | 02.01.24 | 02.01.24 | 02.01.24 | T1 | 01.04.23 | E&H | 11.04.24 | 11.04.24 | 17.04.24 | 17.04.24 | 20.04.24 | 02.01.24 | 19.01.24 | 31.05.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Residual Chlorine Analyzer | LE20M034-I-WS-WT-PR-5513 | LE20M034-I-WS-WT-PR-5513-B | Khrone | Regret offer | PR Closed |  |  |  |  | 27.07.21 | 02.01.24 | 04.01.24 | [22 empty] | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Residual Chlorine Analyzer | LE20M034-I-WS-WT-PR-5513 | LE20M034-I-WS-WT-PR-5513-C | ABB | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 11.01.24 | 20.01.24 | [8 empty] | 20.01.24 | 20.01.24 | 20.01.24 | T2 | [7 empty] | 20.01.24 | 06.02.24 | 06.04.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Residual Chlorine Analyzer | LE20M034-I-WS-WT-PR-5513 | LE20M034-I-WS-WT-PR-5513-D | Hach | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 13.02.24 | 26.02.24 | [8 empty] | 26.02.24 | 26.02.24 | 26.02.24 | T3 | [7 empty] | 26.02.24 | 14.03.24 | 13.05.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Electromagnectic flow meter(AC) | LE20M034-I-WS-WT-PR-5514 | LE20M034-I-WS-WT-PR-5514-A | Khrone Marshall | Approved by Client | PR Closed |  |  |  |  | 27.07.21 | 28.04.23 | 03.05.23 | [8 empty] | 03.05.23 | 03.05.23 | 03.05.23 | T1 | 03.10.23 | Khrone Marshall | 03.11.23 | 03.11.23 | 03.11.23 | 03.11.23 | 22.11.23 | 03.05.23 | 20.05.23 | 19.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Electromagnectic flow meter(AC) | LE20M034-I-WS-WT-PR-5514 | LE20M034-I-WS-WT-PR-5514-B | Siemens | Regret offer | PR Closed |  |  |  |  | 27.07.21 | 28.04.23 | 03.05.23 | [8 empty] | 03.05.23 | 03.05.23 | 03.05.23 | [8 empty] | 03.05.23 | 20.05.23 | 19.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Electromagnectic flow meter(AC) | LE20M034-I-WS-WT-PR-5514 | LE20M034-I-WS-WT-PR-5514-C | SBEM | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 19.06.23 | 21.06.23 | [8 empty] | 21.06.23 | 21.06.23 | 21.06.23 | T2 | [7 empty] | 21.06.23 | 08.07.23 | 06.09.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Electromagnectic flow meter(AC) | LE20M034-I-WS-WT-PR-5514 | LE20M034-I-WS-WT-PR-5514-D | Yokogawa | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 16.10.23 | 25.10.23 | [8 empty] | 25.10.23 | 25.10.23 | 25.10.23 | T3 | [7 empty] | 25.10.23 | 11.11.23 | 10.01.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Electromagnectic flow meter(AC) | LE20M034-I-WS-WT-PR-5514 | LE20M034-I-WS-WT-PR-5514-E | ABB | Sent to BU Operations | PR Closed |  |  |  |  | 27.07.21 | 16.10.23 | 25.10.23 | [8 empty] | 25.10.23 | 25.10.23 | 25.10.23 | T4 | [7 empty] | 25.10.23 | 11.11.23 | 10.01.24 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Multijet water meter | LE20M034-I-WS-WT-PR-5515 | LE20M034-I-WS-WT-PR-5515-A | Baylan | Sent to BU Operations | PR Closed |  |  |  |  | 23.08.22 | 09.03.23 | 10.05.23 | [8 empty] | 10.05.23 | 10.05.23 | 10.05.23 | T3 | [7 empty] | 10.05.23 | 27.05.23 | 26.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Multijet water meter | LE20M034-I-WS-WT-PR-5515 | LE20M034-I-WS-WT-PR-5515-B | Accumeasure | Sent to BU Operations | PR Closed |  |  |  |  | 23.08.22 | 09.03.23 | 10.05.23 | [8 empty] | 10.05.23 | 10.05.23 | 10.05.23 | T2 | [7 empty] | 10.05.23 | 27.05.23 | 26.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Multijet water meter | LE20M034-I-WS-WT-PR-5515 | LE20M034-I-WS-WT-PR-5515-C | Federal | Approved by Client | PR Closed |  |  |  |  | 23.08.22 | 21.04.23 | 19.05.23 | [8 empty] | 19.05.23 | 19.05.23 | 19.05.23 | T1 | 30.05.23 | Federal | 01.06.23 | 01.06.23 | 01.06.23 | 01.06.23 | 21.06.23 | 19.05.23 | 05.06.23 | 29.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M034-I-WS-WT-PR-5516 | LE20M034-I-WS-WT-PR-5516-A | Schneider | Sent to BU Operations | PR Closed |  |  |  |  | 23.08.22 | 14.08.23 | 22.08.23 | 01.09.23 | 04.09.23 | 11.09.23 | 11.09.23 | 15.09.23 | 15.09.23 |  |  | 15.09.23 | 15.09.23 | 15.09.23 | T2 | [7 empty] | 15.09.23 | 02.10.23 | 01.12.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M034-I-WS-WT-PR-5516 | LE20M034-I-WS-WT-PR-5516-B | SATPL | Regret offer | PR Closed |  |  |  |  | 23.08.22 | 03.06.23 | 09.06.23 | [22 empty] | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M034-I-WS-WT-PR-5516 | LE20M034-I-WS-WT-PR-5516-C | SIAS | Approved by Client | PR Closed |  |  |  |  | 23.08.22 | 20.05.23 | 01.06.23 | 02.06.23 | 08.06.23 | 22.06.23 | 26.06.23 | 28.06.23 | 15.07.23 | 16.08.23 | 24.08.23 | 04.09.23 | 04.09.23 | 04.09.23 | T1 | 10.10.23 | SIAS | 19.10.23 | 26.10.23 | 16.11.23 | 04.12.23 | 10.01.24 | 04.09.23 | 21.09.23 | 20.11.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M034-I-WS-WT-PR-5516 | LE20M034-I-WS-WT-PR-5516-D | Autosys | Sent to BU Operations | PR Closed |  |  |  |  | 23.08.22 | 25.04.23 | 20.05.23 | 25.05.23 | 01.06.23 | 09.06.23 | 22.06.23 | 30.06.23 | 17.07.23 | 01.09.23 | 04.09.23 | 04.09.23 | 04.09.23 | 04.09.23 | T3 | [7 empty] | 04.09.23 | 21.09.23 | 20.11.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M034-I-WS-WT-PR-5516 | LE20M034-I-WS-WT-PR-5516-E | ICAM | Sent to BU Operations | PR Closed |  |  |  |  | 23.08.22 | 25.04.23 | 20.05.23 | 01.06.23 | 09.06.23 | 22.06.23 | 26.06.23 | 30.06.23 | 15.07.23 | 11.08.23 | 24.08.23 | 24.08.23 | 24.08.23 | 24.08.23 | T4 | [7 empty] | 24.08.23 | 10.09.23 | 09.11.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Instrumentation Control & signal Cables | LE20M034-I-WS-WT-PR-5517 | LE20M034-I-WS-WT-PR-5517-A | Polycab | Regret offer | PR Closed |  |  |  |  | 23.08.22 | 07.11.23 | 15.11.23 | [22 empty] | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Instrumentation Control & signal Cables | LE20M034-I-WS-WT-PR-5517 | LE20M034-I-WS-WT-PR-5517-B | Cords | Post-order technically cleared | 226 |  |  |  |  | 23.08.22 | 10.11.23 | 15.11.23 | [8 empty] | 15.11.23 | 15.11.23 | 15.11.23 | T1 | 20.12.23 | Cords | 22.12.23 | 22.12.23 | 22.12.23 | 22.12.23 |  | 15.11.23 | 02.12.23 | 31.01.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | UPS | LE20M034-I-WS-WT-PR-5518 | LE20M034-I-WS-WT-PR-5518-A | Hirel | Pre-order technically cleared | 97 |  |  |  |  | 23.08.22 | 03.04.24 | 29.04.24 | [8 empty] | 29.04.24 | 29.04.24 | 29.04.24 | [8 empty] | 29.04.24 | 16.05.24 | 15.07.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | UPS | LE20M034-I-WS-WT-PR-5518 | LE20M034-I-WS-WT-PR-5518-B | Liveline | Pre-order technically cleared | 83 |  |  |  |  | 23.08.22 | 04.04.24 | 13.05.24 | [8 empty] | 13.05.24 | 13.05.24 | 13.05.24 | [8 empty] | 13.05.24 | 30.05.24 | 29.07.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Battery operated Data logger and Pressure sensor | LE20M034-I-WS-WT-PR-5519 | LE20M034-I-WS-WT-PR-5519-A | GSV Microtech | Post-order technically cleared | 376 |  |  |  |  | 23.08.22 | 04.06.23 | 14.07.23 | [8 empty] | 14.07.23 | 14.07.23 | 14.07.23 | T1 | 17.07.23 | GSV Microtech | 25.07.23 | 25.07.23 | 25.07.23 | 25.07.23 |  | 14.07.23 | 31.07.23 | 15.09.23 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | Battery operated Data logger and Pressure sensor | LE20M034-I-WS-WT-PR-5519 | LE20M034-I-WS-WT-PR-5519-B | Enviro | Sent to BU Operations | PR Closed |  |  |  |  | 23.08.22 | 16.12.22 | 14.07.23 | [8 empty] | 14.07.23 | 14.07.23 | 14.07.23 | T2 | [7 empty] | 14.07.23 | 31.07.23 | 29.09.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Battery operated EMFM | LE20M034-I-WS-WT-PR-5520 | LE20M034-I-WS-WT-PR-5520-A | Siemens | Approved by Client | PR Closed |  |  |  |  | 23.08.22 | 28.04.23 | 11.05.23 | [8 empty] | 11.05.23 | 11.05.23 | 11.05.23 | T1 | 24.05.23 | Siemens | 26.06.23 | 26.06.23 | 26.06.23 | 26.06.23 | 26.06.23 | 11.05.23 | 28.05.23 | 23.07.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | Battery operated EMFM | LE20M034-I-WS-WT-PR-5520 | LE20M034-I-WS-WT-PR-5520-B | ABB | Sent to BU Operations | PR Closed |  |  |  |  | 23.08.22 | 19.05.23 | 19.05.23 | [8 empty] | 19.05.23 | 19.05.23 | 19.05.23 | T2 | [7 empty] | 19.05.23 | 05.06.23 | 04.08.23 | gopika.nath@lntecc.com-01.07.2024-15:11:11
Patiala | Instrumentation | CCTV system | LE20M034-I-WS-WT-PR-5521 | LE20M034-I-WS-WT-PR-5521-A | Telso Networks | Pre-order pending with EDRC | 90 |  |  |  |  | 23.08.22 | 06.05.24 | [20 empty] | 17.07.24 | 03.08.24 | 02.10.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | CCTV system | LE20M034-I-WS-WT-PR-5521 | LE20M034-I-WS-WT-PR-5521-B | inttech | Pre-order pending with EDRC | 64 |  |  |  |  | 17.04.24 | 01.06.24 | [20 empty] | 17.07.24 | 03.08.24 | 02.10.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Instrumentation | EPABX system | LE20M034-I-WS-WT-PR-5522 | LE20M034-I-WS-WT-PR-5522-A | Telso Networks | Awaiting pre-offer from vendor | 32 |  |  |  |  | 03.07.24 | [21 empty] | 24.07.24 | 10.08.24 | 09.10.24 | gopika.nath@lntecc.com-11.07.2024-12:35:17
Patiala | Electrical | Transformer | LE20M034-E-WS-WT-PR-4201 | LE20M034-E-WS-WT-PR-4201-A | Nucon | Regret offer | PR Closed |  |  | export@nucon.co.in |  | 13.06.23 | 15.06.23 | 22.06.23 | 05.07.23 | 07.07.23 | [9 empty] | T2 | [10 empty] | usman.mohideen@lntecc.com-03.06.2024-15:48:44
Patiala | Electrical | Transformer | LE20M034-E-WS-WT-PR-4201 | LE20M034-E-WS-WT-PR-4201-B | CGL | Sent to BU Operations | PR Closed |  |  | vignesh.srinivasan@cgglobal.com |  | 05.06.23 | 07.06.23 | 22.06.23 | 30.06.23 | 12.07.23 | 14.07.23 | 21.09.23 | 26.09.23 |  |  |  | 12.12.23 | 13.12.23 | 15.12.23 | T2 | [7 empty] | 13.12.23 | 30.12.23 | 28.02.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | Transformer | LE20M034-E-WS-WT-PR-4201 | LE20M034-E-WS-WT-PR-4201-C | Kirloskar | Sent to BU Operations | PR Closed |  |  | aditya.ksr@kirloskarelectric.com |  | 11.08.23 | 19.08.23 | 24.08.23 | 25.08.23 | 27.09.23 | 06.12.23 | 07.12.23 |  |  |  |  | 11.12.23 | 13.12.23 | 15.12.23 | T2 | [7 empty] | 13.12.23 | 30.12.23 | 28.02.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | Transformer | LE20M034-E-WS-WT-PR-4201 | LE20M034-E-WS-WT-PR-4201-D | Voltamp | Approved by Client | PR Closed |  |  | sasik_vtlchn@voltamptransformers.com |  | 09.11.23 | 02.12.23 | 07.12.23 | 09.12.23 | 11.12.23 | [6 empty] | 13.12.23 | 18.12.23 | 19.12.23 | T1 | 19.12.23 | Voltamp | 21.12.23 | 02.01.24 | 03.01.24 | 04.01.24 | 14.03.24 | 18.12.23 | 04.01.24 | 17.02.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | HT Panel | LE20M034-E-WS-WT-PR-4203 | LE20M034-E-WS-WT-PR-4203-A | CG Power | Sent to BU Operations | PR Closed |  |  | sivakumar.prakasam@cgglobal.com |  | 19.06.23 | 05.07.23 | 06.07.23 | 12.07.23 | 14.07.23 | [6 empty] | 25.07.23 | 27.07.23 | 31.07.23 | T2 | [7 empty] | 27.07.23 | 13.08.23 | 12.10.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | HT Panel | LE20M034-E-WS-WT-PR-4203 | LE20M034-E-WS-WT-PR-4203-B | HTS | Approved by Client | PR Closed |  |  | sales@htswitchgears.com |  | 23.05.23 | 29.05.23 | 31.05.23 | 02.06.23 | 05.06.23 | [6 empty] | 15.07.23 | 17.07.23 | 19.07.23 | T2 | 14.09.23 | HTS | 14.09.23 | 20.09.23 | 21.09.23 | 22.09.23 | 05.10.23 | 17.07.23 | 03.08.23 | 02.10.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | HT Panel | LE20M034-E-WS-WT-PR-4203 | LE20M034-E-WS-WT-PR-4203-C | Symatic India | Sent to BU Operations | PR Closed |  |  | jeyanth.j@siemens.com |  | 23.05.23 | 29.05.23 | 01.06.23 | 06.06.23 | 26.06.23 | [6 empty] | 05.07.23 | 14.07.23 | 17.07.23 | T2 | [7 empty] | 14.07.23 | 31.07.23 | 29.09.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | DG Set | LE20M034-E-WS-WT-PR-4204 | LE20M034-E-WS-WT-PR-4204-A | Caterpillar | Awaiting pre-offer from vendor | 202 |  |  | aftab.ali@gainwellindia.com |  | 15.01.24 | [21 empty] | 05.09.24 | 22.09.24 | 21.11.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | DG Set | LE20M034-E-WS-WT-PR-4204 | LE20M034-E-WS-WT-PR-4204-B | Sudhir power | Awaiting pre-offer from vendor | 202 |  |  | deveshsingh@sudhirpower.com |  | 15.01.24 | [21 empty] | 05.09.24 | 22.09.24 | 21.11.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | HT Cables and Termination kits | LE20M034-E-WS-WT-PR-4205 | LE20M034-E-WS-WT-PR-4205-A | Polycab | Sent to BU Operations | PR Closed |  |  | pvespl@vashiisl.com |  | 09.12.23 | 11.12.23 | 12.12.23 | [8 empty] | 13.12.23 | 14.12.23 | 18.12.23 | T2 | [7 empty] | 14.12.23 | 31.12.23 | 29.02.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | HT Cables and Termination kits | LE20M034-E-WS-WT-PR-4205 | LE20M034-E-WS-WT-PR-4205-B | KEI | Sent to BU Operations | PR Closed |  |  | vincent.kallen@kei-ind.com |  | 08.12.23 | 14.12.23 | 16.12.23 | 20.12.23 | 22.12.23 | [6 empty] | 26.12.23 | 26.12.23 | 28.12.23 | T2 | [7 empty] | 26.12.23 | 12.01.24 | 12.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | HT Cables and Termination kits | LE20M034-E-WS-WT-PR-4205 | LE20M034-E-WS-WT-PR-4205-C | Cords | Post-order technically cleared | 165 |  |  | anuradha@cordscable.com |  | 08.12.23 | 13.12.23 | 15.12.23 | [8 empty] | 27.12.23 | 27.12.23 | 28.12.23 | T2 | 25.01.24 | Cords | 31.01.24 | 31.01.24 | 19.02.24 | 21.02.24 |  | 27.12.23 | 13.01.24 | 13.03.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | LT Panel | LE20M034-E-WS-WT-PR-4206 | LE20M034-E-WS-WT-PR-4206-A | Ragavendra Controls | Sent to BU Operations | PR Closed |  |  | ashok@ragavendracontrol.com |  | 16.05.23 | 05.06.23 | 06.06.23 | 06.07.23 | 19.07.23 | [6 empty] | 16.09.23 | 19.09.23 | 21.09.23 | T2 | [7 empty] | 19.09.23 | 06.10.23 | 05.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | LT panel | LE20M034-E-WS-WT-PR-4206 | LE20M034-E-WS-WT-PR-4206-B | RST | Sent to BU Operations | PR Closed |  |  | design@rstelectricals.com |  | 16.05.23 | 24.07.23 | 28.07.23 | 09.08.23 | 11.08.23 | [6 empty] | 21.09.23 | 22.09.23 | 25.09.23 | T2 | [7 empty] | 22.09.23 | 09.10.23 | 08.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | LT Panel | LE20M034-E-WS-WT-PR-4206 | LE20M034-E-WS-WT-PR-4206-C | Voltech | Approved by Client | PR Closed |  |  | panel@voltechgroup.com |  | 17.05.23 | 05.09.23 | 08.09.23 | [8 empty] | 03.10.23 | 05.10.23 | 12.10.23 | T2 | 19.12.23 | Voltech | 03.01.24 | 11.01.24 | 23.02.24 | 06.03.24 | 08.03.24 | 05.10.23 | 22.10.23 | 21.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | LT Power and Control cables | LE20M034-E-WS-WT-PR-4207 | LE20M034-E-WS-WT-PR-4207-A | Polycab | Sent to BU Operations | PR Closed |  |  | pvespl@vashiisl.com |  | 09.12.23 | 11.12.23 | 12.12.23 | [8 empty] | 13.12.23 | 14.12.23 | 18.12.23 | T2 | [7 empty] | 14.12.23 | 31.12.23 | 29.02.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | LT Power and Control cables | LE20M034-E-WS-WT-PR-4207 | LE20M034-E-WS-WT-PR-4207-B | KEI | Sent to BU Operations | PR Closed |  |  | vincent.kallen@kei-ind.com |  | 08.12.23 | 14.12.23 | 16.12.23 | 20.12.23 | 22.12.23 | [6 empty] | 26.12.23 | 26.12.23 | 28.12.23 | T2 | [7 empty] | 26.12.23 | 12.01.24 | 12.03.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | LT Power and Control cables | LE20M034-E-WS-WT-PR-4207 | LE20M034-E-WS-WT-PR-4207-C | Cords | Post-order technically cleared | 165 |  |  | anuradha@cordscable.com |  | 08.12.23 | 13.12.23 | 15.12.23 | [8 empty] | 27.12.23 | 27.12.23 | 28.12.23 | T2 | 25.01.24 | Cords | 31.01.24 | 31.01.24 | 19.02.24 | 21.02.24 |  | 27.12.23 | 13.01.24 | 13.03.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | Cable Trays & its supports | LE20M034-E-WS-WT-PR-4208 | LE20M034-E-WS-WT-PR-4208-A | Monaj Trading | Post-order technically cleared | 205 |  |  | monajtrading@gmail.com |  | 17.10.23 | 19.10.23 | 20.10.23 | [8 empty] | 07.11.23 | 08.11.23 | 13.11.23 | T2 | 04.12.23 | Monaj Trading | 03.01.24 | 06.01.24 | 11.01.24 | 12.01.24 |  | 08.11.23 | 25.11.23 | 24.01.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | Lighting Fixtures | LE20M034-E-WS-WT-PR-4209 | LE20M034-E-WS-WT-PR-4209-A | Monaj Trading | Post-order technically cleared | 193 |  |  | monajtrading@gmail.com |  | 19.10.23 | 03.11.23 | 06.11.23 | 08.11.23 | 13.11.23 | [6 empty] | 20.11.23 | 20.11.23 | 28.11.23 | T2 | 13.12.23 | Monaj Trading | 03.01.24 | 09.01.24 | 22.01.24 | 24.01.24 |  | 20.11.23 | 07.12.23 | 05.02.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | Earthing & Lightning protection materials with accessories | LE20M034-E-WS-WT-PR-4210 | LE20M034-E-WS-WT-PR-4210-A | Monaj Trading | Post-order technically cleared | 191 |  |  | monajtrading@gmail.com |  | 13.11.23 | 15.11.23 | 20.11.23 | [8 empty] | 06.12.23 | 07.12.23 | 11.12.23 | T2 | 18.12.23 | Monaj Trading | 08.01.24 | 10.01.24 | 22.01.24 | 26.01.24 |  | 07.12.23 | 24.12.23 | 16.02.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | Electrical Safety Items | LE20M034-E-WS-WT-PR-4211 | LE20M034-E-WS-WT-PR-4211-A | Monaj Trading | Post-order technically cleared | 191 |  |  | monajtrading@gmail.com |  | 13.11.23 | 15.11.23 | 20.11.23 | [8 empty] | 06.12.23 | 07.12.23 | 11.12.23 | T2 | 18.12.23 | Monaj Trading | 08.01.24 | 10.01.24 | 22.01.24 | 26.01.24 |  | 07.12.23 | 24.12.23 | 16.02.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | LPBS | LE20M034-E-WS-WT-PR-4212 | LE20M034-E-WS-WT-PR-4212-A | Voltech | Approved by Client | PR Closed |  |  | panel@voltechgroup.com |  | 05.06.23 | 05.09.23 | 08.09.23 | [8 empty] | 03.10.23 | 05.10.23 | 12.10.23 | T2 | 19.12.23 | Voltech | 03.01.24 | 11.01.24 | 23.02.24 | 06.03.24 | 08.03.24 | 05.10.23 | 22.10.23 | 21.12.23 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | Cable Glands and Lugs | LE20M034-E-WS-WT-PR-4213 | LE20M034-E-WS-WT-PR-4213-A | Monaj Trading | Post-order technically cleared | 205 |  |  | monajtrading@gmail.com |  | 17.10.23 | 19.10.23 | 20.10.23 | [8 empty] | 07.11.23 | 08.11.23 | 13.11.23 | T2 | 04.12.23 | Monaj Trading | 03.01.24 | 06.01.24 | 11.01.24 | 12.01.24 |  | 08.11.23 | 25.11.23 | 24.01.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | Distribution Board, Switchboards, Sockets & Other Accessories | LE20M034-E-WS-WT-PR-4214 | LE20M034-E-WS-WT-PR-4214-A | Monaj Trading | Post-order technically cleared | 180 |  |  | monajtrading@gmail.com |  | 16.10.23 | 23.10.23 | 25.10.23 | [8 empty] | 07.11.23 | 10.11.23 | 15.11.23 | T2 | 18.12.23 | Monaj Trading | 08.01.24 | 12.01.24 | 29.01.24 | 06.02.24 |  | 10.11.23 | 27.11.23 | 26.01.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | Lighting pole and Junction Box | LE20M034-E-WS-WT-PR-4215 | LE20M034-E-WS-WT-PR-4215-A | Monaj Trading | Post-order technically cleared | 193 |  |  | monajtrading@gmail.com |  | 19.10.23 | 03.11.23 | 06.11.23 | 08.11.23 | 13.11.23 | [6 empty] | 20.11.23 | 20.11.23 | 28.11.23 | T2 | 13.12.23 | Monaj Trading | 03.01.24 | 09.01.24 | 22.01.24 | 24.01.24 |  | 20.11.23 | 07.12.23 | 05.02.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | Battery and Battery Charger | LE20M034-E-WS-WT-PR-4216 | LE20M034-E-WS-WT-PR-4216-A | Amaraja | Sent to BU Operations | PR Closed |  |  | varshaxenon@gmail.com |  | 11.01.24 | 15.01.24 | 17.01.24 | [8 empty] | 22.01.24 | 25.01.24 | 29.01.24 | T2 | [7 empty] | 25.01.24 | 11.02.24 | 11.04.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | Battery and Battery Charger | LE20M034-E-WS-WT-PR-4216 | LE20M034-E-WS-WT-PR-4216-B | Chabbi | Post-order technically cleared | 97 |  |  | nilesh.c@chhabi-india.com |  | 05.01.24 | 12.01.24 | 18.01.24 | [8 empty] | 06.02.24 | 06.02.24 | 08.02.24 | T2 | 14.03.24 | Chabbi | 19.03.24 | 27.03.24 | 27.04.24 | 29.04.24 |  | 06.02.24 | 23.02.24 | 23.04.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
Patiala | Electrical | Battery and Battery Charger | LE20M034-E-WS-WT-PR-4216 | LE20M034-E-WS-WT-PR-4216-C | Liveline | Sent to BU Operations | PR Closed |  |  | sales2@livelineindia.com |  | 08.01.24 | 10.01.24 | 12.01.24 | [8 empty] | 17.01.24 | 17.01.24 | 19.01.24 | T2 | [7 empty] | 17.01.24 | 03.02.24 | 03.04.24 | ananthakrishnan.krishnan@lntecc.com-01.07.2024-15:49:26
Patiala | Electrical | Busduct | LE20M034-E-WS-WT-PR-4218 | LE20M034-E-WS-WT-PR-4218-A | Star Drive | Post-order technically cleared | 71 |  |  | suji@stardrive.in |  | 09.12.23 | 11.12.23 | 12.12.23 | [8 empty] | 13.12.23 | 13.12.23 | 18.12.23 | T2 | 04.01.24 | Star Drive | 10.04.24 | 30.04.24 | 21.05.24 | 25.05.24 |  | 13.12.23 | 30.12.23 | 28.02.24 | usman.mohideen@lntecc.com-08.07.2024-11:21:14
RAJGHAT | Process | Clariflocculator mechanism | LE20M188-P-WS-WT-PR-2202 | LE20M188-P-WS-WT-PR-2202-A | Shivpad | Post-order technically cleared | 490 |  |  |  | 28.12.21 | 28.12.21 | 18.02.22 | 11.03.22 | [8 empty] | 11.03.22 | 17.05.22 | 28.05.22 |  | 12.07.22 | Shivpad | 29.10.22 | 03.03.23 | 03.03.23 | 09.03.23 | 02.04.23 |  |  | 10.09.22 | karthiga@lntecc.com
RAJGHAT | Process | Clariflocculator mechanism | LE20M188-P-WS-WT-PR-2202 | LE20M188-P-WS-WT-PR-2202-B | Triveni | Sent to BU Operations | PR Closed | Order finalized with Shivpad |  |  | 28.12.21 | 28.12.21 | 18.02.22 | 16.04.22 | [8 empty] | 16.04.22 | 17.04.22 | 05.05.22 | [7 empty] | 16.05.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Air Blower | LE20M188-P-WS-WT-PR-2203 | LE20M188-P-WS-WT-PR-2203-A | Everest | Sent to BU Operations | 62 |  |  |  | 28.12.21 | 28.12.21 | 12.12.22 | 16.02.24 | [8 empty] | 16.02.24 | 16.02.24 | 16.02.24 | T1 | 05.03.24 | Everest | 24.05.24 | 03.06.24 |  |  | 17.03.24 |  |  | 04.05.24 | KUMUTHA@lntecc.com-20.07.2024-11:54:46
RAJGHAT | Process | Air Blower | LE20M188-P-WS-WT-PR-2203 | LE20M188-P-WS-WT-PR-2203-B | Kay | Pre-order technically cleared | 570 |  |  |  | 28.12.21 | 28.12.21 | 04.11.22 | 13.12.22 | [8 empty] | 13.12.22 | 10.01.23 | 10.01.23 | T2 | [6 empty] | 12.01.23 |  |  |  | KUMUTHA@lntecc.com-20.07.2024-11:54:46
RAJGHAT | Process | Agitator | LE20M188-P-WS-WT-PR-2204 | LE20M188-P-WS-WT-PR-2204-A | Shivpad | Post-order technically cleared | 545 | PO placed |  |  | 28.12.21 | 28.12.21 | 28.01.22 | 08.03.22 | [8 empty] | 08.03.22 | 14.09.22 | 20.10.22 |  | 21.10.22 | Shivpad | 29.10.22 | 07.01.23 | 07.01.23 | 26.01.23 | 06.02.23 |  |  | 20.12.22 | karthiga@lntecc.com
RAJGHAT | Process | Agitator | LE20M188-P-WS-WT-PR-2204 | LE20M188-P-WS-WT-PR-2204-B | Triveni | Sent to BU Operations | PR Closed | Order finalized with Shivpad |  |  | 28.12.21 | 28.12.21 | 28.01.22 | 05.08.22 | [8 empty] | 05.08.22 | 14.08.22 | 30.08.22 | [7 empty] | 04.09.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Air Blower | LE20M188-P-WS-WT-PR-2203 | LE20M188-P-WS-WT-PR-2204-C | Atlas Copco | Pre-order technically rejected | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 19.01.23 | 18.02.23 | [8 empty] | 18.02.23 | 18.02.23 | 18.02.23 | T3 | [10 empty] | KUMUTHA@lntecc.com-20.07.2024-11:54:46
RAJGHAT | Process | WTP Sluice gates | LE20M188-P-WS-WT-PR-2205 | LE20M188-P-WS-WT-PR-2205-A | Jash | Post-order technically cleared | 108 |  |  |  | 28.12.21 | 28.12.21 | 18.02.22 | 04.11.22 | [8 empty] | 04.11.22 | 04.11.22 | 16.12.22 | T1 | 18.08.23 | Jash | 17.01.24 | 18.04.24 | 18.04.24 | 18.04.24 |  |  |  | 17.10.23 | KUMUTHA@lntecc.com-18.04.2024-17:43:37
RAJGHAT | Process | WTP Sluice gates | LE20M188-P-WS-WT-PR-2205 | LE20M188-P-WS-WT-PR-2205-B | Oriental | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 03.08.22 | 17.10.22 | [8 empty] | 17.10.22 | 04.11.22 | 11.11.22 | T2 | [6 empty] | 16.11.22 |  |  |  | KUMUTHA@lntecc.com-06.04.2024-17:12:54
RAJGHAT | Process | Chlorination system | LE20M188-P-WS-WT-PR-2206 | LE20M188-P-WS-WT-PR-2206-A | Zion | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 06.04.22 | 15.12.22 | [8 empty] | 15.12.22 | 13.01.23 | 15.12.23 | T2 | [6 empty] | 14.01.23 |  |  |  | KUMUTHA@lntecc.com-21.05.2024-12:45:38
RAJGHAT | Process | Chlorination system | LE20M188-P-WS-WT-PR-2206 | LE20M188-P-WS-WT-PR-2206-B | IEC | Post-order technically cleared | 75 |  |  |  | 28.12.21 | 28.12.21 | 06.04.22 | 06.10.23 | [8 empty] | 06.10.23 | 03.11.23 | 06.10.23 | T1 | 02.03.24 | IEC | 28.03.24 | 21.05.24 | 21.05.24 | 21.05.24 |  |  |  | 01.05.24 | KUMUTHA@lntecc.com-21.05.2024-12:45:38
RAJGHAT | Process | Chlorination system | LE20M188-P-WS-WT-PR-2206 | LE20M188-P-WS-WT-PR-2206-C | ME INFRA | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 10.08.22 | 22.11.23 | [8 empty] | 22.11.23 | 22.11.23 | 22.11.23 | T3 | [6 empty] | 22.12.23 |  |  |  | KUMUTHA@lntecc.com-21.05.2024-12:45:38
RAJGHAT | Process | Chlorination system | LE20M188-P-WS-WT-PR-2206 | LE20M188-P-WS-WT-PR-2206-D | Supreme | Regret offer | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 17.02.23 | 20.01.24 | [8 empty] | 20.01.24 |  | 20.01.24 | T4 | [10 empty] | KUMUTHA@lntecc.com-21.05.2024-12:45:38
RAJGHAT | Process | Chlorine Tonner | LE20M188-P-WS-WT-PR-2207 | LE20M188-P-WS-WT-PR-2207-A | Zion | Pre-order technically cleared | 805 |  |  |  | 28.12.21 | 28.12.21 | 06.04.22 | 22.04.22 | [8 empty] | 22.04.22 | 11.05.22 | [8 empty] | 22.05.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Chlorine Tonner | LE20M188-P-WS-WT-PR-2207 | LE20M188-P-WS-WT-PR-2207-B | Toshcon | Pre-order technically cleared | 805 |  |  |  | 28.12.21 | 28.12.21 | 06.04.22 | 22.04.22 | [8 empty] | 22.04.22 | 15.05.22 | [8 empty] | 22.05.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Chlorine Tonner | LE20M188-P-WS-WT-PR-2207 | LE20M188-P-WS-WT-PR-2207-C | IEC | Pre-order technically cleared | 805 |  |  |  | 28.12.21 | 28.12.21 | 06.04.22 | 22.04.22 | [8 empty] | 22.04.22 | 22.04.22 | [8 empty] | 22.05.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Filter media | LE20M188-P-WS-WT-PR-2208 | LE20M188-P-WS-WT-PR-2208-A | Dalton minerals | Awaiting post-offer from vendor | 240 |  |  |  | 28.12.21 | 28.12.21 | 12.10.23 | 02.11.23 | [8 empty] | 02.11.23 | 05.11.23 | 20.11.23 |  | 20.11.23 | Dalton minerals | 24.11.23 | 08.12.23 | [5 empty] | 19.01.24 | karthiga@lntecc.com
RAJGHAT | Process | Filter media | LE20M188-P-WS-WT-PR-2208 | LE20M188-P-WS-WT-PR-2208-B | Om Sai minerals | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 24.10.23 | 07.11.23 | [8 empty] | 07.11.23 | 12.11.23 | 13.11.23 | [7 empty] | 07.12.23 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Filter media | LE20M188-P-WS-WT-PR-2208 | LE20M188-P-WS-WT-PR-2208-C | Maakalyaneshwari | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 12.10.23 | 02.11.23 | [8 empty] | 02.11.23 | 28.11.23 | 28.11.23 | [7 empty] | 02.12.23 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Backwash pump | LE20M188-P-WS-WT-PR-2209 | LE20M188-P-WS-WT-PR-2209-A | WPIL | Post-order technically cleared | 270 |  |  |  | 28.12.21 | 28.12.21 | 30.06.22 | 12.09.22 | [8 empty] | 12.09.22 | 28.09.22 | 13.01.23 |  | 24.06.23 | WPIL | 19.07.23 | 09.10.23 | 09.10.23 | 13.10.23 | 08.11.23 |  |  | 23.08.23 | karthiga@lntecc.com
RAJGHAT | Process | Backwash pump | LE20M188-P-WS-WT-PR-2209 | LE20M188-P-WS-WT-PR-2209-B | KBL | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 30.06.22 | 31.10.22 | [8 empty] | 31.10.22 | 25.11.22 | 25.11.22 | [7 empty] | 30.11.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Backwash pump | LE20M188-P-WS-WT-PR-2209 | LE20M188-P-WS-WT-PR-2209-C | WILO | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 30.06.22 | 12.09.22 | [8 empty] | 12.09.22 | 02.10.22 | 03.10.22 | [7 empty] | 12.10.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Backwash pump | LE20M188-P-WS-WT-PR-2209 | LE20M188-P-WS-WT-PR-2209-D | MBH | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 29.12.22 | 12.01.23 | [8 empty] | 12.01.23 | 04.02.23 | 09.02.23 | [7 empty] | 11.02.23 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Submersible pump | LE20M188-P-WS-WT-PR-2210 | LE20M188-P-WS-WT-PR-2210-A | MBH | Post-order comments issued | 9 |  |  |  | 28.12.21 | 28.12.21 | 29.12.22 | 01.03.23 | [8 empty] | 01.03.23 | 10.03.23 | 10.03.23 | T1 | 09.07.24 | MBH | 18.07.24 | 26.07.24 |  |  | 31.03.23 |  |  |  | KUMUTHA@lntecc.com-26.07.2024-17:44:06
RAJGHAT | Process | Submersible pump | LE20M188-P-WS-WT-PR-2210 | LE20M188-P-WS-WT-PR-2210-B | KSB | Regret offer | PR Closed | Long pending with vendor |  |  | 28.12.21 | 28.12.21 | 22.11.23 | 09.12.23 | [8 empty] | 09.12.23 |  |  | T2 | [10 empty] | KUMUTHA@lntecc.com-26.07.2024-17:44:06
RAJGHAT | Process | Submersible pump | LE20M188-P-WS-WT-PR-2210 | LE20M188-P-WS-WT-PR-2210-C | Aqua Pumps | Regret offer | PR Closed | Long pending with vendor |  |  | 28.12.21 | 28.12.21 | 18.11.23 | 23.11.23 | [8 empty] | 23.11.23 |  |  | T3 | [10 empty] | KUMUTHA@lntecc.com-26.07.2024-17:44:06
RAJGHAT | Process | Electrical hoist | LE20M188-P-WS-WT-PR-2211 | LE20M188-P-WS-WT-PR-2211-A | Japs | Post-order technically cleared | 117 |  |  |  | 28.12.21 | 28.12.21 | 31.12.22 | 15.09.23 | [8 empty] | 15.09.23 | 18.09.23 | 18.09.23 | T1 | 18.09.23 | Japs | 24.03.24 | 09.04.24 | 09.04.24 | 09.04.24 |  |  |  | 17.11.23 | KUMUTHA@lntecc.com-10.04.2024-12:11:22
RAJGHAT | Process | Electrical hoist | LE20M188-P-WS-WT-PR-2211 | LE20M188-P-WS-WT-PR-2211-B | Reva | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 12.01.24 | 13.03.24 | [8 empty] | 13.03.24 | 19.03.24 | 19.03.24 | T2 | [10 empty] | KUMUTHA@lntecc.com-10.04.2024-12:11:22
RAJGHAT | Process | Manual chain pulley block | LE20M188-P-WS-WT-PR-2212 | LE20M188-P-WS-WT-PR-2212-A | Japs | Post-order technically cleared | 117 |  |  |  | 28.12.21 | 28.12.21 | 31.12.22 | 15.09.23 | [8 empty] | 15.09.23 | 21.09.23 | 15.09.23 | T1 | 18.01.24 | Japs | 24.03.24 | 09.04.24 | 09.04.24 | 09.04.24 |  |  |  | 18.03.24 | KUMUTHA@lntecc.com-10.04.2024-12:12:24
RAJGHAT | Process | Manual chain pulley block | LE20M188-P-WS-WT-PR-2212 | LE20M188-P-WS-WT-PR-2212-B | Indef | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 23.01.24 | 03.02.24 | [8 empty] | 03.02.24 | 05.02.24 | 05.02.24 | T3 | [10 empty] | KUMUTHA@lntecc.com-06.04.2024-18:30:52
RAJGHAT | Process | Manual chain pulley block | LE20M188-P-WS-WT-PR-2212 | LE20M188-P-WS-WT-PR-2212-C | Reva | Sent to BU Operations | PR Closed |  |  |  | 19.01.24 | 19.01.24 | 19.02.24 | 13.03.24 | [8 empty] | 19.03.24 | 19.03.24 | 19.03.24 | T2 | [6 empty] | 19.03.24 |  |  |  | KUMUTHA@lntecc.com-06.04.2024-18:30:52
RAJGHAT | Process | Dosing pump | LE20M188-P-WS-WT-PR-2213 | LE20M188-P-WS-WT-PR-2213-A | Positive metering | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 21.12.22 | 19.01.23 | [8 empty] | 19.01.23 | 29.01.23 | 10.02.23 | [7 empty] | 18.02.23 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Dosing pump | LE20M188-P-WS-WT-PR-2213 | LE20M188-P-WS-WT-PR-2213-B | SR metering | Approved by Client | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 26.12.22 | 21.03.23 | [8 empty] | 21.03.23 | 14.04.23 | 07.08.23 |  | 29.10.23 | SR metering | 30.10.23 | 09.12.23 | 09.12.23 | 10.12.23 | 04.01.24 |  |  | 28.12.23 | karthiga@lntecc.com
RAJGHAT | Process | Air compressor | LE20M188-P-WS-WT-PR-2214 | LE20M188-P-WS-WT-PR-2214-A | Indo Air | Pre-order technically cleared | 138 |  |  |  | 28.12.21 | 28.12.21 | 05.01.23 | 26.02.24 | [8 empty] | 26.02.24 | 07.03.24 | [8 empty] | 19.03.24 |  |  |  | KUMUTHA@lntecc.com-19.06.2024-15:12:42
RAJGHAT | Process | Air compressor | LE20M188-P-WS-WT-PR-2214 | LE20M188-P-WS-WT-PR-2214-B | Elgi | Pre-order comments issued | 46 |  |  |  | 28.12.21 | 28.12.21 | 11.09.23 | 25.10.23 | 14.06.24 | 19.06.24 | [6 empty] | 25.10.23 | [13 empty] | KUMUTHA@lntecc.com-19.06.2024-15:12:42
RAJGHAT | Process | Air compressor | LE20M188-P-WS-WT-PR-2214 | LE20M188-P-WS-WT-PR-2214-C | Atlas Copco | Pre-order technically cleared | 149 | Electrical - Pending (Prosol) |  |  | 28.12.21 | 28.12.21 | 26.12.23 | 16.01.24 | [8 empty] | 07.02.24 | 09.02.24 | [8 empty] | 08.03.24 |  |  |  | KUMUTHA@lntecc.com-19.06.2024-15:12:42
RAJGHAT | Process | Nozzles | LE20M188-P-WS-WT-PR-2215 | LE20M188-P-WS-WT-PR-2215-A | VP Engineers | Approved by Client | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 01.03.22 | 06.04.22 | [8 empty] | 06.04.22 | 28.05.22 | 14.06.22 |  | 21.01.23 | VP Engineers | 24.01.23 | 09.08.23 | 10.08.23 | 10.08.23 | 11.08.23 |  |  | 22.03.23 | karthiga@lntecc.com
RAJGHAT | Process | Nozzles | LE20M188-P-WS-WT-PR-2215 | LE20M188-P-WS-WT-PR-2215-B | Guddi plastcons | Sent to BU Operations | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 07.03.22 | 07.04.22 | [8 empty] | 07.04.22 | 04.05.22 | 05.05.22 | [7 empty] | 07.05.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Sampling pump | LE20M188-P-WS-WT-PR-2216 | LE20M188-P-WS-WT-PR-2216-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 950 | site procurement |  |  | 28.12.21 | 28.12.21 | [24 empty] | karthiga@lntecc.com
RAJGHAT | Process | Submersible mixer | LE20M188-P-WS-WT-PR-2217 | LE20M188-P-WS-WT-PR-2217-A | World Water Tech | Post-order technically cleared | 114 |  | 9319094421 | mailto:wwtechennai@gmail.com | 28.12.21 | 28.12.21 | 28.09.23 | 02.11.23 | [8 empty] | 02.11.23 | 23.11.23 | 23.11.23 | T1 | 19.03.24 | World Water Tech | 19.03.24 | 12.04.24 | 12.04.24 | 12.04.24 | 02.12.23 |  |  | 18.05.24 | KUMUTHA@lntecc.com-12.04.2024-15:15:14
RAJGHAT | Process | Submersible mixer | LE20M188-P-WS-WT-PR-2217 | LE20M188-P-WS-WT-PR-2217-B | FFP | Regret offer | PR Closed | No response from the vendor |  |  | 28.12.21 | 28.12.21 | 15.01.23 | 18.01.24 | [8 empty] | 18.01.24 | 18.01.24 | 18.01.24 | T2 | [10 empty] | KUMUTHA@lntecc.com-06.04.2024-12:32:06
RAJGHAT | Process | Dewatering pump | LE20M188-P-WS-WT-PR-2218 | LE20M188-P-WS-WT-PR-2218-A | KSB | Regret offer | PR Closed |  |  |  | 28.12.21 | 28.12.21 | 22.11.23 | 09.12.23 | [8 empty] | 09.12.23 |  |  | T2 | [10 empty] | KUMUTHA@lntecc.com-26.07.2024-17:41:07
RAJGHAT | Process | Dewatering pump | LE20M188-P-WS-WT-PR-2218 | LE20M188-P-WS-WT-PR-2218-B | MBH | Post-order comments issued | 9 |  |  |  |  | 28.12.21 | 22.06.23 | 22.06.23 | [8 empty] | 22.06.23 | 22.06.23 | 22.06.23 | T1 | 12.07.24 | MBH | 18.07.24 | 26.07.24 | [6 empty] | KUMUTHA@lntecc.com-26.07.2024-17:41:07
RAJGHAT | Process | Dewatering pump | LE20M188-P-WS-WT-PR-2218 | LE20M188-P-WS-WT-PR-2218-C | MBH | Pre-order technically cleared | 379 |  |  |  | 15.06.23 | 15.06.23 | 20.06.23 | 22.06.23 | [8 empty] | 22.06.23 | 18.07.23 | [8 empty] | 22.07.23 |  |  |  | KUMUTHA@lntecc.com-27.02.2024-10:57:28
RAJGHAT | Process | Sludge drying bed media | LE20M188-P-WS-WT-PR-2219 | LE20M188-P-WS-WT-PR-2219-A | Maakalyaneshwari | Sent to BU Operations | PR Closed | PO finalized with Dalton. |  |  | 28.12.21 | 28.12.21 | 12.10.23 | 02.11.23 | [8 empty] | 02.11.23 | 18.11.23 | 29.11.23 | [7 empty] | 02.12.23 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Sludge drying bed media | LE20M188-P-WS-WT-PR-2219 | LE20M188-P-WS-WT-PR-2219-B | Dalton minerals | Awaiting post-offer from vendor | 240 | PO Placed |  |  | 28.12.21 | 28.12.21 | 12.10.23 | 02.11.23 | [8 empty] | 02.11.23 | 03.11.23 | 10.11.23 |  | 14.11.23 | Dalton minerals | 24.11.23 | 08.12.23 | [5 empty] | 13.01.24 | karthiga@lntecc.com
RAJGHAT | Process | Sludge drying bed media | LE20M188-P-WS-WT-PR-2219 | LE20M188-P-WS-WT-PR-2219-C | Om Sai minerals | Sent to BU Operations | PR Closed | PO finalized with Dalton. |  |  | 28.12.21 | 28.12.21 | 24.10.23 | 02.11.23 | [8 empty] | 02.11.23 | 14.11.23 | 24.11.23 | [7 empty] | 02.12.23 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Trolley | LE20M188-P-WS-WT-PR-2220 | LE20M188-P-WS-WT-PR-2220-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 950 | site procurement |  |  | 28.12.21 | 28.12.21 | [24 empty] | karthiga@lntecc.com
RAJGHAT | Process | Platform weighing machine | LE20M188-P-WS-WT-PR-2221 | LE20M188-P-WS-WT-PR-2221-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 950 | site procurement |  |  | 28.12.21 | 28.12.21 | [24 empty] | karthiga@lntecc.com
RAJGHAT | Process | Exhaust fan | LE20M188-P-WS-WT-PR-2222 | LE20M188-P-WS-WT-PR-2222-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 950 | site procurement |  |  | 28.12.21 | 28.12.21 | [24 empty] | karthiga@lntecc.com
RAJGHAT | Process | lab equipment | LE20M188-P-WS-WT-PR-2223 | LE20M188-P-WS-WT-PR-2223-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 950 | site procurement |  |  | 28.12.21 | 28.12.21 | [24 empty] | karthiga@lntecc.com
RAJGHAT | Process | Service water pump | LE20M188-P-WS-WT-PR-2225 | LE20M188-P-WS-WT-PR-2225-A | WPIL | Post-order technically cleared | 270 | PO Placed |  |  | 28.12.21 | 28.12.21 | 30.06.22 | 12.09.22 | [8 empty] | 12.09.22 | 01.01.23 | 13.01.23 |  | 01.05.23 | WPIL | 19.07.23 | 09.10.23 | 09.10.23 | 20.10.23 | 08.11.23 |  |  | 30.06.23 | karthiga@lntecc.com
RAJGHAT | Process | Service water pump | LE20M188-P-WS-WT-PR-2225 | LE20M188-P-WS-WT-PR-2225-B | KBL | Sent to BU Operations | PR Closed | Order finalized with WPIL. |  |  | 28.12.21 | 28.12.21 | 30.06.22 | 31.10.22 | [8 empty] | 31.10.22 | 15.11.22 | 19.11.22 | [7 empty] | 30.11.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Service water pump | LE20M188-P-WS-WT-PR-2225 | LE20M188-P-WS-WT-PR-2225-C | WILO | Sent to BU Operations | PR Closed | Order finalized with WPIL. |  |  | 28.12.21 | 28.12.21 | 30.06.22 | 12.09.22 | [8 empty] | 12.09.22 | 25.09.22 | 09.10.22 | [7 empty] | 12.10.22 |  |  |  | karthiga@lntecc.com
RAJGHAT | Process | Service water pump | LE20M188-P-WS-WT-PR-2225 | LE20M188-P-WS-WT-PR-2225-D | MBH | Sent to BU Operations | PR Closed | Order finalized with WPIL. |  |  | 28.12.21 | 28.12.21 | 29.12.22 | 12.01.23 | [8 empty] | 12.01.23 | 21.01.23 | 23.01.23 | [7 empty] | 11.02.23 |  |  |  | karthiga@lntecc.com
RAJGHAT | Mechanical | Surge valve(ACV,ZVV) | LE20M188-M- | LE20M188-M- | JASH | Pre-order technically cleared | 58 |  |  |  |  | 28.04.24 | 04.06.24 | 07.06.24 | [8 empty] | 07.06.24 | 07.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | SLV | LE20M188-M-001 | LE20M188-M-001-A | Sigmaflow | Approved by Client | PR Closed |  |  |  | 22.05.23 | 22.05.23 | 23.05.23 | 25.05.23 | [8 empty] | 26.05.23 | 26.05.23 | 21.06.23 | T1 | 25.07.23 | Sigmaflow | 01.08.23 | 01.08.23 | 04.09.23 | 04.09.23 | 25.09.23 |  |  | 23.09.23 | mallipudi.raju@lntecc.com-18.05.2024-16:16:52
RAJGHAT | Mechanical | FCV | LE20M188-M-014 | LE20M188-M-002-A | Dorot | Pre-order comments issued | 53 |  |  |  |  | 05.06.24 | 05.06.24 | 12.06.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | FCV | LE20M188-M-014 | LE20M188-M-002-B | Telis | Pre-order comments issued | 53 |  |  |  |  | 05.06.24 | 05.06.24 | 12.06.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | FCV | LE20M188-M-014 | LE20M188-M-002-C | AVK | Pre-order comments issued | 45 |  |  |  |  | 20.12.23 | 19.06.24 | 20.06.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | HSC Pumps | LE20M188-M-003 | LE20M188-M-003-A | Flowmore | Pre-order comments issued | 79 |  |  |  | 22.05.23 | 22.05.23 | 10.08.23 | 11.08.23 | 15.05.24 | 17.05.24 | [6 empty] | 20.09.23 | [10 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | HSC Pumps | LE20M188-M-003 | LE20M188-M-003-B | KBL | Sent to BU Operations | 245 | Orientations are not matching |  |  | 22.05.23 | 22.05.23 | 21.07.23 | 22.07.23 | [8 empty] | 03.11.23 | 03.11.23 | 01.12.23 | T3 | [6 empty] | 03.12.23 | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | HSC Pumps | LE20M188-M-003 | LE20M188-M-003-C | KSB | Pre-order technically cleared | 40 | Orientations are not matching. Last reply given on 20 Sep asking to check orientation of the pumps TC Not Given |  |  | 22.05.23 | 22.05.23 | 07.09.23 | 08.09.23 | 25.06.24 | [7 empty] | 25.06.24 | 25.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | HSC Pumps | LE20M188-M-003 | LE20M188-M-003-D | Wilo | Sent to BU Operations | 182 | Inline with technical specifications |  |  | 22.05.23 | 22.05.23 | 18.07.23 | 18.07.23 | [8 empty] | 05.01.24 | 05.01.24 | 07.01.24 | T2 | [6 empty] | 04.02.24 | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | HSC Pumps | LE20M188-M-003 | LE20M188-M-003-E | WPIL | Sent to BU Operations | 178 |  |  |  | 22.05.23 | 22.05.23 | 02.07.23 | 02.07.23 | [8 empty] | 09.01.24 | 09.01.24 | 31.01.24 | T1 | [6 empty] | 08.02.24 | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | HSC Pumps | LE20M188-M-003 | LE20M188-M-003-F | WPIL | Pre-order technically cleared | 97 | IPS 1,2,7,8 |  | cmktg@wpil.co.in |  | 26.03.24 | 08.04.24 | 09.04.24 | 15.04.24 | 16.04.24 | 29.04.24 | 29.04.24 |  |  |  |  | 29.04.24 | 29.04.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | HSC Pumps | LE20M188-M-003 | LE20M188-M-003-G | Wilo | Pre-order technically cleared | 94 | IPS 1,2,7,8- pump efficiency are deviation |  | manikkandan.pr@wilo.com |  | 01.04.24 | 16.04.24 | 16.04.24 | 26.04.24 | 29.04.24 | 02.05.24 | 02.05.24 |  |  |  |  | 02.05.24 | 02.05.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | Dismantling Joints | LE20M188-M-004 | LE20M188-M-004-A | Shiv Industries | Post-order technically cleared | 237 |  |  |  | 22.05.23 | 22.05.23 | 20.11.23 | 21.11.23 | [8 empty] | 22.11.23 | 14.08.23 | 03.10.23 | T1 | 27.10.23 | Shiv Industries | 09.12.23 | 09.12.23 | 11.12.23 | 11.12.23 |  | 31.08.24 | 17.09.24 | 26.12.23 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | Dismantling Joints | LE20M188-M-004 | LE20M188-M-004-B | Precise Engineers | Sent to BU Operations | PR Closed | All specifications are matching |  |  | 22.05.23 | 22.05.23 | 04.09.23 | 04.09.23 | [8 empty] | 16.09.23 | 16.09.23 | 01.10.23 | T2 |  | Precise Engineers | 16.10.23 | 04.09.23 | 20.09.23 | 20.09.23 |  |  |  |  | mallipudi.raju@lntecc.com-18.05.2024-16:16:52
RAJGHAT | Mechanical | Expansion Bellow | LE20M188-M-005 | LE20M188-M-005-A | Shiv Industries | Post-order technically cleared | 237 |  |  |  | 22.05.23 | 22.05.23 | 30.09.23 | 02.10.23 | [8 empty] | 02.10.23 | 02.10.23 | 03.10.23 | T1 | 04.10.23 | Shiv Industries | 09.12.23 | 09.12.23 | 11.12.23 | 11.12.23 |  | 31.08.24 | 17.09.24 | 03.12.23 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | BFV | LE20M188-M-006 | LE20M188-M-006-A | Durga | Approved by Client | PR Closed |  |  |  | 22.05.23 | 22.05.23 | 29.07.23 | 30.07.23 | [8 empty] | 24.08.23 | 24.08.23 | 29.08.23 | T1 | 29.08.23 | Durga | 15.08.23 | 22.08.23 | 24.08.23 | 24.08.23 | 25.09.23 |  |  | 28.10.23 | mallipudi.raju@lntecc.com-18.05.2024-16:16:52
RAJGHAT | Mechanical | EOT Cranes | LE20M188-M-007 | LE20M188-M-007-A | JAPS | Pre-order technically cleared | 304 |  |  |  | 22.05.23 | 22.05.23 | 25.09.23 | 26.09.23 | [8 empty] | 05.10.23 | 05.10.23 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | EOT Cranes | LE20M188-M-007 | LE20M188-M-007-B | Reva | Pre-order technically cleared | 291 |  |  |  | 22.05.23 | 22.05.23 | 10.10.23 | 11.10.23 | [8 empty] | 18.10.23 | 18.10.23 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | EOT Cranes | LE20M188-M-007 | LE20M188-M-007-C | INDEF | Pre-order technically cleared | 192 |  |  |  | 22.05.23 | 22.05.23 | 23.01.24 | 25.01.24 | [8 empty] | 25.01.24 | 25.01.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | AV | LE20M188-M-008 | LE20M188-M-008-A | VAG | Approved by Client | PR Closed |  |  |  | 22.05.23 | 22.05.23 | 18.08.23 | 19.08.23 | [8 empty] | 04.09.23 | 04.05.23 | 21.06.23 | T1 | 13.07.23 | VAG | 18.10.23 | 18.10.23 | 26.10.23 | 30.10.23 | 17.11.23 |  |  | 11.09.23 | mallipudi.raju@lntecc.com-18.05.2024-16:16:52
RAJGHAT | Mechanical | AV,SV,BFV,NRV | LE20M188-M-009 | LE20M188-M-009-A | R&D | Post-order technically cleared | 200 |  |  |  | 22.05.23 | 22.05.23 | 25.10.23 | 19.12.23 | [8 empty] | 17.01.24 | 17.01.24 | 17.01.24 | T2 | 17.01.24 | R&D | 10.12.23 | 26.11.23 | 02.12.23 | 02.12.23 |  | 31.08.24 | 17.09.24 | 17.03.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | WTP and IBPS valve | LE20M188-M-010 | LE20M188-M-010-A | Durga | Post-order technically cleared | 238 |  |  |  | 22.05.23 | 22.05.23 | 11.10.23 | 11.10.23 | [8 empty] | 08.11.23 | 09.11.23 | 10.11.23 | T1 | 01.12.23 | Durga | 07.12.23 | 07.12.23 | 07.12.23 | 07.12.23 | 10.12.23 | 31.08.24 | 17.09.24 | 30.01.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | WTP pipe line VALVES | LE20M188-M-011 | LE20M188-M-011-A | AVK | Post-order technically cleared | 155 |  |  |  | 22.05.23 | 22.05.23 | 25.12.23 | 02.01.24 | [8 empty] | 12.01.24 | 21.01.24 | 01.02.24 | T2 | 02.02.24 | AVK | 26.02.24 | 27.02.24 | 28.02.24 | 28.02.24 | 02.03.24 | 31.08.24 | 17.09.24 | 02.04.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | VT pumps | LE20M188-M-012 | LE20M188-M-012-A | Jyothi | Pre-order comments issued | 101 |  |  |  |  | 20.12.23 | 22.04.24 | 25.04.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | VT pumps | LE20M188-M-012 | LE20M188-M-012-B | Flow More | Pre-order comments issued | 47 |  |  |  |  | 20.12.23 | 14.06.24 | 14.06.24 | 18.06.24 | 18.06.24 | [17 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | VT pumps | LE20M188-M-012 | LE20M188-M-012-C | WPIL | Pre-order comments issued | 44 |  |  |  |  | 20.12.23 | 20.06.24 | 21.06.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | Exhaust Fan | LE20M188-M-013 | LE20M188-M-013-A | Nadi | Pre-order technically cleared | 39 |  |  |  |  | 27.12.23 | 07.06.24 | 07.06.24 | [8 empty] | 26.06.24 | 26.06.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | Exhaust Fan | LE20M188-M-013 | LE20M188-M-013-B | Power Vent | Pre-order comments issued | 53 |  |  |  |  | 27.12.23 | 12.06.24 | 12.06.24 | [19 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Mechanical | Surge valve(ACV,ZVV) | LE20M188-M-14 | LE20M188-M-B | Sigma Flow | Pre-order technically cleared | 93 |  |  |  |  | 28.04.24 | 02.05.24 | 03.05.24 | [8 empty] | 03.05.24 | 03.05.24 | [9 empty] | 31.08.24 | 17.09.24 | 16.11.24 | rallabandi.bharadwaj@lntecc.com-03.07.2024-17:19:11
RAJGHAT | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M188-I-001 | LE20M188-I-001-A | HGURU | Approved by Client | PR Closed |  |  |  | 6.12.23 | 11.01.23 | 20.01.23 | 31.01.23 | [8 empty] | 19.02.23 | 03.03.23 | 21.03.23 |  | 30.03.23 | HGURU | 05.04.23 | 08.06.23 | 01.12.23 | 06.12.23 | 06.12.23 |  |  | 29.05.23 | sooryaprakash.t@lntecc.com-17.02.2024-12:33:53
RAJGHAT | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M188-I-001 | LE20M188-I-001-B | SIAS | Pre-order technically cleared | 502 |  |  |  | 6.12.23 | 05.01.23 | 20.01.23 | 08.02.23 | [8 empty] | 19.02.23 | 23.02.23 | 21.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE20M188-I-001 | LE20M188-I-001-C | WIKA | Pre-order technically cleared | 502 |  |  |  | 6.12.23 | 08.07.22 | 20.01.23 | 22.01.23 | [8 empty] | 19.02.23 | 18.03.23 | 21.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Pressure Switch | LE20M188-I-002 | LE20M188-I-002-A | HGURU | Approved by Client | PR Closed |  |  |  | 6.12.23 | 05.12.22 | 20.01.23 | 31.01.23 | [8 empty] | 19.02.23 | 25.02.23 | 21.03.23 |  | 27.03.23 | HGURU | 05.04.23 | 02.08.23 | 17.11.23 | 06.12.23 | 06.12.23 |  |  | 26.05.23 | sooryaprakash.t@lntecc.com-17.02.2024-12:33:53
RAJGHAT | Instrumentation | Pressure Switch | LE20M188-I-002 | LE20M188-I-002-B | SIAS | Pre-order technically cleared | 502 |  |  |  | 6.12.23 | 22.10.22 | 20.01.23 | 12.02.23 | [8 empty] | 19.02.23 | 14.03.23 | 21.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Pressure Switch | LE20M188-I-002 | LE20M188-I-002-C | WIKA | Pre-order technically cleared | 502 |  |  |  | 6.12.23 | 02.05.22 | 20.01.23 | 02.02.23 | [8 empty] | 19.02.23 | 20.03.23 | 21.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Pressure transmitter | LE20M188-I-003 | LE20M188-I-003-A | ABB | Pre-order technically cleared | 502 |  |  |  | 20.04.23 | 28.10.22 | 20.01.23 | 25.01.23 | [8 empty] | 19.02.23 | 12.03.23 | 21.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Pressure transmitter | LE20M188-I-003 | LE20M188-I-003-B | E&H | Pre-order technically cleared | 502 |  |  |  | 20.04.23 | 29.11.22 | 20.01.23 | 03.02.23 | [8 empty] | 19.02.23 | 26.02.23 | 21.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Pressure transmitter | LE20M188-I-003 | LE20M188-I-003-C | HGuru | Pre-order technically cleared | 502 |  |  |  | 20.04.23 | 23.12.22 | 20.01.23 | 27.01.23 | [8 empty] | 19.02.23 | 28.02.23 | 21.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Float & Board Level gauge | LE20M188-I-004 | LE20M188-I-004-A | Pune Techtrol | Pre-order technically cleared | 549 |  |  |  | 22.11.23 | 07.05.22 | 16.01.23 | 16.01.23 | [8 empty] | 02.02.23 | 02.02.23 | 02.02.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Float & Board Level gauge | LE20M188-I-004 | LE20M188-I-004-B | SBEM | Pre-order technically cleared | 549 |  |  |  | 22.11.23 | 03.09.22 | 16.01.23 | 22.01.23 | [8 empty] | 02.02.23 | 02.02.23 | 02.02.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | level switch - Conductivity type | LE20M188-I-005 | LE20M188-I-005-A | Pune Techtrol | Pre-order technically cleared | 549 |  |  |  | 22.11.23 | 15.11.22 | 16.01.23 | 18.01.23 | [8 empty] | 02.02.23 | 02.02.23 | 02.02.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | level switch - Conductivity type | LE20M188-I-005 | LE20M188-I-005-B | SBEM | Pre-order technically cleared | 549 |  |  |  | 22.11.23 | 18.05.22 | 16.01.23 | 20.01.23 | [8 empty] | 02.02.23 | 02.02.23 | 02.02.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Ultrasonic level Transmitter | LE20M188-I-006 | LE20M188-I-006-A | E&H | Pre-order technically cleared | 521 |  |  |  | 22.11.23 | 18.05.22 | 01.02.23 | 17.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Ultrasonic level Transmitter | LE20M188-I-006 | LE20M188-I-006-B | Electronet | Pre-order technically cleared | 521 |  |  |  | 22.11.23 | 08.12.22 | 01.02.23 | 12.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Radar Level Transmitter | LE20M188-I-007 | LE20M188-I-007-A | siemens | Awaiting pre-offer from vendor | 256 |  |  |  | 22.11.23 | 22.11.23
RAJGHAT | Instrumentation | Radar Level Transmitter | LE20M188-I-007 | LE20M188-I-007-B | Electronet | Awaiting pre-offer from vendor | 256 |  |  |  | 22.11.23 | 22.11.23
RAJGHAT | Instrumentation | Radar Level Transmitter | LE20M188-I-007 | LE20M188-I-007-C | Forbes marshall | Awaiting pre-offer from vendor | 256 |  |  |  | 22.11.23 | 22.11.23
RAJGHAT | Instrumentation | Loss of head transmitter | LE20M188-I-008 | LE20M188-I-008-A | ABB | Pre-order technically cleared | 489 |  |  |  | 20.04.23 | 16.01.23 | 31.01.23 | 01.02.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Loss of head transmitter | LE20M188-I-008 | LE20M188-I-008-B | E&H | Approved by Client | PR Closed |  |  |  | 20.04.23 | 26.01.23 | 31.01.23 | 28.02.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 |  | 07.04.23 | E&H | 18.04.23 | 18.04.23 | 18.04.23 | 20.04.23 | 20.04.23 |  |  | 06.06.23 | sooryaprakash.t@lntecc.com-17.02.2024-12:33:54
RAJGHAT | Instrumentation | Loss of head transmitter | LE20M188-I-008 | LE20M188-I-008-C | Honeywell | Pre-order technically cleared | 489 |  |  |  | 20.04.23 | 13.11.22 | 31.01.23 | 13.02.23 | [8 empty] | 03.04.23 | 03.04.23 | 03.04.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Rate for flow transmitter | LE20M188-I-009 | LE20M188-I-009-A | E&H | Pre-order technically cleared | 521 |  |  |  | 22.11.23 | 26.10.22 | 01.02.23 | 06.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Rate for flow transmitter | LE20M188-I-009 | LE20M188-I-009-B | Electronet | Pre-order technically cleared | 521 |  |  |  | 22.11.23 | 18.07.22 | 01.02.23 | 17.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Bypass Rotameter | LE20M188-I-010 | LE20M188-I-010-A | Eureka | Sent to BU Operations | 72 |  |  |  | 22.11.23 | 20.05.24 | 20.05.24 | 24.05.24 | 24.05.24 | [7 empty] | 24.05.24 | 24.05.24 | 24.05.24 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-24.05.2024-16:06:13
RAJGHAT | Instrumentation | Bypass Rotameter | LE20M188-I-010 | LE20M188-I-010-B | Scientific devices | Sent to BU Operations | 72 |  |  |  | 22.11.23 | 20.05.24 | 22.05.24 | 24.05.24 | [8 empty] | 24.05.24 | 24.05.24 | 24.05.24 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-24.05.2024-16:06:13
RAJGHAT | Instrumentation | Electromagnectic flow meter | LE20M188-I-011 | LE20M188-I-011-A | E&H | Pre-order technically cleared | 521 |  |  |  | 22.11.23 | 14.01.23 | 23.02.23 | 24.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Electromagnectic flow meter | LE20M188-I-011 | LE20M188-I-011-B | Khrone | Pre-order technically cleared | 521 |  |  |  | 22.11.23 | 01.01.23 | 23.02.23 | 24.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Electromagnectic flow meter | LE20M188-I-011 | LE20M188-I-011-C | siemens | Pre-order technically cleared | 521 |  |  |  | 22.11.23 | 26.01.23 | 23.02.23 | 25.02.23 | [8 empty] | 02.03.23 | 02.03.23 | 02.03.23 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M188-I-012 | LE20M188-I-012-A | E&H | Awaiting pre-offer from vendor | 256 |  |  |  | 22.11.23 | 22.11.23
RAJGHAT | Instrumentation | Ultrasonic type Open channel flow transmitter | LE20M188-I-012 | LE20M188-I-012-B | Electronet | Awaiting pre-offer from vendor | 256 |  |  |  | 22.11.23 | 22.11.23
RAJGHAT | Instrumentation | VTC Flow meter | LE20M188-I-013 | LE20M188-I-013-A | Zenner | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | VTC Flow meter | LE20M188-I-013 | LE20M188-I-013-B | Kranthi water meter | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | pH Meter | LE20M188-I-014 | LE20M188-I-014-A | Emerson | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | pH Meter | LE20M188-I-014 | LE20M188-I-014-B | HACH | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | pH Meter | LE20M188-I-014 | LE20M188-I-014-C | ABB | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | pH Meter | LE20M188-I-014 | LE20M188-I-014-D | E&H | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | Turbidity meter | LE20M188-I-015 | LE20M188-I-015-A | Emerson | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | Turbidity meter | LE20M188-I-015 | LE20M188-I-015-B | HACH | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | Turbidity meter | LE20M188-I-015 | LE20M188-I-015-C | ABB | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | Turbidity meter | LE20M188-I-015 | LE20M188-I-015-D | E&H | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | Residual Chlorine Analyzer | LE20M188-I-016 | LE20M188-I-016-A | Emerson | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | Residual Chlorine Analyzer | LE20M188-I-016 | LE20M188-I-016-B | HACH | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | Residual Chlorine Analyzer | LE20M188-I-016 | LE20M188-I-016-C | ABB | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | Residual Chlorine Analyzer | LE20M188-I-016 | LE20M188-I-016-D | E&H | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M188-I-017 | LE20M188-I-017-A | Siemens | Enquiry yet to float | NA | Awaiting for Hydraulics - IPS finalization |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-04.06.2024-10:35:51
RAJGHAT | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M188-I-017 | LE20M188-I-017-B | Schneider | Enquiry yet to float | NA | Awaiting for Hydraulics - IPS finalization |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-04.06.2024-10:35:51
RAJGHAT | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M188-I-017 | LE20M188-I-017-C | Mitsubishi | Enquiry yet to float | NA | Awaiting for Hydraulics - IPS finalization |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-04.06.2024-10:35:51
RAJGHAT | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE20M188-I-017 | LE20M188-I-017-D | Honeywell | Enquiry yet to float | NA | Awaiting for Hydraulics - IPS finalization |  |  | 19.11.23 | [25 empty] | sooryaprakash.t@lntecc.com-04.06.2024-10:35:51
RAJGHAT | Instrumentation | instrumentation Control & signal Cables | LE20M188-I-018 | LE20M188-I-018-A | Axelon | Sent to BU Operations | 564 |  |  |  | 22.11.23 | 20.05.22 | 21.12.22 | 22.12.22 | [8 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T1 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:53:42
RAJGHAT | Instrumentation | instrumentation Control & signal Cables | LE20M188-I-018 | LE20M188-I-018-B | Cords | Pre-order technically cleared | 160 |  |  |  | 22.11.23 | 22.11.23 | 28.12.23 | 20.01.24 | [8 empty] | 27.01.24 | 30.01.24 | 26.02.24 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | instrumentation Control & signal Cables | LE20M188-I-018 | LE20M188-I-018-C | Delton | Pre-order technically cleared | 160 |  |  |  | 22.11.23 | 22.11.23 | 28.12.23 | 01.01.24 | [8 empty] | 27.01.24 | 15.02.24 | 26.02.24 | [11 empty] | sooryaprakash.t@lntecc.com-17.02.2024-12:27:45
RAJGHAT | Instrumentation | instrumentation Control & signal Cables | LE20M188-I-018 | LE20M188-I-018-D | Thermo | Sent to BU Operations | 564 |  |  |  | 22.11.23 | 30.10.22 | 21.12.22 | 12.01.23 | [8 empty] | 18.01.23 | 18.01.23 | 18.01.23 | T2 | [10 empty] | sooryaprakash.t@lntecc.com-10.07.2024-14:53:42
RAJGHAT | Instrumentation | UPS | LE20M188-I-019 | LE20M188-I-019-A | Vertiv | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | UPS | LE20M188-I-019 | LE20M188-I-019-B | Hirel | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | EPABX System | LE20M188-I-020 | LE20M188-I-020-A | Vendor Name yet to provide | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | EPABX System | LE20M188-I-020 | LE20M188-I-020-B | Vendor Name yet to provide | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Instrumentation | EPABX System | LE20M188-I-020 | LE20M188-I-020-C | Vendor Name yet to provide | Awaiting pre-offer from vendor | 259 |  |  |  | 19.11.23 | 19.11.23
RAJGHAT | Electrical | Transformer | LE20M188-E-001 | LE20M188-E-001-A | Uttam Bharat | Pre-order comments issued | 561 |  |  |  | 16.11.22 | 16.11.22 | 16.12.22 | 21.01.23 | [8 empty] | 06.12.22 | 16.12.22
RAJGHAT | Electrical | Transformer | LE20M188-E-001 | LE20M188-E-001-B | TBEA | Pre-order comments issued | 559 |  |  |  | 16.11.22 | 16.11.22 | 20.12.22 | 23.01.23 | [8 empty] | 10.12.22 | 20.12.22
RAJGHAT | Electrical | Transformer | LE20M188-E-001 | LE20M188-E-001-C | Vardhman | Post-order comments issued | 221 |  |  |  | 16.11.22 | 16.11.22 | 18.01.23 | 02.02.23 | [8 empty] | 10.01.23 | 18.01.23 | 14.06.23 |  | 28.09.23 | Vardhman | 11.12.23 | 27.12.23 | [5 empty] | 27.11.23
RAJGHAT | Electrical | LT Panel | LE20M188-E-002 | LE20M188-E-002-A | BCH | Pre-order technically cleared | 520 |  |  |  | 16.11.22 | 16.11.22 | 30.12.22 | 25.01.23 | [8 empty] | 27.01.23 | 03.03.23
RAJGHAT | Electrical | LT Panel | LE20M188-E-002 | LE20M188-E-002-B | Universal | Pre-order comments issued | 415 |  |  |  | 16.11.22 | 16.11.22 | 01.02.23 | 01.03.23 | [8 empty] | 13.04.23 | 16.06.23
RAJGHAT | Electrical | LT Panel | LE20M188-E-002 | LE20M188-E-002-C | SRCS | Post-order technically cleared | 229 |  |  |  | 16.11.22 | 16.11.22 | 24.05.23 | 29.05.23 | [8 empty] | 12.06.23 | 26.06.23 | 20.09.23 |  | 09.11.23 | SRCS | 01.11.23 | 03.11.23 | 15.12.23 | 19.12.23 |  |  |  | 08.01.24
RAJGHAT | Electrical | HT Panel | LE20M188-E-003 | LE20M188-E-003-A | UPE | Pre-order comments issued | 558 |  |  |  | 16.11.22 | 16.11.22 | 30.12.22 | 24.01.23 | [8 empty] | 27.12.22 | 30.12.22
RAJGHAT | Electrical | HT Panel | LE20M188-E-003 | LE20M188-E-003-B | HTS | Pre-order comments issued | 552 |  |  |  | 16.11.22 | 16.11.22 | 02.01.23 | 30.01.23 | [8 empty] | 22.12.22 | 02.01.23
RAJGHAT | Electrical | HT Panel | LE20M188-E-003 | LE20M188-E-003-C | Popular | Pre-order comments issued | 387 |  |  |  | 16.11.22 | 16.11.22 | 27.06.23 | 11.07.23 | [8 empty] | 13.07.23 | 14.07.23
RAJGHAT | Electrical | Lighting Fixtures | LE20M188-E-004 | LE20M188-E-004-A | Vivid | Pre-order technically cleared | 551 |  |  |  | 16.11.22 | 16.11.22 | 03.01.23 | 31.01.23 | [8 empty] | 26.12.22 | 03.01.23
RAJGHAT | Electrical | LPBS & LDB | LE20M188-E-005 | LE20M188-E-005-A | Vendor Name yet to provide | Sent to BU Operations | 597 | Pre-order offer evaluation is not required |  |  | 16.11.22 | 16.11.22 | 04.12.22 | 05.12.22 | [8 empty] | 07.12.22 | 14.12.22 | 14.12.22 | [7 empty] | 16.12.22
RAJGHAT | Electrical | AAAC Conductor | LE20M188-E-006 | LE20M188-E-006-A | Vendor Name yet to provide | Sent to BU Operations | 597 | Pre-order offer evaluation is not required |  |  | 16.11.22 | 16.11.22 | 11.12.22 | 11.12.22 | [8 empty] | 13.12.22 | 13.12.22 | 14.12.22 | [7 empty] | 16.12.22
RAJGHAT | Electrical | Control & Relay Panel | LE20M188-E-007 | LE20M188-E-007-A | Vendor Name yet to provide | Sent to BU Operations | 597 | Pre-order offer evaluation is not required |  |  | 16.11.22 | 16.11.22 | 25.11.22 | 30.11.22 | [8 empty] | 03.12.22 | 08.12.22 | 09.12.22 | [7 empty] | 16.12.22
RAJGHAT | Electrical | CT & PT | LE20M188-E-008 | LE20M188-E-008-A | Vendor Name yet to provide | Sent to BU Operations | 597 | Pre-order offer evaluation is not required |  |  | 16.11.22 | 16.11.22 | 29.11.22 | 14.12.22 | [8 empty] | 15.12.22 | 15.12.22 | 15.12.22 | [7 empty] | 16.12.22
RAJGHAT | Electrical | Swicthyard Structures | LE20M188-E-009 | LE20M188-E-009-A | Vendor Name yet to provide | Sent to BU Operations | 597 | Pre-order offer evaluation is not required |  |  | 16.11.22 | 16.11.22 | 30.11.22 | 01.12.22 | [8 empty] | 13.12.22 | 14.12.22 | 15.12.22 | [7 empty] | 16.12.22
RAJGHAT | Electrical | HT/ LT Power & Control Cables | LE20M188-E-010 | LE20M188-E-010-A | Vendor Name yet to provide | Pre-order technically cleared | 597 |  |  |  | 16.11.22 | 16.11.22 | 26.11.22 | 27.11.22 | [8 empty] | 08.12.22 | 13.12.22 | [8 empty] | 16.12.22
RAJGHAT | Electrical | Cable Trays & Its accessories | LE20M188-E-011 | LE20M188-E-011-A | Vendor Name yet to provide | Pre-order technically cleared | 597 |  |  |  | 16.11.22 | 16.11.22 | 01.12.22 | 10.12.22 | [8 empty] | 14.12.22 | 14.12.22 | [8 empty] | 16.12.22
RAJGHAT | Electrical | Earthing & Lightning Materials | LE20M188-E-012 | LE20M188-E-012-A | Vendor Name yet to provide | Pre-order technically cleared | 597 |  |  |  | 16.11.22 | 16.11.22 | 27.11.22 | 30.11.22 | [8 empty] | 05.12.22 | 08.12.22 | [8 empty] | 16.12.22
RAJGHAT | Electrical | Galns & Lugs | LE20M188-E-013 | LE20M188-E-013-A | Vendor Name yet to provide | Pre-order technically cleared | 597 |  |  |  | 16.11.22 | 16.11.22 | 17.11.22 | 29.11.22 | [8 empty] | 08.12.22 | 12.12.22 | [8 empty] | 16.12.22
RAJGHAT | Electrical | Safety Accessories | LE20M188-E-014 | LE20M188-E-014-A | Vendor Name yet to provide | Pre-order technically cleared | 597 |  |  |  | 16.11.22 | 16.11.22 | 12.12.22 | 12.12.22 | [8 empty] | 12.12.22 | 15.12.22 | [8 empty] | 16.12.22
Sahibganj | Mechanical | HSC Pumps | LE23M219-M-WS-RW-PR-1059 | LE23M219-M-WS-RW-PR-1059-A | KBL | Sent to BU Operations | 36 | weight of pumps should be reduced |  |  | 22.01.24 | 22.01.24 | 31.01.24 | 20.02.24 | 26.04.24 | 26.04.24 | [6 empty] | 26.04.24 | 26.04.24 | 29.06.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | HSC Pumps | LE23M219-M-WS-RW-PR-1059 | LE23M219-M-WS-RW-PR-1059-B | WPIL | Sent to BU Operations | 36 |  |  |  | 22.01.24 | 22.01.24 | 31.01.24 | 05.02.24 | 08.02.24 | 13.02.24 | [6 empty] | 13.02.24 | 08.02.24 | 29.06.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | HSC Pumps | LE23M219-M-WS-RW-PR-1059 | LE23M219-M-WS-RW-PR-1059-C | WILO | Sent to BU Operations | 36 | GSR -A pumps are cleared |  |  | 22.01.24 | 22.01.24 | 25.03.24 | 28.03.24 | 26.04.24 | 26.04.24 | [6 empty] | 26.04.24 | 26.04.24 | 29.06.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | Pipe line valves(AV,SV,SCOUR, ) | LE23M219-M-WS-RW-PR-1060 | LE23M219-M-WS-RW-PR-1060-A | KBL | Sent to BU Operations | 37 | Scour ,sluice valve |  | Karthikeyan.R@kbl.co.in | 23.01.24 | 23.01.24 | 29.04.24 | 04.05.24 | 20.05.24 | 20.05.24 | [6 empty] | 20.05.24 | 20.05.24 | 28.06.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | Pipe line valves(AV,SV,SCOUR, ) | LE23M219-M-WS-RW-PR-1060 | LE23M219-M-WS-RW-PR-1060-B | Sigma Flow | Sent to BU Operations | 37 |  |  | jagadesh@sigmaflow.in |  | 12.02.24 | 24.03.24 | 25.04.24 | 09.05.24 | 15.05.24 | [6 empty] | 15.05.24 | 09.05.24 | 28.06.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | Pipe line valves(AV,SV,SCOUR, ) | LE23M219-M-WS-RW-PR-1060 | LE23M219-M-WS-RW-PR-1060-C | Magwene | Sent to BU Operations | 37 | Subjected to client approval |  |  | 12.02.24 | 12.02.24 | 28.02.24 | 12.03.24 | 24.04.24 | 03.05.24 | [6 empty] | 03.05.24 | 24.04.24 | 28.06.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | Pipe line valves(AV,SV,SCOUR, ) | LE23M219-M-WS-RW-PR-1060 | LE23M219-M-WS-RW-PR-1060-D | AVK | Sent to BU Operations | 37 |  |  | subhash@avkindia.com |  | 23.01.24 | 01.04.24 | 06.04.24 | 09.04.24 | 16.04.24 | 04.05.24 | 06.05.24 | 09.05.24 | 17.05.24 |  |  | 17.05.24 | 09.05.24 | 28.06.24 | T1 | [7 empty] | 31.07.24 | 17.08.24 | 16.10.24 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | ACV &ZVV | LE23M219-M-WS-RW-PR-1061 | LE23M219-M-WS-RW-PR-1061-A | KBL | Regret offer | PR Closed |  |  |  | 23.01.24 | 23.01.24 | [21 empty] | 31.10.24 | 17.11.24 | 16.01.25 | rallabandi.bharadwaj@lntecc.com-01.07.2024-16:24:51
Sahibganj | Mechanical | Pipe line valves(ACV & ZVV ) | LE23M219-M-WS-RW-PR-1061 | LE23M219-M-WS-RW-PR-1061-B | Sigma Flow | Sent to BU Operations | 37 |  |  | jagadesh@sigmaflow.in |  | 12.02.24 | 24.03.24 | 25.04.24 | 09.05.24 | 15.05.24 | [6 empty] | 15.05.24 | 09.05.24 | 28.06.24 | T1 | [7 empty] | 31.10.24 | 17.11.24 | 16.01.25 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | ACV &ZVV | LE23M219-M-WS-RW-PR-1061 | LE23M219-M-WS-RW-PR-1061-C | Magwene | Regret offer | PR Closed |  |  |  | 12.02.24 | 12.02.24 | 28.02.24 | 12.03.24 | [19 empty] | 31.10.24 | 17.11.24 | 16.01.25 | rallabandi.bharadwaj@lntecc.com-01.07.2024-16:24:51
Sahibganj | Mechanical | ACV &ZVV | LE23M219-M-WS-RW-PR-1061 | LE23M219-M-WS-RW-PR-1061-D | JASH | Sent to BU Operations | 37 |  |  | neeraj@jashindia.com |  | 06.05.24 | 21.05.24 | 23.05.24 | [8 empty] | 23.05.24 | 21.05.24 | 28.06.24 | T1 | [7 empty] | 31.10.24 | 17.11.24 | 16.01.25 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Mechanical | ACV &ZVV | LE23M219-M-WS-RW-PR-1061 | LE23M219-M-WS-RW-PR-1061-E | DURGA | Sent to BU Operations | 37 |  |  | chennai@dvpl.co.in |  | 20.05.24 | 27.05.24 | 30.05.24 | [8 empty] | 30.05.24 | 27.05.24 | 28.06.24 | T1 | [7 empty] | 31.10.24 | 17.11.24 | 16.01.25 | rohit.shaw@lntecc.com-06.07.2024-17:34:05
Sahibganj | Instrumentation | Bourdon/Diaphragm Type Pressure Gauge / Compound Pressure gauge | LE22M219-I-WS-WT-PR-5101 | LE22M219-I-WS-WT-PR-5101-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Pressure transmitter | LE22M219-I-WS-WT-PR-5102 | LE22M219-I-WS-WT-PR-5102-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Float & Board Level gauge | LE22M219-I-WS-WT-PR-5103 | LE22M219-I-WS-WT-PR-5103-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | level switch - Conductivity type | LE22M219-I-WS-WT-PR-5104 | LE22M219-I-WS-WT-PR-5104-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Ultrasonic level Transmitter | LE22M219-I-WS-WT-PR-5105 | LE22M219-I-WS-WT-PR-5105-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Radar Level Transmitter | LE22M219-I-WS-WT-PR-5106 | LE22M219-I-WS-WT-PR-5106-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Rate for flow transmitter | LE22M219-I-WS-WT-PR-5108 | LE22M219-I-WS-WT-PR-5108-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Bypass Rotameter | LE22M219-I-WS-WT-PR-5109 | LE22M219-I-WS-WT-PR-5109-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Electromagnectic flow meter | LE22M219-I-WS-WT-PR-5110 | LE22M219-I-WS-WT-PR-5110-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Ultrasonic type Open channel flow transmitter | LE22M219-I-WS-WT-PR-5111 | LE22M219-I-WS-WT-PR-5111-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | battery operated Flow meter | LE22M219-I-WS-WT-PR-5112 | LE22M219-I-WS-WT-PR-5112-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | pH Meter | LE22M219-I-WS-WT-PR-5113 | LE22M219-I-WS-WT-PR-5113-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Turbidity meter | LE22M219-I-WS-WT-PR-5114 | LE22M219-I-WS-WT-PR-5114-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Residual Chlorine Analyzer | LE22M219-I-WS-WT-PR-5115 | LE22M219-I-WS-WT-PR-5115-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | Conductivity Analyzer | LE22M219-I-WS-WT-PR-5116 | LE22M219-I-WS-WT-PR-5116-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | ICP, PLC panel, RTU & SCADA Accessories | LE22M219-I-WS-WT-PR-5117 | LE22M219-I-WS-WT-PR-5117-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | instrumentation Control & signal Cables | LE22M219-I-WS-WT-PR-5118 | LE22M219-I-WS-WT-PR-5118-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Instrumentation | UPS | LE22M219-I-WS-WT-PR-5119 | LE22M219-I-WS-WT-PR-5119-A | Vendor Name yet to provide | Enquiry yet to float | NA | [26 empty] | 31.03.25 | 17.04.25 | 16.06.25 | sooryaprakash.t@lntecc.com-04.07.2024-15:55:57
Sahibganj | Electrical | CTPT Unit | LE23M219-E-WS-WT-PR-4001 | LE23M219-E-WS-WT-PR-4001-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Poles & conductors | LE23M219-E-WS-WT-PR-4001A | LE23M219-E-WS-WT-PR-4001A-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Transformer | LE23M219-E-WS-WT-PR-4002 | LE23M219-E-WS-WT-PR-4002-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | DG Set | LE23M219-E-WS-WT-PR-4003 | LE23M219-E-WS-WT-PR-4003-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | HT Panel | LE23M219-E-WS-WT-PR-4004 | LE23M219-E-WS-WT-PR-4004-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | HT Fixed Capacitor | LE23M219-E-WS-WT-PR-4005 | LE23M219-E-WS-WT-PR-4005-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | HT Soft Starter | LE23M219-E-WS-WT-PR-4006 | LE23M219-E-WS-WT-PR-4006-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | HT VFD | LE23M219-E-WS-WT-PR-4007 | LE23M219-E-WS-WT-PR-4007-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | LT panels | LE23M219-E-WS-WT-PR-4008 | LE23M219-E-WS-WT-PR-4008-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | DCDB | LE23M219-E-WS-WT-PR-4009 | LE23M219-E-WS-WT-PR-4009-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Bus Duct | LE23M219-E-WS-WT-PR-4010 | LE23M219-E-WS-WT-PR-4010-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Cable | LE23M219-E-WS-WT-PR-4011 | LE23M219-E-WS-WT-PR-4011-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Lugs & Glands | LE23M219-E-WS-WT-PR-4012 | LE23M219-E-WS-WT-PR-4012-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | HT Termination Kit | LE23M219-E-WS-WT-PR-4013 | LE23M219-E-WS-WT-PR-4013-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Cable Tray | LE23M219-E-WS-WT-PR-4014 | LE23M219-E-WS-WT-PR-4014-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Lighting Fixtures | LE23M219-E-WS-WT-PR-4015 | LE23M219-E-WS-WT-PR-4015-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Lighting Materials & accessories | LE23M219-E-WS-WT-PR-4016 | LE23M219-E-WS-WT-PR-4016-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Earthing & Lightning Material | LE23M219-E-WS-WT-PR-4017 | LE23M219-E-WS-WT-PR-4017-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | LDB | LE23M219-E-WS-WT-PR-4018 | LE23M219-E-WS-WT-PR-4018-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | LPBS | LE23M219-E-WS-WT-PR-4019 | LE23M219-E-WS-WT-PR-4019-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03
Sahibganj | Electrical | Safety Accessories | LE23M219-E-WS-WT-PR-4020 | LE23M219-E-WS-WT-PR-4020-A | Vendor Name yet to provide | Enquiry yet to float | NA | [29 empty] | karthiga@lntecc.com-17.05.2024-10:37:03